Project Title: Enhancing Resilience of Communities through Mine Clearance and the Improvement of the Agricultural Infrastructure (Project RECLAIM)

Project Number: 01004918

Implementing Partner: UNDP

Start Date: 15 August 2025		End Date: 15 December 2028	PAC Meeting date: 29 October 2025

Brief Description

Zimbabwe’s National Development Strategy (NDS-1) recognizes the importance of not leaving anyone or any place behind. However, several communities along the border with Mozambique and South Africa have been affected by the legacy of the liberation struggle because they continue to face the brunt of the impact of Explosive Ordinance (EO) contamination forty-four years after the attainment of independence. This prevents return to normal life in the affected communities. At independence, Zimbabwe inherited 310.6 square kilometres of contamination. The Zimbabwe-Mozambique border spans four provinces, 12 districts and currently holds approximately 12 square kilometres of the remaining Explosive Ordinance contamination which is located close to villages in proximity to agricultural and grazing land. Zimbabwe has an obligation and treaty deadline set in terms of Article 5 of the Ottawa Convention (Anti-Personnel Mine Ban Convention (APMBC) to be land mine free by December 2025. However, this target will not be met due to challenges in securing funding needed for clearance amid competing and significant social and economic challenges. The Enhancing Resilience of Communities through Mine Clearance and the Improvement of the Agricultural Infrastructure Project is strategically aligned with three key thematic areas under NDS 2, namely: Good Governance, Institution Building, Peace and Security; Food Security, Climate Resilience and Environmental Protection; and Social Development and Social Protection. Through mine clearance and the restoration of access to land, the project promotes peace and security, strengthens trust in public institutions, and supports local governance structures to deliver on their mandates—thus contributing to institution building and good governance. The safe return of land to communities enhances agricultural productivity and resilience, thereby advancing food security and enabling more sustainable use of natural resources in line with climate resilience and environmental protection objectives. Simultaneously, the project’s support to vulnerable populations through inclusive livelihood opportunities directly contributes to social development and protection, especially for women, youth, persons with disabilities, and communities historically affected by landmines. As such, the project not only addresses the immediate threat of landmines but also catalyses long-term, inclusive, and resilient development outcomes as envisioned in NDS 2. To meet its deadline, Zimbabwe cleared 2.31 square kilometres in 2023 and has a current balance of about 12 square kilometres. Zimbabwe’s request for a planned five-year extension to 2030 was granted and to meet the landmine clearance free target the country still needs to secure additional funding and increase capacity. Completion by the end of 2027 would be a considerable achievement for one of the world’s most heavily mined countries in a particularly challenging political and economic context. There is urgency to support the remaining demining actions and draw linkages with sustainable development through productive use of land that is released so that communities have opportunities to augment their livelihoods. Although most communities are aware of the danger of minefields, human injuries and livestock loss still occur because the fertile farmland as well as the source of water in some areas lies across the minefields. Many people use various paths to cross uncleared minefields to earn a living. Through interventions outlined below, UNDP will support explosive ordinance risk education, victim assistance and institutional capacities of national authorities and mine clearance operators. In addition, the same areas face protracted climate vulnerability which is exacerbated by the fluid macro-economy and limited access to services which leads to grievances and community conflicts. These areas are underdeveloped, underserved with limited basic services, and characterized by limited opportunities for marginalized groups to participate in local development and decision-making processes. For Zimbabwe to attain its ambition to become a middle-income country by 2030, there is a need for investment around these borderlands to strengthen their resilience and create enabling pathways for human security. Recognizing the interconnected nature of borderland development challenges, the project will empower vulnerable groups, especially women, youth, and persons with disabilities, by integrating climate and conflict considerations while addressing gender-based violence through targeted interventions. These targeted interventions will be achieved through three interlinked outputs: - Support demining actions by Land Mine operators to release land and destroy anti-personnel landmines - Diversified livelihood opportunities and infrastructure for resilience utilising the Smallholder Horticulture Empowerment and Promotion (SHEP) Approach. - Strengthened social cohesion for resilience and human security.

| Contributing Outcome (UNSDCF, CPD, RPD): By 2026, all people in Zimbabwe, especially the most vulnerable and marginalized, benefit from greater environmental stability and robust food systems in support of healthy lives and equitable, sustainable, and resilient livelihoods. CPD Outcome: By 2026, all people in Zimbabwe, especially the most vulnerable and marginalized, benefit from more accountable institutions and systems for the rule of law, human rights, and access to justice. Indicative Output(s) with gender marker: Gen 2 |  | Total resources required: | US$10,000,000.00 |  |
| --- | --- | --- | --- | --- |
|  |  | Total resources allocated: |  |  |
|  |  |  | UNDP TRAC: | US$400,000 |
|  |  |  | Donor (Government of Japan): | US$2,946,582.32 |
|  |  |  | Government: | TBA |
|  |  |  | Government of Zimbabwe In-Kind: | TBA US$500,000 |
|  |  | Unfunded: |  |  |

Agreed by (signatures):

| Government | UNDP | Donor |
| --- | --- | --- |
| Print Name: | Print Name: | Print Name: |
| Date: | Date: | Date: |

# Development Challenge (1/4 page – 2 pages recommended)

In 2022, Zimbabwe was re-classified as a Lower-Middle Income Country with a population demographic of 15.5 million people of which 52 % are women, 9.2 % are persons with disabilities and 61% are youth under the age of 25. Zimbabwe ranks 153 out of 193 countries on the 2024/2025 Human Development Index with a ranking of 0.598 and the national poverty rate stands at 38.3 percent. With a rural poverty rate of 52 %, the risks of vulnerable households facing negative impacts of food and nutrition insecurity, income deficit and overall loss of previous development gains are high. Rural poverty trends are particularly worrying as more than half (67.7%) of the population reside in rural areas and is largely dependent on farming. The structural elements of poverty in Zimbabwe are linked to the economic, social, political, cultural dynamics, and the impacts of HIV and AIDS that contribute to unequal access to social services, economic and natural resources, employment, and educational opportunities. The transient components are fuelled by, among others, climate change and variability leading to prolonged dry spells, droughts, floods, and cyclones. Areas with high poverty rates tend to also be areas in which household access to quality water and sanitation is limited.

Zimbabwe has continued to face macro-economic challenges emanating from policy inconsistencies, inflation, and climate change. Persistent inflation, high dependence on low-productivity agriculture, slow structural transformation, and intermittent shocks like droughts, cyclones, and the COVID-19 pandemic have contributed to the high rate of poverty and vulnerability in Zimbabwe and further exacerbated communities’ susceptibility to shocks and stresses. Challenges in the macroeconomic environment, poverty, food insecurity, malnutrition, and environmental degradation, render rural border communities particularly vulnerable to shocks. Such communities will continue to be vulnerable to climate variability if sustained efforts are not made to curtail the impact. The country’s dominant economic activity, rain-fed agriculture, renders much of the population vulnerable to climatic variability.  Although extreme poverty has declined since its peak in 2020, it remains high in the context of cyclical agricultural production and elevated food prices.

Mine action started to develop in the late 1980s as a humanitarian and stand-alone technical measure comprising the identification and destruction of landmines. Over the years it became clear that demining had a development dimension, because the presence of mines affects the social and economic recovery of communities affected by conflict, because landmines can block the use of lands, roads, schools, and other basic facilities. Further, dense belts of land mines — some with about 5,500 per square kilometre — on Zimbabwe’s border with Mozambique have hindered livelihood opportunities and exacerbated inequalities in marginalized communities. Much of the contamination was located close to villages in proximity to agricultural and grazing land, affecting five provinces and 12 districts. A survey of Zimbabwe’s north-eastern region by Halo Trust identified 87 communities (over 75,000 people) that are directly affected by landmines. Communities living along the Zimbabwean border with Mozambique continue to suffer from the effects of anti-personnel mines more than 45 years after they were laid with over 1,500 people and more than 120,000 livestock killed or injured.  Over the years, the Government has made significant progress in clearing contamination. As of December 2024, the Mine Action Review estimates indicate that the remaining contamination comprises five mined areas (12,5sq.km) projected to be cleared by 2030. To illustrate the complexity of this problem, the 2023 landmine monitor indicates that no States Parties reported completing the clearance of antipersonnel mines in 2023. Since the Mine Ban treaty entered into force on 1 March 1999, only 30 States Parties completed clearance of all antipersonnel mines from their territory. The last ones to do so were Chile and the UK in 2020.

During the 22nd Meeting of the States Parties, Anti-Personnel Mine Ban Convention at the Zimbabwe’s National Stakeholder Dialogue: Humanitarian Demining and Assistance to Mine Victims, the Path Forward on 18 February 2025, H.E. Mr YAMANAKA Shinichi, Ambassador of Japan to Zimbabwe on behalf of the President highlighted that landmines pose a significant barrier to sustainable development, security, and social cohesion in mine-affected communities. He pointed out that;

“The presence of landmines not only threatens lives but also restricts access to critical resources such as farmland, schools, and healthcare facilities, exacerbating economic and social vulnerabilities. In Zimbabwe, demining efforts, supported by international partners such as Japan and implemented through organizations like the HALO Trust, have demonstrated the importance of strong national ownership and coordinated action in fostering resilience. Effective mine action goes beyond clearance operations—it integrates victim assistance, community engagement, and capacity building to ensure sustainable recovery”.

By supporting demining initiatives, this project will contribute to restoring safe land for productive use, enhancing economic opportunities, and rebuilding trust within communities. Additionally, regional cooperation, knowledge-sharing, and policy integration, as emphasised in Japan’s approach, will further strengthen the impact of mine action efforts. This project aligns with national and international commitments to a mine-free world and will serve as a catalyst for long-term peace, stability, and social cohesion

Zimbabwe has made significant progress in demining efforts under the Mine Ban Treaty, which sets a 2025 deadline for the complete clearance of landmines. However, during the Anti-Personnel Mine Ban Convention at the Zimbabwe’s National Stakeholder Dialogue: Humanitarian Demining and Assistance to Mine Victims, the Path Forward on 18 February 2025, it was acknowledged that due to resource constraints and funding gaps, Zimbabwe may require an extension to 2030 to fully achieve this goal (that extension to 2030 has since been granted). With over US$$24 million needed to clear the remaining contaminated areas, mobilising additional financial and technical support remains a critical challenge. The dialogue emphasised the need for sustained donor engagement, innovative financing mechanisms, and strengthened partnerships to accelerate mine clearance efforts, ensuring the safety of affected communities and fostering socio-economic development.

Zimbabwe shares a 1,423 sq.km border with Mozambique. The borderline spans four provinces in Zimbabwe (Mashonaland East, Mashonaland Central, Manicaland, and Masvingo). Both Mozambique and Zimbabwe are susceptible to the cyclical, recurrent nature of natural disasters; this has become the new normal. Cyclones Idai and Freddy exposed the vulnerabilities facing border communities along the border, ranging from the need for structural transformation, addressing poverty and inequalities, strengthening resilience, and communities’ and institutional capacities for disaster risk reduction. According to UNDP ZRBF 1 Hazard mapping these border areas are more prone to recurrent shocks and stress that include natural disasters that deepen already prevailing extreme issues and the vulnerability of livelihoods especially a significant concentration of vulnerable population (72%) on livelihoods that are most prone to climatic changes, namely agri-business and small-scale businesses, conflict-sensitivities, sexual and gender-based violence, and low coping capacities and inequalities.

The map below indicates targeted districts.

Table of Geographic Locations and Households in the Areas

| Province | District | Wards | Households (HH) | Population |
| --- | --- | --- | --- | --- |
| Mashonaland East | Mudzi | 1 | 2684 | 9914 |
|  |  | 12 | 2426 | 10360 |
|  |  | 16 | 2030 | 8749 |
|  |  | 17 | 1529 | 6179 |
|  |  | Subtotal | 8669 (HH) | 35202 (People) |
| Mashonaland Central | Rushinga | 1 | 588 | 2589 |
|  |  | 2 | 370 | 1487 |
|  |  | 20 | 494 | 2118 |
|  |  | 21 | 637 | 2572 |
|  |  | 22 | 657 | 2806 |
|  |  | Subtotal | 2746 (HH) | 11572 (people) |
|  | Mt. Darwin | 2 | 3247 | 12954 |
|  |  | 3 | 1235 | 4752 |
|  |  | 4 | 1171 | 4593 |
|  |  | 5 | 1261 | 5046 |
|  |  | 33 | 1763 | 6716 |
|  |  | 34 | 1520 | 5775 |
|  |  | Subtotal | 10197 (HH) | 39836 (people) |
| Total |  |  | 21612 (HH) | 86610 (people) |

Furthermore, conflict at the subnational level is rarely a direct function of poverty alone, rather, it is frequently linked to grievances and perceived injustice associated with access to power and resources. Within border communities, the socio-political power contestation between rural district councils and traditional leadership plays out to the detriment of these vulnerable communities.  This often results in a lack of beneficiation from natural resources, a lack of social service provision, and increased polarization at the local level. For example, as part of the Zimbabwe Gender Commission's (ZGC) research into systemic gender barriers that affect women at designated and undesignated ports of entry in Border towns, the ZGC conducted stakeholder consultations (November 2023) in Mudzi, Mashonaland East where the issue of utilization of de-mined land arose. It highlighted the tensions between the Rural Development Council (RDC) and traditional leadership concerning de-mined land allocation and the provision of service delivery.  In recognition of the above, the project will seek to build resilience that is underpinned by a holistic approach that addresses structural inequalities, fosters community empowerment, and enhances institutional capacities.

Experience from the implementation of the UNDP Zimbabwe Resilience Building Fund (ZRBF 1) programme (2015-2023) has demonstrated that humanitarian assistance alone cannot avert a disaster, nor can it address the underlying causes of the impact on the population. It requires partnership with stakeholders including government, development partners, and peace actors to work collaboratively to address both immediate needs and long-term development priorities.  Informed by lessons from previous programming, this project will integrate mine action and community development whilst taking into cognizance the intersectionality of vulnerabilities caused by climate change, gender inequality, as well as a lack of social and justice services, borne by border communities. Recognizing that there is no “one size fits all” in addressing the aforementioned challenges, it proposes a holistic approach to development assistance that utilizes a whole-of-government and whole-of-community approach in partnership with multi-sector stakeholders to promote productive utilisation of demined land to enhance resilience through agricultural activities while building social cohesion, human security, and resilience in border areas.

# Strategy

The project’s theory of change (ToC) is set under the premise that:

IF investments are made to; release land through the destruction of anti-personnel landmines and Diversify livelihood opportunities and infrastructure for resilience, and

IF devolved governance systems at subnational (community) are strengthened to deliver services iv) and

IF women youth and persons with disabilities are better able to access empowerment initiatives and governance services that build resilience and human security

THEN communities' resilience will improve through strengthened service delivery, community social cohesion and transform lives of at-risk vulnerable rural border communities.

This ToC is underpinned by the following assumptions:

Target households are willing to actively participate in project activities, Government at central and subnational, communities and partners continue to focus on policies and strategies for mine action, resilience building, community harmony interventions, and harmonization of access to multiple services and communities are willing to transition to innovations including accessible technology.

Based on the National Development Strategy 1, the identified thematic areas of National Development Strategy 2 and the UNDP Country Program Document (CPD, 2022-2026), UNDP will support the Government of Zimbabwe and the United Nations system in achieving the outcomes of the NDS and UNSDCF via its integrator role, using a two-pronged strategic approach centred on resilience: resilience of the people and the systems serving the people. These two distinct, yet mutually reinforcing prongs, have been identified based on evaluative feedback on UNDP positioning and experience, and a broadly shared realization that current aid practices promote neither a sustainable nor transformative approach to development. The underlying strategy of the UNSDCF emphasizes the need to shift from humanitarian and operational support in the social sectors – which is outside of, yet complementary to, government – towards building the capacity of national and subnational structures and systems to deliver more people-centered development interventions.

In a forward-looking sense, the Enhancing Resilience of Communities through Mine Clearance and the Improvement of the Agricultural Infrastructure Project is strategically aligned with three key thematic areas under NDS 2 (2026-2030), namely: Good Governance, Institution Building, Peace and Security; Food Security, Climate Resilience and Environmental Protection; and Social Development and Social Protection. Through mine clearance and the restoration of access to land, the project promotes peace and security, strengthens trust in public institutions, and supports local governance structures to deliver on their mandates—thus contributing to institution building and good governance. The safe return of land to communities enhances agricultural productivity and resilience, thereby advancing food security and enabling more sustainable use of natural resources in line with climate resilience and environmental protection objectives. Simultaneously, the project’s support to vulnerable populations through inclusive livelihood opportunities directly contributes to social development and protection, especially for women, youth, persons with disabilities, and communities historically affected by landmines. As such, the project not only addresses the immediate threat of landmines but also catalyses long-term, inclusive, and resilient development outcomes as envisioned in NDS 2.

Furthermore, the project is fully aligned with Japan’s commitment made during TICAD8. The proposed project will contribute to Japan’s long-term commitment to building resilient, sustainable, prosperous, and peaceful societies in a holistic manner focusing on the people’s agency.  The focus was on “investment in people” and “quality growth” through the creation of an environment where people can fully unleash their vitality and maintaining peace and stability so that their livelihoods are not threatened under the overarching principle of realization of human security.  Further, the project is fully aligned with the strategic focus of the Ministry of Foreign Affairs of Japan on the agenda of peace and security which emphasizes that women and the youth must be at the centre of all our efforts to build peaceful, sustainable, and resilient societies, and will continue to promote the implementation of the Women, Peace and Security (WPS) and Youth, Peace and Security (YPS) agendas.

UNDP recognizes that to achieve resilient communities and systems, it is imperative to address the foundational social cohesion issues. Resilience building and resilient development in border communities are only viable when concentrated efforts are made toward the operationalization of an enabling and conducive environment, and targeted empowerment of local communities is undertaken for meaningful engagement in local development initiatives. Communities and other stakeholders are demanding more transparency and accountability from institutions and systems that serve the people, as such there is a need to promote dialogue around this issue, especially on how communities can participate and benefit from local development opportunities.

The urgency of the project is anchored in the lived experiences of affected communities as well as lessons learnt from past projects around the seriousness of the marginalization of border towns and communities, and the impact of economic hardships exacerbated by natural and human-made disasters. Humanitarian assistance, development programmes, and peacebuilding are not serial processes, they are all needed at the same time in the most vulnerable communities, intending to ensure medium- and long-term development solutions. The proposed programme is premised on the background that unfolding impacts of climate change in the country are resulting in more frequent occurrences of natural disasters such as droughts, floods, and cyclones worsening lives and livelihoods of rural communities as well as increased conflict around land rights related to utilization and allocation of de-contaminated land [from conflict remnants] as it becomes available. Small-scale farmers have already been affected by changing climate conditions over the last few decades, and these climate trends are predicted to continue. These continued shocks and stresses, in their different forms, have severely eroded the resilience capacities of most vulnerable communities.  Intervention under this programme will seek to bolster resilience to shocks (climatic, economic, and conflict-related) by building capacities and developing skills of the affected communities; more deliberate and consistent integration of conflict sensitivity and enhancing local capacities for peace. To ensure greater impact and sustainability the project will adopt SHEP model, or Smallholder Horticulture Empowerment and Promotion Approach, a development strategy that transitions farmers from subsistence farming to a market-oriented agriculture system.

The SHEP Approach promotes a fundamental shift from the traditional "grow and sell" model to a more strategic "grow to sell" approach, aligning seamlessly with the project’s emphasis on sustainable livelihood options. By integrating this methodology, the project will empower smallholder farmers in demined areas to adopt market-oriented agricultural practices, ensuring they cultivate crops that are in high demand and maximise their profitability. Furthermore, farmers will be supported in value-addition initiatives, where they will be encouraged to engage in agro-processing and employ post-harvest handling techniques. This will not only enhance their income but also minimise post-harvest losses and promote the development of value-added products such as dried fruits, essential oils, and processed grains. To strengthen financial inclusion and market development, the project will facilitate the establishment of market linkages while promoting investment in agricultural production and marketing. These efforts will create a more robust and sustainable agricultural economy in the affected regions. Additionally, the SHEP principles will be integrated into vocational training and entrepreneurship programs to ensure that women and youth have equitable access to opportunities within the value chain. This targeted approach will help bridge economic gaps, foster inclusivity, and create more resilient communities by enhancing the participation of marginalised groups in market-driven agricultural ventures.

This project will contribute to gender equality and women's empowerment by ensuring that all planned actions mainstream gender and inclusion principles and norms, i.e., by ensuring that both women’s and men's interests and concerns are taken into consideration in the execution of the minimum of 30% gender budget allocation and the Gender 2 marker accompanied by clear gender nuanced baselines, indicators, targets, and results. It will further contribute to advancing gender equality and women's empowerment through dedicated interventions that address all forms of gender-based violence, enhance women’s meaningful participation, promote dialogue on resilience building, social cohesion, conflict prevention, and peacebuilding, and enhance capacities of duty bearers on their roles to implement the Women, Peace, and Security (WPS) agenda and enhance women’s meaningful participation. These interventions will target the specific needs of women from the target communities to the decision-makers at the state level, including the specific needs of vulnerable women and girls.

By adopting an integrated approach to the project and strategically sequencing interventions, the project will effectively address the multifaceted challenges faced by border communities and catalyse positive change for sustainable development along the Zimbabwe-Mozambique border. To optimize efficiency and impact, the interventions have been grouped and sequenced based on their thematic relevance and potential for synergy. Through intentional layering and sequencing of interventions across the three pillars, the project will address immediate challenges while laying the groundwork for long-term resilience. At the first level, the focus will be on foundational interventions, such as demining and the release of contaminated land, infrastructure development and hardware development, capacity building, promoting inclusive decision-making processes, enhancing community resilience and establishing essential frameworks for resilience and human security. Simultaneously, investments in livelihood diversification, including vocational skills training and support for income-generating activities, will empower communities economically, fostering self-reliance and reducing vulnerability. Concurrently, strengthening governance capacities and fostering social cohesion ensures inclusive decision-making processes and enhances community resilience against various risks, including climate change impacts and conflicts. As the project progresses, emphasis will be placed on enhancing agricultural productivity and climate change resilience, thereby fostering economic growth and environmental sustainability in border communities.

The project intervention will implement the following enablers to deliver on the objectives:

- Mine action as a critical factor in restoring livelihood capacities and building resilience: UNDP’s strategic commitment to mine action, calls attention to the need to implement mine action within the context of development interventions. This means focusing on establishing an enabling environment and needed capacities. Such an approach involves designing and implementing livelihoods and poverty reduction programmes that tackle the connected issues of poverty, inequality cohesion and exclusion while transforming productive capacities. This component will also provide support to the national mine authority (ZIMAC) and land mine clearance operators in Mashonaland Central and Mashonaland East to meet their annual targets and release land that can be utilised to promote productivity.

- Technical Capacity Development: A key component of this intervention is the enhancement of technical skills among women and youth in rural border communities. By providing training and resources to individuals and groups, the initiative aims to equip them with the knowledge and expertise needed to engage in various productive activities and improve productivity. This can lead to transformative change and diversify their livelihoods while reducing dependency and promoting participation in higher-value sectors of the economy.

- Value Addition: The emphasis on value addition is crucial for the rural and informal economies. By encouraging the processing and upgrading of primary produce at the district level, the intervention seeks to create more profitable and sustainable economic activities. This can increase income levels, transfer productive assets, reduce post-harvest losses, and stimulate local entrepreneurship, ultimately contributing to a shift from raw material trade to value-added products.

- Women and Youth Economic Empowerment: Empowerment of women, youth, and persons with disabilities with skills, and access to resources, information, and markets is transformative and addresses gender and generational inequalities. Their increased participation in economic activities can lead to more inclusive and dynamic economies. Approaches will draw from the SHEP model, or Smallholder Horticulture Empowerment and Promotion Approach, are critical in this transformative agenda.

- Promoting Greening Practices and Climate Change Mitigation: Promoting environmentally sustainable practices is essential for long-term transformation. By integrating green principles into rural development, the intervention not only ensures the preservation of natural resources but also taps into the growing demand for sustainable products. This can lead to the emergence of eco-friendly enterprises and markets, fostering greener and more resilient rural and informal economies.

- Improved health and protection: Through interventions that address Gender Based Violence, the programme will bring transformative changes, especially to women. The capacity of institutions, duty bearers, and communities will be strengthened to eradicate GBV and other harmful practices targeting women and youth.

- Evidence-based decision-making: The project will support the strengthening of national and sub-national mechanisms that will produce information and knowledge that to inform government policy on women and youth.

# Results and Partnerships

Expected Results

Between 2022 and 2023, UNDP, through its Deep Demonstration Process which preceded the design of the Transformative Governance Portfolio, undertook a comprehensive learning and exploration exercise in some of Zimbabwe’s hard-to-reach and landmine-contaminated areas. This initiative served as a practical experiment, enabling UNDP to engage directly with communities and local stakeholders living in environments affected by uncleared mine ordnance. The process revealed the multifaceted and layered challenges these communities face — ranging from physical safety risks and restricted mobility to limited access to social services, economic opportunities, and humanitarian support. Building on these insights, UNDP has designed this project with multi-layered interventions that focus on mine action, resilient livelihoods, and social cohesion. Together, these efforts aim to strengthen human security, restore safe access to land and resources, and foster inclusive, sustainable development in affected areas.

💥 Clearing Mines, Unlocking Potential!
Demining is not just about safety—it’s about opportunity! 🚜✨ Cleared land fuels agriculture 🌾, cross-border trade 🌍, and brighter futures 🌟. Let’s help #Zimbabwe become mine-free by 2027! 🔓 #SDGs #Resilience

🌟 Hope Beyond Mines!
Mine clearance transforms lives ❤️‍🩹. From empowering women 👩‍🌾 to creating jobs 💼 and boosting trade 💹, every step forward is a win for Zimbabwe 🇿🇼! Together, let’s build peace 🕊️ and prosperity #MineAction #SocialCohesion

The project is firmly situated within the Country Office’s Decentralised Governance for Development Portfolio which aims to strengthen the social contract by enabling citizens, particularly the most vulnerable and marginalised, to participate meaningfully in democratic and development processes, benefit from accountable institutions, and enjoy improved service delivery.

The project directly contributes to the portfolio’s three core components:

- Effective Service Delivery through Devolution – By addressing the physical safety risks posed by uncleared mine ordnance and restoring safe access to productive land, the project creates the foundation for equitable and inclusive local service delivery in hard-to-reach and conflict-affected areas.

- Transparency and Accountability – The project’s community-based mine action and livelihood interventions include participatory planning and monitoring mechanisms that align with the portfolio’s goal of enhancing citizen oversight and fostering trust in local and national institutions.

- Strategic Dialogue and Social Cohesion – Through its focus on resilient livelihoods and social cohesion, the project supports conflict-sensitive dialogue, fosters cooperation between communities and authorities, and promotes the principle of “leaving no one and no place behind,” particularly in marginalized, mine-affected areas.

In this way, the project serves as both a practical implementation pathway and a learning and innovation platform within the portfolio, generating evidence, data and tested models that can be scaled up to other targeted regions in the country.

This project is deliberately leveraging on existing national and sub-national structures, as well as multi-stakeholder partnerships that have already proven effective in resilience building. These include coordination mechanisms established under the Zimbabwe Resilience Building Fund (ZRBF), local government development planning platforms, private sector linkages for markets and finance, as well as civil society and community-based structures that anchor interventions at grassroots level. By aligning with these platforms, the project ensures both continuity and sustainability, while avoiding duplication and promoting collective ownership of resilience outcomes.

In addition, the project builds on the strategic partnerships formed through the Systems Innovation Unit (SIU) funded Deep Demonstration and Systems thinking process between 2022 and 2024 wherein the UNDP Zimbabwe Transformative Governance Unit conducted practical experiments to explore potential layered areas on programming and interventions.

Output 1: Release of land and destruction of anti-personnel landmines

Efforts to clear landmines and other explosive remnants of the liberation war in Mudzi and Rushinga districts—areas heavily affected by contamination, will focus on making communities safer and unlocking the socio-economic potential of previously inaccessible land. By supporting and equipping demining teams, and ensuring all activities adhere to national and international mine action and environmental standards, the project will directly safeguard lives, restore vital agricultural and pastoral land, and create pathways for improved livelihoods, cross-border trade, and local infrastructure development. The indicative activities under this output are as follows;

Activity 1.1 Support demining teams in Mudzi and Rushinga districts by providing necessary resources to safely and effectively clear landmines and other explosive remnants of war. This initiative aims to enhance community safety, promote sustainable development, and restore access to critical land for agriculture and infrastructure. Direct benefit to over 1,000 Zimbabweans; Indirect benefit to 6,000 Zimbabweans. Including employing, training and empowering women and men from the communities affected by landmines. Teams are deployed for 9 months during the 12-month performance period according to Standard Operating Procedures (SOPs) that align with national and International Mine Action Standards (IMAS). All mine action activities in Zimbabwe are conducted in line with the Zimbabwe Environmental Agency (EMA) regulations and requirements. ZIMAC has stated that Zimbabwe has an NMAS on environmental management (ZNMAS 10.07) and a policy on environmental management, with ZNMAS 10.07 updated in 2023 and shared with operators.

Activity 1.2 Conduct Social Environmental Standards (SES) training for the communities and contractors

Activity 1.3 Conduct a baseline landmine victim survey

Output 2: Diversified livelihood opportunities and infrastructure for resilience

The project will ensure the strengthening and diversification of livelihoods opportunities through the development and rehabilitation of resilient infrastructure. The project will apply the Smallholder Horticulture Empowerment and Promotion Approach (SHEP Model), a development strategy that transitions farmers from subsistence farming to a market-oriented agriculture system. The SHEP model emphasizes a shift towards income generation through agriculture.  Indicative activities under this output:

Climate Resilient Infrastructure:

Activity 2.1 Develop climate resilience infrastructure for productive use and ensuring access to social services. This entails but is not limited to support to the rehabilitation of community infrastructures, including water systems, small-scale irrigation schemes, water, and to facilitate the SHEP Approach, in the promoted enterprise. This component will leverage on the expertise within the Ministry of Lands, Agriculture, Fisheries, Water and Rural Development and technical cooperation project by JICA. Smallholder farmers capacity building, in production, business development skills, market research and analysis will be the major focus to ensure that supported enterprise are viable and sustainable.

Activity 2.5 Promote resilience of productive renewable energy for diverse livelihood options.

Financial Inclusion and Market Development:

Activity 2.2 Facilitating vocational skills and entrepreneurship development for skills transfer, and employment creation and ensuring youth’s and women’s economic empowerment.

Activity 2.4 Promote inclusive, viable, and sustainable value chains and market linkages including agro-processing and value-addition.

Activity 2.5 Support to on-farm and off-farm income-generating activities and provision of small grants seed capital for projects.

Output 3: Strengthened governance capacity for resilience and human security.

The project recognizes that weak governance at the sub-national level is a critical constraint to effective and equitable resilience and adaptation planning particularly for vulnerable communities and those in hard-to-reach areas such as border communities. Lack of capacity and will among local governments and service providers to respond to human security gaps leads to huge deficits in service and infrastructure provision, which drives up risk. The following are the indicative activities under this output:

Social Cohesion

Activity 3.1 Strengthen Policy and regulatory frameworks, coordination, institutional, and planning for resilience in border communities.

Activity 3.2 Promote decentralized capacities of governance structures and systems for effective delivery of services in border communities.

Activity 3.2 Promote access to basic and essential services (GBV, Justice, psychosocial, health, and protection) for vulnerable segments of society (women, youth, and PWDs in border communities. (Establishment of the physical one-stop centre, and roll-out of Mobile One-Stop Centres in Border Communities)

Activity 3.3 Support spatial governance and planning systems for enhancing effective utilization of de-minded land in border communities.

Activity 3.4 Creation of platforms for and empowerment of women, youth, and PWDs to claim their rights and participate in local planning, budgeting, and decision-making processes.

Activity 3.5 Support the development and operationalization of community multi-hazards early warning systems, conflict management strategies, disaster risk plans, and contingency planning.

Activity 3.6 Support community awareness campaigns and information-sharing platforms/hubs on security, Conflict Resolution Explosive Ordnance Risk Education, Peace, GBV, and human rights issues within border communities.

Resources Required to Achieve the Expected Results

To achieve the expected results of the project, a range of strategic inputs and resources will be mobilised, aligned with the change pathway outlined in the theory of change. These inputs include dedicated staff time, key operational purchases, technical assistance, and strategic partnerships, all of which will be adequately costed and incorporated into the project budget.

At the core of the implementation effort is the contribution of UNDP Zimbabwe Country Office staff. The Team Leader for the Transformative Governance Unit will dedicate 10% of her time to provide strategic oversight, ensuring the project remains aligned with broader governance and development priorities. The Project Manager, who also serves as the Mine Action and Livelihoods Specialist, will commit 100% of their time to lead the technical and operational execution of the project. This includes day-to-day coordination, stakeholder engagement, and oversight of field implementation.

Additional technical and operational support will be provided by the Participatory Development Officer, contributing 90% of their time to strengthen community engagement, inclusion, and capacity development components of the project. The Programme Associate will allocate 30% of their time to support logistics, procurement, and administrative processes, while the Programme Finance Associate will dedicate 15% of their time to ensure sound financial management and compliance with UNDP’s financial rules and procedures. The Monitoring and Evaluation Officer will contribute 5% of their time to support results-based monitoring, learning, and adaptive management of the project.

The project will be implemented under the overall framework of the Country Programme Document (CPD), ensuring strategic alignment with national priorities and UNDP’s mandate. To safeguard quality and coherence in delivery, the Country Office Programme Management Support Unit (CO PMSU) will play a role in quality assurance, providing technical backstopping and ensuring compliance with corporate standards and procedures.

In addition to personnel, the project will require a range of operational purchases, including demining equipment, protective gear and communication tools to support field operations and remote coordination. Office operational costs, such as utilities and supplies, will also be included to ensure an enabling environment for implementation. To support the livelihoods component of the programme, the project will procure essential start-up kits, tools, and inputs tailored to community-based income-generating activities—such as agricultural inputs, small livestock, vocational tools, and micro-enterprise equipment. Furthermore, the project will invest in small-scale infrastructure development to enable sustainable livelihoods and enhance community resilience in mine-affected areas. This may include the rehabilitation or construction of community assets such as marketplaces, irrigation systems, storage facilities, and WASH facilities—contributing to both economic revitalisation and improved service delivery in cleared and resettled zones.

The project will also rely on strong partnerships. Key government counterparts include the Ministry of Defence, Ministry of Local Government, and the Ministry of Public Service, Labour and Social Welfare. Partnerships will also be established with accredited mine action operators (HALO and MAG) and civil society organisations. Collaboration with development partners, including the Government of Japan, and technical backstopping from UNDP regional and global teams will ensure quality assurance and knowledge sharing.

Finally, the project will invest in technical assistance and capacity building for national stakeholders. This includes training in mine action standards, risk education, and resilient livelihoods approaches, as well as knowledge exchange and documentation to promote sustainability and scale-up. All resources will be carefully planned, costed, and integrated into the project’s overall budget framework to ensure effective and impactful implementation.

Partnerships

The Ministry of Defence will serve as the primary implementing Partner for this project, given its statutory mandate and oversight role over landmine clearance in Zimbabwe. Through the Zimbabwe Mine Action Centre (ZIMAC), the Ministry will provide strategic direction and coordination of demining operations. Technical implementation will be supported by HALO Trust and the Mines Advisory Group (MAG), who bring internationally recognised expertise, equipment, and field presence as Responsible Parties. The Ministry of Agriculture will also act as a Responsible Party, ensuring that cleared land is systematically transitioned into productive use to support food security, income generation, and rural development. This cross-sectoral collaboration is critical to realising the project’s theory of change, which assumes that safety, sustainable livelihoods, and community resilience are mutually reinforcing outcomes that must be pursued in parallel.

The Zimbabwe Mine Action Centre (ZIMAC), under the Ministry of Defence, has signed Memoranda of Understanding (MoUs) with HALO Trust and Mines Advisory Group (MAG) to facilitate the clearance of landmines in key regions. The project is specifically focused on Mashonaland East and Mashonaland Central provinces, where the minefield stretches from Musengezi to Rwenya River, affecting districts such as Mudzi and Rushinga. These areas have been prioritised due to their high contamination levels and the urgent need to restore safe access to land and infrastructure. In accordance with the MoUs and national allocation requirements, the minefield has been subdivided into operational segments: HALO Trust is responsible for the Musengezi to Mazowe River and Mazowe River to Nyahuku stretches and MAG is clearing the Nyamapanda to Rwenya River segment. The selection of HALO Trust and MAG as implementing partners reflects their operational presence and capacity in the targeted districts, ensuring a coordinated and effective response to landmine contamination in these high-priority areas.

The Ministry of Public Service, Labour and Social Welfare will be a key partner in the implementation of survivor assistance interventions. Partnership between ZIMAC and the Department of Disability Affairs under the Ministry has managed to ensure that survivors of explosive ordnances are not left behind and are benefitting from Government sponsored projects. A national survey for mine victims will be conducted to create a comprehensive database. The Ministry of Local Government and Public Works will be roped in to assist with spatial planning and land use of the cleared areas.

The project will further draw on the platforms, capacities, and community networks established under the Zimbabwe Resilience Building Fund Phase II (ZRBF II), funded by the European Union and the African Development Bank. These linkages will enable a more holistic response, aligning mine clearance and land rehabilitation with ongoing resilience-building and adaptive capacity strengthening efforts in vulnerable communities.

Implementation will rely on strong collaboration and complementary roles between UNDP and key national stakeholders, particularly the Government of Zimbabwe, through the Ministry of Defence and supported by the Ministry of Lands, Agriculture, Fisheries, Water And Rural Development, Ministry of Public Service, Labour and Social Welfare, the Ministry of Local Government and Public Works and the Zimbabwe Mine Action Centre. These institutions will be engaged throughout the project cycle to ensure alignment with national priorities, facilitate access and ownership, and strengthen institutional capacities for sustainability. This joint approach reinforces the achievement of shared outcomes—safer communities, revitalised livelihoods, and strengthened national systems for mine action and resilience.

Accredited mine action operators, namely HALO Trust and the Mines Advisory Group (MAG), will play a central role in the technical delivery of demining activities. The operators will lead clearance operations in areas and facilitate community engagement to identify contaminated land and ensure safe clearance. Key to this will be the conducting of technical survey operations, delivering mine risk education in affected communities and supporting the exchange of knowledge with national mine action authorities. Both operators will work in close coordination with Government and UNDP counterparts to ensure the integration of mine action with broader development efforts, maintain high standards for safety and quality assurance, and ensure that cleared land is effectively handed over for productive and sustainable use.

Implementation will follow the Direct Implementation Modality (DIM), with UNDP assuming overall accountability. The project will be managed by the UNDP Transformative Governance Unit, with strategic oversight from the Team Leader. Day-to-day operations will be led by the Project Coordinator – Mine Action and Resilient Livelihoods, supported by the Participatory Development Officer and Japan/JICA-funded UN Volunteers. UNDP will constitute a dedicated project team to ensure coherence, technical quality, and timely delivery of results. These strategic and operational partnerships collectively underpin the achievement of the project’s outcomes—safer communities, revitalised livelihoods, and strengthened national capacities for mine action and resilience.

Risks and Assumptions (See Attached Risk Template)

Risk management is one of the core pillars of the accountability framework for the programme and it enhances the understanding of the potential upside and downside of factors that can affect the programming. Risk management increases the probability of success and reduces both the probability of failure, and the level of uncertainty associated with achieving the objectives of the programme. A risk registry has been developed (see Risk Matrix below in Section II) as part of a risk management framework to ensure that priority risks are identified, monitored, analysed, and mitigated. Key broad categories of risks identified will be monitored every quarter and these include contextual, political, financial, reputational, and delivery risks.

Stakeholder Engagement

The success and sustainability of this project depend on inclusive, transparent, and sustained engagement with all key stakeholders. Stakeholder engagement will be undertaken throughout the project lifecycle to ensure ownership, accountability, and responsiveness to the needs and priorities of affected communities and institutions.

Target Groups (Beneficiaries):

The primary beneficiaries of the project are communities living in border areas of Mudzi, Mt. Darwin, and Rushinga, who continue to be exposed to the risks and impacts of landmines. Particular attention will be paid to women, youth, and persons with disabilities (PWDs), as well as mine survivors and families of victims. Engagement with these groups will be facilitated through participatory community dialogues, focus groups among other engagement mechanisms. Explosive Ordnance Risk Education (EORE) will be rolled out in schools, marketplaces, and farming communities to strengthen awareness and prevent injuries. Communities will also be supported with dedicated feedback mechanisms to ensure their voices are heard in decision-making.

Other Potentially Affected Groups:

Beyond the direct beneficiaries, the project acknowledges the importance of engaging other groups who may be indirectly affected by the interventions. These include traditional leaders and Rural District Councils (RDCs), whose roles in land allocation could generate tensions once cleared land becomes available; livestock owners and traders, whose activities are impacted by minefields; and local service providers who will experience increased demand once communities gain safe access to social services and infrastructure. These groups will be engaged through structured dialogue platforms to address potential conflicts, joint planning forums to promote inclusive land use, and capacity-building workshops. The project will also promote awareness of land-use rights, gender-based violence prevention, and environmental safeguards to mitigate risks associated with social and environmental impacts.

To ensure accountability and safeguard the rights of all stakeholders, the project will make communities aware of UNDP’s Social and Environmental Screening Procedure and Stakeholder Response Mechanism. These global mechanisms will be complemented by locally accessible grievance redress systems, including community-based grievance committees, RDC offices, and mobile one-stop centres. Confidential reporting channels will be available for sensitive cases such as gender-based violence.

Sustainability of Engagement:

To ensure that stakeholder participation extends beyond the life of the project, engagement processes will be institutionalised within existing community and subnational governance structures. Community monitoring committees, grievance redress systems, and inclusive dialogue platforms will be designed to continue functioning with the support of Rural District Councils and traditional leaders. At the national level, strengthened capacities of ZIMAC and line ministries will enable the government to continue leading mine action and resilience-building initiatives. By embedding stakeholder engagement into government-led structures and promoting community ownership, the project will leave behind a durable framework for inclusive participation, accountability, and sustainable development.

Knowledge

Beyond its operational outputs, the project places strong emphasis on generating, documenting, and disseminating knowledge to support national capacity-building, inform policy, and contribute to regional and global mine action dialogue. A range of targeted knowledge products will be developed to capture lessons learned, inform decision-making, and promote transparency, inclusion, and sustainability of mine action in Zimbabwe.

Key knowledge products will include:

- A National Database of Landmine Survivors, which will serve as a central repository for data on victim profiles, needs, and geographic distribution, supporting targeted assistance and policy planning.

- A comprehensive National Victim Assistance Study Report, detailing gaps, services, and recommendations to strengthen inclusive recovery and social protection systems.

- A Landmine Victim Survey, which will not only support the database but also provide evidence for improving health and psychosocial support systems.

- Policy Papers and Research Briefs on mine action, survivor assistance, and post-clearance livelihoods, aimed at informing national policy and contributing to global discourse.

- A Documentary on Landmine Survivors to raise public awareness, humanise the data, and support advocacy for continued demining and victim assistance.

- Community Safeguarding Trainings aligned with the Social and Environmental Screening Procedures (SESP) will be conducted to raise awareness of rights, risks, and responsibilities, particularly for vulnerable groups.

To promote visibility and learning, the project will systematically document implementation processes, lessons learned, and good practices through knowledge briefs, blogs, and media features. These will be shared through UNDP Zimbabwe’s digital platforms and partner networks, and at key national, regional, and international forums.

Importantly, the project will actively contribute to the Community of Practice for Mine Action, engaging with the Geneva International Centre for Humanitarian Demining (GICHD), the United Nations Mine Action Service (UNMAS), and the broader global mine action community. Participation in relevant international dialogues and conventions—such as the Anti-Personnel Mine Ban Convention (Ottawa Convention)—will be leveraged to showcase Zimbabwe’s experiences, elevate survivor voices, and align national practices with global standards.

Through this layered knowledge approach, the project not only delivers results but also builds a legacy of evidence, learning, and visibility that strengthens national systems and informs global mine action efforts.

Sustainability and Scaling Up

The project sustainability strategy is underpinned on the implementation and institutionalisation of the development results within the Government of Zimbabwe programmes and projects on demining, agriculture and the provision of social services in hard-to-reach areas. The Government of Zimbabwe will provide the leadership and ownership in the execution of the project in collaboration with the stakeholders and communities in the targeted areas. To this end, the project will:

- Embed sustainability in project implementation: All interventions will be designed in alignment with national policies and priorities under NDS1, the forthcoming NDS2 thematic priority areas on Good Governance, Institution Building, Peace and Security; Food Security, Climate Resilience and Environmental Protection; and Social Development and Social Protection, as well as the government’s devolution agenda. This ensures that the project is not a stand-alone effort but contributes directly to ongoing national planning, monitoring, and evaluation systems.

- Strengthen subnational and community capacities: The project will build the technical, institutional, and organisational capacities of local authorities, community-based structures, and service providers to plan, implement, and monitor resilience, governance, and social protection initiatives. This includes training on results-based management, participatory monitoring, data collection and analysis, financial accountability, and adaptive planning.

- Support institutionalisation of approaches: By working through existing government structures and national systems at both central and subnational levels, the project will help institutionalise participatory processes, transparent governance mechanisms, and community-driven service delivery models. This will ensure that practices piloted under the project are integrated into national systems and budgets, increasing the likelihood of scale-up and replication.

- Ensure national ownership through Co-Creation: Project interventions will be co-created with government institutions, subnational structures, communities, and other stakeholders to guarantee alignment with national priorities and to embed ownership from the outset.

The project’s exit strategy is anchored on ensuring that the outcomes and approaches developed during implementation are fully absorbed, owned, and sustained by national and subnational institutions. By embedding interventions within existing government systems, structures, and policy frameworks, the project will ensure continuity of interventions. Furthermore, through co-creation and continuous collaboration with stakeholders, the project will establish feedback and accountability mechanisms that will endure beyond the project’s lifespan, ensuring that the benefits achieved are sustained, scaled up, and replicated within the framework of national development priorities and the devolution agenda.

# Project Management

Cost Efficiency and Effectiveness

The project is designed to deliver maximum results within the available resources by applying a layered, evidence-based, and partnership-driven approach grounded in the project’s theory of change. The pathway prioritises targeted demining in high-impact areas where cleared land can be rapidly transitioned into productive use, particularly for agriculture and livelihoods recovery. This sequencing ensures that the benefits of demining are not only immediate in terms of safety but also catalytic in terms of long-term resilience and socio-economic development. Evidence from the Zimbabwe Resilience Building Fund Phase 1 has demonstrated that integrating humanitarian interventions with development-focused outcomes—particularly where community engagement and early recovery measures are aligned—leads to more sustainable and cost-effective results.

The project adopts a portfolio management approach, leveraging synergies with existing initiatives such as ZRBF II and and other governance programmes supported by UNDP and its development partners. This enables the efficient sharing of resources, institutional platforms, and delivery mechanisms while avoiding duplication of efforts. For example, targeting mechanisms and community-based structures established under ZRBF II will be used to accelerate beneficiary outreach, ensure contextual appropriateness, and reduce transaction costs.

In terms of operational efficiency, the project will explore joint operations in areas such as procurement, monitoring, and reporting—particularly with demining partners such as HALO Trust and MAG who already operate under economies of scale in Zimbabwe. This coordinated approach not only ensures quality control and compliance with international mine action standards but also drives down unit costs through bulk procurement and shared logistics.

By implementing under the Direct Implementation Modality (DIM), UNDP ensures full alignment with its financial, procurement, and monitoring standards, while maintaining flexibility to reallocate resources as needed to respond to evolving ground realities. The choice of this modality is informed by lessons learned from previous DIM projects in Zimbabwe, which have demonstrated high levels of accountability, adaptive management, and results-oriented delivery when UNDP plays a central convening and coordinating role.

In the spirit of deepening strategic partnerships and fostering mutual economic collaboration, the Government of Japan has expressed interest in exploring opportunities for engagement with Japanese public and private sector entities within the framework of this project. This includes encouraging the consideration of Japanese brands and technologies in the procurement of equipment and goods, where appropriate and aligned with project needs. Such collaboration is seen as a pathway to enhance innovation, quality assurance, and long-term sustainability, while also strengthening bilateral ties and promoting knowledge exchange between Zimbabwean and Japanese stakeholders. UNDP commits to make efforts to comply with Japan’s requirements regarding the above while ensuring UNDP rules and regulations on any of the programming and operational guidelines are followed.

Project Management

The project will be implemented by UNDP in close collaboration with the Ministry of Defence as the lead Government entity supported by the Ministry of Lands, Agriculture, Fisheries, Water, and Rural Development (MLAFWRD) and the Zimbabwe Mine Action Centre (ZIMAC). Identified responsible partners in other entities will be co-opted to implement selected interventions. UNDP will ensure management, good governance, and fiduciary oversight of the project.

Audits will be carried out in line with the UNDP Programme and Project Management Guidelines set out in the Programme and Operations Policies and Procedures (PoPP).

UNDP has zero tolerance for fraud and corruption and is committed to preventing, identifying, and addressing all acts of fraud and corruption. These are avoided through raising awareness of fraud risks and implementing controls aimed at preventing and detecting fraud and corruption. UNDP is guided by the policies and guidelines and carries out the following fraud prevention measures which will be embedded in the project: Enforce the UNDP Policy against Fraud and other Corrupt Practices; Perform Fraud Risk Assessments and build Fraud and Misconduct Prevention into Programme & Project Design; Establish strong Internal Control Systems; Establish clear Roles & Responsibilities; Apply and adhere to standards and codes of conduct; Identify and flag out high-risk vendors; Carry out external and internal audits; and adhere to UNDP’s Social and Environmental safeguards policy and Social and Environmental Screening procedures.

# Results Framework (See attached RRF)

Intended Outcome as stated in the UNSDCF/Country [or Regional] Programme Results and Resource Framework: ZUNSCDF Outcome 2 and 4 By 2026, all people in Zimbabwe, especially the most vulnerable and marginalized, benefit from greater environmental stability and robust food systems in support of healthy lives and equitable, sustainable, and resilient livelihoods. By 2026, all people in Zimbabwe, especially the most vulnerable and marginalized, benefit from more accountable institutions and systems for the rule of law, human rights, and access to justice.

Outcome indicators as stated in the Country Programme [or Regional] Results and Resources Framework, including baseline and targets: 2.1.2. Number of people whose resilience has been improved as a result of resilience-building support. Baseline: 529,686 people (2020), 194,627 males, 269,938 females, youth 133,611: Target: 830,000 (2023) 60% females, 40% males, 20% youth Source: ZRBF 4.1.2. Number of institutions implementing human rights recommendations in fulfilment of national and internationally ratified human rights obligations. Baseline: 10 (2020) Target: 20 (2026) Source: Partner reports

Applicable Output(s) from the UNDP Strategic Plan: Signature Solution 2 on Governance: 2.3 Responsive governance systems and local governance strengthened for socio economic opportunity, inclusive basic service delivery, community security, and peacebuilding Signature Solution 3 on Resilience: Risk-informed and gender-responsive recovery solutions, including stabilization efforts and mine action, implemented at regional, national and sub-national levels

Project title and Quantum Project Number: Enhancing Resilience of Communities through Mine Clearance and the Improvement of the Agricultural Infrastructure (Project RECLAIM) - 01004918

| UNSDCF/CPD (2022-2026) Outcome: UNSCDF Outcome 2 and 4 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Partnership Strategy: Bring national level stakeholders including community and target groups together to discuss strategic level partnerships and development linkages; Identify mutual areas of synergy, common interests and spaces and opportunities for collaboration |  |  |  |  |
| Project ID and title: 01004918 - Enhancing Resilience of Communities through Mine Clearance and the Improvement of the Agricultural Infrastructure |  |  |  |  |
| Output ID and title: |  |  |  |  |
| INTENDED OUTPUTS | OUTPUT TARGETS FOR (YEARS) | INDICATIVE ACTIVITIES | RESPONSIBLE PARTIES | AMOUNT (USD) |
| Project Output 1: Release of land and destruction of anti-personnel landmines (UNDP CPD Output 4.2) (Outcome Indicator 2.1.2) Baseline: 2000 sqm of land; 1000 landmines destroyed annually Indicators: - Number of square metres of land cleared annually for safe use by the community - Number of land mines safely removed to protect lives annually by mine operators - Landmine victim surveys conducted disaggregating data by age, sex, gender. - Number of Community Engagement Meetings on SESP and EORE conducted per district per year | Targets (Year 1 &2): Indicator 1.1: At least 245,000 sqm of land cleared; Targets: Indicator 1.2: A minimum of 1000 of Land mines destroyed annually; Target: Indicator 1.3: National Landmine victim survey conducted to help create a national database for victims Target: Indicator 1.4: 3 meetings conducted per district per year | Activity 1.1 Land clearance and land reduction of 245,000sqm (3 teams) Indicative Activities: This entails employing, training and empowering women and men from the communities to become deminers. Deployment of one 9-person mixed-gender manual demining team (from 3 land mine operators). Teams are deployed for 9 months during the 12-month performance period according to SOPs that align with national and International Mine Action Standards (IMAS). Activity 1.2 Activity Conduct Social Environmental Standard (SES) training for the community and contractors and related Environmental and social impact assessments Activity 1.3 Conduct a baseline landmine victim survey. Support will also include technical assistance. | Mine Action Operators: Halo Trust; Mine Advisory Group (MAG). ZIMAC | 1,517,400.12 |
| Project Output 2: Diversified livelihood opportunities and infrastructure for resilience (UNDP CPD Output 2.1 and 2.3) (Outcome Indicator 2.1.2) Baseline: Indicators: - Number of infrastructures developed for productive use and access to social services - Number of people engaged in vocational skills and entrepreneurship development. - Average household monthly income from supported projects - Proportion of people with access to financial services promoted by the project. - Proportion of households with access to productive renewable energy sources CPD Indicator: 2.1.2. Number of people whose resilience has been improved as a result of resilience-building support. | Targets: Indicator 2.1: At least 5 community infrastructure facilities developed to improve access to productive assets and basic services. with at least 70 households benefitting Targets Indicator 2.2: At least 1,000 people (50% women and youth) trained in vocational skills and entrepreneurship to enhance self-reliance and local economic activity. Targets Indicator 2.3: Supported households achieve an average monthly income increase of 30% within the life span of the project participation. Targets Indicator 2.4: At least 40% of targeted beneficiaries gain access to financial services promoted by the project. Targets Indicator 2.5: At least 20% of targeted households access productive renewable energy solutions (e.g., solar-powered water pumps, lighting or agro-processing equipment) by project end. | Activity 2.1 Infrastructure development for productive use and ensuring access to social services. Indicative Activities: Support to the construction/ rehabilitation through hardware of community infrastructures, including water systems, small-scale irrigation Activity 2.2: Vocational skills and entrepreneurship development for skills transfer, and employment creation Indicative Activities: Facilitating vocational skills and entrepreneurship development for skills transfer, and employment creation and ensuring youth's and women's economic empowerment. This will draw from training manuals as well as a pool of skills in the Ministry of Agriculture developed during the technical cooperation with JICA which utilised the SHEP approach. Activity 2.3: Income-generating activities. Indicative Activities: Provision of In-Field Technical Training by Extension Officers to support to on-farm and off-farm income-generating activities and the provision of small grants and high seed capital to increase yields Activity 2.4: Financial and market inclusion Indicative Activities: Access to finance through the promotion of internal savings and lending schemes and promoting the farm business linkage stakeholder platforms Activity 2.5: Productive renewable energy for diversified livelihood options Indicative Activities: Promote the use of productive renewable energy for diverse livelihood options | UNDP, Ministry of Agriculture | 540,043.00 |
| Project Output 3: Strengthened governance capacity for resilience and human security. (UNDP CPD Output 4.1) (Outcome indicator 4.2.1) Baseline: Indicators: - Number of policies and frameworks developed that enhance the delivery of governance services. - Number of citizens accessing essential services in border communities. Disaggregated by type of services, gender, age, disability. - Number of citizens empowered to claim their rights and participate in local development processes. - Early warning and early response platform/system developed and deployed for use. CPD Indicator: 4.2.1. Number of draft laws, policies and plans relevant to administrative and fiscal reforms developed and submitted to Cabinet and Parliament. | Targets Indicator 3.1: At least 1 policies or frameworks developed and/or strengthened to improve delivery, coordination, and accountability in governance service provision. Targets Indicator 3.2: At least 3,000 citizens in border communities access essential services Establishment of 3 satellite offices to be utilised for the provision of social services Target Indicator 3.3: At least 3,000 citizens (50% women, 30% youth, 10% persons with disabilities) empowered through awareness sessions, training, and platforms to claim rights and actively participate in local development and governance processes. Target Indicator 3.3: A functional Early Warning and Early Response (EWER) system developed, piloted, and deployed in at least 3 border districts, with local authorities and communities trained in its use. | Activity 3.1. Strengthen Policy and regulatory frameworks, coordination, institutional planning for resilience in border communities. Indicative Activities: Development of coordination frameworks for devolved service delivery in line with devolution policy; strengthening community coordination structures; development of gender and inclusion sensitive policy and regulatory frameworks, coordination and institutional planning for resilience at the sub-national level Activity 3.2. Promote decentralized capacities of governance structures and systems for effective delivery of services in border communities. Indicative Activities: Support harmonization of service delivery infrastructure and subnational level; Conduct collaborative SGBV Mobile One Stop Centres for Women and Children in border communities. Activity 3.3. Support spatial governance and planning systems for enhancing effective utilization of de-mined land in border communities. Indicative Activities: Support the development of key frameworks to support the effective utilization of demined areas. Activity 3.4. Support the development of platforms for and empowerment of marginalized groups to participate in local planning, budgeting, and decision-making processes. Indicative Activities: Support organic community grievance redress infrastructure; Conduct dialogue, engagement, and accountability mechanisms for stakeholder and civic participation. Activity 3.5. Support the development and operationalization of community early warning systems, conflict management strategies, disaster risk plans and contingency planning. Indicative Activities: Operationalize an integrated multi-hazard mechanism for early warning and detection of areas of potential conflicts and disputes as a basis for informing appropriate prevention measures. Activity 3.6. Support community awareness campaigns and information-sharing platforms/hubs on social cohesion within border communities. Indicative Activities: Conduct advocacy and awareness campaigns through community radios, social media, community events, and educational institutions to inform people about the importance harmonious community existence drawing from normative frameworks such as of UNSC Resolutions 1325 on women and peace and 2250 on youth in peace to elaborate the critical roles these groups play towards attainment of human security. | UNDP | 358,586.00 |
| Project Management and related costs |  | GMS, RCO Levy, Communication, M&E, GMR, Direct Management Costs – 11% (Human Resource Costs USD$247,000; finance, procurement administration, issuance of contracts, security, travel, general services and information and communications technology USD$39,000) |  | 901,379.12 |
| Total |  |  |  | 3,317,408.24 |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans: [Note: monitoring and evaluation plans should be adapted to project context, as needed]

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. | GoZ, UNDP, HALO, MAG | USD$3,000 |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. | UNDP | USD$7,000 |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. | GoZ, UNDP | USD$3,000 |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. | UNDP | USD$5,000 |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. | Project Board | USD$5,000 |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) |  | GoZ, UNDP, HALO, MAG | USD$2,000 |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | At least once a year and most 3 times (i.e., at least annually) | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. | Project Board | USD$6,200 |

# Multi-Year Work Plan  (See Attached Workplan)

All anticipated programmatic and operational costs to support the project, including development effectiveness and implementation support arrangements, need to be identified, estimated and fully costed in the project budget under the relevant output(s). This includes activities that directly support the project, such as communication, human resources, procurement, finance, audit, policy advisory, quality assurance, reporting, management, etc. All services which are directly related to the project need to be disclosed transparently in the project document.

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Y1 2025 | Y2 2026 | Y3 2027 | Y4 2028 |  | Funding Source | Budget Description Codes | Amount |
| Output 1: Release of land and destruction of anti-personnel landmines Gender marker: 1 | - Activity Land clearance and land reduction | 75,000.00 | 793,798.62 | 558,601.50 |  | HALO MAG | 00141 | 72200/75700 | 1,427,400.12 |
|  | - Activity Establish community grievance mechanism, conduct community safeguarding trainings (SESP) and monitor social environmental risks |  | 14,500.00 | 14,500.00 | 11,000.00 | UNDP | 00141 | 71600/75700 | 40,000.00 |
|  | - Activity Conduct landmine victim survey |  | 50,000.00 |  |  | Ministry of Defence/UNDP | 00141 | 71300/71600/72410/74200/75700/ | 50,000.00 |
|  | Sub-Total for Output 1 |  |  |  |  |  |  |  | 1,517,400.12 |
| Output 2: Diversified livelihood opportunities and infrastructure for resilience (UNDP CPD Output 2.1 and 2.3) Gender marker: 2 | 2.1 Activity Infrastructure development for productive use and ensuring access to social services |  | 10,000.00 | 120,000.00 | 95,000.00 | Ministry of Agriculture/Ministry of Defence/UNDP | 00141 | 71600/72100/74700/75700 | 225,000.00 |
|  | 2.2 Activity Facilitating vocational skills and entrepreneurship development for skills transfer, and employment creation and ensure youths' and women's economic empowerment. |  | 27,500.00 | 63,500.00 | 5,000.00 | Ministry of Agriculture/Ministry of Defence/UNDP | 00141 | 71300/71600/72100/75700 | 96,000.00 |
|  | 2.3 Activity Support to on-farm and off-farm income-generating activities and provision of small grants seed capital for projects |  | 32,000.00 | 62,500.00 |  | Ministry of Agriculture/Ministry of Defence/UNDP | 00141 | 71300/71600/72100/74200/75700 | 94,500.00 |
|  | 2.4 Activity Promote inclusive, viable and sustainable value chains and market linkages including agro-processing and value addition |  | 17,000.00 | 44,800.00 |  | Ministry of Agriculture/Ministry of Defence/UNDP | 00141 | 71300/71600/72100/74200/75700/ | 61,800.00 |
|  | 2.5 Activity Promote the use of productive renewable energy for diverse livelihood options |  |  | 62,743.00 |  | Ministry of Agriculture/Ministry of Defence/UNDP | 00141 |  | 62,743.00 |
|  | Sub-Total for Output 2 |  |  |  |  |  |  |  | 540,043.00 |
| Output 3: Strengthened governance capacity for resilience and human security. (UNDP CPD Output 4.1) Gender marker: 2 | 3.1 Activity Strengthen Policy and regulatory frameworks, coordination, institutional and planning for resilience in border communities. | 30,000.00 | 17,670.00 | 17,670.00 | 24,660.00 | Min of Defence/UNDP | 00141 | 71300/71600/74200/75700 | 90,000.00 |
|  | 3.2 Activity Promote decentralized capacities of governance structures and systems for effective delivery of services in border communities. |  | 105,000.00 |  |  | UNDP | 00141 | 71600/72100/75700 | 105,000.00 |
|  | 3.3 Activity Support spatial governance and planning systems for enhancing effective utilization of released land in border communities. |  | 38,440.00 |  |  | Min of Local Government/Ministry of Defence/UNDP | 00141 | 71300/71600/74200/75700 | 38,440.00 |
|  | 3.4 Activity Support the development of platforms for and empowerment of marginalized groups to participate in local planning, budgeting, and decision-making processes. |  | 17,790.00 | 17,790.00 | 18,850.00 | UNDP/Min of Public Service/Ministry of Local Government | 00141 | 71300/71600/72100/72410/75700 | 54,430.00 |
|  | 3.5 Activity Support the development and operationalisation of community early warning systems, conflict management strategies, disaster risk plans and contingency planning |  |  | 45,311.00 | 8,880.00 | Ministry of Defence/Ministry of Agriculture/UNDP | 00141 | 71600/74200/74700/75700 | 54,191.00 |
|  | 3.6 Activity Support community awareness campaigns and information-sharing platforms/hubs on security, Conflict Resolution Explosive Ordinance Risk Education, Peace, GBV, Victim support and human rights issues within border communities. |  | 11,125.00 | 30,125.00 | 5,275.00 | Min of Defence/UNDP | 00141 | 71600/74200/74700/75700 | 46,525.00 |
|  | Sub-Total for Output 3 |  |  |  |  |  |  |  | 358,586.00 |
| Direct Management Costs |  | 17,016.17 | 206,459.69 | 206,459.69 | 142,209.26 |  | 00141 |  | 572,144.81 |
| Indirect Costs - security, travel, general services and information and communications technology |  | 800.00 | 6,000.00 | 10,000.00 |  |  | 00141 |  | 16,000.00 |
| Monitoring & Evaluation and Communications |  | 12,530.00 | 6,000.00 | 10,000.00 | 20,000.00 |  | 00141 |  | 36,000 |
| Audit |  | 3,800.00 |  | 10,000.00 | 10,000.00 |  |  |  | 20,000.00 |
| Global Monitoring, Advocacy, and Reporting |  |  | 6,000.00 | 10,000.00 | 8,000.00 |  | 00141 |  | 24,000.00 |
| General Management Support |  | 7,761.29 | 96,193.65 | 91,371.00 | 20,778.37 |  | 00141 |  | 216,104.31 |
| Sub-Total Project Costs |  | 24,777.46 | 216,290.64 | 233,467.99 | 126,843.03 |  |  |  | 901,379.12 |
| Coordination Levy |  | 29,174.08 |  |  |  |  |  |  | 29,174.08 |
| TOTAL (Excluding Coordination Levy) |  | 99,777.46 | 1,301,114.26 | 1,236,008.49 | 280,508,.03 |  |  |  | 3,317,408.24 |

RISK MITIGATION MEASURES FRAMEWORK Risk management is one of the core pillars of the accountability framework for the programme and it enhances the understanding of the potential upside and downside of factors that can affect the programming. Risk management increases the probability of success and reduces both the probability of failure, and the level of uncertainty associated with achieving the objectives of the programme. A risk registry has been developed (see Table 1: Risk Matrix below) as part of a risk management framework to ensure that priority risks are identified, monitored, analysed, and mitigated. Key broad categories of risks identified will be monitored every quarter and these include contextual, political, financial, reputational, and delivery risks. TYPE; DESCRIPTION; Impact; Likelihood; COUNTERMEASURES / MNGT RESPONSE/MITIGATION MEASURES; OWNER. Strategic; The sustained commitment to prioritise and invest in long-term resilience-building efforts may vary due to competing development priorities; Substantial; Low; The UNDP will continue to build the evidence base for resilience interventions and advocate with government and partners for inclusion in policy and programming decisions; Steering Committee. Environmental; Presence and management of residual contamination; Moderate; Medium; GoZ will work together with landmine-operating NGOs to manage residual contamination through the residual contamination strategy.; GoZ/ZIMAC. Potential natural weather phenomena (drought, floods, cyclones); Substantial; Medium; Prioritisation of activities and adaptive planning; UNDP and development partners. Project beneficiaries at risk from crossing into demining areas; Substantial; Low; Project will invest and strengthen EORE component (mine risk education for all beneficiaries); GoZ, Mine Operators, ZIMAC. Occupational Health and Safety; High; Medium; Adequate safeguarding measures. Ensure that mine operators adhere to strict protocols, procedures and utilise adequate Personal Protective Equipment (PPE); GoZ/ZIMAC/Mine Operators. Political; Community access may be delayed due to the need for alignment with local leadership structures and coordination protocols; Substantial; Low; Close engagement and cooperation with central and local authorities and traditional leadership will show the value added for communities; essential operational activities or events will not be planned during certain time periods around the elections. Grantees continue to work with existing government structures for sustainability and easy access to communities.; UNDP, Government, and partners. Economic; Reduced donor and government funds; High; Medium; Build a base of potential co-donors, and partner government and identify/raise private sector resources to work within existing structures.; UNDP, Donors, and Government. Liquidity is constrained and markets are not functioning properly; Substantial; Medium; The liquidity constraint is currently affecting the way partners and the market can operate. UND will work closely with its partners and government to minimize the impact.; Steering Committee. Inflation and multi-tier pricing systems prevailing on the market. This affects grantees budgets; Substantial; Medium; Risk monitoring and analysis every month to understand the impact on programming and operation and possible solutions. Regular meetings will be conducted with partners to find ways to minimize the impact.; UNDP Implementing Partners and Grantees. Social; Vulnerable beneficiaries being left behind (women, youth, PWDs); High; Low; Project interventions will utilise a beneficiary selection criterion that prioritises the most vulnerable; GOZ/Community Leadership/Mine operators.

# Governance and Management Arrangements

Project Board and Oversight

A Project Board will provide strategic oversight and guidance in the implementation of the project in accordance with UNDP Programming rules and regulations. The Board will be co-chaired by the Government of Zimbabwe (Ministry of Defence) and UNDP with membership comprising the Ministry of Lands, Agriculture, Fisheries, Water and Rural Development, the Government of Japan, Zimbabwe Mine Action Centre (ZIMAC), HALO Trust, Mines Advisory Group (MAG), and other key stakeholders who will be roped on an activity and need basis. These will include the Ministry of Finance, Economic Development and Investment Promotion, Ministry of Public Service, Labour and Social Welfare, Ministry of Women Affairs, Community, Small and Medium Enterprises Development and the Zimbabwe Gender Commission. It will meet at least once and up to three times per year to review progress, address implementation challenges, and ensure responsiveness to stakeholder feedback. It will also receive regular progress reports, monitoring and evaluation reports to ensure the project remains on track. UNDP and the Government of Japan will jointly agree on financial, procurement, and other relevant policies to as stipulated in the funding agreement signed on the 15th of August 2025. Terms of Reference for the Board will be developed.

# Legal Context

# Option a. Where the country has signed the Standard Basic Assistance Agreement (SBAA)

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Zimbabwe and UNDP, signed on 27 May 1980.   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

UNDP (DIM)

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism , that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Project Document, UNDP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor, and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - Each responsible party, subcontractor and sub-recipient (each a “sub-party” and together “sub-parties”) acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the sub-parties, and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, each sub-party shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, each sub-party, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

  - In the performance of the activities under this Project Document, each sub-party shall (with respect to its own activities), and shall require from its sub-parties (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, sub-parties will and will require that their respective sub-parties will take all appropriate measures to:

(i) Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

(ii) Offer employees and associated personnel training on prevention and response to SH and SEA, where sub-parties have not put in place its own training regarding the prevention of SH and SEA, sub-parties may use the training material available at UNDP;

(iii) Report and monitor allegations of SH and SEA of which any of the sub-parties have been informed or have otherwise become aware, and status thereof;

(iv) Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

(v) Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. Each sub-party shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the relevant sub-party shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

  - Each sub-party shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the relevant sub-party to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

  - Each responsible party, subcontractor and sub-recipient will ensure that any project activities undertaken by them will be implemented in a manner consistent with the UNDP Social and Environmental Standards and shall ensure that any incidents or issues of non-compliance shall be reported to UNDP in accordance with UNDP Social and Environmental Standards.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud, corruption or other financial irregularities, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption, anti-fraud and anti-money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption other financial irregularities with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - Each responsible party, subcontractor or sub-recipient agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud corruption or other financial irregularities or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

Special Clauses. In case of government cost-sharing through the project, the following clauses should be included:

- The schedule of payments and UNDP bank account details.

- The value of the payment, if made in a currency other than United States dollars, shall be determined by applying the United Nations operational rate of exchange in effect on the date of payment.  Should there be a change in the United Nations operational rate of exchange prior to the full utilization by the UNDP of the payment, the value of the balance of funds still held at that time will be adjusted accordingly.  If, in such a case, a loss in the value of the balance of funds is recorded, UNDP shall inform the Government with a view to determining whether any further financing could be provided by the Government.  Should such further financing not be available, the assistance to be provided to the project may be reduced, suspended or terminated by UNDP.

- The above schedule of payments takes into account the requirement that the payments shall be made in advance of the implementation of planned activities.  It may be amended to be consistent with the progress of project delivery.

- UNDP shall receive and administer the payment in accordance with the regulations, rules and directives of UNDP.

- All financial accounts and statements shall be expressed in United States dollars.

- If unforeseen increases in expenditures or commitments are expected or realized (whether owing to inflationary factors, fluctuation in exchange rates or unforeseen contingencies), UNDP shall submit to the government on a timely basis a supplementary estimate showing the further financing that will be necessary. The Government shall use its best endeavours to obtain the additional funds required.

- If the payments referred above are not received in accordance with the payment schedule, or if the additional financing required in accordance with paragraph 6 above is not forthcoming from the Government or other sources, the assistance to be provided to the project under this Agreement may be reduced, suspended or terminated by UNDP.

- Any interest income attributable to the contribution shall be credited to UNDP Account and shall be utilized in accordance with established UNDP procedures.

In accordance with the decisions and directives of UNDP's Executive Board:

The contribution shall be charged:

- 8% cost recovery for the provision of general management support (GMS) by UNDP headquarters and country offices

- Direct cost for implementation support services (ISS) provided by UNDP and/or an executing entity/implementing partner.

- Ownership of equipment, supplies and other properties financed from the contribution shall vest in UNDP.  Matters relating to the transfer of ownership by UNDP shall be determined in accordance with the relevant policies and procedures of UNDP.

- The contribution shall be subject exclusively to the internal and external auditing procedures provided for in the financial regulations, rules and directives of UNDP.”

# ANNEXES

- Project Quality Assurance Report

- Risk Register

- ANNEX 2: OFFLINE PROJECT RISK REGISTER TEMPLATE

| Project Title: | Project Number: | Date: Click or tap to enter a date. |
| --- | --- | --- |

| # | Event | Cause | Impact(s) | Risk Category and Sub-category (including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (individual accountable for managing the risk) | Risk Treatment and Treatment Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | There is a risk of Vulnerable beneficiaries being left behind (women, youth, PWDs | As a result of Cultural norms, lack of gender-sensitive strategies, limited outreach to women. | Which will impact in missed opportunities for women’s empowerment Reduced social inclusion of men, women, youths and people leaving with disabilities | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 15-Aug-25 To: 15-Aug-28 | Tafadzwa Muvingi | Risk Treatment 1.1: Project interventions will utilize a beneficiary selection criterion that prioritizes the most vulnerable Risk Treatment Owner: Tafadzwa Muvingi |
|  |  |  |  |  |  |  |  | Risk Treatment 1.2: The project will develop meaningful engagement and Participation of Women and Youth in National Development Processes including on Youth, Peace and Security, and Women, Peace and Security. Risk Treatment Owner: Tafadzwa Muvingi |
| 2 | There is a risk of improper disposal of explosive remnants | As a result of Land Release & Demining Inadequate technical capacity, weak enforcement of disposal protocols, lack of monitoring | Which will impact environmental pollution and and risk of accidents | 1. SOCIAL AND ENVIRONMENTAL (1.6. Community health, safety and security) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 2 - Low likelihood Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 15-Aug-25 To: 15-Aug-28 | Tafadzwa Muvingi | Risk Treatment 2.1: GoZ will work together with landmine-operating NGOs to manage residual contamination through the approved National Mine Action Standards. Risk Treatment Owner: Tafadzwa Muvingi |
|  |  |  |  |  |  |  |  | Risk Treatment 2.2: The projects will comply with the Environmental Management Act and Statutory Instrument (SI) 10 of 2007 on handling of Hazardous substances and SI 268 of 2018 which prohibits the discharge the hazardous substances into the environment. Risk Treatment Owner: Tafadzwa Muvingi |
| 3 | There is a risk of Potential natural weather phenomena (drought, floods, cyclones) | As a result of the project location area vulnerable to climate change impacts such as flash floods and drought including natural disasters that deepen already prevailing extreme issues | Which will impact in Water depletion is causing agriculture challenge. Damage to project infrastructure | 1. SOCIAL AND ENVIRONMENTAL (1.5. Climate change and disaster risks) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 2 - Low likelihood Impact: 3 - Intermediate Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 15-Aug-25 To: 15-Aug-28 | Tafadzwa Muvingi | Risk Treatment 3.1: Prioritization of activities and adaptive planning Risk Treatment Owner: Tafadzwa Muvingi |
|  |  |  |  |  |  |  |  | Risk Treatment 3.2: The project will develop climate resilience infrastructure for productive use. Risk Treatment Owner: Tafadzwa Muvingi |
|  |  |  |  |  |  |  |  | Risk Treatment 3.3: The project will build capacity on climate change, early warning and resilient practice. Risk Treatment Owner: Tafadzwa Muvingi |
| 4 | There is a risk that Project beneficiaries at risk from crossing into demining areas | As a result of a lack of knowledge and an absence of warning signs | Which will have an impact of either injuries or loss of life | 1. SOCIAL AND ENVIRONMENTAL (1.6. Community health, safety and security) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 4 - Highly likely Impact: 2 - Minor Risk level: PLEASE SELECT | From: 15-Aug-25 To: 15-Aug-28 | Tafadzwa Muvingi | Risk Treatment 4.1: Communities will be sensitized to the dangers of getting into the mining area Risk Treatment Owner: Tafadzwa Muvingi |
|  |  |  |  |  |  |  |  | Risk Treatment 4.2: The project will implement Environmental, Health and Safety measure including warning signs Risk Treatment Owner: Tafadzwa Muvingi |
|  |  |  |  |  |  |  |  | Risk Treatment 4.3: … Risk Treatment Owner: … |
| 5 | There is a risk of accidents/injuries during demining activities | As a result of demining activities | Which will impact project timelines and delays due to physical injuries and/or loss of life | 3. OPERATIONAL (3.7. Occupational safety, health and well-being) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 3 - Moderately likely Impact: 2 - Minor Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 15-Aug-25 To: 15-Aug-28 | Tafadzwa Muvingi | Risk Treatment 5.1: project will use trained/ qualified de-mining operators Risk Treatment Owner: … |
|  |  |  |  |  |  |  |  | Risk Treatment 5.2: Strict adherence to protocols and procedures (for example International Mine Action Standards) Risk Treatment Owner: Tafadzwa Muvingi |
|  |  |  |  |  |  |  |  | Risk Treatment 5.3: Ensure there is adequate Personal Protective Equipment (PPE) and monitor its utilization Risk Treatment Owner: Tafadzwa Muvingi |
| 6 | There is a risk Land Use Rights/Land-use conflicts | As a result of cleared land being made available to the communities | Which will impact livelihood opportunities | 1. SOCIAL AND ENVIRONMENTAL (1.4. Biodiversity conservation and sustainable natural resource management) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 2 - Low likelihood Impact: 2 - Minor Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 15-Aug-25 To: 15-Aug-28 | Tafadzwa Muvingi | Risk Treatment 6.1: The project will engage the relevant government ministries and departments responsible for land allocation post de-mining. Risk Treatment Owner: Tafadzwa Muvingi |
|  |  |  |  |  |  |  |  | Risk Treatment 6.2: The project will support stakeholder engagements, inclusive consultations, clear land-use agreements. Risk Treatment Owner: … |
|  |  |  |  |  |  |  |  | Risk Treatment 6.3: … Risk Treatment Owner: … |
| 7 | There is a risk that Pollution from agrochemicals | As a result ofTafa increased agriculture production | Which will impact agricultural production | 1. SOCIAL AND ENVIRONMENTAL (1.11. Pollution prevention and resource efficiency) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 2 - Low likelihood Impact: 2 - Minor Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 15-Aug-25 To: 15-Aug-28 | Tafadzwa Muvingi | Risk Treatment 7.1: The project promote Integrated Pest Management (IPM), which minimizes chemical use by combining biological, cultural, and targeted chemical tactics Risk Treatment Owner: Tafadzwa Muvingi |
|  |  |  |  |  |  |  |  | Risk Treatment 7.2: The project will ensure proper storage handling and disposal of chemicals and containers Risk Treatment Owner: Tafadzwa Muvingi |
|  |  |  |  |  |  |  |  | Risk Treatment 7.3: … Risk Treatment Owner: … |

- Social and Environmental Screening Template [English] [French] [Spanish], including additional Social and Environmental Assessments or Management Plans as relevant. (NOTE: The SES Screening is not required for projects in which UNDP is Administrative Agent only and/or projects comprised solely of reports, coordination of events, trainings, workshops, meetings, conferences, preparation of communication materials, strengthening capacities of partners to participate in international negotiations and conferences, partnership coordination and management of networks, or global/regional projects with no country level activities).

Project Reclaim SESP.docx

- Capacity Assessment: Results of capacity assessments of Implementing Partner (including Partner Capacity Assessment Tool (PCAT) and HACT Micro Assessment)

- Project Board Terms of Reference and TORs of key management positions. The standard Project Board TOR can be found here.

2022 Population and Housing Census (PHC)

ibid.

https://hdr.undp.org/content/human-development-report-2025

https://countryeconomy.com/hdi/zimbabwe

Poverty and Equity Brief: World Bank

6th Request for Extension of the Deadline for Fulfilment of Obligations Under Article 5 of the Convention on the Prohibition of the Use, Stockpiling, Production and Transfer of Anti-Personnel Mines and their Destruction

PM Kishida’s Closing Remarks at the TICAD 8

https://www.mineactionstandards.org/standards/

Request for Extension of the Deadline for Fulfilment of Obligations Under Article 5 of the Convention on the Prohibition of the Use, Stockpiling, Production and Transfer Of Anti-Personnel Mines and Their Destruction

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards.  Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a project budget affecting the scope (outputs), completion date, or total estimated project costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner