## Guidelines
This file contains three specific planning tools to complete the supplementary information required when submitting a proposal for Readiness Programme support (including for Objetive 3. Aptation planning):
- Budget plan and accompany Budget notes - Procurement and HR plan - Implementation plan
The following considerations are important when completing the budget:
1. Before preparing the Readiness and budget, procurement and HR, and implementation plans, please read the full guidance contained in the Readiness Programme Guidebook, specifically Part IV Sections 5 and 6
2. You can select the appropriate budget categories from the dropdown list in the budget plan:
3. To insert additional rows, right click on the row number below where you wish to insert the new row and choose INSERT.
4. Additional budget categories may be added by manually typing them on the Budget Category sheet:
5. The Budget Notes sheet should be used to record explanations, further details or cost breakdowns for individual lines
Project Management Cost:
Project management costs (PMC) are the direct administrative costs incurred to execute a grant. They should cover only incremental costs incurred due to the GCF contribution. In most cases, these costs are directly related to the support of a dedicated project management unit which manages the day to day execution related activities of the grant.
General Principles for PMC costs:
1. The percentage of PMC financed by GCF should not be more than the percentage share of the overall budget financed by GCF
2. PMC budget thresholds: Up to 7.5 per cent of total activity budget.
> PMC exceeding 7.5 per cent for the readiness (including NAPs) proposals, up to $ 3 million will require detailed documentation
and justification supporting the entire PMC budget.
> The PMC should be shown as a separate component in the project budget. A detailed breakdown of PMC should be provided by budget category.
> Indicative list of eligible project management costs:
> Project staffing and consultants: Project manager, Project Assistant, Procurement personnel, Finance personnel & Support/admin. Personnel
> Other direct costs: Office equipment, Mission related travel cost of the PMU, Project management systems and information technology,
Office supplies, Audit cost
Contingency :
1. Select the appropriate % of Contingency Budget from the dropdown list :
2. Contingency budget for unforeseen costs arising during the grant implementation should not be included in the outcome budget separately.
3. Contingency budget must be used for any unforeseen programme (output level) cost that is unrelated to implementation/service fee.
4. Any use of contingency must be reported to and agreed by the GCF Secretariat in writing in advance provided with justifications that are acceptable to the GCF.
5. If by the end of the grant implementation period, you have not spent Contingency, you may not increase the scope of the project or make any other expenditures using the Contingency.
If you are unsure about how to complete the budget template, please send your query to: countries@gcfund.org
Readiness Grant Budget Preparation Guidelines

## Budget Category
Budget Categories
Audio Visual & Printing
Audit Fee
Consultant - Individual - International
Consultant - Individual - Local
Professional Services – Companies/Firm
IT Equipment
Office Supplies
Travel - International
Travel – Local
Workshop/Training
Services to Project | Indicate additional budget categories
Contractual Services- Individual
Miscellaneous
IT Equipment
Choose percentage
0
1%
2%
3%

## 6.1 Budget Plan
6.1 Budget Plan
Please add rows for Outcomes, Outputs and Cost Categories as required. Additional budget categories may be added by manually typing them on the Budget Category sheet.
Objectives/Outcomes / Outputs |  |  | Detailed Budget (in US$) | [5 empty] | Total Budget (per outcome) | Expenditure Plan |  |  |  | Executing Entity | Budget notes
|  |  | Budget Categories choose from the drop-down list | Unit | # of Unit | Unit Cost | Total Budget (per budget category) | Total Budget (per sub-outcome) |  | Year 1 | Year 2 | Year 3 | Year 4
Objective 3: National Adaptation Plans and Adaptation Planning Processes | Outcome 3.1 - Adaptation planning governance and institutional coordination strengthened | Output 3.1.1 - National, sub-national and/or sectoral adaptation plans developed or updated | Professional Services – Companies/Firm | Lumpsum | 1 | 160000 | 160000 | 210144 | 1153144 | 160000 | 0 | 0 | 0 | UNDP | A
|  |  | Workshop/Training | Event | 5 | 5000 | 25000 |  |  | 25000 | 0 | 0 | 0 | UNDP | B
|  |  | Miscellaneous | Annual | 4 | 1486 | 5944 |  |  | 1486 | 1486 | 1486 | 1486 | UNDP | AM
|  |  | Contractual Services- Individual | Month | 9 | 1800 | 16200 |  |  | 4050 | 4050 | 4050 | 4050 | UNDP | AI
|  |  | Travel - International | Trip | 1 | 3000 | 3000 |  |  | 3000 | 0 | 0 | 0 | UNDP | C
|  | Output 3.1.2 - Adaptation policy and/or regulations developed or strengthened for integrating adaptation actions/measures in sectoral, subnational and national development strategies and plans | Professional Services – Companies/Firm | Lumpsum | 1 | 140000 | 140000 | 168000 |  | 140000 | 0 | 0 | 0 | UNDP | D
|  |  | Workshop/Training | Event | 5 | 5000 | 25000 |  |  | 25000 | 0 | 0 | 0 | UNDP | E
|  |  | Travel - International | Event | 1 | 3000 | 3000 |  |  | 3000 | 0 | 0 | 0 | UNDP | G
|  | Output 3.1.3 - Inter and intra institutional coordination and decision-making mechanisms established or strengthened | Professional Services – Companies/Firm | Lumpsum | 1 | 140000 | 140000 | 369500 |  | 80000 | 60000 | 0 | 0 | UNDP | H
|  |  | Consultant - Individual - Local | W/M | 48 | 2000 | 96000 |  |  | 24000 | 24000 | 24000 | 24000 | UNDP | I
|  |  | Workshop/Training | Event | 1 | 18750 | 18750 |  |  | 18750 | 0 | 0 | 0 | UNDP | J
|  |  | Workshop/Training | Event | 1 | 15000 | 15000 |  |  | 15000 | 0 | 0 | 0 | UNDP | K
|  |  | Workshop/Training | Event | 1 | 3750 | 3750 |  |  | 3750 | 0 | 0 | 0 | UNDP | L
|  |  | Workshop/Training | Event | 18 | 5000 | 90000 |  |  | 45000 | 45000 | - | - | UNDP | L2
|  |  | Travel - International | Trip | 2 | 3000 | 6000 |  |  | 3000 | 3000 | 0 | 0 | UNDP | M
|  | Output 3.1.4 - Stakeholder engagement frameworks, agreements and awareness raising conducted or strengthened | Professional Services – Companies/Firm | Lumpsum | 1 | 160000 | 160000 | 405500 |  | 0 | 80000 | 80000 | 0 | UNDP | N
|  |  | Consultant - Individual - Local | W/M | 36 | 3000 | 108000 |  |  | 0 | 36000 | 36000 | 36000 | UNDP | O
|  |  | Workshop/Training | Event | 10 | 3750 | 37500 |  |  | 0 | 25000 |  | 12500 | UNDP | P
|  |  | Workshop/Training | Event | 10 | 5000 | 50000 |  |  | 0 | 25000 | 25000 | 0 | UNDP | Q
|  |  | Workshop/Training | Event | 10 | 5000 | 50000 |  |  | 0 | 25000 | 25000 | 0 | UNDP | R
| Outcome 3.2 - Evidence produced to design adaptation solutions for maximum impact | Output 3.2.1 - Adaptation impact monitoring, evaluation and learning systems established or strengthened for strategic planning and investment | Professional Services – Companies/Firm | Lumpsum | 1 | 120000 | 120000 | 185644 | 386588 | 0 | 120000 | 0 | 0 | UNDP | S
|  |  | Consultant - Individual - Local | W/M | 12 | 3000 | 36000 |  |  | 0 | 36000 | 0 | 0 | UNDP | U
|  |  | Miscellaneous | Annual | 4 | 1486 | 5944 |  |  | 1486 | 1486 | 1486 | 1486 | UNDP | AM
|  |  | Workshop/Training | Events | 1 | 7500 | 7500 |  |  | 0 | 7500 | 0 | 0 | UNDP | V
|  |  | Contractual Services- Individual | Month | 9 | 1800 | 16200 |  |  | 4050 | 4050 | 4050 | 4050 | UNDP | AI
|  | Output 3.2.2 - Studies on climate vulnerability, and identification of adaptation solutions conducted (and used) for strengthening adaptation investment | Professional Services – Companies/Firm | Lumpsum | 1 | 195000 | 195000 | 200944 |  | 0 | 0 | 195000 | 0 | UNDP | W
|  |  | Miscellaneous | Annual | 4 | 1486 | 5944 |  | 322450 | 1486 | 1486 | 1486 | 1486 | UNDP | AM
| Outcome 3.3 - Private sector engagement in adaptation catalized | Output 3.3.1 - Strategies, policies, and incentives developed to foster private investment in adaptation solutions | Professional Services – Companies/Firm | Lumpsum | 1 | 110000 | 110000 | 128750 |  | - | - | 110000 | - | UNDP | W1
|  |  | Workshop/Training | Event | 5 | 3750 | 18750 |  |  | - | - | 18750 | - | UNDP | W2
|  | Output 3.3.3 - Capacity building provided to the private sector on adaptation options | Professional Services – Companies/Firm | Lumpsum | 1 | 140000 | 140000 | 193700 |  | 0 | 0 | 100000 | 40000 | UNDP | Z
|  |  | Workshop/Training | Event | 10 | 3750 | 37500 |  |  | 0 | 0 | 12500 | 25000 | UNDP | AA
|  |  | Contractual Services- Individual | Monthly | 9 | 1800 | 16200 |  |  | 4050 | 4050 | 4050 | 4050 | UNDP | AI
| Outcome 3.4 - Adaptation finance increased | Output 3.4.1 - Mechanisms established to prioritize adaptation options based on objective criteria | Professional Services – Companies/Firm | Lumpsum | 1 | 120000 | 120000 | 167144 | 296394 | 0 | 0 | 100000 | 20000 | UNDP | AB
|  |  | Contractual Services- Individual | Monthly | 9 | 1800 | 16200 |  |  | 4050 | 4050 | 4050 | 4050 | UNDP | AI
|  |  | Miscellaneous | Annual | 4 | 1486 | 5944 |  |  | 1486 | 1486 | 1486 | 1486 | UNDP | AM
|  |  | Workshop/Training | Event | 5 | 5000 | 25000 |  |  | 0 | 0 | 15000 | 10000 | UNDP | AC
|  | Output 3.4.2 - Number of concept notes and/or funding proposals developed for adaptation priority actions | Professional Services – Companies/Firm | Lumpsum | 1 | 120000 | 120000 | 129250 |  | 0 | 0 | 80000 | 40000 | UNDP | AD
|  |  | Workshop/Training | Event | 2 | 3125 | 6250 |  |  | 0 | 0 | 3000 | 3250 | UNDP | AE
|  |  | Travel - International | Trip | 1 | 3000 | 3000 |  |  | 0 | 0 | 3000 | 0 | UNDP | AF
Total Outcome Budget | [8 empty] | 2158576 | 567644 | 508644 | 849394 | 232894 | 0
Project Management Cost (PMC) Up to 7.5% of Total Activity Budget |  |  | Contractual Services- Individual | Month | 12 | 1800 | 21600 | Actual amount and % of PMC requested: | Maximum PMC that can be requested: | 5400 | 5400 | 5400 | 5400 | UNDP | AI
|  |  | Contractual Services- Individual | Month | 48 | 1500 | 72000 |  |  | 18000 | 18000 | 18000 | 18000 | UNDP | AJ
|  |  | Contractual Services- Individual | Month | 12 | 1500 | 18000 | do not change the formula | do not change the formula | 6000 | 12000 | 0 | 0 | UNDP | AK
|  |  | Audit Fee | Year | 4 | 4000 | 16000 |  |  | 4000 | 4000 | 4000 | 4000 | UNDP | AL
|  |  | Services to Project | Lumpsum | 4 | 3300 | 13200 | 149200 | 161893.2 | 3300 | 3300 | 3300 | 3300 | UNDP | AN
|  |  | Office Supplies | Lumpsum | 4 | 2100 | 8400 | 6.912% | 7.5% | 2100 | 2100 | 2100 | 2100 | UNDP | AO
FOR GREEN CLIMATE FUND SECRETARIAT'S USE ONLY
Breakdown (per budget category) |  |  | Total (per budget category)
Audit Fee |  |  | 16000
IT Equipment |  |  | 0
Miscellaneous |  |  | 23776
Consultant - Individual - Local |  |  | 240000 |  |  |  | FOR GREEN CLIMATE FUND SECRETARIAT'S USE ONLY
Professional Services – Companies/Firm |  |  | 1405000
Travel - International |  |  | 15000 |  |  |  | Total Outcome Budget | [6 empty] | 2158576
Workshop/Training |  |  | 410000 |  |  |  | Project Management Cost (PMC) |  | 6.912% | requested |  |  |  | 149200
Services to Project |  |  | 13200 |  |  |  | Contingency | 0% |  | requested |  |  |  | 0
Office Supplies |  |  | 8400
Contractual Services- Individual |  |  | 176400
Total Outcome Budget + PMC |  |  | 2307776
[7 empty] | Sub-Total (Total Outcome Budget + Contingency + PMC) | [6 empty] | 2307776
[7 empty] | Delivery Partner Fee (DP) - Up to 8.5% of the Sub-Total | [6 empty] | 196160.96
[7 empty] | Total Project Budget (Total Activity Budget + Contingency + PMC + DP) | [5 empty] | 2503937

## Budget Notes
Budget Notes
Please check out the example in the table below, and remove them before including the proposal's entries
Budget Note | Detailed Description
A | Professional services - Firm (Consulting Company 1 – Sectoral Planning and Adaptation Framework Consulting Company): to engage a firm for USD 160,000 lumpsum to implement activity 3.1.1 (Sub-activity 3.1.1a, Sub-activity 3.1.1b, Sub-activity 3.1.1c) to lead the review and update of adaptation planning frameworks, develop five sector-specific adaptation plans aligned with the NAP and LAPs, and integrate them into a cohesive national framework. All outputs will be evidence-based, participatory, and aligned with Mozambique’s climate resilience goals. The company will also coordinate with other project firms to ensure alignment and consistency across all activities. This lumpsum amount includes 5 sectoral review workshops.
B | Five one-day workshops for discussing sectorial vulnerabilities (Sub-activity 3.1.1b - consultations on sector-specific vulnerabilities) estimated at USD5,000 per event to include venue and catering for 25 persons (USD200/person).
C | Travel of the International Consultant (Team Leader proposed by the Consulting Company 1 - Sub-activity 3.1.1a, Sub-activity 3.1.1b, Sub-activity 3.1.1c) to attend stakeholder consultations. @1500 USD ticket cost and @1500 USD per diem for 6 overnight stays (6*250, 3,000 USD total).
D | Professional services - Firm (Consulting Company 2 – Policy and Regulatory Alignment Consulting Company): to engage a firm for USD 140,000 lumpsum to implement activity 3.1.2 (Sub-activity 3.1.2a, Sub-activity 3.1.2b, Sub-activity 3.1.2c, Sub-activity 3.1.2d, Sub-activity 3.1.2e) To lead the review of sectoral policies, identify gaps, and propose amendments to strengthen climate resilience integration in Mozambique’s planning systems. The company will facilitate 5 sectoral workshops, each with around 40 participants, to validate amendments and create a Policy Operationalization Toolkit for sectoral agencies. It will also organize 5 targeted training sessions for public officials and experts on climate-adaptive policies. Coordination with other project firms will ensure alignment across planning, policy, and stakeholder engagement activities.
E | Five one-day workshops for discussing sectorial policy allighnment options (Sub-activity 3.1.2b) estimated at USD5,000 per event to include venue and catering for 40 persons (USD125/person).
G | Travel of the International Consultant (Team Leader proposed by the Consulting Company 2 - Sub-activity 3.1.2a, Sub-activity 3.1.2b, Sub-activity 3.1.2c, Sub-activity 3.1.2d, Sub-activity 3.1.2e) to attend stakeholder consultations. @1500 USD ticket cost and @1500 USD per diem for 6 overnight stays (6*250 USD, 3,000USD total).
H | Professional services - Firm (Consulting Company 4 – Institutional Governance and Coordination Consulting Company): to engage a firm for USD 140,000 lumpsum to implement activity 3.1.3 (Sub-activity 3.1.3a, Sub-activity 3.1.3b, Sub-activity 3.1.3c, Sub-activity 3.1.3d, Sub-activity 3.1.3e) to strengthen Mozambique’s climate adaptation governance by formalizing the GIIMC’s mandate, establishing sectoral working groups, and creating a national decision-making framework. The company will conduct needs assessments, provide capacity-building through targeted trainings, and facilitate the creation of 5 sector-specific working groups. It will also organize 8 biannual GIIMC meetings and 10 sectoral workshops to promote cross-sectoral communication and learning. Coordination with other project firms will ensure alignment and complementarity across all activities. Trainings and workshops under 3.1.3a, 3.1.3b 3.1.3d, and 3.1.3e will be held in Maputo and engage only national stakeholders
I | Consultant – Individual - Local: Institutional Coordination Coordinator (Sub-activity 3.1.3a, Sub-activity 3.1.3b, Sub-activity 3.1.3c, Sub-activity 3.1.3d, Sub-activity 3.1.3e) @ 2,000 USD per month for 48 months to supervise and coordinate activities of the Consulting Company 4 and carry out follow up facilitation activities until completion of the project.
J | One five-days training on effective adaptation coordination (Sub-activity 3.1.3a) estimated at USD18,750 per event to include venue and catering for 30 persons (USD125/person/day). This activity will be held in Maputo and will engage only national-level stakeholders.
K | One three-day trainings for members of GIIMC (Sub-activity 3.1.3b) estimated at USD15,000 per event to include venue and catering for 40 persons (USD125/person). This activity will be held in Maputo and will engage only national-level stakeholders.
L | 1 one-day training on Decision-Making Framework and operational coordination (Sub-activity 3.1.3d) at USD3,750 per event to include venue and catering for 30 persons (USD125/person). This activity will be held in Maputo and will engage only national-level stakeholders.
L2 | 8 one-day biannual meetings on inter-institutional coordination and 10 sectorial coordination workshops (Sub-activity 3.1.3e) at USD5,000 per event to include venue and catering for 40 persons (USD125/person). This activity will be held in Maputo and will engage only national-level stakeholders.
M | 2 Travels of the International Consultant (Team Leader proposed by the Consulting Company 3 - Sub-activity 3.1.3a, Sub-activity 3.1.3b, Sub-activity 3.1.3c, Sub-activity 3.1.3d, Sub-activity 3.1.3e, Sub-activity 3.1.3f) to attend stakeholder consultations. Costs of each travel - @3,000 USD for 2 the cost of 2 tickets and @ 3,000 USD per diem for 6 overnight stays (2*6*250 USD, 3,000USD Total).
N | Professional services - Firm (Consulting Company 3 – Stakeholder Engagement and Awareness Consulting Company): to engage a firm for USD 160,000 lumpsum to implement Sub-activities 3.1.4a, 3.1.4b, 3.1.4c, 3.1.4d, 3.1.4e, 3.1.4f and 3.1.4g to lead the design of Mozambique’s first Comprehensive Stakeholder Engagement Framework for adaptation. It will organize 10 national and sectoral workshops, conduct a Stakeholder Mapping and Needs Assessment, and develop 30 Partnership Agreements to secure collaboration across sectors. The company will implement a multimedia Awareness Raising Campaign and deliver 10 targeted training sessions to strengthen participatory planning and policy integration. Additionally, it will organize 10 science-to-policy dialogue events. Coordination with other project firms will ensure integrated implementation across the project components.
O | Consultant – Individual - Local: Community Engagement and Awareness Raising Expert (Sub-activity 3.1.4e) @ 3,000 USD per month for 36 months to supervise and coordinate activities related to the awareness raising.
P | Ten consultative workshops (for 5 priority sectors) with key stakeholders (Sub-activity 3.1.4c) to validate adaptation priorities and promote inclusive dialogueestimated at USD3,750 per event to include venue and catering for 30 persons (USD125/person).
Q | Ten one-day trainings (for 5 priority sectors) with key stakeholders on climate adaptation roles and strategies (Sub-activity 3.1.4f) estimated at USD5,000 per event to include venue and catering for 40 persons (USD125/person).
R | Ten one-day dialogues (for 5 priority sectors) on focus on adaptation planning, policy integration, institutional coordination, and monitoring and evaluation basics (Sub-activity 3.1.4g) estimated at USD5,000 per event to include venue and catering for 40 persons (USD125/person).
S | Professional services - Firm (Consulting Company 5 – Adaptation Monitoring, Evaluation and Learning Systems Consulting Company): to engage a firm for USD 120,000 lumpsum to implement activity 3.2.1 (Sub-activities 3.2.1a, 3.2.1b, 3.2.1c, 3.2.1d, 3.2.1e) to strengthen Mozambique’s National Monitoring and Evaluation System for Climate Change (SNMAMC) with a focus on adaptation. It will revise legal and institutional frameworks, develop adaptation indicators, design and pilot a Climate Budget Tagging System, and deliver two training sessions on MEL and financial tracking. The company will also implement the MEL system in pilot sectors and establish baseline datasets. Coordination with Consulting Company 1 and Consulting Company 4 will occur during the pilot phase to ensure alignment with sectoral priorities and institutional frameworks.
U | Consultant – Individual - Local: Legal and Regulatory Improvement Expert (Sub-activity 3.2.1c, Sub-activity 3.2.1d) @ 3,000 USD per month for 12 months to provide with the regulatory support to SNMAMC operations
V | One two-day trainings for stakeholders on CBT and adaptation monitoring indicators (Sub-activity 3.2.1d) estimated at USD7,500 per event to include venue and catering for 30 persons (USD125/person/day).
W | Professional services - Firm (Consulting Company 6 – Climate Vulnerability Assessment and Knowledge Management Consulting Company): to engage a firm for USD 195,000 lumpsum to implement activity 3.2.2 (Sub-activity 3.2.2a, Sub-activity 3.2.2b, Sub-activity 3.2.2c, Sub-activity 3.2.2d, Sub-activity 3.2.1c, Sub-activity 3.2.1d) to lead the harmonization of Mozambique’s climate data across five sectors and conduct regional and sectoral vulnerability assessments. The regional assessents will produce three reports focused on the country's six key climatic regions - south, center, north, highlands, arid and coastal. It will prioritize adaptation solutions based on feasibility assessments and reactivate the Center for Knowledge Management and Research (CKMR) to establish a public knowledge repository for climate adaptation. The company will conduct stakeholder consultations to ensure data relevance for adaptation planning. Coordination with Consulting Company 1 and Consulting Company 5 will ensure integration of vulnerability findings into sectoral plans and alignment with MEL indicators. However, most activities will be carried out autonomously under the data and knowledge management pillar.
W1 | Professional services - Firm (Consulting Company 7 – Private Sector Adaptation Finance Framework Consulting Company): to engage a firmfor USD 110,000 lumpsum to implement activity 3.3.1 (Sub-activity 3.3.1a, Sub-activity 3.3.1b, Sub-activity 3.2.1c) conduct a regulatory and market barrier analysis to identify the root causes of low private sector engagement in adaptation financing. Based on this analysis, it will design a package of policy, regulatory, and fiscal incentives for Mozambique’s key adaptation sectors. The company will organize five co-creation workshops with stakeholders to ensure the proposed incentives are practical and sector-specific. Coordination with Consulting Company 1 and Consulting Company 8 will ensure alignment with sectoral adaptation priorities and future private sector capacity-building efforts. However, Consulting Company 7 will lead independently on policy and incentive design, with technical exchanges ensuring integration across related outputs.
W2 | Five one-day sectorial workshops on adaptation finance frameworks (Sub-activity 3.3.1c) estimated at USD3,750 per event to include venue and catering for 30 persons (USD125/person).
Z | Professional services - Firm (Consulting Company 8 – Private Sector Adaptation Capacity Building Consulting Company): to engage a firm for USD 140,000 lumpsum to implement activity 3.3.3 (Sub-activities 3.3.3a, 3.3.3b, 3.3.3c and 3.3.3d) to lead efforts to enhance the private sector’s capacity to engage in climate adaptation planning and investment. The company will organize five sector-specific seminars and co-creation workshops to develop adaptation project ideas, followed by a structured mentorship program with adaptation finance experts to support private companies in developing investment-grade projects. Coordination with Consulting Company 7 will ensure alignment with the incentive frameworks being developed. However, Consulting Company 8 will operate independently in providing technical capacity-building and hands-on support to unlock adaptation investment opportunities.
AA | Ten one-day introductory awareness-raising seminars for business leaders (one per priority sector) (Sub-activity 3.3.3b) and five one-day co-creation workshops for private sector adaptation project development estimated at USD3,750 per event to include venue and catering for 30 persons (USD125/person).
AB | Professional services - Firm (Consulting Company 9 – Adaptation Prioritization and Investment Framework Consulting Company): to engage a firm for USD 120,000 lumpsum to implement activity 3.4.1 (Sub-activity 3.4.1a, Sub-activity 3.4.1b, Sub-activity 3.4.1c) to design Mozambique’s first evidence-based project prioritization framework for adaptation, using internationally recognized methodologies such as MCA, CEA, and CBA. It will organize five training sessions for national and subnational authorities on operationalizing the framework. The company will also facilitate pilot testing in selected sectors or provinces, refining the framework based on lessons learned.
AC | Five one-day trainings for the key stakeholders on prioritization options (Sub-activity 3.3.3b) estimated at USD5,000 per event to include venue and catering for 40 persons (USD125/person).
AD | Professional services - Firm (Consulting Company 10 – Adaptation Concept Notes and Pre-feasibility Studies Consulting Company): to engage a firm for USD 120,000 lumpsum to implement activity 3.4.2 aimed at designing 2 fully developed GCF Concept Notes for high-priority adaptation projects, each accompanied by Pre-Feasibility Studies and initial Impact Assessments.
AE | Two two-day stakeholder engagement workshops for project priorities validation (Sub-activity 3.4.2b) estimated at USD3,125 per event to include venue and catering for 25 persons (USD125/person).
AF | Travel of the International Consultant (Team Leader proposed by the Consulting Company 10 - Sub-activity 3.4.2b) to attend stakeholder consultations. Costs of travel - @1500 USD ticket cost and @1500 USD per diem for 6 overnight stays (6*250 USD, 3,000 USD total).
AI | Contractual Services- Individual: NAP Project Manager (all activities) @ 1,800 USD per month for 48 months to provide with overall management of the Project. The cost is split equally between all outcomes 9 months per outcome x 4 = 36 months across the four outcomes + 12 months charged to PMC
AJ | Contractual Services- Individual: Finance and Operations Analyst (all activities) @ 1,500 USD per month for 48 months to provide with overall adminsitrative support
AK | Contractual Services- Individual: M&E Analyst (all activities) @ 1,500 USD per month for 12 months (part-time throughout project implementation) to provide with overall M&E support
AL | Professional services - Firm : to engage an audit firm (all activities) for USD 4,000 (4 times - on the annual basis) lumpsum to implement expenditure verification as per GCF requirements
AM | Unforeseen programme cost, such as FX gain and loss, bank charges etc., which is unrelated to implementation/service fee.
AN | Services to Project: Budget to cover costs for various functions provided by UNDP Country Office that including finance, human resources, administrative and procurement services, payroll management, payments, travel services, consultant recruitments, procurement of goods and services, etc. Costs for various project management functions will be charged based on the UNDP universal price list
AO | Cost of office supplies budgeted at USD 2,100 per annum

## Guidlines for Procurement Plan
The following considerations are important when completing the Procurement Plan:
1. Before preparing the Readiness and budget, procurement and HR, and implementation plans, please read the full guidance contained in the Readiness Programme Guidebook, specifically Part IV Sections 5 and 6
2. Please start populating information on planned procurement items next to dedicated rows titled 'Planned'. Utilize slicer buttons at the top of the worksheet to easily filter out rows dedicated to planned items.
3. Please Specify Item and Item Description under Column C.
4. Choose the appropriate Procurement categories from the dropdown list available in the Procurement plan under column D.
5. Specify the Estimated cost of the Item under Column E.
6. Populate the applicable Procurement Method (e.g., open, limited RFP, ITB, RFQ) in Column G. Ensure alignment with the thresholds (Min-Max monetary value for the indicated procurement method) outlined in Column H, in accordance with the applicable procurement policy.
7. In Column I, specify the name of the Entity executing Procurement (DP/EE, etc.).
8. Indicate estimated timelines under Columns J and K.
9. The Procurement Plan Template provides twenty (20) dedicated rows. To insert additional rows, right-click on the row number below where the new row is desired and select INSERT. When inserting new rows, allocate three rows for each item (Planned, Revised1, Actual) and extend existing dropdown menus or other formulas.
10. Utilize Column L, labeled "Remarks," to record explanations, additional details, or any other pertinent information as needed.
The following considerations are important when completing the Change Request impacting the Procurement Plan:
1. Upon approval of the procurement plan by the GCF, the 6.2 Procurement Plan will be locked. Simultaneously, the additional tab 6.2.1 Procurement Plan will be activated for inputs. In this tab, planned items will be automatically populated from the approved procurement plan. Only revisions and actuals can be modified.
2. Change requests within 20% threshold of cost reallocation per procurement category (column D) are not subject to GCF pre-approval provided that the procurement process adheres applicable procurement policy AND follows competitive process.
3. Any change from the approved competitive procurement method to a less competitive method, irrespective of financial value, requires GCF pre-approval. Such changes should be submitted as a change request for clearance.
4. Any change constituting a new procurement item irrespective of financial value requires GCF pre-approval. Such changes should be submitted as a change request for clearance.
5. When revising a procurement item, utilize the designated row labeled "Revised1" and update the relevant columns from the approved procurement plan. After updating, populate Column F with the Current Estimated Cost (latest estimated/actual cost).
6. For subsequent revisions, please add dedicated rows i.e. "Revised2" for the second revision, "Revised3" for the third revision, etc and update Column F on Current Estimated cost accordingly.
7. To add new procurement items outside the approved procurement plan, allocate three rows for each new item (Planned, Revised 1, Actual). Extend existing drop-down menus or other formulas and input information under "Revised 1"
8. For ease of reference please also highlight indicated changes in yellow
9. When deleting procurement items, employ strikethrough and indicate "0" under Column F for the Current Estimated Cost (latest estimated/actual cost).
The following considerations are important when preparing the Annual Progress Report:
1. Please attach this procurement plan to your Annual Progress Report to demonstrate implementation progress as well as any changes that were not sibject to GCF pre-approval as defined in the section above.
The following considerations are important when preparing the Completion Report:
1. Dedicated tab - 6.2.1 Procurement Plan shall illustrate the actual execution of the procurement plan, as a component of the project completion reporting process, in the row titled 'Actual'.
2. Upon provision of actual inputs, the consolidated spreadsheet should delineate information pertaining to the project approval stage. Specifically, the spreadsheet should distinguish between what was initially approved (under the row dedicated to "planned" items), what underwent a single revision (Revised1), what underwent two revisions (Revised2), or remain blank if no revisions occurred. Populate fields related to actual execution, costs, and timelines accordingly.
If you are unsure about how to complete the Procurement Plan template, please send your query to: countries@gcfund.org
Readiness Grant Procurement Plan Preparation Guidelines

## 6.2 Procurement Plan
6.2 Procurement Plan
For goods, services, and consultancies to be procured, please list the items, descriptions in relation to the activities in Section 3, estimated cost, procurement method, relevant threshold, and the estimated dates. Please provide a full procurement plan for the entire duration of the implementation period.
Procurement Plan Approval Date:
Please check out the example in the table below, and remove the items before including the proposal's entries. At the proposal submision stage, please populate the raws dedicated to planned items.
No | Status | Item Description | Category | Estimated Cost (US$) | Current Estimated Cost (please indicate latest estimated/actual cost) | Procurement Method (e.g. open, limited RFP,ITB,RFQ) | Thresholds as per applicable procurement policy (Min-Max monetary value for which indicated procurement method must be used) | Name of Entity executing Procurement (DP/EE, etc.) | Date of initiating procurement (Tender Issuence) | Estimated contract start date | Remarks
1 | Planned | Consulting Company 1 – Sectorial vulnerability assessment | Consulting Services (Professional Firms) | 160000 |  | Open tender | USD 150,000 and above | UNDP | 2025-09-01 | 2025-12-01 | Budget Note A
1 | Revised1
1 | Actual
2 | Planned | Consulting Company 2 – Sectorial Policies’ Adjustment | Consulting Services (Professional Firms) | 140000 |  | Open tender | USD 10,000 to 150,000 | UNDP | 2025-09-01 | 2025-12-01 | Budget Note D
2 | Revised1
2 | Actual
3 | Planned | Consulting Company 3 – Institutional coordination and decision making | Consulting Services (Professional Firms) | 160000 |  | Open tender | USD 10,000 to 150,000 | UNDP | 2025-09-01 | 2025-12-01 | Budget Note N
3 | Revised1
3 | Actual
4 | Planned | Consulting Company 4 – Public awareness raising | Consulting Services (Professional Firms) | 140000 |  | Open tender | USD 10,000 to 150,000 | UNDP | 2026-09-01 | 2026-12-01 | Budget Note H
4 | Revised1
4 | Actual
5 | Planned | Consulting Company 5 – Adaptation indicators development | Consulting Services (Professional Firms) | 120000 |  | Open tender | USD 10,000 to 150,000 | UNDP | 2026-09-01 | 2026-12-01 | Budget Note S
5
5
6 | Planned | Consulting Company 6 – Climate change vulnerability assessment | Consulting Services (Professional Firms) | 195000 |  | Open tender | USD 10,000 to 150,000 | UNDP | 2026-09-01 | 2026-12-01 | Budget Note W
6 | Revised1
6 | Actual
7 | Planned | Consulting Company 7 – Private sector finance | Consulting Services (Professional Firms) | 110000 |  | Open tender | USD 10,000 to 150,000 | UNDP | 2027-09-01 | 2027-12-01 | Budget Note W1
7 | Revised1
7 | Actual
8 | Planned | Consulting Company 8 – Private sector capacity building | Consulting Services (Professional Firms) | 140000 |  | Open tender | USD 10,000 to 150,000 | UNDP | 2027-09-01 | 2027-12-01 | Budget Note Z
8 | Revised1
8 | Actual
9 | Planned | Consulting Company 9 – Adaptation prioritization | Consulting Services (Professional Firms) | 120000 |  | Open tender | USD 10,000 to 150,000 | UNDP | 2027-09-01 | 2027-12-01 | Budget Note AB
9 | Revised1
9 | Actual
10 | Planned | Audit Company | Consulting Services (Professional Firms) | 16000 |  | Open tender | USD 10,000 and above | UNDP | 2025-09-01 | 2025-12-01 | Budget Note AL
10 | Revised1
10 | Actual
11 | Planned | Institutional Coordination and Capacity Enhancement Coordinator | Consulting Services (Individual Consultants) | 96000 |  | Open tender | USD 10,000 and above | UNDP | 2025-09-01 | 2025-12-01 | Budget Note I
11 | Revised1
11 | Actual
12 | Planned | Community Engagement and Awareness Raising Expert | Consulting Services (Individual Consultants) | 108000 |  | Open tender | USD 150,000 and above | UNDP | 2025-09-01 | 2025-12-01 | Budget Note O
12 | Revised1
12 | Actual
13 | Planned | Legal and Regulatory Improvement Expert | Consulting Services (Individual Consultants) | 36000 |  | Open tender | Open tender | UNDP | 2025-09-01 | 2025-12-01 | Budget Note U
13 | Revised1
13 | Actual
14 | Planned | Consulting Company 10-Adaptation Concept Notes and Pre-feasibility Studies Consulting Company | Consulting Services (Professional Firms) | 120000 |  | Open tender | Open tender | UNDP | 2025-09-01 | 2025-12-01 | Budget Note AD
14 | Revised1
14 | Actual
15 | Planned | Venue and Catering for 84 workshops and trainings | Non-Consulting Services | 410000 |  | Open tender | USD 10,000 and above | UNDP | 2025-09-01 | 2026-12-01 | Budget Notes B, E, J, K, L, L2, P, Q, R, V, W2, AA, AC, AE
15 | Revised1
15 | Actual
16 | Planned | 5 Travel- Air Ticket (Excluding DSA of USD 7,500) | Non-Consulting Services | 7500 |  | Direct Purchase | Less than 10,000 | UNDP | 2025-09-01 | 2026-12-01 | Budget Notes C, G, M, AF
16 | Revised1
16 | Actual
17 | Planned | Office Supplies | Goods | 8400 |  | Direct Purchase | Less than 10,000 | UNDP | 2025-09-01 | 2029-12-01 | Budget Note AO
17 | Revised1
17 | Actual
| Planned | Total $(USD) |  | 2086900
| Revised1 | Total $(USD) |  | 0
| Actual | Total $(USD) |  | 0
Breakdown per Category
| Planned Goods | Total $(USD) |  | 0
| Planned Non-Consulting Services | Total $(USD) |  | 417500
| Planned Works | Total $(USD) |  | 0
| Planned Consulting Services (PS) | Total $(USD) |  | 1421000
| Planned Consulting Services (IC) | Total $(USD) |  | 240000
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## 6.2.1 Procurement Plan Revision
6.2 Procurement Plan
For goods, services, and consultancies to be procured, please list the items, descriptions in relation to the activities in Section 3, estimated cost, procurement method, relevant threshold, and the estimated dates. Please provide a full procurement plan for the entire duration of the implementation period.
Procurement Plan Approval Date:
Please check out the example in the table below, and remove the items before including the proposal's entries. At the proposal submision stage, please populate the raws dedicated to planned items.
No | Status | Item Description | Category | Estimated Cost (US$) | Current Estimated Cost (please indicate latest estimated/actual cost) | Procurement Method (e.g. open, limited RFP,ITB,RFQ) | Thresholds as per applicable procurement policy (Min-Max monetary value for which indicated procurement method must be used) | Name of Entity executing Procurement (DP/EE, etc.) | Date of initiating procurement (Tender Issuence) | Estimated contract start date | Remarks
1 | Planned | Consulting Company 1 – Sectorial vulnerability assessment | Consulting Services (Professional Firms) | 160000 | 0 | Open tender | USD 150,000 and above | UNDP | 2025-09-01 | 2025-12-01 | Budget Note A
1 | Revised1
1 | Actual
2 | Planned | Consulting Company 2 – Sectorial Policies’ Adjustment | Consulting Services (Professional Firms) | 140000 | 0 | Open tender | USD 10,000 to 150,000 | UNDP | 2025-09-01 | 2025-12-01 | Budget Note D
2 | Revised1
2 | Actual
3 | Planned | Consulting Company 3 – Institutional coordination and decision making | Consulting Services (Professional Firms) | 160000 | 0 | Open tender | USD 10,000 to 150,000 | UNDP | 2025-09-01 | 2025-12-01 | Budget Note N
3 | Revised1
3 | Actual
4 | Planned | Consulting Company 4 – Public awareness raising | Consulting Services (Professional Firms) | 140000 | 0 | Open tender | USD 10,000 to 150,000 | UNDP | 2026-09-01 | 2026-12-01 | Budget Note H
4 | Revised1
4 | Actual
5 | Planned | Consulting Company 5 – Adaptation indicators development | Consulting Services (Professional Firms) | 120000 | 0 | Open tender | USD 10,000 to 150,000 | UNDP | 2026-09-01 | 2026-12-01 | Budget Note S
5 | 0
5 | 0
6 | Planned | Consulting Company 6 – Climate change vulnerability assessment | Consulting Services (Professional Firms) | 195000 | 0 | Open tender | USD 10,000 to 150,000 | UNDP | 2026-09-01 | 2026-12-01 | Budget Note W
6 | Revised1
6 | Actual
7 | Planned | Consulting Company 7 – Private sector finance | Consulting Services (Professional Firms) | 110000 | 0 | Open tender | USD 10,000 to 150,000 | UNDP | 2027-09-01 | 2027-12-01 | Budget Note W1
7 | Revised1
7 | Actual
8 | Planned | Consulting Company 8 – Private sector capacity building | Consulting Services (Professional Firms) | 140000 | 0 | Open tender | USD 10,000 to 150,000 | UNDP | 2027-09-01 | 2027-12-01 | Budget Note Z
8 | Revised1
8 | Actual
9 | Planned | Consulting Company 9 – Adaptation prioritization | Consulting Services (Professional Firms) | 120000 | 0 | Open tender | USD 10,000 to 150,000 | UNDP | 2027-09-01 | 2027-12-01 | Budget Note AB
9 | Revised1
9 | Actual
10 | Planned | Audit Company | Consulting Services (Professional Firms) | 16000 | 0 | Open tender | USD 10,000 and above | UNDP | 2025-09-01 | 2025-12-01 | Budget Note AL
10 | Revised1
10 | Actual
11 | Planned | Institutional Coordination and Capacity Enhancement Coordinator | Consulting Services (Individual Consultants) | 96000 | 0 | Open tender | USD 10,000 and above | UNDP | 2025-09-01 | 2025-12-01 | Budget Note I
11 | Revised1
11 | Actual
12 | Planned | Community Engagement and Awareness Raising Expert | Consulting Services (Individual Consultants) | 108000 | 0 | Open tender | USD 150,000 and above | UNDP | 2025-09-01 | 2025-12-01 | Budget Note O
12 | Revised1
12 | Actual
13 | Planned | Legal and Regulatory Improvement Expert | Consulting Services (Individual Consultants) | 36000 | 0 | Open tender | Open tender | UNDP | 2025-09-01 | 2025-12-01 | Budget Note U
13 | Revised1
13 | Actual
14 | Planned | Consulting Company 10-Adaptation Concept Notes and Pre-feasibility Studies Consulting Company | Consulting Services (Professional Firms) | 120000 | 0 | Open tender | Open tender | UNDP | 2025-09-01 | 2025-12-01 | Budget Note AD
14 | Revised1
14 | Actual
15 | Planned | Venue and Catering for 84 workshops and trainings | Non-Consulting Services | 410000 | 0 | Open tender | USD 10,000 and above | UNDP | 2025-09-01 | 2026-12-01 | Budget Notes B, E, J, K, L, L2, P, Q, R, V, W2, AA, AC, AE
15 | Revised1 |  | 0 | 0 | 0
15 | Actual |  | 0 | 0 | 0
16 | Planned | 5 Travel- Air Ticket (Excluding DSA of USD 7,500) | Non-Consulting Services | 7500 | 0 | Direct Purchase | Less than 10,000 | UNDP | 2025-09-01 | 2026-12-01 | Budget Notes C, G, M, AF
16 | Revised1 |  | 0
16 | Actual |  | 0
17 | Planned | Office Supplies | Goods | 8400 | 0 | Direct Purchase | Less than 10,000 | UNDP | 2025-09-01 | 2029-12-01 | Budget Note AO
17 | Revised1
17 | Actual
0 | Planned | Total $(USD) | 0 | 2086900 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Revised1
0 | Actual
| Planned | Total $(USD) |  | 2086900
| Revised1 | Total $(USD) |  | 0
| Actual | Total $(USD) |  | 0
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## 6.3 HR plan
6.3 Human Resources (HR) Plan
For staff to be employed for the duration of the grant.
Please use examples in the table below, and remove them before indicating proposal's requirements.
Item | Item Description | Estimated Cost (US$) | Recruitment Method | Thresholds as per applicaple policy (if any) | Name of Entity executing recruitment (DP/EE, etc.) | Date of initiating recruitment | Estimated contract start date
NAP Project Manager (Budget Note AI) | Full time project manager | 86400 | HR process (open advertisement) | above 10,000 | UNDP | 2025-09-01 | 2025-10-01
Finance and Operations Analyst (Budget Note AJ) | Full time finance and operations associate | 72000 | HR process (open advertisement) | above 10,000 | UNDP | 2025-09-01 | 2025-10-01
ME& Analyst (Budget Note AK) | Part-time M&E expert | 18000 | HR process (open advertisement) | above 10,000 | UNDP | 2025-09-01 | 2025-10-01
Sub-Total (US$) |  | 176400

## 6.4 Implementation Plan
6.3 Implementation Plan
Column B: Please list all output codes the proposed proposal aims to achieve (e.g., 1.2.1 or 2.1.3., etc.)
Column C: Please indicate the month number in which the output will start the implementation (e.g., month 3 = 3)
Column D: Please indicate the month number in which the output will finish the implementation (e.g., month 9 = 9)
Column E: The duration of the implementation for each output will appear automatically using the formula (C-D); therefore, it is not expected for editing.
Column F: Dependency output(s): If the output listed is depending on other output(s), please list those outputs respectively; otherwise, please type "none"
Please check out the example in the table below, and remove them before including the proposal's entries
Output | Start Date (Month#) | End date (Month#) | Implementation period (Months) | Interdependency output(s)
Output 3.1.1 - National and local adaptation plans are updated and sectoral adaptation plans developed | 3 | 12 | 9 | Deliverable 3.1.1a Deliverable 3.1.1b Deliverable 3.1.1c Deliverable 3.1.1d Deliverable 3.1.1e
Output 3.1.2 - Adaptation policies and regulations for sectorial integration are developed and stregthened | 3 | 12 | 9 | Deliverable 3.1.2a Deliverable 3.1.2b Deliverable 3.1.2c Deliverable 3.1.2d Deliverable 3.1.2e
Output 3.1.3 - Inter- and intra-institutional coordination and decision-making mechanisms strengthened | 3 | 12 | 9 | Deliverable 3.1.3a Deliverable 3.1.3b Deliverable 3.1.3c Deliverable 3.1.3d Deliverable 3.1.3e Deliverable 3.1.3f
Output 3.1.4 - Stakeholder engagement frameworks are enhanced and awareness raising activities conducted | 13 | 24 | 11 | Deliverable 3.1.3e
Output 3.2.1 - Adaptation impact Monitoring, Evaluation and Learning (MEL) Systems are Established or Stregthened | 13 | 24 | 11 | Deliverable 3.2.1b Deliverable 3.2.1d Deliverable 3.2.1e Deliverable 3.2.1c Deliverable 3.2.1d
Output 3.2.2 - Climate vulnerability studies are conducted and adaptation solutions identified | 13 | 24 | 11 | Deliverable 3.2.2a Deliverable 3.2.2b Deliverable 3.2.1c Deliverable 3.2.1d
Output 3.3.1 - Strategies, policies and incentives to foster private investment in adaptation solutions are developed | 13 | 24 | 11 | Deliverable 3.3.1a Deliverable 3.3.1b Deliverable 3.2.1c
Output 3.3.2 - Knowledge products to inform the private sector on adaptation options and GCF financing are developed | 13 | 24 | 11 | Deliverable 3.3.2a Deliverable 3.3.2b Deliverable 3.2.2c
Output 3.3.3 - Capacity-building for the private sector on adaptation options is provided | 25 | 36 | 11 | Deliverable 3.3.3a Deliverable 3.3.3b Deliverable 3.3.3c
Output 3.4.1 - Mechanisms to prioritize adaptation options based on objective criteria established | 25 | 36 | 11 | Deliverable 3.4.1a Deliverable 3.4.1b Deliverable 3.4.1c
Output 3.4.2 - Concept Notes, pre-feasibility studies and impact assessments for priority adaptation actions are developed | 30 | 42 | 12 | Deliverable 3.4.3
Output 3.4.4 - National systems for tracking adaptation finance flows developed | 32 | 46 | 14 | Deliverable 3.4.4