## PROJ-DATA
NARRATIVE PROJECT PROGRESS REPORT
PROJECT DATA
COUNTRY: | Jamaica
REPORTING PERIOD (dd/mm/yyy): | 2025-11-15 | TO (dd/mm/yyy): | 2026-06-30
PROJECT NUMBER & TITLE: | Jamaica Resilient Recovery Initiative (JARRI)/Hurricane Melissa Project 01005173
PROJECT DURATION (dd/mm/yyy): | 2025-11-15 | TO (dd/mm/yyy): | 2027-06-30 | 1 Years, 7 Months
DONORS | UNDP
IMPLEMENTING PARTNER: | UNDP
RESPONSIBLE PARTIES:
PROJECT COORDINATOR: | Jamaro Marville
INITIAL APPROVED BUDGET (USD): | 2150000 | REVISED APPROVED BUDGET (USD):
TOTAL ANNUAL BUDGET (USD): |  | TOTAL ANNUAL EXPENDITURE (USD):
| JMD: | 0 |  | JMD: | 0
ANNUAL DELIVERY:

## EXEC-SUMM
NARRATIVE PROJECT PROGRESS REPORT
EXECUTIVE SUMMARY
The Jamaica Resilient Recovery Initiative (JARRI) was established by the United Nations Development Programme (UNDP) following the catastrophic landfall of Hurricane Melissa on October 28, 2025. As a Category 5 storm and the strongest hurricane to strike Jamaica in 174 years, Hurricane Melissa caused unprecedented destruction across the island, particularly devastating western parishes including St. James, Hanover, St. Elizabeth, Westmoreland, Manchester, and Trelawny. Nationwide damages were initially estimated at a staggering 41% of Jamaica’s 2024 GDP, characterized by massive infrastructure damage, agricultural losses, widespread power/communications outages, and the generation of roughly 5 million metric tonnes of debris. In response to the Government of Jamaica (GOJ) declaring the country a disaster area, JARRI was launched as a 15-month initiative (November 15, 2025 – June 30, 2027). Funded through a USD $2.150 million multi-donor pool—including regular UNDP funds, the CARICOM Development Fund, ACP-EU, EUROCLIMA, and EUCARES—the project transitions emergency response into resilient recovery. JARRI combines technical and financial assistance to help national sectors "Build Forward Better" by integrating climate-resilient, nature-based, and gender-responsive methodologies into long-term infrastructure and livelihood recovery. The initiative is structured across four main interlinked components: Component 1: Support to Recovery Governance and Planning Component 2: Community-Driven Resilient Recovery Component 3: Livelihood Recovery Component 4: Solar Solutions for Community Resilience

## PROJ-RESULTS
NARRATIVE PROJECT PROGRESS REPORT
PROJECT RESULTS
OUTPUT | INDICATORS | ANNUAL TARGETS | RESULTS ACHIEVED | OVERALL PROGRESS TO ACHIEVING OUTPUT RESULT | CHALLENGES EXPERIENCED
Output 3: Economic Resilience of MSMEs owned by women and other vulnerable groups impacted by the crisis strengthened to ecover and be more sustainable and resilient | Number of beneficiaries receiving livelihood recovery inputs | 135 | 136 (148) | Target exceeded; 101% achieved. | Minor delay in finalizing support for 12 additional beneficiaries; completion expected by end of May 2026.
| 1.2.1: Number of beneficiaries receiving technical coaching | 135 | 135 plus supporting evidence for delivery | Target achieved, with participation documented through photos, recordings, virtual session records, and related evidence. | Attendance registers were not maintained consistently for all sessions.
| 1.2.2: Number of enterprises restarted or stabilized | 135 | 136 | Target exceeded; outputs are above the annual target. | Final support package for 12 additional beneficiaries is still being completed, which may raise the total further to 148.
| % of women and vulnerable persons supported | ≥ 50% women | 35% women | Below target; progress is partial and reflects the composition of the beneficiary group. | The fishing community at Galleon Beach was predominantly male, limiting the proportion of women reached.
| Beneficiaries showing improved livelihood resilience (self-reported & field officer verification) | ≥ 80% restored operations | 91% | Target exceeded; strong progress toward livelihood recovery. | Some results rely on self-reporting and field verification rather than uniform attendance records.
Output 2: Safely demonlished, removed and managed debris in line with enviornmental standards | 1.1.1 Extent of completion of Debris management, household and business impact assessment | Completed | 27 area assessments completed for debris management; 37 business/household impact assessments done; 33 caregiver assessments done | Output substantially achieved; assessment activities were completed across the targeted communities and provided the evidence base for implementation | Debris management assessment tools required adjustment to reflect field realities, and tracking methods had to be revised because assessments and debris collection did not always occur at the same time
| Number of beneficiaries reporting enhanced capacity to implement debris removal, safe demolition, occupational safety solutions and provision of care disaggregated by sex and age | 55 | 58 beneficiaries trained/enhanced capacity reported (22M, 36F) | Target exceeded; beneficiaries demonstrated improved capacity in debris removal, safe demolition, occupational safety, and care-related support | Venue availability was limited due to hurricane damage, and training logistics were affected by transport constraints and communications difficulties
| Number of beneficiaries employed under the cash for work & care programmes disaggregated by sex. | 55 | 56 beneficiaries employed (24M, 32F) | Target exceeded; cash for work and care activities were successfully implemented with strong participation, including women and men | Payment disbursement in the field was complicated by poor connectivity, lack of electricity/data, and some participants lacking bank accounts or identification
| Number of beneficiaries receiving MSME Business Inputs | 10 | 24 beneficiaries received MSME business inputs | Target significantly exceeded; support to MSMEs was expanded beyond the original target and contributed to local economic recovery | Business input costs were higher than anticipated, requiring budget trade-offs and reallocation of savings from other lines
| 1.2 Volume of cubic metres/truck loads of rubble/waste that is safely removed,treated and disposed including reuse in other project areas | 39 truck loads | 39 truck loads; 850 tonnes in Savanna-la-Mar and 40 tonnes in Salt Spring | Target achieved; substantial debris was removed and disposed of safely, with some materials reused where possible | Shortage of trucks and backhoes, site sequencing issues, limited nearby venues, unreliable phone contact, and high transport costs affected implementation

## LESSONS-LEARNT
NARRATIVE PROJECT PROGRESS REPORT
LESSONS LEARNT
OUTPUT | TYPE OF LESSON | IMPLEMENTATION SUCCESS/CHALLENGES | DETAILS OF LESSON LEARNT | CORRECTIVE MEASURES TAKEN
Output 3: Economic Resilience of MSMEs owned by women and other vulnerable groups impacted by the crisis strengthened to ecover and be more sustainable and resilient | Beneficiary Engagement | Success - Beneficiary consultation improved project relevance and acceptance | Early consultation with beneficiaries helped ensure the livelihood inputs responded to actual needs, increased ownership, and improved participation in implementation. | Consultation was maintained throughout implementation to validate beneficiary needs and adjust support accordingly.
| Procurement and Supply Chain | Challenge - Post-disaster procurement delays and stock uncertainty | Procurement after the disaster required flexibility because stock levels were unpredictable and suppliers had long lead times, which affected timely delivery of inputs. | Procurement planning was adjusted with buffer time, closer supplier follow-up, and alternative sourcing options.
| Integrated Support | Success - Combining livelihood inputs with psychosocial and DRR support strengthened recovery | Beneficiaries responded better when material support was complemented by psychosocial assistance and disaster risk management support, which improved resilience and recovery outcomes. | Livelihood support was linked with awareness and support activities to reinforce recovery beyond material assistance.
| Asset Management | Challenge - Community-owned assets need stronger accountability systems | Shared or community-owned assets require clear management agreements, usage logs, and accountability arrangements to prevent misuse and ensure sustainability. | Management responsibilities were clarified, and record-keeping and accountability measures were strengthened.
| Community Engagement and Assessment | Success - Community consultation and CTB involvement improved relevance and participation | Engaging communities and Community Transformation Boards early helped identify actual debris, housing, and caregiving needs, improved acceptance of the assessments, and strengthened local ownership of the process. | Continued use of CTBs and community engagement during planning and implementation to validate findings and support beneficiary participation.
Output 2: Safely demonlished, removed and managed debris in line with enviornmental standards | Debris Management and Procurement | Challenge - Post-disaster debris work required flexibility in logistics and procurement | Debris removal after the disaster was affected by uncertain stock availability, limited trucks and backhoes, long supplier lead times, and changing field conditions, so implementation had to adapt in real time. | Flexible procurement arrangements were used, additional removal services were procured where needed, and partnerships with municipal actors and NSWMA were leveraged.
| Integrated Recovery Support | Success - Combining cash for work with care, safety, and training improved recovery outcomes | Livelihood recovery was stronger when cash for work, care services, safety training, and psychosocial or disaster risk support were delivered together, because beneficiaries needed both income and practical recovery skills. | The project linked work opportunities with training on occupational safety, safe demolition, care-related support, and environmental safeguards.
| Asset Management and Accountability | Challenge - Clear systems were needed for work verification, payment, and shared resource management | Community-based work and shared equipment require clear supervision, attendance verification, payment procedures, and accountability for tools and materials to avoid confusion and ensure transparency. | Supervisors and CSO partners verified work, payment waivers and alternative disbursement arrangements were introduced, and photos, invoices, and sign-offs were used for validation.
| Partnerships and Local Capacity | Success - Local partnerships improved delivery and technical quality | Partnerships with municipal bodies, NSWMA, churches, schools, and local suppliers helped secure venues, equipment, technical vetting, and logistics support, which improved implementation despite constraints. | Collaboration with local authorities and partners was strengthened, and concessionary supplier arrangements were used to reduce costs and improve access to inputs.

## RISK-LOG
NARRATIVE PROJECT PROGRESS REPORT
RISK LOG
RISK CATEGORY | SECONDARY CATEGORY | EVENT | CAUSE | IMPACT | VALIDITY WHEN WAS THE RISK IDENTIFIED? WHEN WILL IT END? | MITIGATION STRATEGY
Operational | Access and Logistics | Limited access to affected communities due to damaged roads or flooding | Damaged roads, flooding, and difficult terrain after the disaster | Delays in assessments, debris removal, cash for work implementation, and delivery of inputs |  | Coordinate with local authorities; use alternative routes; use smaller vehicles or manual transport where necessary; schedule activities during safe weather windows.
Safety / Operational | Occupational Safety | Safety hazards during debris removal | Handling rubble, debris, and demolition materials in unsafe conditions | Injury or harm to workers and participants; disruption of implementation |  | Provide personal protective equipment; enforce safety protocols; conduct mandatory safety training for all workers.
Environmental | Waste Management | Improper debris disposal | Lack of proper sorting, disposal, and environmental compliance | Environmental damage and unsafe disposal of waste |  | Identify approved disposal sites; implement recycling where possible; monitor compliance with environmental standards.
Social | Inclusion | Risk of exclusion of vulnerable groups (women, persons with disabilities, elderly) | Weak inclusion criteria or participation barriers | Unequal access to project benefits and reduced fairness of implementation |  | Apply clear inclusion criteria; monitor beneficiary lists; engage national gender and disability standards in selection process.
Security | Asset Protection | Theft of materials or equipment | Open storage of tools, supplies, or machinery in affected areas | Loss of project assets and delays in implementation |  | Store materials in secure locations; maintain inventory tracking; engage community watch systems; set protocols for acceptable loss and response when items are missing.

## MONITORING
NARRATIVE PROJECT PROGRESS REPORT
MONITORING
TYPE OF MONITORING ACTION | DATE COMPLETED | EVIDENCE OF MONITORING ACTION

## PROJ-STATUS (hidden)
NARRATIVE PROJECT PROGRESS REPORT
PROJECT STATUS
PROJECT FINANCIAL STATUS:
TOTAL ANNUAL BUDGET: | JMD: | 0
| USD: | 0
TOTAL EXPENDITURE TO DATE: | JMD: | 0
| USD: | 0
% DELIVERY: | #DIV/0!
TOTAL COMMITMENTS:
ON TRACK TO ACHIEVE DELIVERY: | YES
ESTIMATED REVISED BUDGET:

## ASSET INVENTORY
ASSET INVENTORY
Project Title: |  | Jamaica Resilient Recovery Initiative (JARRI)/Hurricane Melissa Project 01005173
Award Number:
Project Number:
Date of Report: | [11 empty] | JAMAICA
Asset Profile 1 - Vehicles
S/N | Country Code | Business Unit | Item Description | Make & Model | Quantity | Serial Number | Location | Tag Number | Date acquired | Value | Custodian | Remarks
1 | JAM10 | B0512 | Vehicle
2 | JAM10 | B0512 | Vehicle
3 | JAM10 | B0512 | Vehicle
4 | JAM10 | B0512 | Vehicle
Asset Profile 2 - Furniture
5 | JAM10 | B0512 | Furniture or Fixture
6 | JAM10 | B0512 | Furniture or Fixture
7 | JAM10 | B0512 | Furniture or Fixture
8 | JAM10 | B0512 | Furniture or Fixture
Asset Profile 3 - Electrical
9 | JAM10 | B0512 | Electrical Equip. or Computer
10 | JAM10 | B0512 | Electrical Equip. or Computer
11 | JAM10 | B0512 | Electrical Equip. or Computer
12 | JAM10 | B0512 | Electrical Equip. or Computer
Asset Profile 4 - Heavy Machinery
13 | JAM10 | B0512 | Heavy Equip. or Generator
14 | JAM10 | B0512 | Heavy Equip. or Generator
15 | JAM10 | B0512 | Heavy Equip. or Generator
16 | JAM10 | B0512 | Heavy Equip. or Generator
Asset Profile 5 - Non Capitalized Items
17 | JAM10 | B0512 | Other (less than 1,000 $)
18 | JAM10 | B0512 | Other (less than 1,000 $)
19 | JAM10 | B0512 | Other (less than 1,000 $)
20 | JAM10 | B0512 | Other (less than 1,000 $)
TOTAL | [9 empty] | 0
Project Manager |  |  |  | Programme Specialist |  |  |  |  | Asst. Resident Representative
Date and Signature |  |  |  | Date and Signature |  |  |  |  | Date and Signature

## DATA TAB (do not edit) (hidden)
COUNTRIES | LESSONS_LEARNT |  | MONITORING ACTIONS |  | UNORE | Version Tracking
Afghanistan | Institutionalisation |  | Annual Review |  | 153.37 | 1 | Initial creation of document | Kirrin Jones | 2021-11-30
Albania | Participation |  | Annual RPT (PIR)
Algeria | Partnership |  | Audit
Andorra | Project Management and Design |  | Donor Report
Angola | Scaling-Up |  | Final Evaluation
Antigua and Barbuda | Sustainability |  | Mid-Term Evaluation
Argentina | Other |  | Monitor Visit
Armenia |  |  | RPT Publication
Australia |  |  | Special Evaluation
Austria |  |  | Workplan
Azerbaijan |  |  | Workshop
The Bahamas |  |  | Other
Bahrain
Bangladesh
Barbados
Belarus
Belgium | RISK LOG - CATEGORY | ENVIRONMENT | FINANCIAL | OPERATION | STRATEGIC
Belize | Environment | Biodiversity and use of Natural Resources | Corruption and Fraud | Alignment with National Priorities | Alignment with UNDP Strategic Priorities
Benin | Financial | Climate Change and Disaster | Cost Recovery | Capacity Development of National Partners | Capacities of the Partners
Bhutan | Operation | Community Health and Safety | Delivery | Engagement of National Partners in Decision-Making | Code of Conduct and Ethics
Bolivia | Organisational | Cultrual Heritage | Fluctuation in Credit Rate, Market, Currency | Flexibility and Opportunity Management | Public Opinion and Media
Bosnia and Herzegovina | Political | Displacement and Resettlement | Value for Money | Leadership and Management | Roles and Responsibilities Among Partners
Botswana | Regulatory | Gender |  | Partnership | Synergy with UN/Delivery As One
Brazil | Security | Human Rights |  | Reporting and Communication | Theory of Change
Brunei | Strategic | Labour Conditions/Standards |  | Responsiveness to Lessons Learnt and Evaluations
Bulgaria | Other | Pollution and Resource Efficiency |  | Synergy Potential (Linking Other Initiatives as Relevant)
Burkina Faso |  | Rights of Indigenous Peoples |  | Transition and Exit Strategy
Burundi |  | Sexual Exploitation and Abuse
Cabo Verde |  | Stakeholder Agreement
Cambodia
Cameroon |  | ORGANISATIONAL | POLITICAL | REGULATORY | SECURITY
Canada |  | Budget Availability and Cash Flow | Change/Turnover in Government | Change in the International Regulatory Framework Affecting the Whole Organisation | Armed Conflict
Central African Republic |  | Due Diligence of Private Sector Partners | Government Commitment | Changes in the Regulatory Framework Within the Country of Operation | Civil Unrest
Chad |  | Governance | Political Instability | Deviation from UNDP Internal Rules and Regulations | Crime
Chile |  | Grievances | Political Will |  | Manmade Hazards
China |  | Human Resources |  |  | Natural Hazards
Colombia |  | Independence and Quality of Evaluation |  |  | Terrorism
Comoros |  | Innovating, Piloting, Experimenting |  | OTHER
Congo, Democratic Republic of the |  | Internal Control |  | Other
Congo, Republic of the |  | Knowledge Management
Costa Rica |  | Monitoring
Côte d’Ivoire |  | Procurement
Croatia
Cuba
Cyprus
Czech Republic
Denmark
Djibouti
Dominica
Dominican Republic
East Timor (Timor-Leste)
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Fiji
Finland
France
Gabon
The Gambia
Georgia
Germany
Ghana
Greece
Grenada
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
Hungary
Iceland
India
Indonesia
Iran
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Korea, North
Korea, South
Kosovo
Kuwait
Kyrgyzstan
Laos
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Moldova
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar (Burma)
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
North Macedonia
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Romania
Russia
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Sudan, South
Suriname
Sweden
Switzerland
Syria
Taiwan
Tajikistan
Tanzania
Thailand
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom
United States
Uruguay
Uzbekistan
Vanuatu
Vatican City
Venezuela
Vietnam
Yemen
Zambia
Zimbabwe