Country/Region/Global: _______________

Initiation Plan

Project Title	:	 Strong and Resilient Local Communities

Expected UNSDCF/CPD Outcome(s)	:	Outcome 1: By 2027, all people, especially vulnerable people, benefit from improved management and state of natural resources and increasingly innovative, competitive, gender-responsive and inclusive economic development that is climate resilient and low carbon

Expected CPD Output(s)	:	Output 1.2: Policies and financial mechanisms developed to protect, value and sustainably manage natural resources.

Initiation Plan Start/End Dates	:	 December 2025 – May 2027

Implementing Partner	:	 United Nations Development Programme (UNDP)

Programme Period:	                2023-2027

Quantum Project Number:	01005184

Quantum Output Number:	01005184

Gender Marker:		                GEN 2

Total resources required           	_________

Total allocated resources:	_________

- Regular			_________

- Other:

  - Zeta Municipality	_________

  - Plužine Municipality	_________

Unfunded budget:		_________

In-kind Contributions		_________

Brief Description

This Initiation Plan represents the first step towards a comprehensive local development project, which will combine technical expertise, institutional support, and investment implementation.

UNDP will pilot an integrated model of technical assistance that covers:

(a) the development and validation of technical documentation, execution and supervision of construction works; the application of SES and the promotion of transparency, inclusion, gender equality, and sustainability and;

(b) strengthening municipal resilience and adaptive capacities through enhanced climate-resilient planning, inter-municipal coordination and exchange of good practices, and strategic positioning to access and leverage future funding opportunities.

Agreed by UNDP:

# Purpose and Expected Output

Municipalities are at the forefront of addressing complex challenges related to urban development, climate resilience, energy efficiency, water and waste management, and disaster risk reduction. Yet many face capacity and resource constraints that limit their ability to prepare and implement investments that meet national and EU standards and respond equitably to the diverse needs of women, men, and vulnerable groups.

Under this Initiation Plan, UNDP will pilot an integrated model of technical assistance that covers (a) the development and validation of technical documentation, execution and supervision of construction works; the application of SES; and the promotion of transparency, inclusion, gender equality, and sustainability; and (b) strengthening municipal resilience and adaptive capacities through enhanced climate-resilient planning, inter-municipal coordination and exchange of good practices, and strategic positioning to access and leverage future funding opportunities.

The activities will focus on building the institutional and technical capacities of the municipalities of Zeta and Plužine for risk-informed, inclusive and climate-resilient development through a practical, learning-by-doing approach. Municipal teams will gain hands-on experience in preparing and implementing investment projects that address local vulnerabilities and strengthen community resilience and participation. Systematically applied the lessons and tools developed through this process will provide a solid foundation for scaling up the model to strengthen local capacities and institutionalize climate-resilient and equitable development practices in other municipalities across Montenegro.

The Initiation Plan includes a significant civil works component with specific construction activities in both municipalities. These investments will focus on enhancing critical local infrastructure needed to improve communal services and demonstrating scalable examples of climate-resilient and socially inclusive urban development. The following facilities are planned for construction works:

- Fire Station in Municipality of Zeta,

- Funeral home in Municipality of Zeta,

- Sidewalk (pedestrian pathway) along the M18 main road, and a parking area next to the municipal Funeral home, in the Municipality of Plužine.

For all three planned construction works feasibility assessments have been completed, and all construction works will be formally supervised by an authorized supervision company contracted prior to the commencement of works.

Overall, this Initiation Plan represents the first step in the conceptualisation of a comprehensive local development project, which will combine technical expertise, institutional support, and investment implementation.

The envisaged Local Development Project will aim to strengthen the capacity of Montenegrin municipalities to plan, attract, and implement investments in sustainable, inclusive, energy-efficient, and climate-resilient local infrastructure and services, fully aligned with national development priorities, EU standards, and UNDP’s Social and Environmental Standards (SES). Gender equality, social inclusion, and the empowerment of underrepresented groups will be mainstreamed across all project components to ensure that benefits reach all members of society equitably.

In addition, the project will encompass the full range of UNDP support options and activities, with a particular focus on strengthening municipal resilience and adaptive capacities. It will support municipalities in developing risk-informed, gender-responsive, climate-resilient planning frameworks; fostering inter-municipal coordination and exchange of best practices; and enhancing their strategic positioning to access national and international climate finance and development funding.

So far, the following potential elements have been identified for the project:

- Strategic planning assistance for inclusive, sustainable and climate-resilient local development,

- Preparation and implementation of bankable, adaptation- and mitigation-aligned projects consistent with national, EU and various donor funding mechanisms,

- Design and implementation of local incentive schemes for citizens and businesses that promote resilience, gender-equality and sustainability,

- Facilitating sustainable waste management and circular economy models,

- Energy transition and decarbonization of municipal assets,

- Risk-informed, inclusive spatial planning and disaster risk reduction (DRR),

- Sustainable mobility and liveable cities and

- Nature-based solutions (NBS) for resilient and healthy communities.

Expected Output of the Initiation Plan:

- Targeted technical support provided to the municipalities of Zeta and Plužine to strengthen their ability to design and manage sustainable, inclusive, and climate-resilient infrastructure and municipal service projects, in line with Social and Environmental Standards (SES) and national investment planning standards.

- Conceptualization of a comprehensive Local Development Project based on the lessons learned from the pilot.

# Management Arrangements

The Initiation Plan will be implemented under the Direct Implementation Modality (DIM) by UNDP Montenegro, ensuring compliance with UNDP’s financial, procurement, and quality assurance procedures.

Within the Inclusive and Green Growth Cluster a Project team will be established to manage day-to-day implementation, coordination, and monitoring of activities.

Project Team:

- Project Manager: responsible for overall leadership and strategic coordination of the project. He/she will oversee planning, budgeting, and implementation of all activities, ensuring full compliance with UNDP procedures and Social and Environmental Standards (SES). The Project Manager will supervise project personnel, consultants, and contractors; ensure quality assurance of deliverables; prepare progress and validate and financial reports; and maintain strategic communication with UNDP, government counterparts, and key partners.

- Project Coordinator: A civil engineer, responsible for the operational and day-to-day implementation of project activities that require specialized technical oversight. He/she will coordinate procurement processes for construction and infrastructure works, support the preparation and verification of technical specifications, and oversee field operations in line with engineering standards. The Project Coordinator will organize stakeholder consultations and public participation activities, work closely with the Project Manager and other team members, technical experts and partners, and ensure that all construction-related activities are implemented on time, safely, and in accordance with the work plan.

- Project Assistant: responsible for administrative, logistical, and financial support to the project. He/she will handle procurement and payment documentation, support the organization of events and field missions, maintain project files and records, and assist in travel arrangements, correspondence, and preparation of administrative and financial sections of reports. The Project Assistant will ensure effective day-to-day administrative functioning of the project.

The team is supported by the Cluster Team Leader for providing strategic guidance, overall oversight and alignment with UNDP’s Country Programme.

Technical Experts / Consultants will be engaged on a needs basis to provide specialized expertise in areas such as preparation of technical documentation, monitoring and supervision of construction works, SES application, energy efficiency, climate resilience, nature-based solutions etc.

The implementation will be supported by the Cluster’s internal technical and policy capacities, costed to the project as technical assistance to implementation, to ensure access to relevant expertise in institutional building, infrastructure development, climate resilience, and environmental sustainability, and to secure high-quality and timely delivery of results.

The team will rely on the capacities of UNDP’s operations team to support with services such as HR and procurement. It will also engage the communications teams to ensure visibility of the initiative.

Project Board and Coordination

A Project Board will be established to provide strategic guidance and oversight, ensuring that implementation remains aligned with national priorities and the UNDP Country Programme. The Project Board will include representatives of:

- UNDP Montenegro,

- Partner municipalities Zeta and Plužine, and

- Other relevant institutions, as needed.

The Board will meet once a year to review progress, approve key deliverables, and provide strategic direction. Ad-hoc meetings in person or online can be called should decisions be required.

Regular consultations will be held with the Ministry of Public Works, Eco Fund, and other relevant national stakeholders to ensure coherence with national frameworks and alignment with the future comprehensive Local Development Programme.

# Monitoring

Progress under this Initiation Plan will be monitored and reviewed regularly throughout its 18 months duration to ensure effective and timely implementation, quality assurance, and achievement of planned results. Monitoring apply UNDP’s Results-Based Management (RBM) principles and follow corporate M&E standards and guidance.

The Project Manager will be supported by the Monitoring and Evaluation (M&E) Officer with oversight, technical guidance, and quality assurance to ensure that all monitoring processes and data management comply with UNDP’s corporate requirements.

Monitoring mechanisms will include:

- Regular internal progress reviews bi-monthly by the Project Team,

- At least one annual Project Board and if needed ad-hoc meeting,

- Regular, demand driven field monitoring visits and quality assurance checks for activities related to technical documentation and supervision of works,

- End-of-Initiation Phase Report, summarizing key achievements, outputs delivered, and lessons learned, including the full Project Document developed.

All monitoring data, progress reports, and evaluations will inform the preparation of the forthcoming comprehensive Local Development Project, supporting evidence-based decision-making and continuous improvement of project design and delivery.

# WORK PLAN

Period: 1 December 2025 – 31 May 2027

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2025 | 2026 |  |  |  | 2027 |  |  |  |  |  |  |
| And baseline, indicators including annual targets | List activity results and associated actions | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  | Funding Source | Budget Description | Amount EUR | Amount USD |
| Output 1: Targeted technical support provided to the municipalities of Zeta and Plužine to strengthen their ability to design and manage sustainable, inclusive, and climate-resilient infrastructure and municipal service projects, in line with Social and Environmental Standards (SES) and national investment planning standards. Indicators: 1.1: Number of completed local infrastructure projects in adherence to SES and climate resilience principles Baseline (2025): 0 Target (2027): 3 1.2.: Function grievance redress mechanism (levels: 0= not existing, 1 conceptualise, 2 = established, 3= used) Baseline (2025): 0 Target (2027): 3 1.3: Number of new investment projects developed by municipal staff applying SES and climate resilience principles Baseline (2025): 0 Target (2027): 2 Related CP outcome: Outcome 1: By 2027, all people, especially vulnerable people, benefit from improved management and state of natural resources and increasingly innovative, competitive, gender-responsive and inclusive economic development that is climate resilient and low carbon | 1.1 Tendering, implementation and supervision of Zeta Fire Station |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 71300-Local Consultants | 10,000 | 11,587 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 72100-Contractual Services-Companies | 1,225,000 | 1,419,467 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 71600 - Travel | 500 | 579 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 74200-Audio Visual&Print Prod | 1,000 | 1,159 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 71400-Contractual Services-Individ | 20,148 | 23,347 |
|  |  |  |  |  |  |  |  |  |  | Municipality Zeta | 67200 - Labour Cost - Staff | 3,358 | 3,891 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 74596-DPC | 25,200 | 29,201 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 75100 - GMS | 64,260 | 74,462 |
|  | TOTAL 1.1. |  |  |  |  |  |  |  |  |  |  | 1,349,467 | 1,563,692 |
|  | 1.2. Tendering, implementation and supervision of Zeta Funeral Home |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 71300-Local Consultants | 10,000 | 11,587 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 72100-Contractual Services-Companies | 200,000 | 231,750 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 71600 - Travel | 500 | 579 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 74200-Audio Visual&Print Prod | 1,000 | 1,159 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 71400-Contractual Services-Individ | 20,148 | 23,347 |
|  |  |  |  |  |  |  |  |  |  | Municipality Zeta | 67205 - Labour Cost - NO Staff | 3,358 | 3,891 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 74596-DPC | 4,700 | 5,663 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 75100 - GMS | 11,985 | 13,899 |
|  | TOTAL 1.2. |  |  |  |  |  |  |  |  |  |  | 251,692 | 291,875 |
|  | 1.3 Tendering, implementation and supervision of Pluzine sidewalk pavement |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 71300-Local Consultants | 10,000 | 11,587 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 72100-Contractual Services-Companies | 340,000 | 393,975 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 71600 - Travel | 1,000 | 1,159 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 74200-Audio Visual&Print Prod | 1,000 | 1,159 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 71400-Contractual Services-Individ | 20,148 | 23,347 |
|  |  |  |  |  |  |  |  |  |  | Municipality Pluzine | 67205 - Labour Cost - NO Staff | 3,358 | 3,891 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 74596-DPC | 7,510 | 8,702 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 75100 - GMS | 19,151 | 22,191 |
|  | TOTAL 1.3. |  |  |  |  |  |  |  |  |  |  | 402,167 | 466,011 |
|  | 1.4. Establishing an accountability and transparency mechanism - Zeta Municipality |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 74200-Audio Visual&Print Prod | 1,000 | 1,159 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 71400-Contractual Services-Individ | 20,148 | 23,347 |
|  |  |  |  |  |  |  |  |  |  | Municipality Zeta | 67205 - Labour Cost - NO Staff | 3,358 | 3,891 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 74596-DPC | 490 | 852 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 75100 - GMS | 1,250 | 1,462 |
|  | TOTAL 1.4. |  |  |  |  |  |  |  |  |  |  | 26,246 | 30,711 |
|  | 1.5. Establishing an accountability and transparency mechanism - Pluzine Municipality |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 71300-Local Consultants | 10,000 | 11,587 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 71400-Contractual Services-Individ | 20,148 | 23,347 |
|  |  |  |  |  |  |  |  |  |  | Municipality Pluzine | 67205 - Labour Cost - NO Staff | 3,358 | 3,891 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 74596-DPC | 670 | 1,165 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 75100 - GMS | 1,709 | 1,999 |
|  | TOTAL 1.5. |  |  |  |  |  |  |  |  |  |  | 35,885 | 41,989 |
|  | 1.6 Capacity development for municipal staff on preparing and managing climate-resilient local investment projects - Zeta Municipality |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 74200-Audio Visual&Print Prod | 1,000 | 1,159 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 71400-Contractual Services-Individ | 20,148 | 23,347 |
|  |  |  |  |  |  |  |  |  |  | Municipality Zeta | 67205 - Labour Cost - NO Staff | 3,358 | 3,891 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 75700-Training, Workshops&Confer | 10,000 | 11,587 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 74596-DPC | 690 | 1,200 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Zeta | 75100 - GMS | 1,760 | 2,059 |
|  | TOTAL 1.6. |  |  |  |  |  |  |  |  |  |  | 36,956 | 43,243 |
|  | 1.7 Capacity development for municipal staff on preparing and managing climate-resilient local investment projects - Pluzine Municipality |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 71300-Local Consultants | 19,000 | 22,016 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 74200-Audio Visual&Print Prod | 1,000 | 1,159 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 71400-Contractual Services-Individ | 20,148 | 23,347 |
|  |  |  |  |  |  |  |  |  |  | Municipality Pluzine | 67205 - Labour Cost - NO Staff | 3,358 | 3,891 |
|  |  |  |  |  |  |  |  |  |  | Municipality Pluzine | 74596-DPC | 490 | 852 |
|  |  |  |  |  |  |  |  |  | UNDP | Municipality Pluzine | 75100 - GMS | 2,200 | 2,563 |
|  | TOTAL 1.7. |  |  |  |  |  |  |  |  |  |  | 46,196 | 53,828 |
|  |  |  |  |  |  |  |  |  |  | Municipality Zeta |  | 1,664,360 | 1,929,521 |
|  |  |  |  |  |  |  |  |  |  | Municipality Pluzine |  | 484,248 | 561,828 |
|  |  |  |  |  |  |  |  |  |  |  | TOTAL | 2,148,609 | 2,491,348 |

Maximum 18 months