| Quantum Project ID: | 01005272 | Project Title: | Integrated Management of Permafrost Peatland in Northern China for Biodiversity Conservation and Climate Actions |
| --- | --- | --- | --- |
| Quantum Award ID: | 1537495 | Award Title: | PIMS-10140-Integrated Management of Permafrost Peatland in Northern China for Biodiversity Conservation and Climate Actions |
| Business Unit: | UNDP-CHN |  |  |
| PIMS number: | 10140 |  |  |
| Implementing Partner: | UNDP China (DIM) |  |  |

| GEF Outcome/Quantum Activity | RP | Fund ID | Donor Name | Quantum Budgetary Account Code | QUANTUM Budget Description | Approved amount | 2026 budget | 2027 budget | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project preparation grant to finalize the UNDP-GEF project document for project Integrated Management of Permafrost Peatland in Northern China for Biodiversity Conservation and Climate Actions | UNDP | 62000 | GEF TRUSTEE | 71200 | International Consultants | 62,250 | 62,250 | 0 | The project is projected to employ two international consultants. The commencement of their employment is scheduled for early 2026, with corresponding budgetary allocations anticipated to be incurred in 2026. The formulation team aims to leverage specialized expertise to enhance the project's capabilities and deliverables. |
|  |  |  |  | 71300 | Local Consultants | 61,800 | 61,800 | 0 | The project is projected to employ seven national consultants. The commencement of their employment is scheduled for early 2026, with corresponding budgetary allocations anticipated to be incurred in 2026. The formulation team aims to leverage specialized expertise to enhance the project's capabilities and deliverables. |
|  |  |  |  | 71400 | Contractual Services – Individual | 29,900 | 19,940 | 9,960 | To guarantee the project’s timely and high-quality advancement, the National Coordinator will ensure active participation in key processes, while primarily providing support for the execution of relevant procedures, documentation preparation, and stakeholder communication. This role is designed to reinforce process integrity, streamline administrative workflows, and facilitate effective coordination among involved parties. |
|  |  |  |  | 71600 | Travel | 34,800 | 34,800 | 0 | The field mission is designated as a primary and core activity during the PPG phase. It ensures the accuracy and feasibility of Prodoc package, thereby validating that proposed interventions align with on-the-ground realities and can be effectively implemented. Travel-related budgets for this activity are primarily allocated to field mission in the first half of 2026. These funds are expected to cover transportation tickets and DSA. |
|  |  |  |  | 74100 | Audit | 3,500 | 3,500 | 0 | For the purpose of robust project risk management, it is imperative to ensure the ongoing effectiveness of relevant reviews pertaining to government partners. It is anticipated that audits of these relevant partners will be conducted during 2026. |
|  |  |  |  | 72400 | Communic & Audio Visual Equip | 2,750 | 1,000 | 1,750 | During PPG phase, the relevant budgetary allocations will be utilized to cover expenses associated with mobile charges, land telephone charges, connectivity costs, courier charges, and other related activities and tasks. |
|  |  |  |  | 75700 | Trainings, workshops | 5,000 | 2,500 | 2,500 | During PPG phase, relevant budgetary allocations will be designated for the preparation of key meetings, such as the inception workshop, validation workshop, LPAC, etc. |
|  |  |  |  |  | PROJECT TOTAL | 200,000 | 185,790 | 14,210 |  |