## KBF Workplan GMS ACT
KUNMING BIODIVERSITY FUND - UNDP HONDURAS PLAN - HONDURAS
Multi-Year Work Plan
Pre-filled | Pre-filled | Countries will fill-out details, TAs to review Note: Activities encoded are just an example. Please revise as necessary | [8 empty] | Pre-filled Do not delete a line, but you may add lines if necessary NOTE: The introduction of new budget items/or components cannot exceed 5% of original GEF allocation. |  |  |  |  | ORIGINAL BUDGET BASED ON PRODOC DO NOT EDIT THIS PORTION |  |  | Countries will fill-out details, TAs to review Please revise as necessary |  |  | PLEASE DO NOT EDIT If highlighted in RED, please provide budget explanation for changes If highlighted in GREEN, no need to add a justification | Countries will fill-out details Global Implementation PA to review | Countries will fill-out Please provide additional information (% tranche of consultant, how many workshops, details of travel cost) PLEASE REVISE AS NECESSARY | TA Comments
Quantum Output (GEF Outcome) | PLANNED ACTIVITIES/OUTPUTS Quantum Activity (GEF Output) | ACTIVITIES | TIMELINE Nov 30, 2025- Nov 30, 2026 |  |  |  | TIMELINE Nov 30, 2026-Nov 30, 2027 |  |  |  | RESPONSIBLE PARTY (IA Code) | Fund Codes | Donor Codes | Budget Code | Budget Description | ORIGINAL BUDGET BASED ON PRODOC |  |  | PROPOSED BUDGET |  |  | Deviation from budget approved in Prodoc | Justification for changes ABOVE 5,000 USD | Description of Expense | TA Comments
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | [5 empty] | Amount (USD) 2026 | Amount (USD) 2027 | TOTAL Amount (USD) | Amount (USD) 2026 | Amount (USD) 2027 | TOTAL Amount (USD)
Component 1: Strengthened Biodiversity Conservation Efforts
1. Two Marine Protected areas (MAPs) in the Garifuna regions of Colón effectively implementing action plans through multi-stakeholders’ committees promoting women active participation | 1.1 Two (2) MPAs benefit from the implementation of Managed Access with Reserve (MA+R) actions and enhancing biodiversity conservation | Activity 1.1.1 - MPA Committee meetings or workshops (3-5) identifying biodiversity and habitat conservation measures within their specifics actions plans in 2 MPAs (Santa Rosa de Aguan and Trujillo) | [8 empty] | UNDP (001981) | 30000 | 014381 | 72100 | Transfers and Grants to Counterparts (CEM) | 27000 | 18000 | 45000 | 27000 | 18000 | 45000 | 0 |  | Cost associated for travel for the workshops and meetings for committees , local transportation, accomodations trainers, Cost associated with the logistics for the workshops and meetings for committees ( Food and Service) and Cost associated to trainers ot the workshops and meetings for committees | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2 to TIMELINE Nov 30, 2025- Nov 30, 2026 Q4
[14 empty] | 74100 | General Operating and Other Direct Costs (PNUD) | 3000 | 3000 | 6000 | 1147.01 | 4852.99 | 6000 | 0 |  | Cost associated to Microevaluation and Spottchecks for Responsible Partners | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2 to TIMELINE Nov 30, 2025- Nov 30, 2026 Q4
[14 empty] | 75100 | Facilities and administration (GMS) | 2100 | 1470 | 3570 | 1970.2907 | 1599.7093 | 3570 | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2 to TIMELINE Nov 30, 2025- Nov 30, 2026 Q4
|  | Activity 1.1.2 – Implementing (MA+R) community monitoring and surveillance actions and habitat conservation for mangroves and seagrass meadows in 2 MPAs from Santa Rosa de Aguan and Trujillo approved by local Committees | [11 empty] | 72100 | Transfers and Grants to Counterparts (CEM) | 83268 | 55512 | 138780 | 83268 | 55512 | 138780 | 0 |  | Cost associated with supplies for control and surveillance activities, fuel, reforestacion and restoration mangrove and seagrass meadow, Cost associated with travel for reforestacion and restoration mangrove and seagrass meadow and Cost associated with field logistics for control and surveillance activities, monitoring equipment purchase | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q3 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q4
[14 empty] | 71600 | Travel (PNUD) | 2500 | 2500 | 5000 | 2500 | 2500 | 5000 | 0 |  | Costs related to organizing and conducting training sessions for government participation | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q3 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q4
[14 empty] | 71400 | Staff and other personnel (PNUD RLAC) | 1768.33 | 1768.33 | 3536.66 | 1768.33 | 1768.33 | 3536.66 | 0 |  | Technical advisory support by CTA | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q3 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q4
[14 empty] | 75100 | Facilities and administration (GMS) | 6127.5431 | 4184.6231 | 10312.1662 | 6127.5431 | 4184.6231 | 10312.1662 | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q3 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q4
| Total Output 1.1.1: | [14 empty] | 125763.8731 | 86434.9531 | 212198.8262 | 123781.1738 | 88417.6524 | 212198.8262 | 0
Total component 1 | [15 empty] | 125763.8731 | 86434.9531 | 212198.8262 | 123781.1738 | 88417.6524 | 212198.8262 | 0
Component 2: Enhance community governance and capacity:
Outcome 2. Garifunas and local representatives from the five (5) MPA committees empowered and trained for effective decision-making in coastal marine resources with inclusive gender approach | 2.1. At least 600 community members amongst the five (5) MPAs empowered and trained with skills to improve governance, knowledge and capacity for decision making including women active participation (180 women participating, 30% from beneficiaries) | Activity 2.1.1 One Gender analysis workshop for 5 MPA committees | [8 empty] | UNDP (001981) | 30000 | 014381 | 72100 | Transfers and Grants to Counterparts (RARE) | 10000 |  | 10000 | 10000 |  | 10000 | 0 |  | Costs related to travel, supplies, trainers, food and service for organizing and conducting training sessions for committees | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2
[14 empty] | 75100 | Facilities and administration (GMS) | 700 |  | 700 | 700 |  | 700 | 0 | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2
|  | Activity 2.1.2 – Gender-focused workshops (2-3) on inclusive production systems for communities | [11 empty] | 72100 | Transfers and Grants to Counterparts (RARE) | 16000 | 9000 | 25000 | 17000 | 8000 | 25000 | 0 |  | Costs related to travel, supplies, trainers, food and service for organizing and conducting training sessions for committees | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q3 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q1
[14 empty] | 75100 | Facilities and administration (GMS) | 1120 | 630 | 1750 | 1190 | 560 | 1750 | 0 | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q3 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q1
|  | Activity 2.1.3 – Trainings (2-4) on best marine practices for sustainable fisheries for improved food security and environmental sustainability in 5 MPAs | [11 empty] | 72100 | Transfers and Grants to Counterparts (RARE) | 16140 | 16140 | 32280 | 32280 |  | 32280 | 0 |  | Costs related to travel, supplies, trainers, food and service for organizing and conducting training sessions for committees | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2; TIMELINE Nov 30, 2025- Nov 30, 2026 Q4 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q1
[14 empty] | 75100 | Facilities and administration (GMS) | 1129.8 | 1129.8 | 2259.6 | 2259.6 |  | 2259.6 | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2; TIMELINE Nov 30, 2025- Nov 30, 2026 Q4 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q1
|  | Activity 2.1.4 - Workshops (1–2) on good policy and leadership in community governance and protected areas management, ensuring equitable participation of women and men and with a focus on strengthening women’s leadership. | [11 empty] | 72100 | Transfers and Grants to Counterparts (RARE) | 12500 | 12500 | 25000 | 14800 | 10200 | 25000 | 0 |  | Costs related to travel, supplies, trainers, food and service for organizing and conducting training sessions for committees | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2; TIMELINE Nov 30, 2026-Nov 30, 2027 Q1
[14 empty] | 71600 | Travel (PNUD) | 2500 | 2500 | 5000 | 2500 | 2500 | 5000 | 0 |  | Costs related to organizing and conducting training sessions for government participation | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2; TIMELINE Nov 30, 2026-Nov 30, 2027 Q1
[14 empty] | 74100 | General opeating and otjer Direct costs (PNUD) | 3000 | 3000 | 6000 | 1147.01 | 4852.99 | 6000 | 0 |  | Cost associated to Microevaluation and Spottchecks for Responsible Partners | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2; TIMELINE Nov 30, 2026-Nov 30, 2027 Q1
[14 empty] | 71400 | Staff and other personnel (PNUD RLAC) | 1768.33 | 1768.34 | 3536.67 | 1768.33 | 1768.34 | 3536.67 | 0 |  | Technical advisory support by CTA | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2; TIMELINE Nov 30, 2026-Nov 30, 2027 Q1
[14 empty] | 75100 | Facilities and administration (GMS) | 1383.78 | 1383.79 | 2767.57 | 1415.0738 | 1352.4962 | 2767.57 | 0 | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2; TIMELINE Nov 30, 2026-Nov 30, 2027 Q1
|  | Activity 2.1.5 - One Peer-to-peer community exchange for knowledge sharing on community-based management for bioiversity conservation and MA+R Docusign Envelope ID: 7E8066B2-450A-4A28-85CE-3B8F38EE7359 18 for biodiversity conservation and MA+R | [11 empty] | 72100 | Transfers and Grants to Counterparts (RARE) |  | 30000 | 30000 | 17000 | 13000 | 30000 | 0 |  | Costs related to organizing and conducting peer-to-peer exchanges including travels for attendees and trainers (national or international) | bar: TIMELINE Nov 30, 2026-Nov 30, 2027 Q1
[14 empty] | 75100 | Facilities and administration (GMS) |  | 2100 | 2100 | 1190 | 910 | 2100 | 0
|  | Activity 2.1.6 - Visibility and communications – materials for Fishing for Life campaigns for community awareness | [11 empty] | 72100 | Transfers and Grants to Counterparts (RARE) | 18000 | 7000 | 25000 | 17000 | 8000 | 25000 | 0 |  | Development of materials and supplies for awareness campaign for communities outreach. | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q3; TIMELINE Nov 30, 2026-Nov 30, 2027 Q1; TIMELINE Nov 30, 2026-Nov 30, 2027 Q3
[14 empty] | 75100 | Facilities and administration (GMS) | 1260 | 490 | 1750 | 1190 | 560 | 1750
| Total Output 2.1.1: | [14 empty] | 85501.91 | 87641.93 | 173143.84 | 121440.0138 | 51703.8262 | 173143.84 | 0
Total Component 2 | [15 empty] | 85501.91 | 87641.93 | 173143.84 | 121440.0138 | 51703.8262 | 173143.84 | 0
Component 3: Sustainable Livelihoods for Garifuna Communities
Outcome 3.1 Garifuna communities in Colon and north Moskitia empowered to pursue sustainable livelihoods, biodiversity conservation, and gender-inclusive development . | 3.1.1 10 community groups in Colon and north Moskitia strengthen their livelihoods through sustainable practices, food security, and biodiversity-friendly economic alternatives with 30% of them implemented by women. | Activity 3.1.1 - Baseline and diagnosis meetings/site visits (2-3) to identify the communities´ ideas | [8 empty] | UNDP (001981) | 30000 | 014381 | 71600 | Travel (PNUD) | 6000 |  | 6000 | 6000 | 0 | 6000 | 0 |  | Costs related to organizing and conducting diagnosis sessions for communities including travels for trainers and staff | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q1
[14 empty] | 75700 | Contractual services - Individuals (PNUD) Training, Workshop and Conference | 5000 |  | 5000 | 1200 | 3800 | 5000 | 0 |  | Costs related to organizing and conducting diagnosis sessions for communities including travels for trainers and staff ( Food and Services) | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q1
[14 empty] | 75100 | Facilities and administration (GMS) | 770 |  | 770 | 504 | 266 | 770 | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q1
|  | Activity 3.1.2 - Formulation workshop to facilitate development of Garifuna community grants portfolio, led by the Small Grants Program (SGP) of Honduras using their community driven methodology. | [11 empty] | 71400 | Contractual Service Individ (RLAC) | 1768.33 | 1768.34 | 3536.67 | 1768.33 | 1768.34 | 3536.67 | 0 |  | Costs related to organizing and conducting training sessions for communities beneficiaries groups | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2
[14 empty] | 71600 | Travel (PNUD) | 7500 |  | 7500 | 3192.79 | 4307.21 | 7500 | 0 |  | Costs related to organizing and conducting training sessions for communities beneficiaries groups ( Food and Services) | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2
[14 empty] | 72500 | supplies, commodities materials (PNUD) | 3000 |  | 3000 | 1500 | 1500 | 3000 | 0 |  | Costs related to office supplies for organizing and conducting training sessions for communities beneficiaries groups | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2
[14 empty] | 74100 | Professional Services (GMS) | 1278.78 | 123.79 | 1402.57 | 872.2784 | 530.2885 | 1402.5669 | -0.0031
[14 empty] | 75700 | Training, Workshops and cont | 6000 |  | 6000 | 6000 |  | 6000 | 0 |  | Technical advisory support by CTA | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2
|  | Activity 3.1.3- Implementation of the small grants' community projects (10) focused on biodiversity conservation, food security, and social development activities within the Garifuna region in Colon in North Moskitia (3 grants lead by women) | [11 empty] | 71300 | Contractual services - Individuals (PNUD) | 21000 | 24000 | 45000 | 45000 |  | 45000 | 0 |  | Cost related individual consultant to implement and monitoring on the ground small grants and liason implementation activities in component 1 and 2 | Se realizo el cambio de categoria de gasto debido a que se realizara la contratacion de tecnico (71300) del socio responsable CEM (72100) | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q2 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q4
[14 empty] | 72600 | Transfers and Grants to Counterparts | 175000 | 175000 | 350000 | 175000 | 175000 | 350000 | 0 |  | Small grants to be provided to community projects (10) focused on biodiversity conservation, food security and social development activities within the Garifuna region in Colon in North Moskitia | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q3 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q4
[14 empty] | 75100 | Facilities and administration (GMS) | 13720 | 13930 | 27650 | 15400 | 12250 | 27650
| Total Output 3.1.1: | [14 empty] | 241037.11 | 214822.13 | 455859.24 | 256437.3984 | 199421.8385 | 455859.2369 | -0.0031
Total Component 3 | [15 empty] | 241037.11 | 214822.13 | 455859.24 | 256437.3984 | 199421.8385 | 455859.2369 | -0.0031
Component 4: Risk Management, M&E and Quality Assurance
Outcome 4.Risk Management, M&E and Quality Assurance | 4.1. Prepare, implement and monitor an integrated Risk management system for the project in line with UNDP and national policies (including stakeholder engagement, gender mainstreaming, social and environmental standards and accountability to stakeholders) | Activity 4.1.1 Implementation and monitoring of safeguards risk framework | [8 empty] | UNDP (001981) | 30000 | 014381 | 71400 | Contractual Service Individ | 5000 | 3000 | 8000 | 8000 |  | 8000 | 0 |  | Undertake social and environmental risk screenings and assessments, and prepare appropriate management measures, in line with UNDP’s SES Policy and applicable national requirements. At a minimum, this will include development of Stakeholder Engagement Plan, Gender Action Plan and other frameworks or plans as indicated in the SESP. Indigenous Peoples Plans and FPIC will be required where project affected IP&LC are present in the targeted landscapes. | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q1 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q4
[14 empty] | 75100 | Facilities and administration (GMS) | 420 | 280 | 700 | 630 | 70 | 700
[14 empty] | 75700 | Contractual services - Individuals (PNUD) Training, Workshop and Conference | 1000 | 1000 | 2000 | 1000 | 1000 | 2000 | 0 |  | Cost associated to workshops and meetings for SES implementation related to updating RPs safeguards under UNDP's framework | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q1 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q4
|  | Activity 4.1.2 Developing a Risk Management system for the project | [11 empty] | 71400 | Staff and other personnel (PNUD) | 1000 | 1000 | 2000 | 1000 | 1000 | 2000 | 0 |  | To implement, monitor and maintain the project Risk Management Matrix and related mitigation measures. | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q1 to TIMELINE Nov 30, 2025- Nov 30, 2026 Q2
[14 empty] | 74100 | Professional Services (GMS) | 70 | 70 | 140 | 70 | 70 | 140 | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q1 to TIMELINE Nov 30, 2025- Nov 30, 2026 Q2
| Total Output 4.1.1: | [14 empty] | 7490 | 5350 | 12840 | 10700 | 2140 | 12840 | 0
| 4.2 Monitoring & Evaluation and Quality Assurance Systems | Activity 4.2.1 Establishing a Monitoring and Evaluation system for the project | [8 empty] | UNDP (001981) | 30000 | 014381 | 71400 | Contractual service - individ | 1000 | 1000 | 2000 | 1000 | 1000 | 2000 | 0 |  | Development of M&E framework | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q1 to TIMELINE Nov 30, 2025- Nov 30, 2026 Q2
[14 empty] | 74100 | Professional Services (GMS) | 70 | 70 | 140 | 70 | 70 | 140 | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q1 to TIMELINE Nov 30, 2025- Nov 30, 2026 Q2
|  | Activity 4.2.2: Providing quality assurance of technical outputs, knowledge products, M&E and SES implementation | [11 empty] | 71400 | Contractual services - Individ (RBLAC) | 14766 | 9844 | 24610 | 14766 | 9844 | 24610 | 0 |  | Technical advisory support, quality assurance of results, knowledge sharing and coordination, compliance support, reporting | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q1 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q4
[14 empty] | 71600 | Travel (PNUD RLAC) | 3500 | 3500 | 7000 | 3500 | 3500 | 7000 | 0 |  | Costs related to trave for Regional technical advisory support, quality assurance of results, knowledge sharing and coordination, compliance support, reporting | bar: TIMELINE Nov 30, 2025- Nov 30, 2026 Q1 to TIMELINE Nov 30, 2026-Nov 30, 2027 Q4
[14 empty] | 75100 | Facilities and administration (GMS) | 1278.62 | 934.08 | 2212.7 | 1278.62 | 934.08 | 2212.7
| Total Output 4.1.2: | [14 empty] | 20614.62 | 15348.08 | 35962.7 | 20614.62 | 15348.08 | 35962.7 | 0
Total Component 4 | [15 empty] | 28104.62 | 20698.08 | 48802.7 | 31314.62 | 17488.08 | 48802.7 | 0
GMS | [15 empty] | 35026.5031 | 30394.0631 | 65420.5662
Project Management Cost | [13 empty] | 71400 | Contractual Services- individ | 47090 | 47090 | 94180 | 47090 | 47090 | 94180 | 0
[14 empty] | 71600 | Travel | 4309.72 | 4309.72 | 8619.44 | 4309.72 | 4309.72 | 8619.44
[14 empty] | 75100 | Facilities and administration (GMS) | 3597.98 | 3597.98 | 7195.96 | 3597.9804 | 3597.9804 | 7195.9608
Total PMU | [15 empty] | 54997.7 | 54997.7 | 109995.4 | 7907.7004 | 54997.7004 | 62905.4008
Grand Total | [15 empty] | 535405.2131 | 464594.7931 | 1000000.0062 | 540880.9064 | 412029.0975 | 952910.0039 | -0.0031
Observaciones:
Note on C5: Kamille Rosales: Narrative written here is just an example
Note on Y5: Kamille Rosales: All remarks written here are just an example
Note on Z5: Kamille Rosales: All remarks written here are just an example
Note on V6: Kamille Rosales: Delete rows that are not applicable
Note on P9: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: Auditorias

## Resumen Staff Personnel
| Descripcion | Costo Mensual/ Costo Viaje | Meses/ Cantidad | Porcentaje | Monto
Staff and Personnel | Coordinación/Monitoreo | 3000 | 20 | 100% | 60000
| Administrativo | 2000 | 24 | 10% | 4800
| Genero | 3000 | 24 | 10% | 7200
| Comunicación | 1800 | 12 | 5% | 1080
| Apoyo Oficina UDSR | 400 | 24 | 5% | 9600
| DPC |  |  |  | 11500
94180
Viajes | Viáticos | 1068 | 8 |  | 8619.44
8619.44
102799.44