## Detailed Budget (hidden)
Activities | Deliverables | Sub-activities | Modality | Consultants | Participants | Frequency | Unit cost (DSA, fees, venue, refreshments, logistics etc) | Total | ImplementationPeriod |  |  | Budget Breakdown |  |  | Amount (USD) | Moved Total/Subtotal
[9 empty] | Year1 | Year2 | Year3 | Year 1 | Year 2 | Year 3
Project Output 1: The digital health ecosystem is strengthened
1.1 Build the capacity of the Information, Communication, and Technology (ICT) Department of the Ministry of Health (MOH). | 1. On the job training package 2. Annual training reports | 1. Conduct a needs assessment to identify the specific skills and knowledge gaps | Technical Assistance | Matiko + Consultants | 2 | 14 | 400 | 11200 | X | X | X | 3733.3333 | 3733.3333 | 3733.3333 | 11200
|  | 2. Define the training objectives based on the identified needs | Technical Assistance | Matiko + Maryam | 2 | 5 | 300 | 3000 | X |  |  | 3000 |  |  | 3000
|  | 3. Develop a comprehensive training plan for the ICT department | Technical Assistance | Matiko + Maryam | 2 | 5 | 300 | 3000 | X |  |  | 3000 |  |  | 3000
|  | 4. Develop training materials | Technical Assistance | Matiko + Consultants | 2 | 10 | 300 | 6000 | X |  |  | 6000 |  |  | 6000
|  | 5. Conduct practical for one week long on-the-Job training | Technical Assistance | Matiko + Consultants | 3 | 20 | 400 | 24000 | X | X | X | 8000 | 8000 | 8000 | 24000
|  |  | Workshops | MoH | 10 | 20 | 30 | 6000 | X | X | X | 2000 | 2000 | 2000 | 6000
|  | 6. Establish pre and post training evaluation mechanism to collect input from participants during and after the training to determine if the learning objectives have been met | Technical Assistance | Matiko + Maryam | 2 | 5 | 300 | 3000 | X | X | X | 1000 | 1000 | 1000 | 3000
|  | 7. Provide remote technical backstopping and mentoring to staff as they apply their new skills in their daily tasks | Technical Assistance | Matiko + consultants | 3 | 4 | 300 | 3600 | X | X | X | 1200 | 1200 | 1200 | 3600
|  | 8. Conduct semi-annual evaluations to assess the effectiveness of the training program vis a vis the objectives | Technical Assistance | Matiko + Maryam | 2 | 10 | 400 | 8000 | X | X | X | 2666.6667 | 2666.6667 | 2666.6667 | 8000
|  | 9. Documentation best practices, lessons learned and challenges emerged during the training | Technical Assistance | Matiko + Maryam | 2 | 10 | 400 | 8000 | X | X | X | 2666.6667 | 2666.6667 | 2666.6667 | 8000
[8 empty] | 75800 | SubTotal |  |  | 33266.6667 | 21266.6667 | 21266.6667 | 75800
1.2 Update the functionality and disease classification in DHIS-2, ZanEMR, and Jamii ni Afya. | MOH-approved user acceptance test report for the improved DHIS-2, ZanEMR, and Jamii ni Afya | 1. Conduct a system review to understand the current state of DHIS-2, ZanEMR, and Jamii ni Afya | Technical Assistance | Matiko + consultants | 3 | 10 | 400 | 12000 | X |  |  | 12000 |  |  | 12000
|  | 2. Engage with key stakeholders, including users, developers, and decision-makers, to gather input on required improvements and interoperability features. | Technical Assistance | Matiko + Maryam | 2 | 10 | 400 | 8000 | X |  |  | 8000 |  |  | 8000
|  |  | Workshops | HCW, CHMT, MOH | 30 | 5 | 30 | 4500 | X |  |  | 4500 |  |  | 4500
|  | 3. Establish data standards and protocols for interoperability, including a common data model and communication standards and adopt international standards such as HL7 (Health Level Seven) for health information exchange) | Technical Assistance | Matiko + consultants | 3 | 15 | 300 | 13500 | X |  |  | 13500 |  |  | 13500
|  | 4. Conduct data mapping and harmonization among these systems | Technical Assistance | Consultants | 2 | 21 | 400 | 16800 | X |  |  | 16800 |  |  | 16800
|  | 5. Customize each system to align with the defined standards and interoperability requirements | Technical Assistance | Matiko + consultants | 3 | 21 | 300 | 18900 | X |  |  | 18900 |  |  | 18900
|  | 6. Create Application Programming Interfaces (APIs) | Technical Assistance | Consultants | 2 | 21 | 300 | 12600 | X |  |  | 12600 |  |  | 12600
|  | 7. Test and train end-users, administrators, and IT staff on the updated systems and new interoperability features | Technical Assistance | Matiko + consultants | 3 | 10 | 400 | 12000 |  | X |  |  | 12000 |  | 12000
|  |  | Workshops | HCW, CHMT, MOH | 134 | 10 | 30 | 40200 |  | X |  |  | 40200 |  | 40200
|  | 8. Deploy the updated systems to live environment at ZICTA data centre | Technical Assistance | Matiko + consultants | 3 | 5 | 400 | 6000 |  | X |  |  | 6000 |  | 6000
|  | 9. Collect feedback from users and stakeholders to identify areas for further improvement | Technical Assistance | Matiko + Maryam | 2 | 10 | 400 | 8000 |  | X |  |  | 8000 |  | 8000
|  | 10. Do a continuous improvement based on feedback for 2 years | Technical Assistance | Matiko + consultants | 3 | 32 | 400 | 38400 |  | X |  |  | 38400 |  | 38400
|  | 11. Document the entire process, including system configurations, data mappings, and interoperability protocols | Technical Assistance | Matiko + Maryam | 2 | 21 | 400 | 16800 |  | X |  |  | 16800 |  | 16800
[8 empty] | 207700 | SubTotal |  |  | 86300 | 121400 | 0 | 207700
1.3 Create the digital integration pathways for key systems. | 1.2 Update the functionality and disease classification in DHIS-2, ZanEMR, and Jamii ni Afya. | 1. Identify the key data elements that need to be synchronized between Jamii ni Afya, ZanEMR and DHIS2 | Technical Assistance | Matiko + Maryam+consultants | 3 | 10 | 400 | 12000 | X |  |  | 12000 |  |  | 12000
|  | 2. Map the data fields from Jamii ni Afya and ZanEMR to the corresponding data elements in DHIS2 | Technical Assistance | Matiko + consultants | 3 | 21 | 400 | 25200 | X |  |  | 25200 |  |  | 25200
|  |  | Workshops | MoH | 20 | 10 | 50 | 10000 | X |  |  | 10000 |  |  | 10000
|  | 3. Define data formats in Jamii ni Afya and ZanEMR, standardized them and make compatible with DHIS2 requirements | Technical Assistance | Matiko | 1 | 21 | 400 | 8400 | X |  |  | 8400 |  |  | 8400
|  | 4. Explore APIs provided by the respective systems as well as for the ZHIL and create additional API's to allow smooth data exchanges | Technical Assistance | Matiko + consultants | 3 | 21 | 400 | 25200 | X |  |  | 25200 |  |  | 25200
|  | 5. Implement data validation rules, security standards checks and cleaning in ZanEMR and DHIS2 | Technical Assistance | Matiko + consultants | 3 | 10 | 300 | 9000 | X |  |  | 9000 |  |  | 9000
|  | 6. Conduct Testing and Train of ToT on the updated systems | Technical Assistance | Matiko + consultants | 3 | 12 | 400 | 14400 |  | X |  |  | 14400 |  | 14400
|  |  | Workshops | MoH | 22 | 10 | 50 | 11000 |  | X |  |  | 11000 |  | 11000
|  | 7. Define the frequency and timing of data aggregation between ZanEMR and DHIS-2 to ensure timely reporting | Technical Assistance | Matiko + consultants | 1 | 10 | 300 | 3000 |  | X |  |  | 3000 |  | 3000
|  | 8. Set up regular maintenance activities to address any issues that may arise and to keep the integration up-to-date with system changes | Technical Assistance | Matiko + consultants | 2 | 10 | 400 | 8000 |  | X |  |  | 8000 |  | 8000
|  | 9. Documentation for all the processes | Technical Assistance | Maryam +Matiko | 2 | 18 | 300 | 10800 |  | X |  |  | 10800 |  | 10800
[8 empty] | 137000 | SubTotal |  |  | 89800 | 47200 | 0 | 137000
1.4 Create a user-friendly Executive Data Visualization Dashboard. | Sample of the dashboard showcasing the analysis of five selected indicators | 1. Conduct a needs assessment to identify the needs from senior managers | Technical Assistance | Matiko + Maryam + Consultants | 5 | 5 | 300 | 7500 |  | X |  |  | 7500 |  | 7500
|  | 2. Conduct the data mapping (use cases) | Technical Assistance | Matiko + consultant | 4 | 10 | 300 | 12000 |  | X |  |  | 12000 |  | 12000
|  | 3. Create APIs | Technical Assistance | Matiko + consultant | 4 | 14 | 300 | 16800 |  | X |  |  | 16800 |  | 16800
|  | 4. Actual Integration | Technical Assistance | Matiko + consultant | 4 | 14 | 300 | 16800 |  | X |  |  | 16800 |  | 16800
|  | 5. Test | Technical Assistance | Matiko + consultant | 4 | 3 | 300 | 3600 |  | X |  |  | 3600 |  | 3600
|  | 6. Create the Dashboard | Technical Assistance | Matiko + consultant | 4 | 5 | 300 | 6000 |  | X |  |  | 6000 |  | 6000
[8 empty] | 62700 | SubTotal |  |  | 0 | 62700 | 0 | 62700
1.5 Develop a standardized essential ICT equipment list. | Draft ICT equipment list and maintenance plans | 1. Consult relevant stakeholders to establish a standardized list of essential ICT equipment that suits the diverse needs of different health facilities | Technical Assistance | Matiko + consultant | 2 | 14 | 400 | 11200 | X |  |  | 11200 |  |  | 11200
|  | 2. Define maintenance requirements for each type of equipment | Technical Assistance | Consultant | 1 | 21 | 400 | 8400 | X |  |  | 8400 |  |  | 8400
|  | 3. Create detailed maintenance procedures for each type of equipment | Technical Assistance | Consultant | 1 | 18 | 400 | 7200 | X |  |  | 7200 |  |  | 7200
|  | 4. Define clear criteria for determining when ICT equipment should be replaced | Technical Assistance | Consultant | 1 | 14 | 400 | 5600 | X |  |  | 5600 |  |  | 5600
|  | 5. Develop plans for replacing ICT equipment at the end of its lifecycle | Technical Assistance | Matiko + consultants | 2 | 14 | 400 | 11200 | X |  |  | 11200 |  |  | 11200
|  | 6.Provide training to healthcare staff on the proper use and maintenance of ICT equipment | Technical Assistance | Matiko + consultants | 2 | 21 | 400 | 16800 | X | X |  | 8400 | 8400 |  | 16800
|  |  | Workshops | ICTO - ToT | 20 | 5 | 50 | 5000 |  | X |  |  | 5000 |  | 5000
[8 empty] | 65400 | SubTotal |  |  | 52000 | 13400 | 0 | 65400
1.6 Conduct a baseline assessment of health facility connectivity. | 1. Baseline connecticity assessment report 2. DHIS-2 report showing the introduction of the new indicator | 1. Develop Assessment Criteria | Technical Assistance | Matiko +Maryam | 2 | 5 | 400 | 4000 | X |  |  | 4000 |  |  | 4000
|  | 2. Create appropriate tools for conducting the assessment | Technical Assistance | Matiko +Maryam+Consultant | 3 | 10 | 400 | 12000 | X |  |  | 12000 |  |  | 12000
|  | 3. Develop plan and schedule visits to health facilities for on-site assessments | Technical Assistance | Matiko +Maryam | 2 | 5 | 400 | 4000 | X |  |  | 4000 |  |  | 4000
|  | 4. Collect data on various aspects of connectivity, such as internet speed, network reliability, availability of backup systems, and the presence of essential communication tools | Technical Assistance | Consultants | 1 | 21 | 400 | 8400 | X |  |  | 8400 |  |  | 8400
|  | 5. Document the existing network infrastructure in each health facility | Technical Assistance | Consultants | 1 | 21 | 400 | 8400 | X |  |  | 8400 |  |  | 8400
|  | 6. Develop a connectivity indicator that can be used for regular reporting in DHIS-2 | Technical Assistance | Consultants | 1 | 21 | 400 | 8400 |  | X |  |  | 8400 |  | 8400
|  | 7. Evaluate the availability and quality of telecommunication services (e.g., phone lines, mobile networks) that support communication within and outside the health facility. | Technical Assistance | Consultants | 1 | 21 | 400 | 8400 |  | X |  |  | 8400 |  | 8400
|  | 8. Analyze the collected data to identify patterns, trends, and areas of improvement. | Technical Assistance | Consultants | 1 | 21 | 400 | 8400 |  | X |  |  | 8400 |  | 8400
|  | 9. Create a dashboard to monitor the indicator for regular reporting on connectivity status using the established connectivity indicator. | Technical Assistance | Matiko | 1 | 14 | 300 | 4200 |  | X |  |  | 4200 |  | 4200
|  | 10. Compile the findings into a comprehensive report which includes options to improve facilities' connectivity by entering long term contractual agreement with connectivity providers. | Technical Assistance | Maryam +Matiko | 2 | 10 | 300 | 6000 |  | X |  |  | 6000 |  | 6000
|  | 11. Advocacy to implement recommendations to effectively improve facilities' connecitivity | Technical Assistance | Maryam | 1 | 10 | 300 | 3000 |  |  | X |  |  | 3000 | 3000
[8 empty] | 75200 | SubTotal |  |  | 36800 | 35400 | 3000 | 75200
Sub-total | [11 empty] | 298166.6667 | 301366.6667 | 24266.6667 | 623800
Project Output 2: The use of digital solutions for quality improvement is enhanced
2.1 Design, develop, and roll out a digital supportive supervision solution. | 1. Demo supportive supervision solution 2. User acceptance test report | 1. Consult users to to ensure the solution aligns with their needs and expectations, define busines processes and produce the System Requiremement Specification (SRS) document | Technical Assistance | Matiko+Maryam | 2 | 14 | 400 | 11200 | X |  |  | 11200 |  |  | 11200
|  |  | Technical Assistance | MoH | 20 | 5 | 50 | 5000 | X |  |  | 5000 |  |  | 5000
|  | 2. Conduct SRS validation with few technical colleagues and senior officials | Technical Assistance | Matiko+Maryam | 2 | 2 | 400 | 1600 | X |  |  | 1600 |  |  | 1600
|  |  | Workshops | MoH | 20 | 2 | 30 | 1200 | X |  |  | 1200 |  |  | 1200
|  | 3. Conduct design sessions for detailed design of the user interface (UI) and user experience (UX) based on the SRS | Technical Assistance | Matiko + consultants | 3 | 21 | 400 | 25200 | X |  |  | 25200 |  |  | 25200
|  | 4. Coding of the system | Technical Assistance | Consultants | 2 | 21 | 400 | 16800 | X |  |  | 16800 |  |  | 16800
|  | 5. Conduct user Acceptance test (UAT) to identity errors, bugs and improve accordingly | Technical Assistance | Matiko + consultants | 3 | 10 | 400 | 12000 | X |  |  | 12000 |  |  | 12000
|  |  | Technical Assistance | MoH | 52 | 5 | 50 | 13000 | X |  |  | 13000 |  |  | 13000
|  | 6. Conduct training of trainers and capacity building end users | Technical Assistance | Matiko + Maryam | 2 | 10 | 400 | 8000 |  | X |  |  | 8000 |  | 8000
|  |  | Workshops | MoH | 60 | 5 | 50 | 15000 |  | X |  |  | 15000 |  | 15000
|  |  | DSA | Pemba | 9 | 5 | 110 | 4950 |  | X |  |  | 4950 |  | 4950
|  |  | DSA | Unguja | 27 | 5 | 80 | 10800 |  | X |  |  | 10800 |  | 10800
|  | 7. Rollout and Deployment (Deploy the solution to live environment) | Technical Assistance | Matiko + consultants | 3 | 5 | 400 | 6000 |  | X |  |  | 6000 |  | 6000
|  | 8. Establish mechanisms for ongoing monitoring and evaluation of the digital solution (Collect feedback from users and stakeholders to make continuous improvements) | Technical Assistance | Matiko + Maryam | 2 | 10 | 300 | 6000 |  | X |  |  | 6000 |  | 6000
|  | 9. Evaluate the performance and impact of the solution over time | Technical Assistance | Matiko + Maryam | 2 | 10 | 300 | 6000 |  | X |  |  | 6000 |  | 6000
|  | 10. Maintain and administer the platfom | Technical Assistance | Matiko + consultants | 3 | 32 | 300 | 28800 |  | X |  |  | 28800 |  | 28800
[8 empty] | 171550 | SubTotal |  |  | 86000 | 85550 | 0 | 171550
2.2 Design, develop, and roll out an e-learning platform for CHWs. | 1. The demo digital e-learning platform will be shared 2. The user acceptance test report | 1. Consult stakeholders to to ensure that the solution aligns with their needs and expectations and produce System Requiremement Specification (SRS) document | Technical Assistance | Matiko+Maryam + consultant | 3 | 10 | 400 | 12000 |  | X |  |  | 12000 |  | 12000
|  |  | Technical Assistance | MoH | 20 | 5 | 50 | 5000 |  | X |  |  | 5000 |  | 5000
|  | 2. Conduct SRS validation with senior officials | Technical Assistance | Matiko+Maryam | 2 | 2 | 400 | 1600 |  | X |  |  | 1600 |  | 1600
|  |  | Workshops | MoH and SUZA | 20 | 1 | 50 | 1000 |  | X |  |  | 1000 |  | 1000
|  | 3. Conduct design sessions for detailed design of the user interface (UI) and user experience (UX) based on the SRS | Technical Assistance | Matiko + consultants | 3 | 14 | 400 | 16800 |  | X |  |  | 16800 |  | 16800
|  | 4. Coding of the system | Technical Assistance | Matiko + consultants | 3 | 30 | 400 | 36000 |  | X |  |  | 36000 |  | 36000
|  | 5. Conduct user Acceptance test (UAT) to identity errors, bugs and improve accordingly | Technical Assistance | Matiko + Maryam | 3 | 10 | 400 | 12000 |  |  | X |  |  | 12000 | 12000
|  |  | Workshops | MoH and SUZA | 52 | 5 | 50 | 13000 |  |  | X |  |  | 13000 | 13000
|  | 6. Conduct training and capacity building end users | Technical Assistance | Matiko + Maryam | 2 | 10 | 400 | 8000 |  |  | X |  |  | 8000 | 8000
|  |  | Workshops | MoH | 60 | 5 | 50 | 15000 |  |  | X |  |  | 15000 | 15000
|  |  | DSA | Pemba | 9 | 5 | 110 | 4950 |  |  | X |  |  | 4950 | 4950
|  |  | DSA | Unguja | 27 | 5 | 80 | 10800 |  |  | X |  |  | 10800 | 10800
|  | 7. Rollout and Deployment (Deploy the solution to live environment) | Technical Assistance | Matiko + consultant | 2 | 10 | 400 | 8000 |  |  | X |  |  | 8000 | 8000
|  | 8. Establish mechanisms for ongoing monitoring and evaluation of the digital solution (Collect feedback from users and stakeholders to make continuous improvements) | Technical Assistance | Matiko + Maryam | 2 | 10 | 300 | 6000 |  |  | X |  |  | 6000 | 6000
|  | 9. Evaluate the performance and impact of the solution over time | Technical Assistance | Matiko + Maryam | 2 | 10 | 300 | 6000 |  |  | X |  |  | 6000 | 6000
|  | 10. Support and Maintanance for the platform | Technical Assistance | Matiko +consultants | 2 | 16 | 300 | 9600 |  |  | X |  |  | 9600 | 9600
[8 empty] | 165750 | SubTotal |  |  | 0 | 72400 | 93350 | 165750
2.3 Design, develop, and roll a peer exchange collaborative tool. | 1. The demo peer exchange platform 2. the user acceptance test report | 1. Consult stakeholders to to ensure that the solution aligns with their needs and expectations and produce System Requiremement Specification (SRS) document | Technical Assistance | Matiko+Maryam + consultant | 3 | 10 | 400 | 12000 |  | X |  |  | 12000 |  | 12000
|  |  | Technical Assistance | MoH | 20 | 5 | 50 | 5000 |  | X |  |  | 5000 |  | 5000
|  | 2. Conduct SRS validation with senior officials | Technical Assistance | Matiko+Maryam | 2 | 2 | 400 | 1600 |  | X |  |  | 1600 |  | 1600
|  |  | Workshops | MoH and SUZA | 20 | 1 | 50 | 1000 |  | X |  |  | 1000 |  | 1000
|  | 3. Conduct design sessions for detailed design of the user interface (UI) and user experience (UX) based on the SRS | Technical Assistance | Matiko + consultants | 3 | 14 | 400 | 16800 |  | X |  |  | 16800 |  | 16800
|  | 4. Coding of the system | Technical Assistance | Matiko + consultants | 3 | 30 | 400 | 36000 |  | X |  |  | 36000 |  | 36000
|  | 5. Conduct user Acceptance test (UAT) to identity errors, bugs and improve accordingly | Technical Assistance | Matiko + Maryam | 3 | 10 | 400 | 12000 |  |  | X |  |  | 12000 | 12000
|  |  | Workshops | MoH and SUZA | 52 | 5 | 50 | 13000 |  |  | X |  |  | 13000 | 13000
|  | 6. Conduct training and capacity building end users | Technical Assistance | Matiko + Maryam | 2 | 10 | 400 | 8000 |  |  | X |  |  | 8000 | 8000
|  |  | Workshops | MoH | 60 | 5 | 50 | 15000 |  |  | X |  |  | 15000 | 15000
|  |  | DSA | Pemba | 9 | 5 | 110 | 4950 |  |  | X |  |  | 4950 | 4950
|  |  | DSA | Unguja | 27 | 5 | 80 | 10800 |  |  | X |  |  | 10800 | 10800
|  | 7. Rollout and Deployment (Deploy the solution to live environment) | Technical Assistance | Matiko + consultant | 2 | 10 | 400 | 8000 |  |  | X |  |  | 8000 | 8000
|  | 8. Establish mechanisms for ongoing monitoring and evaluation of the digital solution (Collect feedback from users and stakeholders to make continuous improvements) | Technical Assistance | Matiko + Maryam | 2 | 10 | 300 | 6000 |  |  | X |  |  | 6000 | 6000
|  | 9. Evaluate the performance and impact of the solution over time | Technical Assistance | Matiko + Maryam | 2 | 10 | 300 | 6000 |  |  | X |  |  | 6000 | 6000
|  | 10. Support and Maintanance for the platform | Technical Assistance | Matiko +consultants | 2 | 16 | 300 | 9600 |  |  | X |  |  | 9600 | 9600
[8 empty] | 165750 | SubTotal |  |  | 0 | 72400 | 93350 | 165750
2.4 Integrate the new digital solutions with DHIS-2. | The API document and integration report | 1. Conduct needs and requirement gathering for the kind of data needed to be exchanged with e-learning, digital supportive supervision, other HIS and DHIS2 | Technical Assistance | Matiko+ Maryam | 2 | 5 | 300 | 3000 |  |  | X |  |  | 3000 | 3000
|  |  | Workshops | MoH | 10 | 5 | 50 | 2500 |  |  | X |  |  | 2500 | 2500
|  | 2. Clearly define the interoperability requirements, including data exchange formats, communication protocols, and system interfaces | Technical Assistance | Matiko +consultant | 2 | 14 | 400 | 11200 |  |  | X |  |  | 11200 | 11200
|  | 3. Establish Standards (adopt and adhere to industry or international standards for data formats, communication protocols, and system interfaces) | Technical Assistance | Matiko +consultant | 2 | 21 | 300 | 12600 |  |  | X |  |  | 12600 | 12600
|  | 4. Develop a comprehensive data dictionary that defines the data elements, their meanings, and the relationships between them | Technical Assistance | Matiko +consultants | 3 | 21 | 300 | 18900 |  |  | X |  |  | 18900 | 18900
|  | 5. Develop mechanisms for data mapping and transformation to convert data formats between systems | Technical Assistance | Matiko+Maryam+consultants | 4 | 21 | 300 | 25200 |  |  | X |  |  | 25200 | 25200
|  |  | Workshops | MoH | 10 | 10 | 50 | 5000 |  |  | X |  |  | 5000 | 5000
|  | 6. Design and implement well-documented APIs that allow different systems to communicate with each other | Technical Assistance | Matiko+consultants | 3 | 18 | 300 | 16200 |  |  | X |  |  | 16200 | 16200
|  | 7. Employ ZHIL to facilitate communication between different systems. | Technical Assistance | Matiko+consultants | 3 | 14 | 300 | 12600 |  |  | X |  |  | 12600 | 12600
|  | 8. Implement Message Queues techniques to allow a sequential and smooth data exchanges in integratiol layer | Technical Assistance | Matiko+consultants | 3 | 10 | 300 | 9000 |  |  | X |  |  | 9000 | 9000
|  | 9. Implement robust authentication and authorization mechanisms to secure data exchange between systems | Technical Assistance | Matiko | 1 | 10 | 300 | 3000 |  |  | X |  |  | 3000 | 3000
|  | 10. Conduct thorough testing with stakeholders to validate that the systems can effectively exchange data and collaborate as intended | Technical Assistance | Matiko +consultant | 2 | 5 | 400 | 4000 |  |  | X |  |  | 4000 | 4000
|  |  | Workshops | MoH | 20 | 5 | 50 | 5000 |  |  | X |  |  | 5000 | 5000
|  | 11. Train end users including administrators | Technical Assistance | Matiko +consultants | 3 | 10 | 400 | 12000 |  |  | X |  |  | 12000 | 12000
|  |  | Workshops | MoH | 10 | 10 | 50 | 5000 |  |  | X |  |  | 5000 | 5000
|  | 12. Deploy the solution to live server at ZICTIA | Technical Assistance | Matiko +consultant | 2 | 5 | 400 | 4000 |  |  | X |  |  | 4000 | 4000
|  | 12. Documentation of the API's | Technical Assistance | Matiko | 1 | 10 | 300 | 3000 |  |  | X |  |  | 3000 | 3000
|  | 13. Conduct support and maintanance | Technical Assistance | Matiko +consultants | 3 | 32 | 300 | 28800 |  |  | X |  |  | 28800 | 28800
[8 empty] | 181000 | SubTotal |  |  | 0 | 0 | 181000 | 181000
2.5 Foster a culture of data use for quality improvement. | The training material and report will be shared by the end of year three. | 1. Advocacy with DPPR, ICT, M&E, QA department to gain commitment from MoH leadership to prioritize and support a data-driven culture for quality improvement | Technical Assistance | Matiko+Maryam | 2 | 12 | 300 | 7200 |  |  | X |  |  | 7200 | 7200
|  | 2. Develop/rejuvenate a robust data governance framework that includes policies, procedures, and roles for managing and using data | Technical Assistance | Matiko+Maryam+consultants(2) | 4 | 5 | 300 | 6000 |  |  | X |  |  | 6000 | 6000
|  | 3. Provide training programs to build the data literacy and analytical skills of staff at all levels | Technical Assistance | Matiko+Maryam+consultants(2) | 4 | 5 | 300 | 6000 |  |  | X |  |  | 6000 | 6000
|  |  | Workshops | MoH | 60 | 5 | 50 | 15000 |  |  | X |  |  | 15000 | 15000
|  |  | DSA | Pemba | 9 | 5 | 110 | 4950 |  |  | X |  |  | 4950 | 4950
|  |  | DSA | Unguja | 27 | 5 | 80 | 10800 |  |  | X |  |  | 10800 | 10800
|  | 4. Regularly assess and address data quality issues shared by users to ensure the reliability and accuracy of the information being used for decision-making | Technical Assistance | Matiko + Maryam | 2 | 32 | 300 | 19200 |  |  | X |  |  | 19200 | 19200
|  | 5. Emberd the process into a rouitine health facility planing processes | Technical Assistance | Matiko+Maryam+consultants | 4 | 12 | 100 | 4800 |  |  | X |  |  | 4800 | 4800
[8 empty] | 73950 | SubTotal |  |  | 0 | 0 | 73950 | 73950
Sub-total | [11 empty] | 86000 | 230350 | 441650 | 758000
Project Output 3: The use of the Client Feedback Mechanism is institutionalised.
3.1 Expand the content of Afya Zan Maoni | The MOH-approved user acceptance test report | 1. Consult stakeholders to ensure that the solution aligns with their needs and expectations of the contents (Requirement gathering) | Technical Assistance | Matiko + Maryam | 2 | 5 | 400 | 4000 | X |  |  | 4000 |  |  | 4000
|  |  | Workshops | MoH | 35 | 5 | 50 | 8750 | X |  |  | 8750 |  |  | 8750
|  | 2. Conduct SRS validation with senior officials | Technical Assistance | Matiko + Maryam | 4 | 2 | 400 | 3200 | X |  |  | 3200 |  |  | 3200
|  |  | Workshops | MoH | 20 | 2 | 50 | 2000 | X |  |  | 2000 |  |  | 2000
|  | 3. Design and customize the platform | Technical Assistance | Matiko + consultants | 3 | 21 | 400 | 25200 | X |  |  | 25200 |  |  | 25200
|  | 4. Conduct UAT with selected end users and MoH | Technical Assistance | Matiko + Maryam | 2 | 3 | 300 | 1800 | X |  |  | 1800 |  |  | 1800
|  |  | Workshops | MoH | 35 | 3 | 50 | 5250 | X |  |  | 5250 |  |  | 5250
|  | 5. Refine the platform as per the feedack collected from UAT | Technical Assistance | Matiko | 1 | 10 | 300 | 3000 | X |  |  | 3000 |  |  | 3000
|  | 6. Train end users (ToT) | Technical Assistance | Matiko + Maryam | 2 | 2 | 400 | 1600 | X |  |  | 1600 |  |  | 1600
|  |  | Workshops | MoH | 20 | 2 | 50 | 2000 | X |  |  | 2000 |  |  | 2000
|  | 7. Deploy the revised platform to live environment and roll out | Technical Assistance | Matiko + consultant | 1 | 10 | 400 | 4000 | X |  |  | 4000 |  |  | 4000
|  | 8. Monitor the platform for continous improvement | Technical Assistance | Matiko | 1 | 10 | 300 | 3000 | X |  |  | 3000 |  |  | 3000
|  | 9. Provide administration, support and maintenance | Technical Assistance | Matiko + consultant | 2 | 32 | 300 | 19200 | X |  |  | 19200 |  |  | 19200
|  | 10. Develop sustainability plan | Technical Assistance | Matiko + Maryam | 2 | 14 | 400 | 11200 | X |  |  | 11200 |  |  | 11200
[8 empty] | 94200 | SubTotal |  |  | 94200 | 0 | 0 | 94200
3.2 Integrate Afya Zan Maoni with Jamii ni Afya | The API document and integration report | 1.Define Interoperability Requirements between the two systems | Technical Assistance | Matiko + consultant | 2 | 5 | 400 | 4000 |  | X |  |  | 4000 |  | 4000
|  |  | Workshops | MoH | 10 | 5 | 50 | 2500 |  | X |  |  | 2500 |  | 2500
|  | 2. Establish data Standards and frequency of data exchanges between the two systems | Technical Assistance | Matiko + consultant | 2 | 5 | 400 | 4000 |  | X |  |  | 4000 |  | 4000
|  | 3. Conduct data mapping to identify use cases for exchanges | Technical Assistance | Matiko + consultants | 3 | 21 | 400 | 25200 |  | X |  |  | 25200 |  | 25200
|  |  | Workshops | MoH | 10 | 10 | 50 | 5000 |  | X |  |  | 5000 |  | 5000
|  | 4. Create API's | Technical Assistance | Matiko + consultants | 3 | 14 | 300 | 12600 |  | X |  |  | 12600 |  | 12600
|  | 5. Implement robust authentication and authorization mechanisms to secure data exchange between systems. | Technical Assistance | Matiko | 1 | 10 | 300 | 3000 |  | X |  |  | 3000 |  | 3000
|  | 6. Employ ZHIL to facilitate communication between Zan Afya Maoni, DHIS2, and Jamii ni Afya | Technical Assistance | Matiko + consultants | 3 | 5 | 400 | 6000 |  | X |  |  | 6000 |  | 6000
|  | 7.Test and Validate Interoperability | Technical Assistance | Matiko + consultants | 2 | 5 | 400 | 4000 |  | X |  |  | 4000 |  | 4000
|  |  | Workshops | MoH | 20 | 5 | 50 | 5000 |  | X |  |  | 5000 |  | 5000
|  | 8. Train end-users and IT staff on the interoperability features and functionalities | Technical Assistance | Matiko + consultants | 3 | 5 | 400 | 6000 |  | X |  |  | 6000 |  | 6000
|  |  | Workshops | MoH | 10 | 5 | 50 | 2500 |  | X |  |  | 2500 |  | 2500
|  | 9. Deploy the interoperable solution to live environment | Technical Assistance | Matiko + consultants | 3 | 5 | 400 | 6000 |  | X |  |  | 6000 |  | 6000
|  | 10. Develop supporting and maintenance plan, as well as monitor the integrated platforms | Technical Assistance | Matiko + consultants | 3 | 10 | 300 | 9000 |  | X |  |  | 9000 |  | 9000
[8 empty] | 94800 | SubTotal |  |  | 0 | 94800 | 0 | 94800
3.3 Build capacity of the ICT Department of the MOH to use and maintain Afya Zan Maoni | The training material and report | 1. Develop a comprehensive training plan | Technical Assistance | Matiko +Maryam | 2 | 3 | 400 | 2400 |  |  | X |  |  | 2400 | 2400
|  | 2. Develop/customize training materials | Technical Assistance | Matiko+Consultant | 2 | 3 | 400 | 2400 |  |  | X |  |  | 2400 | 2400
|  | 3. Conduct practical On-the-Job training on quartely basis with ICT coalegues at MoH | Technical Assistance | Matiko+Consultant | 2 | 24 | 400 | 19200 |  |  | X |  |  | 19200 | 19200
|  |  | Workshops | MoH | 10 | 24 | 50 | 12000 |  |  | X |  |  | 12000 | 12000
|  | 6. Establish pre and post training evaluation mechanism to collect input from participants during and after the training to determine if the learning objectives have been met | Technical Assistance | Matiko+Maryam | 2 | 10 | 400 | 8000 |  |  | X |  |  | 8000 | 8000
|  | 5. Provide ongoing support and mentoring to staff as they apply their new skills in their daily tasks | Technical Assistance | Matiko+Consultant | 2 | 24 | 400 | 19200 |  |  | X |  |  | 19200 | 19200
|  | 6. Documentation of best practices and lessons learned during the training | Technical Assistance | Matiko+Maryam | 2 | 10 | 400 | 8000 |  |  | X |  |  | 8000 | 8000
[8 empty] | 71200 | SubTotal |  |  | 0 | 0 | 71200 | 71200
3.4 Promote clients’ registration on Afya Zan Maoni through facilities and CHWs’ sensitization. | Sensitization material | 1. Develop sensitization materials | Technical Assistance | Matiko+Maryam+Consultant | 3 | 5 | 400 | 6000 |  |  | X |  |  | 6000 | 6000
|  | 2. Conduct sensitization to required cadres at levels | Workshops | MoH | 252 | 2 | 50 | 25200 |  |  | X |  |  | 25200 | 25200
|  | 3. Conduct periodic evaluations to assess/monitor the effectiveness of the sensitization program | Technical Assistance | Matiko+Maryam | 2 | 24 | 400 | 19200 |  |  | X |  |  | 19200 | 19200
|  | 4. Documentation of best practices and lessons learned during the sensitization | Technical Assistance | Matiko+Maryam | 2 | 10 | 400 | 8000 |  |  | X |  |  | 8000 | 8000
|  | 5. Monitor the platform adopation as a result of sensitization | Technical Assistance | Matiko+Maryam | 2 | 10 | 300 | 6000 |  |  | X |  |  | 6000 | 6000
[8 empty] | 64400 | SubTotal |  |  | 0 | 0 | 64400 | 64400
Sub-total | [11 empty] | 94200 | 94800 | 135600 | 324600
Total | [11 empty] | 478366.6667 | 626516.6667 | 601516.6667 | 1706400
[12 empty] | 23918.3333 | 31325.8333 | 30075.8333
[12 empty] | 502285 | 657842.5 | 631592.5
|  |  |  | STAFF | [7 empty] | 21571

## UNDP TASFAM Workplan
Activities | Deliverables | Modality | ImplementationPeriod |  |  |  | TOTAL (USD)
|  |  | Q1 | Q2 | Q3 | Q4
Project Output 1: Development of ToRs & RfPs for cold chain, storage, processing
Sub-outputs 1.1-1.4 (Q1)
1.1 Conduct infrastructure needs assessment (cold chain, storage, processing nodes). | Needs assessment | TA | 3000 | x | x | x | 3000
1.1.1 Field mission to Zanzibar to inform needs assessment/cold storage/processing models (late Jan/earlyFeb.2026) | Missions | TA | TBD
1.2 Review existing national & regional procurement frameworks. | Procurement policy review assessment | TA | 2000 | x | x | x | 2000
1.3 Draft structure of Terms of Reference (ToRs): scope, technical standards, KPIs, sustainability clauses. | Draft ToR template | TA | 2000 | x | x | x | 2000
1.4 Begin early market engagement to identify technical specifications. | Technical specifications identified | TA | 3500 | x | x | x | 3500
Sub-total sub-outputs 1.1-1.4 |  |  | 10500 | x | x | x | 10500
Sub-outputs 1.5-1.8 (Q2)
1.5 Finalize technical specifications & service requirements. | Technical specifications & service requirements produced | TA | x | 2500 | x | x | 2500
1.5.1 Field mission best practice cold stroage/processing facilities to inform technical specifications & service requirements (March 2026) | Missions | TA | x | TBD
1.6 Create Request for Proposals (RfPs) template: eligibility, evaluation scoring, vendor qualification. | RfP template completed | TA | x | 2500 | x | x | 2500
1.7 Internal review with legal/procurement teams. | Report on outcomes of internal review and recommendations | TA | x | 2000 | x | x | 2000
1.8 Submit ToRs drafts for feedback to project steering committee | Draft ToRs submitted to project steering committee | TA | x | 2000 | x | x | 2000
Sub-total sub-outputs 1.5-1.8 |  |  | x | 9000 | x | x | 9000
Sub-outputs 1.9-1.11 (Q3)
1.9 Iterate on ToRs & RfPs based on stakeholder and governance feedback. | Report on ToRs & RfPs based on stakeholder and governance feedback | TA | x | x | 2000 | x | 2000
1.10 Integration of compliance elements (import regulations, energy standards, etc.). | ToRs & RfPs updated with compliance elements |  | x | x | 2000 | x | 2000
1.11 Develop vendor evaluation matrices and scoring rubrics. | Vendor evaluation model and scoring rubrics developed |  | x | x | 2500 | x | 2500
Sub-total sub-outputs 1.9-1.11 |  |  | x | x | 6500 | x | 6500
Sub-outputs 1.12-1.14 (Q4) |  | TA
1.12 Package ToRs & RfPs into procurement-ready documents | Finalize package of ToRs & RfPs into procurement package | TA | x | x | x | 2000 | 2000
1.13 Prepare dissemination materials. | Dissemination materials finalized | TA | x | x | x | 1000 | 1000
1.14 Support procurement launch (if applicable). | Procurement initiated | TA | x | x | x | 1000 | 1000
Sub-total sub-outputs 1.12-1.14 |  |  | x | x | x | 4000 | 4000
Sub-total Project Output 1 |  |  | 10500 | 9000 | 6500 | 4000 | 30000
Project Output 2: Socio-economic & environmental criteria development for infrastructure
Sub-outputs 2.1-2.3 (Q1)
2.1 Baseline review of environmental regulations and social safeguards. | Report on review of environmental regulations & social safeguards | TA | 2000 | x | x | x | 2000
2.2 Identification of local economic impacts (jobs, livelihoods, price stability). | Analysis report of local economic impacts | TA | 2000 | x | x | x | 2000
2.3 Stakeholder mapping for affected communities | Report on mapping of affected communities | TA | 3500 | x | x | x | 3500
Sub-total sub-outputs 2.1-2.3 |  |  | 7500 | x | x | x | 7500
Sub-outputs 2.4-2.5 (Q2)
2.4 Develop draft criteria for infrastructure | Draft criteria developed including: -Environmental impact factors -Social inclusion & gender metrics -Energy efficiency thresholds -Climate resilience standards | TA | x | 3000 | x | x | 3000
2.5 Begin risk screening framework | Draft risk screening framework developed including GHG emissions, land use, water use, and other factors. | TA | x | 3000 | x | x | 3000
Sub-total sub-outputs 2.4-2.5 |  |  | x | 6000 | x | x | 6000
Sub-outpts 2.6-2.8 (Q3)
2.6 Integrate socio-economic indicators with infrastructure procurement requirements. | Socio-economic indicators integrated into infrastructure procurement requirements. | TA | x | x | 2000 | x | 2000
2.7 Develop scoring framework for infrastructure proposals. | Scoring framework developed | TA | x | x | 2000 | x | 2000
2.8 Pilot test criteria on hypothetical facility scenarios. | Analysis of modelled test criteria results | TA | x | x | 2000 | x | 2000
Sub-total sub-outpts 2.6-2.8 |  |  | x | x | 6000 | x | 6000
Sub-outpts 2.9-2.11 (Q4)
2.9 Finalize criteria package | Report on criteria for infrastructure selection | TA | x | x | x | 2000 | 2000
2.10 Produce technical guidance for decision makers | Technicalguidance report for decision makers | TA | x | x | x | 2000 | 2000
2.11 Compile lessons learned into policy brief | Policy brief on lessons learnt | TA | x | x | x | 1500 | 1500
Sub-total sub-outpts 2.9-2.11 | [5 empty] | 5500 | 5500
Sub-total Project Output 2 |  |  | 7500 | 6000 | 6000 | 5500 | 25000
Project Ouput 3: PPP model evaluation and business case analysis
Sub-outputs 3.1-3.3 (Q1)
3.1 Landscape review of potential private partners (logistics, processing, energy). | Report on landscape review | TA | 2000 | x | x | x | 2000
3.2 Financial viability analysis—CapEx/OpEx benchmarks | Financial viability analysis complete | TA | 2000 | x | x | x | 2000
3.3 Identify potential PPP structures (concession, JV, service contract, etc.). | Repport on PPP structure options (concession, JV, service contract, etc, exit strategy, etc.) | TA | 1500 | x | x | x | 1500
Sub-total sub-outputs 3.1-3.3 |  |  | 5500 | x | x | x | 5500
Sub-outputs 3.4-3.6 (Q2)
3.4 Develop financial models | Analysis of viable financial models/options (e.g. cash flow projections, demand, pricing, subsidy levels, etc.) | TA | x | 2000 | x | x | 2000
3.5 Draft business case assumptions and revenue models | Analysis of business case & revenue models | TA | x | 2000 | x | x | 2000
3.6 Support legal and regulatory review of PPP options. | Report on legal and regulatory review of PPP options. | TA | x | 1000 | x | x | 1000
Sub-total sub-outputs 3.4-3.6 |  |  |  | 5000 | x | x | 5000
Sub-outputs 3.7-3.9 (Q3)
3.7 Prepare PPP scenario matrix with risks and incentives. | PPP scenario matrix developed | TA | x | x | 1500 | x | 1500
3.8 Stress-test business models against policy and market constraints | Analysis of stress-test scenario modelling | TA | x | x | 1500 | x | 1500
3.9 Synthesize preferred PPP structure(s) per infrastructure category | Analysis of preferred/optimal PPP structures completed, per infrastructure category (cold storage, hubs, processing high-value strains, etc.) | TA | x | x | 1500 | x | 1500
Sub-total sub-outputs 3.7-3.9 |  |  | x | x | 4500 | x | 4500
Sub-outputs 3.10-3.12 (Q4)
3.10 Final business case documentation | Final package of business case documentation prepared | TA | x | x | x | 2000 | 2000
3.11 Investor/partner outreach package | Final package for investor/partner outreach completed | TA | x | x | x | 2000 | 2000
3.12 Prepare recommendations for decision makers | Report on recommendations for decision makers | TA | x | x | x | 1500 | 1500
Sub-total sub-outputs 3.10-3.12 |  |  | x | x | x | 5500 | 5500
Sub-total Project Output 3 |  |  | 5500 | 5000 | 4500 | 5500 | 20500
Project Output 4: Studies & assessments informing infrastructure design and distribution models
Sub-outputs 4.1-4.3 (Q1)
4.1 Collect technical field data | Report on field data collected | TA | 3000 | x | x | x | 3000
4.2 Benchmark infrastructure capacity requirements | Analysis of infrastructure requirements based on technical field data analysis | TA | 3000 | x | x | x | 3000
4.3 Conduct GIS-based mapping of distribution points (if applicable) | Mapping (including GIS, as applicable) of distribution points completed | TA | 3500 | x | x | x | 5000
Sub-total sub-outputs 4.1-4.3 |  |  | 9500 | x | x | x
Sub-outputs 4.4-4.6 (Q2)
4.4 Engineering pre-feasibility assessments | Pre-feasability assessment completed (e.g., site suitability, power, access, etc.) | TA | x | 3000 | x | x | 3000
4.5 Evaluate distribution network performance (last-mile connectivity). | Evaluation of distribution network (e.g. ,last-mile connectivity) | TA | x | 3000 | x | x | 3000
4.6 Identify constraints: perishability, supply seasonality, energy availability. | Report on factors and recommendations to address market constraints | TA | x | 3000 | x | x | 3000
Sub-total sub-outputs 4.4-4.6 |  |  | x | 9000 | x | x | 9000
Sub-outputs 4.7-4.9 (Q3)
4.7 Develop infrastructure design concepts—modular vs centralized | Analysis of infrastrucure design options | TA | x | x | 3000 | x | 3000
4.8 Model transportation cost vs storage proximity | Report on modelling of transporation costs vs storage proximity | TA | x | x | 2500 | x | 2500
4.9 Sustainability scenario modelling | Report on sustainability scenario modelling (e,g, solar hybrid cold chain, circular processing; mixed products – e.g. sea cucumber & seaweed applicability) | TA | x | x | 3000 | x | 3000
Sub-total sub-outputs 4.7-4.9 |  |  | x | x | 8500 | x | 8500
Sub-outputs 4.10-4.12 (Q4)
4.10 Consolidated assessment report | Assessment report completed | TA | x | x | x | 2000 | 2000
4.11 Adaptation recommendations to procurement & PPP models | Report on recommendations for decision makers | TA | x | x | x | 3000 | 3000
4.12 Technical annexes for integration in ToRs/RfPs | Technical annexes completed | TA | x | x | x | 3000 | 3000
Sub-total sub-outputs 4.10-4.12 |  |  | x | x | x | 8000 | 8000
Sub-total Project Output 4 |  |  | 9500 | 9000 | 8500 | 8000 | 35000
Project Output 5: Stakeholder consultations & validation workshops
Sub-outputs 5.1-5.3 (Q1)
5.1 Initial stakeholder engagement | Stakeholder engagement constituents and schedule identified ((government, producers, processors, logistics providers, et. al.) | TA | 2000 | x | x | x | 2000
5.2 Informative sessions to align on objectives and data collection protocols | Stakeholder preparatory meetings | TA | 1500 | x | x | x | 1500
5.3 Participatory needs assessment workshops | Workshops | TA | 1500 | x | x | x | 1500
Sub-total sub-outputs 5.1-5.3 |  |  | 5000 | x | x | x | 5000
Sub-outputs 5.4-5.6 (Q2)
5.4 Presentation of draft criteria | Presentation of draft criteria developed | TA | x | 1500 | x | x | 1500
5.5 Consultative workshops to refine PPP and procurement directions | Workshops | TA | x | 2000 | x | x | 2000
5.6 Sector-specific roundtables | Meetings/workshops/roundtables | TA | x | 2000 | x | x | 2000
Sub-total sub-outputs 5.4-5.6 |  |  | x | 5500 | x | x | 5500
Sub-outputs 5.7-5.9 (Q3)
5.7 Validation workshops for design concepts & distribution models. | Workshops | TA | x | x | 1750 | x | 1750
5.8 Community consultations on environmental and livelihood framework. | Workshops | TA | x | x | 1750 | x | 1750
5.9 Capture “lessons learned” and stakeholder input. | Report on lessions learnt & stakeholder feedback | TA | x | x | 1000 | x | 1000
Sub-total sub-outputs 5.7-5.9 |  |  | x | x | 4500 | x | 4500
Sub-outputs 5.10-5.12 (Q4)
5.10 High-level validation and endorsement of final outputs | Validation workshops with decision makers | TA | x | x | x | 1000 | 1000
5.11 Investor dialogue sessions | Investor dialogue/workshop | TA | x | x | x | 2000 | 1000
5.12 Policy & strategy dissemination workshops | Workshops | TA | x | x | x | 2000 | 1000
Sub-total sub-outputs 5.10-5.12 |  |  | x | x | x | 5000 | 5000
Sub-total Project Output 5 |  |  | 5000 | 5500 | 4500 | 5000 | 20000
Sub-total Project Outputs 1-5 |  |  | 38000 | 34500 | 30000 | 28000 | 130500
UN General Management Services (GMS) (8%) | [6 empty] | 12000
Direct Project Management Costs/DPC (5%) | [6 empty] | 7500
Sub-total GMS+DPC | [6 empty] | 19500
TOTAL | [6 empty] | 150000

## QUANTUM PROJECT LAYOUT
|  |  |  | GMS | DPC
|  | REVISED | 8% | 8% | 5%
Project Output 1: Development of ToRs & RfPs for cold chain, storage, processing | 30000.24 | 27778 | 2222.24 | 2400.0192 | 1500.012
Project Output 2: Socio-economic & environmental criteria development for infrastructure | 24999.84 | 23148 | 1851.84 | 1999.9872 | 1249.992
Project Ouput 3: PPP model evaluation and business case analysis | 22000 | 18981 | 1519 | 1760 | 1100
Project Output 4: Studies & assessments informing infrastructure design and distribution models | 34999.56 | 32407 | 2592.56 | 2799.9648 | 1749.978
[6 empty] | 10619.4912 | 6637.182 | 150000.3132
Project Output 5: Stakeholder consultations & validation workshops | 20744 | 18518.5 | 1481.48 | 1659.52 | 1037.2
| 132743.64 | 120832.5 | 9667.12 | 10619.4912 | 6637.182
Project costs DPC 5%
150000.3132

## Workplan Inputs (hidden)
Activities | Year 1 | [8 empty] | Year 2 | [7 empty] | Year 3
| TA | ICT Salary | Health Salary | Consultants | Workshops | DSA | Health Connekt | SUZA | TA Balance | TA | ICT Salary | Health Salary | Consultants | Workshops | DSA | Health Connekt | SUZA | TA | ICT Salary | Health Salary | Consultants | Workshops | DSA | Health Connekt | SUZA
1.1 Build the capacity of the Information, Communication, and Technology (ICT) Department of the Ministry of Health (MOH). | 31266.6667 | #REF! |  | #REF! | 2000 |  |  |  | #REF! | 19266.6667 |  |  | 19266.6667 | 2000 |  |  |  | 19266.6667 |  |  | 19266.6667 | 2000
1.2 Update the functionality and disease classification in DHIS-2, ZanEMR, and Jamii ni Afya. | 81800 |  |  | 81800 | 4500 |  |  |  | 0 | 81200 | #REF! |  | #REF! | 40200
1.3 Create the digital integration pathways for key systems. | 79800 |  |  | 79800 | 10000 |  |  |  | 0 | 36200 |  |  | 36200 | 11000
1.4 Create a user-friendly Executive Data Visualization Dashboard. | [8 empty] | 0 | 62700 | #REF! |  | #REF!
1.5 Develop a standardized essential ICT equipment list. | 52000 | [7 empty] | 52000 | 8400 |  |  | 8400 | 5000
1.6 Conduct a baseline assessment of health facility connectivity. | 36800 | [5 empty] | 160000 |  | -123200 | 35400 | [7 empty] | 3000
2.1 Design, develop, and roll out a digital supportive supervision solution. | 84800 |  |  | #REF! | 1200 |  |  |  | #REF! | 54800 |  | #REF! | #REF! | 15000 | 15750 |  |  | 0
2.2 Design, develop, and roll out an e-learning platform for CHWs. | [8 empty] | 0 | 71400 |  | #REF! | #REF! | 1000 |  |  | #REF! | 49600 |  | #REF! | #REF! | 28000 | 15750
2.3 Design, develop, and roll a peer exchange collaborative tool. | [8 empty] | 0 | 71400 |  |  | 71400 | 1000 |  |  |  | 49600 |  |  | 49447 | 28000 | 15750
2.4 Integrate the new digital solutions with DHIS-2. | [8 empty] | 0 | [8 empty] | 163500 | #REF! |  |  | 17500
2.5 Foster a culture of data use for quality improvement. | [8 empty] | 0 | [8 empty] | 43200 |  | #REF! |  | 15000 | 15750
3.1 Expand the content of Afya Zan Maoni | 76200 |  | #REF! |  | 18000 |  |  | 50000 | #REF!
3.2 Integrate Afya Zan Maoni with Jamii ni Afya | [8 empty] | 0 | 79800 |  | #REF! | #REF! | 15000 |  |  |  | 0
3.3 Build capacity of the ICT Department of the MOH to use and maintain Afya Zan Maoni | [8 empty] | 0 | [8 empty] | 59200 |  | #REF! |  | 12000
3.4 Promote clients’ registration on Afya Zan Maoni through facilities and CHWs’ sensitization. | [8 empty] | 0 | [8 empty] | 39200 |  | #REF! |  | 25200
Total | 442666.6667 | #REF! | #REF! | #REF! | 35700 | 0 | 160000 |  | #REF! | 520566.6667 | #REF! | #REF! | #REF! | 90200 | 15750 |  | #REF! | 426566.6667 | #REF! | #REF! | #REF! | 127700 | 47250 | #REF! | 0
|  |  |  | #REF! | [8 empty] | #REF! | [7 empty] | #REF!
| TA Balance | #REF! | [7 empty] | TA Balance | #REF! | [6 empty] | TA Balance | #REF!

## Old Budget (hidden)
Activities | Outputs | Steps needed toward realising the Outputs | Modality | Pax's/ Consultants | Frequency | Costs (DSA, fees, venue, refreshments, logistics etc) | Total | Implementation Period |  |  | Amount (USD)
[8 empty] | Year 1 | Year 2 | Year 3
Project Output 1: The digital health ecosystem is strengthened
1.1 Build capacity of the Information, Communication and Technology (ICT) Department of the Ministry of Health (MOH), and Council ICTO through on the job training to properly use and maintain the existing digital health platforms (i.e. DHIS-2, and ZanEMR) | Atleast four capacity building sessions are held annually. | 1. Needs Assessment to identify the specific skills and knowledge gaps 2. Define the training objectives based on the identified needs 3. Develop a comprehensive training plan 4.Develop/customize training materials 5.conduct practical On-the-Job training 6.Establish a feedback mechanism to collect input from participants during and after the training 7.Provide ongoing support and mentoring to staff as they apply their new skills in their daily tasks 8. Conduct periodic evaluations to assess the effectiveness of the training program 9. Documentation of best practices and lessons learned during the training | Technical Assistance | 25 | 4 | 500 | 50000 | X | X | X | 150000
1.2 Improve the functionality of DHIS-2, ZanEMR, and Jamii ni Afya, and harmonise the disease classification to enable their interoperability | 1. DHIS-2, ZanEMR and Jamii ni Afya are available and accessible to all healthcate workers 2. The harmonised disease classification is available in DHIS-2 and ZanEMR. | 1. Conduct needs assessment to understand the current state of DHIS-2, ZanEMR, and Jamii ni Afya. 2. Engage with key stakeholders, including users, developers, and decision-makers, to gather input on required improvements and interoperability features. 3. Define Standards ( Establish data standards and protocols for interoperability, including a common data model and communication standards and adopt international standards such as HL7 (Health Level Seven) for health information exchange) 4. Data mapping and harmonization 5. Customize each system to align with the defined standards and interoperability requirements 6. Create Application Programming Interfaces (APIs) 7. Train end-users, administrators, and IT staff on the updated systems and new interoperability features 8. Deploy the updated systems 9.Collect feedback from users and stakeholders to identify areas for further improvement 10. Do a continuous improvement based on feedback 11. Document the entire process, including system configurations, data mappings, and interoperability protocols | Technical Assistance | 5 | 12 | 2500 | 150000 | X | X |  | 300000
1.3 Align the data entry system and process of the MTUHA books and ZanEMR, and developing the pathway for data aggregation to DHIS2 | 1. The MTUHA books are a paper-based version of ZanEMR 2. DHIS-2 data automatically aggregated data from ZanEMR | 1. Identify the key data elements that need to be synchronized between MTUHA books, ZanEMR and DHIS2 2. Map the data fields from MTUHA books and ZanEMR to the corresponding data elements in DHIS2. 3. Define data formats in MTUHA books and ZanEMR, standardized them and make compatible with DHIS2 requirements 4. Explore APIs provided by the respective systems as well as for the ZHIL 5. Implement data validation, security standards and cleaning 6. Train users on the updated data entry processes 7.Conduct thorough testing of the integrated system to identify and resolve any issues 8. Define the frequency and timing of data aggregation to ensure timely reporting 9. Set up regular maintenance activities to address any issues that may arise and to keep the integration up-to-date with system changes 10. Documentation for all the processes | Technical Assistance | 5 | 12 | 2500 | 150000 | X |  |  | 150000
1.4 Create a standardised essential ICT equipment list for all health facilities, with related maintenance and replacement plans, overseen and coordinated by ICT MoH | The standard essential ICT equipment list is approved by the Permanent Secretary of the Ministry of Health | 1. Assess the ICT needs of various health facilities including identifying the essential equipment required for efficient operations 2. Work with relevant stakeholders to establish a standardized list of essential ICT equipment that suits the diverse needs of different health facilities 3. Define maintenance requirements for each type of equipment. 4. Create detailed maintenance procedures for each type of equipment 5. Define clear criteria for determining when ICT equipment should be replaced. 6. Develop plans for replacing ICT equipment at the end of its lifecycle 7. Create budget estimates for the initial setup, maintenance, and replacement of ICT equipment 8.Provide training to healthcare staff on the proper use and maintenance of ICT equipment | Technical Assistance | 4 | 12 | 4000 | 192000 | X |  |  | 192000
1.5 Conduct a baseline assessment of health facility connectivity. Include a connectivity indicator to enable regular reporting on connectivity status. | 1. The baseline assessment of health facility connectivity report is available 2. A connectivity indicator is integrated in DHIS-2. | 1. Clearly define the objectives of the baseline assessment 2. Develop Assessment Criteria 3. Develop a connectivity indicator that can be used for regular reporting 4. create appropriate tools for conducting the assessment 5. Develop plan and schedule visits to health facilities for on-site assessments 6. Collect data on various aspects of connectivity, such as internet speed, network reliability, availability of backup systems, and the presence of essential communication tools 7. Document the existing network infrastructure in each health facility 8. Interview key stakeholders, including IT personnel, healthcare providers, and administrators, to gather insights into their experiences with the current connectivity infrastructure 9. Evaluate the availability and quality of telecommunication services (e.g., phone lines, mobile networks) that support communication within and outside the health facility. 10 Analyze the collected data to identify patterns, trends, and areas of improvement. 11. Compile the findings into a comprehensive baseline report 12. Implement a system for regular reporting on connectivity status using the established connectivity indicator. 13. Create budget estimates for the initial setup of the connectivity at the health facility | Technical Assistance | 4 | 12 | 2500 | 120000 | X | X |  | 240000
1.6 Facilitate regular stakeholders’ engagement through the Digital Health Technical Working Group. | Atlest four technical working groups are held every annually | Demand the TWG converning by creating the agenda and objectives oevery two months specifically to over see, coordinate and approve all these initiatives | Cash | 30 | 6 | 200 | 36000 | X | X | X | 36000
Sub-total | [10 empty] | 1068000
Project Output 2: The use of digital solutions for quality improvement is enhanced
2.1 Design, develop and roll out a digital supportive supervision solution | A digitial supportive supervision solution is created and made operational | 1. Conduct requirement gathering to collect inputs and feedback from stakeholders to ensure that the solution aligns with their needs and expectations and produce System Requiremement Specification (SRS) document 2. Conduct SRS validation with senior officials 3. Conduct design sessions for detailed design of the user interface (UI) and user experience (UX) based on the SRS 4. Coding of the system 5. Conduct user Acceptance test (UAT) to identity errors, bugs and improve accordingly 6. Conduct training and capacity building end users 7. Rollout and Deployment( Deploy the solution to live environment 8. Establish mechanisms for ongoing monitoring and evaluation of the digital solution (Collect feedback from users and stakeholders to make continuous improvements) 9. Evaluate the performance and impact of the solution over time 10. Develop a sustainability plan to ensure the long-term success of the digital solution | Technical Assistance | 5 | 12 | 5000 | 300000 | X |  |  | 300000
2.2 Design, develop and roll out a peer learning and exchange digital collaborative tools accessible to all health workers | A digitial peer learning and exchange solution is created and made operational | 1. Conduct requirement gathering to collect inputs and feedback from stakeholders to ensure that the solution aligns with their needs and expectations and produce System Requiremement Specification (SRS) document 2. Conduct SRS validation with senior officials 3. Conduct design sessions for detailed design of the user interface (UI) and user experience (UX) based on the SRS 4. Coding of the system 5. Conduct user Acceptance test (UAT) to identity errors, bugs and improve accordingly 6. Conduct training and capacity building end users 7. Rollout and Deployment( Deploy the solution to live environment 8. Establish mechanisms for ongoing monitoring and evaluation of the digital solution (Collect feedback from users and stakeholders to make continuous improvements) 9. Evaluate the performance and impact of the solution over time 10. Develop a sustainability plan to ensure the long-term success of the digital solution 11. Support and Maintanance for the platform | Technical Assistance | 5 | 12 | 2500 | 150000 | X | X |  | 300000
2.3 Integrate the supportive supervision solution and digital collaborative tool with DHIS-2 through the Zanzibar Health Integration Layer | Data from the digital supporting supervision and peer learning and exchange solutions is accessible in DHIS-2 | 1. Clearly define the interoperability requirements, including data exchange formats, communication protocols, and system interfaces 2. Establish Standards (adopt and adhere to industry or international standards for data formats, communication protocols, and system interfaces0 3. Develop a comprehensive data dictionary that defines the data elements, their meanings, and the relationships between them 4.Develop mechanisms for data mapping and transformation to convert data formats between systems 5. Design and implement well-documented APIs that allow different systems to communicate with each other 6. Employ ZHIL to facilitate communication between different systems. 7. Implement Message Queues 8. Implement robust authentication and authorization mechanisms to secure data exchange between systems 9. Conduct thorough testing with stakeholders to validate that the systems can effectively exchange data and collaborate as intended 10. Train end users including administrators. 11. Deploy the solution 12. Documentation of the API's 13. Conduct support and maintanance | Technical Assistance | 5 | 12 | 5000 | 300000 |  | X |  | 300000
2.4 Institute data use for quality improvement culture | At least three workshops on data use for quality improvement are held. | 1. Advocacy to gain commitment from MoH leadership to prioritize and support a data-driven culture for quality improvement 2. Develop/rejuvenate a robust data governance framework that includes policies, procedures, and roles for managing and using data 3. Provide training programs to build the data literacy and analytical skills of staff at all levels 4. Regularly assess and address data quality issues shared by users to ensure the reliability and accuracy of the information being used for decision-making 5. Emberd the process into a rouitine health facility planing processes | Cash | 300 | 4 | 50 | 60000 |  |  | X | 60000
Sub-total | [10 empty] | 960000
Project Output 3: The use of the Client Feedback Mechanism is institutionalised.
3.1 Expand the content of Afya Zan Maoni to new thematic areas to encompass PHC | Afya Zan Maoni covers all PHC thematic areas | 1. Conduct requirement gathering to collect inputs from stakeholders to ensure that the solution aligns with their needs and expectations of the contents 2. Conduct SRS validation with senior officials 3. Design and customized the platform 4. Conduct UAT 5. Refine the platform as per the feedack collected from UAT 6. Train end users 7. Roll out and deploy the platform. 8. Monit the platform for continous improvement 9. Provide support and maintance 10. Develop sustainability plan | Technical Assistance | 5 | 12 | 2000 | 120000 |  | X | X | 240000
3.2 Integrate Afya Zan Maoni with Jamii ni Afya community system | Afya Zan Maoni captures community-level data through Jamii ni Afya | 1.Define Interoperability Requirements 2. Establish Standards 3. Conduct data mapping 4. Create API's 5. Implement robust authentication and authorization mechanisms to secure data exchange between systems. 6. Employ ZHIL to facilitate communication between different systems 8.Test and Validate Interoperability 9. Train end-users and IT staff on the interoperability features and functionalities 10. Deploy the interoperable solution to live environment 11. Develop supporting and maintenance plan as well as sustainability plan. 12. Monitor, administer and maintain the solution | Technical Assistance | 5 | 12 | 2500 | 150000 |  | X | X | 150000
3.3 Build capacity of the ICT Department of the MOH to use and maintain Afya Zan Maoni | Atleast four capacity building sessions are held annually. | 1. Define the training objectives 2. Develop a comprehensive training plan 3.Develop/customize training materials 4.conduct practical On-the-Job training 5.Establish a feedback mechanism to collect input from participants during and after the training 6.Provide ongoing support and mentoring to staff as they apply their new skills in their daily tasks 7. Conduct periodic evaluations to assess the effectiveness of the training program 8. Documentation of best practices and lessons learned during the training | Technical Assistance | 10 | 6 | 500 | 30000 |  | X | X | 60000
3.4 Sensitise health facilities to register on the platform, and communities and individuals to use Afya Zan Maoni | 1. 70% of health facilities and community health volunteers are trained on the adoption of the Afya Zan Maoni 2. 70% of the shehia's leaders are sensistised on the use of Afya Zan Maoni | 1. Identify stakeholders needed for sensitization 2. Develop sensitization materials 3. Conduct sensitization 4. Conduct periodic evaluations to assess the effectiveness of the sensitization program 5. Documentation of best practices and lessons learned during the sensitization 6. Monitor the platform adopation as a result of sensitization | Cash | 600 | 4 | 50 | 120000 |  | X |  | 120000
3.5 Promote the regular use of Afya Zan Maoni data for decision making around facility based quality improvement initiatives. | At least three workshops on data use for facility based quality improvement are held. | 1. Advocacy to gain commitment from MoH leadership to prioritize and support a data-driven culture for quality improvement 2. Develop/rejuvenate a robust data governance framework that includes policies, procedures, and roles for managing and using data 3. Provide training programs to build the data literacy and analytical skills of staff at all levels 4. Regularly assess and address data quality issues shared by users to ensure the reliability and accuracy of the information being used for decision-making 5. Emberd the process into a rouitine health facility planing processes | Cash | 600 | 4 | 50 | 120000 |  | X |  | 120000
Sub-total | [10 empty] | 690000
Total | [10 empty] | 2718000