Funding Windows Proposal Template

Countries:  Ukraine, Honduras, Egypt and Bhutan.

Operational Overview

Proposal Title*: EQUANOMICS: Making public finance work for women’s economic empowerment.

Funding Windows (FWs) resources will support (please check one) *:

☒  An ongoing output within an existing Prodoc

☐  A new output within an existing Prodoc

☐  A new Prodoc (please provide estimated PAC date)

Linked SDG Goal(s) and Target(s):

SDG 5. Gender Equality:

- Target 5.a: Undertake reforms to give women equal rights to economic resources, as well as access to ownership and control over land and other forms of property, financial services, inheritance and natural resources, in accordance with national laws.

- Target 5.c: Adopt and strengthen sound policies and enforceable legislation for the promotion of gender equality and the empowerment of all women and girls at all levels.

SDG 10. Reduced inequalities:

- Target 10.4: Adopt policies, especially fiscal, wage and social protection policies, and progressively achieve greater equality.

Linked Draft SP (2026-29) Output*:

- B.2.1 Institutions, policies and laws improved to offer better opportunities for women’s economic prosperity.

Linked Draft SP (2026-29) Indicator*:

- B.2.1.2 Number of economic or fiscal policies adopted or revised to support women’s economic empowerment (new).

- B.2.1.3 Number of new or strengthened policies, legislations and regulations or investment in national care systems in place.

Linked Flagship target(s)*: Equanomics Flagship initiative: 4 additional countries working to reform fiscal and tax policies (overall target 25)

Linked CPD Output(s):  Gender Equality Global Programme: Output 1.3 Public and private finance unlocked for gender equality. Output 2.1 Strengthened public institutions to deliver gender responsive and informed public policies and services.

Expected FW funding duration*:		18 months

Technical Engagement and Endorsement

Names and expertise of the experts who have contributed to this proposal:

- Gender*:			Aroa Santiago, Juanita Ardila

- M&E/RBM*:			Juanita Ardila

- Other Technical expertise*:	Dajna Sorensen

- Global/Regional Hub thematic focal point*:	Aroa Santiago

- RB advisor/country desk*:	Corneliu Eftodi, Sudha Gooty, Tshering Choden, Rania Tarazi ( RB Gender Advisors)

- Global Substantive Lead for Flagship*:	 Raquel Lagunas, Cate Owren

Department ID: 	Click or tap here to enter text.

Quantum Project Award:

Project/Output ID(s):	Click or tap here to enter text.

Gender Marker*:	GEN3

Total resources required*:	500,000 USD

Total allocated resources: 500,000 USD

  - Funding Windows*:	 500,000 USD

Brief Description (200-250 words)

EQUANOMICS supports governments to reform fiscal policy so that tax and spending actively reduce gender gaps, especially in work, entrepreneurship, assets and time poverty, while strengthening gender responsive public finance and debt management.

This initiative will contribute to the EQUANOMICS portfolio, providing targeted technical assistance to Ukraine, Honduras, Egypt and Bhutan, supporting each country in adopting transformative public finance strategies that promote gender equality, with a focus on advancing women’s economic empowerment.

Each country’s proposal will be tailored to its specific context and progress in public finance reform. The initiative will expand UNDP’s EQUANOMICS initiative and help country offices to:

- Eliminating economic discrimination via fiscal reforms.

- Reduce women’s poverty through fiscal incidence.

- Mobilize and align public finance with national gender equality goals.

Allocation Proposal

# Development Challenge (1/2 page)

Gender equality and women’s empowerment are inextricably linked to all dimensions of sustainable development. Evidence shows that women’s empowerment is fundamental to the enjoyment of human rights, the achievement of peace and security, economic growth, environmental sustainability and the realization of human potential in its fullest sense.

However, the investment gap towards gender equality is $360 billion per year. Public finance can contribute not only to close this investment gap, but also to reshape the foundational economic structures that generate gender inequalities. Public finance systems, covering revenue mobilization, taxation, budgeting, and public expenditure, are powerful tools to shape economic structures towards gender-equal economies.

This intervention aims to tackle the following challenges:

- Persistent poverty and gender poverty gap amid increasing global wealth.

- Economic discrimination based on gender and intersectional factors.

- Inadequate financing for gender equality commitments despite formal endorsements.

- Undervaluation and underfunding of care systems that are essential to economic functioning and human subsistence.

- Limited institutional capacities and frameworks to achieve gender equality objectives.

- Disconnection between gender equality goals with national goals on fiscal sustainability and economic growth.

Egypt faces persistent development challenges rooted in high levels of poverty, gender inequality, and a labor market marked by informality and limited opportunities for women. As of 2024, around 29.7% of the population lives below the national poverty line, with rural and marginalized communities particularly affected (CAPMAS, 2024; World Bank, 2024). The economy remains vulnerable due to inflation, high public debt, and external shocks, such as energy price fluctuations and geopolitical instability. These factors constrain inclusive growth and exacerbate socioeconomic disparities.

Female labor force participation remains low—just 14.3% compared to 67.5% for men—one of the lowest rates in the MENA region (ILO, 2024; CAPMAS Labor Force Survey, 2024). Women who do work are often concentrated in informal, low-paid, and insecure jobs with limited access to social protection. A key barrier to women’s economic participation is the unequal distribution of unpaid care work. Egyptian women spend significantly more time on domestic and caregiving responsibilities than men, which directly limits their engagement in the formal labor market. A lack of accessible and affordable public care services, such as nurseries, early childhood education, and elder care, compounds this issue, in particularly in low-income households where private alternatives are unaffordable.  (UN Women Egypt, 2024; World Bank, 2024).

Honduras faces a challenging economic situation, characterized by high levels of poverty, inequality, and an economy heavily reliant on the informal sector and remittances. More than 60% of the population lives in poverty, and nearly 40% in extreme poverty, limiting development opportunities and disproportionately affecting women (World Bank, 2024; INE Honduras, 2023). Limited economic growth and the lack of formal employment worsen the precarious conditions, while women often occupy the most unstable jobs with the least social protection (UNDP, 2024).

In this context, unpaid care work represents one of the main barriers to women’s economic autonomy. On average, women dedicate three times more time than men to domestic and caregiving tasks, which restricts their participation in the formal labor market —only 40.9% of women are employed compared to 73.9% of men— and limits their access to personal income and social protection (INE Honduras, Time Use Survey 2023; EPHPM 2024; ECLAC, 2024). The absence of public care services, such as childcare centers and elderly care facilities, forces many women to leave or decline paid jobs in order to take on these responsibilities at home.

As of 2025, the female labour force participation rate in Bhutan stands at 56.3%, compared to 73.5% for men. Urban women exhibit the lowest participation rates across the life cycle, lagging behind rural women, rural men, and urban men. The agriculture sector, which employs 52% of the female labour force, is constrained by low productivity, limited growth, and increasing climate-related impacts. Women in Bhutan also bear a disproportionate burden of unpaid care and domestic work, performing 71% of all unpaid care activities. This burden is particularly acute for elderly women, exacerbated by the mass migration of young Bhutanese overseas, often leaving children in the care of older female relatives.

Structural barriers, including unequal access to productive resources, limited childcare infrastructure, and entrenched gender norms continue to restrict women’s economic empowerment and reduce their visibility in formal employment.

In the political sphere, women’s representation in Parliament declined from 15.8% in 2018 to 6.9% in 2024, marking the lowest level since Bhutan’s transition to a parliamentary democracy in 2008. Within the civil service, women occupy only 23% of executive positions, falling short of global benchmarks. Gendered expectations around leadership, stereotypes, limited exposure to leadership opportunities, and family responsibilities are key factors constraining women’s advancement to decision-making roles.

Bhutan has taken important steps to advance gender equality through its policy and legal frameworks. The National Gender Equality Policy (NGEP) 2020 envisions a society where all individuals, regardless of gender, have equitable opportunities to thrive and contribute to national development. The country’s Five-Year Plans adopt a dual approach to gender equality, through standalone initiatives and mainstreaming across sectoral policies and programmes. The National Commission for Women and Children (NCWC) lead these efforts, supported by a network of gender focal points across ministries, agencies, and local governments.

Bhutan has also initiated efforts toward gender-responsive public financial management, beginning with high-level sensitization in 2010, followed by the development of a strategic framework for gender mainstreaming and budgeting in 2013. Gender budgeting was piloted in four key ministries—Health, Education, Agriculture, and Labour. However, capacity gaps among planners and budget officials hinder full integration of gender perspectives into fiscal policies and public financial management systems, including resource tracking for gender equality.

Ukraine faces persistent development challenges shaped by the ongoing war, economic disruption, and deep-rooted gender inequalities that constrain inclusive recovery and growth. While the country has demonstrated strong resilience, the full-scale Russian aggression has devastated infrastructure, displaced millions, and strained social systems. These pressures have deepened existing socioeconomic disparities, particularly affecting women, internally displaced persons, and rural populations (UNDP Ukraine, 2025; State Statistics Service of Ukraine, 2024).

Gender inequality remains a structural barrier to Ukraine’s sustainable development and EU integration. According to the Gender Equality Index 2025, Ukraine scored 61.4 points, nearly 9 points below the EU average, indicating persistent gaps across key areas such as work, income, and decision-making. Women’s employment rate (42.9%) remains significantly lower than men’s (56.9%), and women continue to be concentrated in lower-paid sectors such as education, healthcare, and social services. Limited access to flexible work arrangements and childcare services further restricts women’s participation in the formal labor market (Ukrainian Women’s Fund & State Statistics Service, 2025).

Unpaid care and domestic work remain a significant barrier to women’s economic empowerment. Ukrainian women spend substantially more time than men on caregiving and household responsibilities, which has intensified during the war due to displacement, loss of services, and expanded care needs. Although Ukraine ranks first in Europe in terms of civic and volunteer engagement—reflecting exceptional social cohesion—this unpaid contribution often comes at the expense of women’s time, income, and wellbeing (UWF, 2025). Addressing these gaps—by expanding care infrastructure, promoting equal pay and leadership opportunities, and institutionalizing gender-sensitive policies—will be critical to Ukraine’s equitable recovery and European integration.

This intervention will leverage the methodologies and tools of EQUANOMICS, which has been at the forefront of supporting fiscal and institutional reforms for gender equality. Currently present in 30 countries, it is implementing full-fledged interventions in Tanzania, Kenya, Rwanda, and Zimbabwe. It has developed technical tools that help countries reform their public finance frameworks not only to advance gender equality but also to enhance the wellbeing of all citizens and build more resilient, inclusive economies.

# Strategy (1/2 page)

This project is built on the assumption that fiscal policy can:

- Contribute to eliminating economic discrimination via fiscal reforms. Using targeted tax and expenditure reforms to expand women’s labor force participation, entrepreneurship, de facto land/property ownership and other gender equality goals by influencing behavioral change.

- Reduce women’s poverty through fiscal incidence. Analyzing how taxes and transfers affect women and men differently and implement concrete reforms to close the post tax/transfer gender poverty gap.

- Mobilize and align finance. Scaling gender responsive budgeting (GRB), improving GRB impact analyses, and developing gender responsive debt management to align public resources with national equality goals.

The causal pathway is as follows: If public institutions are equipped with the tools and capacities to design gender responsive policies for tax and financial reform including and we build the evidence base to identify specific policy reform areas and investment cases and  advocate for and implement supportive and gender responsive legal and policy frameworks, and we conduct awareness campaigns to shift gender norms within public institutions, then these institutions can experience a transformative improvement in the way they prioritize, design, plan, invest and/or deliver, then institutions will design more gender-responsive policies for tax and financial reform, eventually resulting in the provision of gender responsive public goods and services, and greater equity in the delivery and the impact of such services helping to address gender inequalities, and improved accessibility for women and men, and then we will enhance the economic participation of women and marginalized groups, reduce unpaid care work, and ultimately achieve gender equality and inclusive economic growth.

# Results and Partnerships (1.5-2 pages)

Expected Results

The initiative will directly contribute to strengthening national fiscal systems so that they deliver on gender equality and women’s empowerment goals, in line with international commitments such as the Beijing Platform for Action, the 2030 Agenda for Sustainable Development, and CEDAW. The interventions are designed to ensure that gender equality is not an “add-on,” but a structural principle guiding fiscal sustainability, resilience, and inclusive growth.

The overall objective is to implement the EQUANOMICS model in four countries—Ukraine, Honduras, Egypt, and Bhutan. By the end of the intervention, the following outcomes and outputs are expected:

- Output 1: Enhanced gender responsiveness and inclusivity of public finance institutions through the adoption and implementation of the EQUANOMICS methodology Gender

- Output 2: Strengthened evidence base and institutional capacity to integrate gender equality into public finance reforms.

Taken together, these results will set the stage for profound fiscal reforms that can reduce economic discrimination, narrowing the gender poverty gap, and ensure that national gender equality commitments are not only resourced but integrated into fiscal sustainability agendas. The initiative will also produce global public goods in the form of piloting draft methodologies, evidence, and lessons that can be replicated across other countries engaged in EQUANOMICS.

Partnerships

The success of this initiative relies on strategic and multi-layered partnerships that bring together governments, multilateral institutions, civil society, and knowledge partners. EQUANOMICS has already established itself as a convening platform and will leverage this role in the four participating countries.

National Partners:

- Ministries of Finance and Economy will serve as primary counterparts, leading the reform process and ensuring ownership.

- Tax Administrations and Audit Institutions will engage directly in diagnostics, reform design, and monitoring.

- Line ministries (e.g., health, education, labor, social protection) will be included to ensure coherence between sectoral allocations and gender equality objectives.

- National Women’s Machineries will be integral partners to align fiscal reforms with broader gender equality strategies and ensure women’s rights advocacy informs fiscal priorities.

Global and Regional Partners:

- UNDP will provide technical leadership, global methodologies, and on-the-ground support through its country offices.

- UN Women, IMF, World Bank, and regional development banks will be engaged for policy coherence, joint capacity building, and leveraging financing instruments. UNDP places strong emphasis on collaboration and coordination with other UN partners at the local level, as well as with development banks, given their significant technical expertise and financial capacity. For the implementation of this Funding Window proposal on public finance and care systems, UN Women and the ILO are key partners due to their extensive experience, strong field presence, and trusted relationships with civil society organizations. UN Women’s leadership on the Women, Peace and Security agenda provides valuable insights to ensure that care and economic recovery efforts contribute to peacebuilding and social cohesion in crisis and post-crisis settings. Meanwhile, the ILO’s Decent Work approach offers a critical framework to promote employment, social protection, and rights at work, ensuring that investments in care and public finance reforms generate quality jobs and inclusive economic opportunities. Strengthening dialogue and partnerships with UN Women and the ILO will help avoid duplication of efforts and foster synergies that enhance the overall impact of the Funding Window proposal.

- OECD and regional tax organizations will be invited to contribute to the design of benchmarks and comparative analysis.

Civil Society and Academia:

- Women’s rights organizations, think tanks, and universities will play a role in providing evidence, monitoring, and holding governments accountable.

- Civil society actors will also help to ensure that reforms respond to the lived realities of women, especially those in poverty or marginalized groups.

Donor Partners:

- Collaboration with existing donors to the EQUANOMICS initiative, particularly NORAD, Gates and Hewlett will help ensure coherence to the initiative.

Resources Required to Achieve the Expected Results

Human resources and technical expertise. This includes specialized technical advisors in public finance, tax policy, expenditure analysis, and gender economics will be mobilized at global, regional, and national levels. These experts will provide diagnostics, reform design, fiscal incidence analyses, and policy roadmaps. It also includes programme management and coordination staff will be required to oversee project implementation, reporting, and knowledge management.

Knowledge tools and methodologies. Piloting EQUANOMICS methodologies and toolkits; and development of country-specific diagnostic reports and reform roadmaps to guide decision-making.

Operational and logistical resources to organize national consultations, technical workshops, and high-level policy dialogues, enabling buy-in and consensus-building.

Communications and Advocacy

The communication and advocacy strategy will ensure that the lessons, results, and innovations emerging from the project are widely shared, with a particular focus on integrating gender equality into fiscal policy and public finance—especially in recovery and crisis settings. It will form part of the broader EQUANOMICS communications strategy, while giving specific visibility to the contribution of the Funding Window (FW) in priority countries and to the piloting of the EQUANOMICS tool. Messaging will prioritize evidence-based impact stories, tailored to different audiences and communication channels.

The strategy will be adapted to the context, activities, and priorities of each participating country, ensuring that communication efforts reflect local realities and partners. It will focus on disseminating information about the FW initiatives, their partners, and progressive results, while serving as a mechanism to strengthen engagement with key stakeholders at the country and regional levels. Planned communication activities include media campaigns around relevant international days, periodic posts on social media, short videos featuring key stakeholders, and dissemination of milestones and achievements linked to the FW.

Engagement with donors and Funding Window partners will be integrated throughout all communication materials and events to highlight their contributions and strengthen visibility.

At the country level, UNDP Country Offices (COs) will ensure that partners and donors are actively involved in workshops, trainings, and public events, providing opportunities for them to showcase their contributions to EQUANOMICS and the broader care and fiscal equality agenda.

The primary target audience includes Ministries of Finance, tax administrations, and civil service institutes, as well as national policymakers and legislators responsible for fiscal policy and social protection. Secondary audiences include civil society organizations, women’s rights groups, labor associations, development partners such as UN agencies, international financial institutions and bilateral donors, as well as media and opinion leaders in economics, gender, and recovery. Finally, the broader public, especially women in informal and care economies, are an important audience to ensure reforms are grounded in and responsive to people’s realities and well-communicated at the national level.

Risks and Assumptions

Specify the key risks that can threaten achieving results and describe how risks will be mitigated.

| Risk type | Risk description | Risk assessment (Impact, Likelihood & Risk Level) | Mitigation measures |
| --- | --- | --- | --- |
| Technical | Technical complexity may limit understanding among non-specialist audiences. | Impact: 4 – Extensive; Likelihood: 3 – Moderately likely Risk Level: Medium | Use accessible language, infographics, and real-life stories of impact. |
| Political | Political instability, contested elections, or shifts in government priorities undermine political will to implement public finance reforms. | Impact: 4 – Extensive; Likelihood: 3 – Moderately likely Risk Level: Medium | Maintain strong relationships with national and local counterparts across political spectrum; engage through UN Resident Coordinators and political dialogue platforms; sequence interventions to adapt to political cycles; ensure flexibility in workplans. |
| Political | Resistance to gender equality framing in public finance debates. | Impact: 4 – Extensive; Likelihood: 3 – Moderately likely Risk Level: Medium | Emphasize evidence on economic returns, fiscal sustainability, and inclusive growth. |
| Security | Deterioration of security or escalation of conflict in targeted areas disrupts implementation and endangers staff and partners. | Impact: 5 – Extreme; Likelihood: 2 – Low likelihood; Risk Level: Medium | Apply UN security risk management protocols; maintain contingency plans; adapt delivery modalities to remote or third-party implementation where necessary; coordinate closely with UN missions, UNDSS, and humanitarian actors. |
| Data Accessibility | Limited access to data sources may hinder comprehensive monitoring. | Impact: 4 – Extensive; Likelihood: 2 – Low likelihood; Risk Level: Medium | Partner with regional data providers as well as local CSOs and NGOs; create alternative monitoring methods. |

Stakeholder and Beneficiary Engagement

The intervention will ensure active and inclusive engagement of stakeholders and beneficiaries at both local and national levels throughout its implementation. Core government partners, such as Ministries of Finance, Economic Development, Social Development, Women’s Affairs, National Treasuries, and Planning Bureaus, will be engaged as primary duty bearers and reform leaders. Complementing this, members of parliament, associations of civil servants, and oversight bodies will be included to strengthen accountability and institutional ownership. Civil society organizations, women’s rights and feminist movements will play a central role in shaping reform priorities, ensuring that diverse perspectives, especially those of women and young people, are reflected in policy design and implementation. The initiative will also foster dialogue platforms and participatory mechanisms to capture community voices, particularly those of women in informal employment and crisis-affected settings. Partnerships with think tanks, academic institutions, and research centers will provide evidence-based inputs to inform fiscal reforms, while sustained engagement with women leaders will help build momentum and advocacy for change. This multi-stakeholder approach will guarantee that the reforms are both technically robust and socially legitimate, grounded in the lived realities of beneficiaries.

South-South and Triangular Cooperation (SSC/TrC)

The initiative will harness South-South and Triangular Cooperation as key mechanisms to achieve and sustain transformative results. By fostering structured exchanges of best practices and lessons learned, it will promote mutual learning across diverse implementation contexts with a particular focus on adapting innovations from crisis and recovery settings. To broaden its reach, the initiative will also engage countries already participating in UNDP’s EQUANOMICS initiative, such as Tanzania, Rwanda, Zimbabwe, and Kenya, creating a vibrant community of practice on gender-responsive public finance. This peer learning platform will ensure a two-way flow of insights and innovations, accelerating the uptake of reforms and enhancing their relevance across different socio-political environments.

Through these partnerships, the intervention aims to identify the most impactful reforms and strategies, document them through evidence-based analysis and peer learning, and support their replication and scale-up in additional countries. These efforts will be underpinned by a combination of institutional strengthening, reform roadmaps, and broad-based alliances, creating the enabling environment needed to embed gender equality within fiscal policy.

By institutionalizing these exchanges, the initiative will not only reinforce national capacities but also contribute to a global dialogue on gender-responsive fiscal policy as a driver of inclusive and sustainable development and recovery.

Sustainability and Scaling Up

Sustainability will be driven by the intervention’s focus on capacity building, support in legislative reforms, building national consensus through policy dialogues, facilitating government leadership and ownership, and engagement of a wide variety of stakeholders. If public institutions are equipped, legislative frameworks ensure accountability, and there is an active engagement from civil society and women’s organizations, reforms are more likely to be sustained and embedded in national systems.

The Funding Windows allocation is investing in a global flagship initiative that is working to scale up globally. The FW allocation will act as a catalytic capital, showcasing how gender-responsive public finance can boost socioeconomic development, strengthen governance, institutions, gender equality, and resilience. Success stories generated through this initiative will be used in donor engagement, enabling UNDP country offices and EQUANOMICS partners to mobilize additional support from bilateral and multilateral actors.

# Management and Governance Arrangements, and Accountability (1/2 page)

The project will be coordinated from UNDP Headquarters, under the direct leadership of the EQUANOMICS team within the Global Gender Equality Team. The HQ team will provide overall project oversight, quality assurance, and technical guidance to ensure that methodologies, tools, and approaches are consistently applied across the four target countries.

The EQUANOMICS lead (Economist and Gender Specialist) will serve as the overall project manager, providing strategic direction, oversight, and accountability for results. The Lead will ensure coherence with UNDP’s global frameworks on gender equality and public finance reform and report progress to senior management and funding partners.

The Public Finance and Gender Equality Specialist within the HQ team will provide day-to-day technical and programmatic support, including direct backstopping to country offices, coordination of diagnostics, and monitoring of project delivery. This role will also oversee the production of knowledge products and facilitate cross-country peer learning.

The Inclusive Economies Analyst at HQ will provide the operational support on budgets, authorizations and related operations.

At the country level, project implementation will be led jointly by the Chief Economist and the Gender Equality Specialist in each Country Office. They will ensure alignment of project activities with national priorities, oversee the delivery of diagnostics and technical assistance, and coordinate with government counterparts, civil society, and other UN agencies. The national Operations Officer will support the operations aspects of the program. Country teams will be responsible for integrating EQUANOMICS interventions into ongoing UNDP programmes and national development frameworks.

Implementation of Funding Windows resources will adhere to the established UNDP corporate policies and procedures as prescribed in the POPP. The UNDP Resident Representative will be held accountable for the effective and prudent use of the funds allocated to Country offices, including following the Social and Environmental Screening Procedure.

# Monitoring and Learning (1/2 page)

The EQUANOMICS HQ team will coordinate monitoring activities, with country offices responsible for reporting on progress against agreed outputs and outcomes. The initiative  will:

- Develop a results monitoring framework with key milestones and indicators linked to outcomes.

- Conduct monthly internal check-ins (virtual) between HQ and country offices to track progress, troubleshoot challenges, and document emerging lessons.

- Produce two consolidated progress updates (mid-term and end-of-project) that summarize achievements, challenges, and next steps, satisfying UNDP corporate requirements for evaluation.

- Submition of annual reports to the FW Secretariat.

The global team will issue annual reports to the Funding Windows by the first quarter of the following year, through the FWs dedicated template and reporting process. The global team will be responsible for coordinating and overseeing the submission of a quality report, aggregating country level results to provide narrative and overall data on the impact of UNDP Funding Window investments, as per the partners requirements.

Learning will be embedded in the project’s monitoring approach, with an emphasis on capturing practical insights that can inform ongoing and future EQUANOMICS interventions and identify impact when possible.

Key approaches include:

- After-action reviews at mid-point and endline, involving HQ and country teams, to reflect on achievements and challenges.

- Cross-country exchanges through webinars or virtual peer-learning sessions.

- Development of brief knowledge notes summarizing key findings.

- Most Significant Change (MSC): document stories of how the initiative changed their lives, institutions, or communities. These stories are discussed and validated by different stakeholders to identify what kind of change is most valued.

- Outcome Harvesting methodology: identifying unexpected or emergent outcomes, through the collection of qualitative stories from the field. This methodology goes beyond the completion assessment of indicators and digs deeper on understanding what is driving change and impactful transformation.

- Participatory sense making (PMS): workshops or reflection sessions bring together diverse actors (e.g., UN partners, government, civil society) to interpret results and co-create learning.

The team responsible for implementing the Funding Window will design a tailored Monitoring, Evaluation, and Learning (MEL) framework, selecting the most appropriate methodologies based on each country’s context and planned activities. The detailed MEL approach will be outlined in the country-specific Funding Window Action Plan.

# Distribution of the FWs allocations

| Country/Region/Global | Fund Code | Donor Code | Amount |
| --- | --- | --- | --- |
| UNDP Honduras | 28500 | 012711 | $ 58,411 |
|  | 28800 | 012711 | $ 58,411 |
| UNDP Ukraine | 28500 | 012711 | $ 58,411 |
|  | 28800 | 012711 | $ 58,411 |
| UNDP Egypt | 28500 | 012711 | $ 58,411 |
|  | 28800 | 012711 | $ 58,411 |
| UNDP Bhutan | 28500 | 012711 | $ 58,411 |
|  | 28800 | 012711 | $ 58,411 |
| UNDP Technical Accompaniment HQ (7%) | 28500 | 012711 | $ 16,356 |
|  | 28800 | 012711 | $16,356 |
| Total |  |  | $ 500,000 |

# WORK PLAN

If resources will be used beyond one calendar year, please use the resource framework in the project document template.

Period (November-2025 to May-2026):

| SP Indicator: B.2.1.2 Number of economic or fiscal policies adopted or revised to support women’s economic empowerment Baseline: 0 Target: 4 B.2.1.3 Number of new or strengthened policies, legislations and regulations or investment in national care systems in place Baseline: 0 Target: 4 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED OUTPUTS And indicators, baselines, and annual targets | PLANNED ACTIVITIES List activity and associated actions | TIMEFRAME |  |  |  |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
|  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 |  |  | Funding Source | Specific Budget Description | Amount |
| Output 1. Enhanced gender responsiveness and inclusivity of public finance institutions. Indicator 1: At least two institutional reform policies, actions or services for gender equality have been implemented. Baseline: 0 Target: 4 SP indicator: 2.1.2, 2.1.3 Gender Marker: GEN3 | Activity 1.1: Organize and facilitate technical roundtables among government delegates (particularly public finance authorities), civil society organizations and think tanks to discuss and agree on key areas for the advancement towards gender equality. Actions: 1. Identification of relevant stakeholders. 2. Design of a methodology for the policy dialogues with stakeholder form different sectors. 3. Consolidate the key objectives to pursue on gender equality through fiscal policy. |  |  |  |  |  |  |  | UNDP country offices | FWs | Consultants Travel Conferences | $60,000 $10,000 $10,000 |
|  | Activity 1.2: carry out a specialized technical learning workshops on fiscal policy, tax, and gender equality for public institutions. Actions: 1. Together with relevant national think tanks and universities, and national institutes for civil servants, when possible, design a training strategy. 2. Implement trainings. |  |  |  |  |  |  |  | UNDP country offices | FWs | Consultants Travel Conferences | $60,000 $10,000 $15,000 |
|  | Activity 1.3: Provide technical assistance to the government in revising policies, legislation, GRB procedures and/or PFM regulations. Actions: - Map calendar moments of influence during the PFM cycle. - Provide technical assistance to the government on reforms that the government conducts. |  |  |  |  |  |  |  | Country offices with support from consultants and HQ | FWs | Consultants | $40,000 |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal: | $205,000 |
| Output 2. Strengthened evidence base and institutional capacity to integrate gender equality into public finance reforms. Indicator 1: At least one analysis, research or diagnostic study carried out on public finance and gender equality and results disseminated in a multi-stakeholder dialogue. Baseline: 0 Target: 1 Indicator 2: A reform plan for gender-responsive public finance and/or tax reforms is developed and presented to the competent authority. Baseline: 0 Target: 1 SP indicator: 2.1.2, 2.1.3 Indicator 3: Number of countries initiating or adopting fiscal policy reforms that support women’s economic empowerment or care systems. Baseline: 0 Target: 4 SP indicator: 2.1.2, 2.1.3 Gender Marker: GEN3 | Activity 2.1: Conduct an assessment of data availability and data use on public finance and gender equality. Actions: 1. Map existing data. 2. Analysis of the availability of data. Identification of areas where it can be improved. |  |  |  |  |  |  |  | UNDP country offices (with recruited national consultants, and HQ guidance) | FWs | Consultants | $40,000 |
|  | Activity 2.2: Introduce the results of the data gaps analysis to country stakeholders and discuss possibilities of reforms. Actions: 1. Organization and invitations to the workshop. 2. Delivery of the workshop and identification of a roadmap to implement. |  |  |  |  |  |  |  | UNDP country offices UNDP country offices with tools from HQ | FWs | Consultants Conferences | $20,000 $10,000 |
|  | Activity 2.3: Conduct the selected diagnostics to identify gender biases in fiscal policy, tax systems and/or GRB. Actions: 1. Identify the diagnostic tools to use based on the selected gender equality objectives in activity 1.1.1. 2. Implement the diagnostics together with governmental officials. 3. Present the results for validation. |  |  |  |  |  |  |  | UNDP country offices together with national and international consultants, and guidance from HQ | FWs | Consultants | $40,000 |
|  | Activity 2.4: Develop a policy reform proposal to finance and expand care systems based on the results of the diagnostics and data analyses. Actions: - Draft policy reform proposals for gender equality and for the expansion of care systems based on the assessments and studies carried out. -Present them to governmental officials for finetuning and revision. - Present a final policy reform roadmap agreed with the government in a stakeholder meeting. - Organization of a virtual learning exchange between countries of the FW initiative. |  |  |  |  |  |  |  | Country offices with support from HQ (HQ to organize the virtual exchange) | FWs | Consultants Conferences | $40,000 $9,000 |
|  | Activity 2.5: Provide technical assistance to the government in revising policies, legislation, GRB procedures and/or PFM regulations. Actions: - Map calendar moments of influence during the PFM cycle. - Provide technical assistance to the government on reforms that the government conducts. |  |  |  |  |  |  |  | Country offices with support from consultants and HQ | FWs | Consultants | $10,000 |
|  | Monitoring/Learning: South-south exchange of results of diagnostics, recommendations and policy options considered. |  |  |  |  |  |  |  | UNDP country offices (1,967.29 per country) | FWs |  | $7,869.16 |
|  | Communications/Advocacy: Broad dissemination with leaflets and a virtual global event on policy reforms and stories of impact from these and other countries. |  |  |  |  |  |  |  | UNDP Country offices (5,000 per country) | FWs | Publications and translation | $20,000 |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal: | $196,869.16 |
| Project Management Costs (across all proposed countries) | Coordinate activities, manage budget and operations |  |  |  |  |  |  |  |  |  | Subtotal: | $32,710.28 |
| Global Technical Accompaniment (at the HQ or Hub) | Provide technical advise, training to country offices, and missions as necessary |  |  |  |  |  |  |  |  |  | Subtotal: | $32,710.28 |
| General Management Support (7% of FWs programmable budget) (use GMS calculator) |  |  |  |  |  |  |  |  |  |  | Subtotal: | $32,710.28 |
|  |  |  |  |  |  |  |  |  |  |  | TOTAL: | $500,000 |

As per UNDP’s Enterprise Risk Management Policy

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a budget affecting the scope (outputs), completion date, or total estimated costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

Flagship initiative results should be based on the results mentioned in section 3 (Results and Partnerships). Country office contributions to the results should be included in the workplan as activities but NOT as separate outputs.

i.e. Grants, Contractual Services – Companies, Consultants, Travel, Equipment, etc.

The CO costs to implement the project, including programme and operational support at the CO level, such as personnel, rent of project premises, and delivery enabling services charges.

The global/regional level costs associated with oversight, coordination, management, and reporting to ensure strategic alignment, quality assurance, and effective support to implementation across countries.