Project Title: Leveraging enhanced climate and biodiversity financing for nature positive investment in PNG’s cocoa value chain

Project Number:

Implementing Partner:

Start Date: 01.02.2026			End Date: 30.07.2028			PAC Meeting date:

Brief Description

Papua New Guinea’s (PNG) cocoa sector faces an interconnected climate, environmental and development challenge: enhancing rural incomes while complying with increasing value chain traceability and quality requirements, avoiding further deforestation thus protecting one of the planet’s most biodiverse forest landscapes, and strengthening resilience to climate shocks. Smallholders produce the vast majority of cocoa in PNG but are constrained by outdated wood-fired drying that taints quality and contributes to deforestation. Smallholder farmers in PNG have limited access to finance and premium cocoa buyers, lack technical capacity, and are exposed to structural vulnerabilities including pests and climate shocks. Women are disproportionately affected spending significant time collecting fuelwood and tending wood-fired dryers, facing greater exposure to smoke and heat, and encountering structural barriers to credit and participation due to collateral norms and care responsibilities. These barriers curtail prices, limit export readiness, and weaken incentives for conservation. This 30-month project addresses these constraints by establishing a dedicated cocoa investment facility that provides financing for improved post-harvest assets such as solar and hybrid dryers, coupled with targeted technical assistance and capacity building on certification and standards, market linkages, agroforestry, and business skills. Pilots will prioritize women-led producer groups and ensure safe, inclusive participation and outreach to increase women’s access to finance and decision-making roles. Pilots on New Britain Island will demonstrate how nature-positive and deforestation-free value chains can improve household economics while reducing pressure on biodiversity. By project end, expected results include direct benefits to at least 1,200 people (50% women); a ≥50% increase in average net cocoa income among participating smallholders; annual reductions of ≥600 tonnes of firewood and 1,080 tCO₂e of direct GHG emission reductions. The project will contribute to increased quality and traceability of cocoa beans and facilitate linkages of producer groups to premium buyers increasing product prices and household incomes, while reducing labour burden (especially for women) through faster, cleaner processing. At least 35% of trainees will be women and the project wil lead to an increased number of female borrowers and co-signatories accessing tailored financial products, and participation of women in the O&M service enterprise and producer governance. By displacing wood in the cocoa drying process, the project also decreases fuel costs, emissions, and agricultural pressure on forests. As a demonstrator of nature-positive investment, the project will showcase how rural development can be achieved hand-in-hand with biodiversity conservation and climate resilience, providing a replicable model for other commodities and regions in PNG.

| Contributing Outcome (UNSDCF, CPD, RPD ): # 5. Environment and climate change Indicative Output(s) with gender marker: Sustainable livelihoods of local and indigenous communities in New Britain Island enhanced through establishing and increasing access to deforestation-free value chains (GEN 2) |  | Total resources required: | USD 1,283,920 |  |
| --- | --- | --- | --- | --- |
|  |  | Total resources allocated: |  |  |
|  |  |  | UNDP TRAC: | - |
|  |  |  | Donor: | USD 1,283,920 |
|  |  |  | Government: | - |
|  |  |  | In-Kind: | - |
|  |  | Unfunded: | - |  |

Agreed by (signatures):

| Government | UNDP | Implementing Partner |
| --- | --- | --- |
| Print Name: | Print Name: | Print Name: |
| Date: | Date: | Date: |

# Development Challenge (1/4 page – 2 pages recommended)

Papua New Guinea (PNG) possesses significant ecological wealth and is considered one of the world’s 17 megadiverse countries by hosting around 7% of global species on less than 1% of the planet’s land area. Around 78% of the country’s land is forested and its concentration of terrestrial and marine biodiversity positions PNG as a critical steward of global ecological health while being a priority geography for conservation and climate action. However, like other Small Island Developing States (SIDS), the country is very vulnerable to the impacts of climate change due to its dispersed coastal and island communities, reliance on subsistence agriculture and fisheries, and limited adaptive capacity.

Agriculture, forestry and fishing are a core pillar of PNG’s economy and accounted for around 17.2% of GDP in 2024 while employing most of the country’s labor force. Agriculture accounts for about 20% of total exports. PNG is the world’s 10th largest cocoa producer and cocoa is the third-largest agricultural export after palm oil and coffee. The cocoa sector is dominated by smallholder farmers (responsible for ca. 80% of the production) and thus a critical cornerstone of rural livelihoods sustaining more than 150,000 households. Although the cocoa industry in PNG suffered setbacks in the past decade mostly due to pests, cocoa production has recovered in recent years, and current historically high global cocoa prices create a strong potential for market development. However, the majority of smallholder cocoa farmers in PNG are effectively excluded from global pricing opportunities due to the use of traditional wood-fired cocoa drying which taints flavor, undermines traceability, and reduces quality of the products thus holding back income and market access for those smallholders. At the same time, regulation of high value import nations increasingly requires commodity value chains to be fully traceable to land plots with no deforestation (e.g. the EU Deforestation-Free Regulation (EUDR)).

PNG’s ecological wealth and forest cover present a clear opportunity to interlink rural development with nature-positive, climate resilient, deforestation-free economic and livelihood activities. Yet, a convergence of drivers, pressures, barriers and needs require urgent action and support. The main threats to PNG’s biodiversity are industrial logging, subsistence and commercial agriculture, mining, bushfires, climate change, invasive species and the direct exploitation of biodiversity. At the same time, high-value markets are tightening commodity import requirements rules such as by traceability and no-deforestation requirements. The following barriers are preventing PNG’s cocoa sector from embarking on a nature-positive development pathway that also yields in sustainable biodiversity and climate gains.

Barrier 1: Post-harvest constraints limiting quality, market access, and biodiversity outcomes

PNG’s cocoa supply chain is characterized by a heavy reliance on traditional wood-fired drying in the post-harvesting. Most fermenters rely on this technique, which has several disadvantages as it can cause smoky flavor of beans undermining quality and traceability of beans. Wood-fired dryers also degrade over time leading to cracks and exacerbated smoke exposure of the beans. Furthermore, their reliance on fuel wood can contribute to deforestation and fuel collection is often a laborious task that falls on rural households and especially women. A lack of appropriate infrastructure to meet quality standards or connect farmers to premium buyers has been major challenge for millions of smallholder farmers in PNG. While cocoa has been one of PNG’s most important commodity crops, outdated post-harvest and drying systems have held back quality, income and market access for many smallholders. Over the past years, alternatives and improvements to wood-fired cocoa dryers have been tested and piloted in PNG (e.g. solar-combination units; “bubble” dryers; stainless-steel vs mild steel pipe retrofits) but they frequently failed to reach scale due to factors such as high costs, low processing capacity, complexity or maintenance intensity. More recent initiatives by the EU (EU-STREIT) and Australia (APEP) have shown promising results of cocoa solar dryers leading to up to seven times higher reported prices and reduced firewood compared to traditional methods. To address this barrier, PNG needs scalable, smoke-free post-harvest infrastructure such as affordable solar/hybrid dryers to allow smallholders consistently meeting premium-buyer standards while reducing pressure on forest and labor-intense fuel collection.

Barrier 2: limited or no access to finance, markets, and technical capacity for smallholders

Over 90% of cocoa farmers are subsistence-oriented smallholders responsible for over 80% of the cocoa production. These subsistence-oriented smallholders have constrained access to finance, with little collateral, little or non-existent credit histories, and exposure to seasonal cashflows that exclude them from formal lending. For this reason, there is limited capital necessary to invest in post-harvest equipment. Market access for smallholders is similarly restricted as production is dispersed among many producers with relatively weak bargaining power, high transport costs, and limited buyer linkages that mean beans are often sold into lower-value channels at discounted prices. Due to limited or no access to finance, markets, and technical capacity for smallholders, there is a further need for targeted, grant-funded solar dryers coupled with technical assistance and capacity building for smallholder farmers on issues like value addition and processing, quality standards and certification, market linkages, and marketing and buyer matchmaking. Furthermore, there is a need to expand cocoa farmer techniques to new areas of cocoa growth such as the Highlands and introduce affordable, higher-capacity, clean-energy dryers that centralize processing and therefore improve monitoring, consistency and product quality.

Barrier 3: Structural supply chain challenges and climate/ecological pressures

Cocoa production in PNG is affected by these various challenges including pests and diseases (such as the Cocoa Pod Borer (CPB) and Black Pod Disease), effects of climate change including intense rainfall and potential droughts, low soil fertility and high cadmium levels, and financial and logistical issues such as cash shortages for farmer payments, a lack of export containers, and low incomes and financial capacity. Environmental issues like deforestation and inadequate quality control in fermentation also negatively impact cocoa production. In addition to environmental and climate stressors, PNG’s cocoa supply chain is characterized by structural challenges. For example, when the CPB started to decimate crops in 2006, its impacts were widespread and persistent because there was no coordinated programme to propagate and distribute CPB-resistant seedlings, nor a sustained extension effort to ensure smallholders understood and applied effective CPB control practices. There is a continued need to promote new and innovative approaches and techniques (e.g. agroforestry systems, introducing improved seedlings) that mitigate vulnerabilities of PNG’s cocoa sector, such as exposure to pests, climate shocks, and unsustainable land-use expansion.

Against this backdrop of accelerating climate impacts, a worsening biodiversity crisis, and tightening market access excluding non-compliant commodity exports, this proposed project aims to protect PNG’s biodiversity and build climate resilience investment in nature-positive cocoa value chains that support smallholder farmers and enhance rural livelihoods. Implemented over 30 months from January 2026 to June 2028 by the United Nations Development Programme (UNDP) in partnership with the UN Capital Development Fund (UNCDF) and the Government of PNG, the project is directly in line with PNG’s national climate, biodiversity and development objectives including its Nationally Determined Contribution (NDC), its Vision 2050, and the recently (2024) adopted 23 National Biodiversity Targets defining PNG’s commitments under the Kunming-Montreal Global Biodiversity Framework of the Convention on Biodiversity. The project will support local and indigenous cocoa smallholder farmers and processers in adopting deforestation-free value chains by replacing wood-based drying with clean and traceable post-harvest systems.  The project will channel enhanced climate and biodiversity finance into investment projects and thus ensure that sufficient capital flows continuously and reliably to where communities and nature need it most for achieving climate, biodiversity and sustainable development objectives alike. The project interventions therefore address the principal drivers of nature loss while improving the livelihoods of 1,200 people (50% female) in remote areas of PNGs’ New Britain Provinces. The project will be closely aligned with relevant ongoing partner initiatives such the EU Forestry, Climate Change and Biodiversity Programme (EU-FCCB) and the Australia funded Papua New Guinea Economic Partnership (APEP). Specifically, the project will build on the scaling-up of successes achieved under the Food Systems, Land Use and Restoration Impact Program (FOLUR-IP) child project supported by UNDP and CEPA with funding from Global Environment Facility (GEF). The proposed project will leverage tools established under this project (e.g. an Information Management System for New Britain), use lessons from the cocoa awareness workshops for the capacity building activities and scale-up investment in deforestation-free cocoa value chains.

# Strategy (1/2 page - 3 pages recommended)

This proposed project directly responds to the barriers preventing PNG’s cocoa sector from transitioning to a nature-positive and climate-resilient development pathway. By addressing outdated post-harvest systems, limited finance and market access, and structural vulnerabilities in the cocoa value chain, the project will demonstrate how investments in sustainable production can simultaneously enhance rural livelihoods, protect biodiversity, and strengthen climate resilience.

First, the project tackles the heavy reliance on wood-fired post-harvest systems that reduce cocoa quality, prevent traceability, and contribute to deforestation and forest degradation. By introducing solar and hybrid dryers, the project will raise product quality, eliminate smoke taint, improve compliance with international standards such as the EU Deforestation-Free Regulation, and reduce pressure on forests from fuelwood use.

Second, the project addresses smallholders’ limited or no access to finance, markets, and technical capacity. Smallholder farmers (responsible for the majority of PNG’s cocoa production) lack affordable credit to invest in sustainable technologies, are poorly connected to premium markets, and have limited knowledge of certification, business skills, and agroforestry. To overcome these barriers, the project will establish a dedicated cocoa investment facility, provide targeted technical assistance on quality standards and certification, and deliver capacity-building for smallholders (with at least 35% women participants) to improve their agronomy, post-harvest techniques, business development, and access to markets.

Third, the project mitigates structural and ecological vulnerabilities of PNG’s cocoa sector, including exposure to pests, climate shocks, and unsustainable land-use expansion. By promoting agroforestry systems, introducing improved seedlings, and integrating non-deforestation supply chain practices, the project will reduce drivers of biodiversity loss and position cocoa as a contributor to forest conservation and restoration rather than deforestation.

Through these interventions, the project will enhance the livelihoods of 1,200 smallholder farmers (50% women) in PNG’s New Britain Provinces. It will increase household incomes by improving product quality and market access, reduce labor burdens (particularly for women) through cleaner processing, and safeguard biodiversity by lowering reliance on forest resources. By introducing solar cocoa dryers that harness renewable energy, reliance on biomass will be lowered and associated GHG emissions will be reduced providing reliable and sustainable access to energy for remote smallholders. As a demonstrator of nature-positive investment, the project will showcase how rural development can be achieved hand-in-hand with biodiversity conservation and climate resilience, providing a replicable model for other commodities and regions in PNG.

The project will be implemented from January 2026 to June 2028 by the UNDP in partnership with the Government of PNG with the following Output and activities:

Output: Sustainable livelihoods of local and indigenous communities in New Britain Island enhanced through establishing and increasing access to deforestation-free value chains

Addressing the needs identified in the previous section, this project aims to support nature-positive investment and capacity building for cocoa farmers and act as demonstrator how nature-positive investment can couple income gains with reduced pressure on biodiversity. The focus will be on PNG’s New Britain Island (East New Britain and West New Britain Provinces) since palm oil development has caused significant deforestation and forest degradation in the New Britain Provinces and deforestation is continuing despite a national policy to combat deforestation from agriculture. Furthermore, around 40% of cocoa in New Britain Provinces were heavily pruned between 2006 and 2015 as a result of CPB, many smallholders still operate far below potential due to aged trees, low input management, and shortages of certified seedlings. Further, competing commodity crops like Balsa and Oil Palm has made smallholders farmers to switch crops. At 3,330,890 ha, the island ranges from dense lowland plains to a central mountainous spine with peaks of over 2,000 m. With high levels of forest cover, the island represents an area of high value biodiversity but is also threatened from rapid forest loss due to agricultural conversion with over 450,000 ha under permits for forest clearance. This pressure is driven by PNG’s socio-economic status, which includes a desire for economic development and income, rapid population growth, and the high importance of agriculture in PNG’s economy. These impacts are further exacerbated within the agricultural sector due to knowledge gaps in sustainable production, prevalence of unsustainable practices, unresponsive supply chains and limited access to finance.

In close collaboration with the relevant Government authority (CEPA, Cocoa Board of PNG), and UNCDF, Credit Guarantee Corporation, the private sector and industry groups, this Output, will (co-)finance advanced cocoa post-harvesting equipment and processes (e.g. solar cocoa dryers) in PNG’s New Britain Island. Solar cocoa dryers harness solar energy to accelerate and stabilize the drying process, delivering uniformly cured beans (a critical quality attribute for premium-grade cocoa in international markets) while preserving size, aroma, and consistent color. As an eco-friendly technology, solar cocoa dryers cut curing time without smoke taint, reduce reliance on firewood (and associated emissions), and thus lower the overall carbon footprint of cocoa farming and processing. These investments are intended to demonstrate bankable projects that mobilize and expand nature positive value chains and position PNG cocoa products competitively in high-standard markets, while raising household incomes, improving livelihoods, reducing pressure on forests and on biodiversity, and leading to climate resilience benefits. Each investment will be accompanied by targeted technical assistance (e.g. on quality standards and certification; market linkages and export readiness; digital marketing and e-commerce) and capacity building (e.g. agroforestry; value addition and processing; business development and financial literacy) to scale business-oriented smallholder production through targeted extension, improved market-access infrastructure, and stronger stakeholder coordination. Activities under this Output are as follows:

Activity 1. Programme setup, coordination and management

A clear governance structure involving UNDP, UNCDF, a licensed financial institution, and CEPA as well as the Cocoa Board will be established with defined roles, responsibilities, and decision-making mechanisms, ensuring accountability and effective collaboration.

Activity 2. Establish a Cocoa investment facility with UNCDF

In partnership with UNCDF, Credit Guarantee Corporation, and a licensed financial institution, the project will establish a dedicated (revolving) lending portfolio designed to unlock finance deforestation-free, climate-smart assets (solar and hybrid dryers, PV-battery ventilation systems and other clean technologies).

By combining guarantees, blended finance, and technical expertise, the facility will enable cocoa farmers and cooperatives to access affordable credit for equipment that not only improves quality and yields but also reduces reliance on firewood cutting both costs and emissions.

The  facility’s final design will be shaped during  the inception phase and baseline study which will include  borrower mapping and pipeline development, techno-economic analysis of the cocoa market, and a detailed assessment of funding eligibility, tenor, pricing, equity contribution, repayment terms linked to estimated avoided firewood fuel costs and quality premiums.

Furthermore, as a key technical partner, the Cocoa Board of PNG will be supported in piloting a cocoa farmer and fermenter directory informing the borrower mapping and pipeline and aimed at further strengthening the coordination among stakeholders and information centralization across the supply chain.  The aim is to establish a self-sustainable financing mechanism that utilizes grants to de-risk and provides access to finance for the poorest and most vulnerable smallholder farmers while leveraging grants with other forms of public and private/commercial co-finance. The investment from the facilty (Act.3) will be combined with targeted technical assistance (Act. 4) and capacity building (Act. 5) to support business development and protect asset performance.

Activity 3. Targeted investment into nature-positive cocoa post-harvesting equipment enhancing product quality and rural livelihoods

While the concrete investments will be informed by defined selection and eligibility criteria for the investment facility (Act. 2) and defined in the baseline and inception report, they will prioritize most vulnerable and low-income smallholder farmers, women-led farms and other marginalized populations. Investments will be channeled both into individual farm-level  and centralized processing plants owned by smallholders or smallholder groups, by plantations, or by traders serving several farmers and allowing for 24/7 drying capacity independent of daylight and weather (Table 1). Funds will be channeled in the beginning of the second year of implementation through the investment facility (Act. 2) with the financing modality and detailed technology options to be confirmed during project inception.

Table 1: Indicative investments of the project

| Indicative number of investments | Farming model | Type of processing equipment | Processing capacity per year (t) | Est. costs per investment (USD) | Total investment per model (USD) |
| --- | --- | --- | --- | --- | --- |
| 30 | Subsistence-oriented (lower intensity input) | Forced convection solar dryer for remote subsistence-oriented smallholder farmers designed for a yearly drying capacity of 0.5t of cocoa consisting of a solar collector and a solar PV powered electrical fans, sensors and control box | 0.5 | 1,170 | 35,100 |
| 30 | Business-oriented (higher intensity input) | Forced convection solar dryer for more business-oriented cocoa farmers with designed for a yearly drying capacity of 1t of cocoa consisting of a solar collector and a solar PV powered electrical fans, sensors and control box | 1 | 2,340 | 70,200 |
| 2 | Centralized processing plants owned by smallholders, plantations, or traders severing several farmers | Centralized cluster drying unit with solar PV-battery battery system (24/7 airflow, QC station etc.) | 100 | 135,000 | 270,000 |

Activity 4. Targeted technical assistance to smallholder cocoa farmers to enhance cocoa products and sales

This activity will provide hands-on advisory to the beneficiaries of the investments under Activity 3 (and if feasible also beyond this group) on quality standards and certification, market linkages and export readiness, and digital marketing and e-commerce. Smallholder farmers will be supported in certification, improving product traceability and network establishment with specialty buyers to improve export capacity of cocoa in PNG. Delivered from the second year of project implementation via targeted technical assistance support, this activity will be sequenced with the investments (Act. 3) and aims to support beneficiaries in converting improved post-harvest quality into premium cocoa products and sales.

Activity 5. Targeted capacity building for smallholder cocoa farmers to improve farming and post-harvesting processing techniques and business development

This activity will provide targeted capacity building for the beneficiaries of the investments under Activity 2  (and if feasible also beyond this group). Smallholder knowledge of best practices for growing is still limited and dedicated training for smallholder farmers will be developed and rolled out into new and expanded cocoa production areas (such as the Highlands) and include promotion of cocoa agroforestry systems that shift cocoa from being a driver of deforestation to a contributor for conservation and restoration. Examples include combining improved agronomy and post-harvest practices with sustainability certifications (e.g., Rainforest Alliance) that reward compliant producers, introduce robust traceability to verify no-deforestation supply, and initiate community-led reforestation initiatives that provide economic incentives for protecting and restoring forest ecosystems such as by grow cocoa alongside native trees in “forest gardens” or productive forests. Farmers and fermenters will also be supported to enhance their capacity in business development to help them understand the markets, conduct informed price negotiations, and enhance access to credit. Delivered from the second year of project implementation, training and capacity buildings will be sequenced with the investments (Act. 3) to ensure that cocoa farmers and processors can apply and optimize supplied post-harvest technology sustainably.

Activity 6. Supporting the establishment of solar dryer service and maintenance enterprise

To ensure that the solar dryers and their key components (such as the solar PV panels; sensors; control box etc.) are maintained, serviced and replaced in the long term, the project will support the establishment of a dedicated solar dryer service and maintenance enterprise. The business and financing model for such enterprise will be determined in a feasibility study but could involve either funds from the cocoa investment facility (at least in the short term) and/or from the benefiting farmers through additional income from higher sales (in the medium and long term). Activities will include a detailed feasibility study, identification of potential service providers, assistance in developing key components such as service level agreement templates or a tariff model, and training of technicians. Initiated with the feasibility study at the start of the project, establishment of the enterprise will be sequenced with investment (Act. 3) and technical assistance/capacity building (Act. 4 and 5). The enterprise will be registered locally and provide maintenance and repair services to the benefiting farmers during the project and beyond.

# Results and Partnerships (1.5 - 5 pages recommended)

Expected Results

This project delivers integrated socio-economic and environmental benefits. The project aims to benefit directly 1,200 people (50% female) by enhancing the income of remote smallholder cocoa farmers in PNGs’ New Britain Provinces. Indirect beneficiaries from the project that will benefit from enhanced biodiversity and climate finance on the national scale are estimated at 10,000 people.

Solar-powered, smoke-free cocoa drying raises quality and traceability of cocoa beans and enables linkages to producer groups to premium buyers increasing product prices and household incomes while reducing labor burden (especially for women) through faster, cleaner processing. By displacing wood in the cocoa drying process, the project also decreases fuel costs, emissions, and agricultural pressure on forests. Complemented with on-farm restoration and cocoa-agroforestry, this will offer positive alternatives for smallholders (e.g. oil palm small holder farmers). Paired with targeted business skills, certification and export-readiness support, these measures build a more efficient, resilient cocoa value chain and a healthier environment, translating into higher incomes for less work and more reliable market access. The project indicators are as follows:

By the end of the project (June 2028),

• the average net annual income from cocoa of participating smallholders increases by ≥50% over the 2025 baseline (PGK);

• participating cocoa producers reduce annual firewood use by ≥600 tonnes compared to the 2025 baseline reducing pressure on forest and farmers and fermenters operating costs;

• the project achieves ≥1,080 tCO₂e of annual direct emissions reductions from avoided firewood combustion versus the 2025 baseline.

The project indicators will be finalized and quantified during the project baseline and inception phase and subsequently tracked and assessed at project mid-term and final evaluation. The baseline will set targets and definitions including means of verification and disaggregation by sex, age and location through surveys, key-informant interviews, review of farmer and enterprise records, data on traceability, and dryer performance. The final evaluation will replicate the methodology of the baseline study to measure change against targets and to confirm outcomes and lessons for scale-up.

A detailed summary of all project benefits is provided in the table below:

Table 2: Anticipated social, economic and environmental benefits of the project

| Benefit Category | Benefit Sub-category | Description |
| --- | --- | --- |
| Economic | Increase of household income | - Benefitting farmers income will increase by 50% due to higher prices from increased product quality and linkages to premium buyers resulting in annual estimated sales of PGK 367,500. |
|  | Business activity and SME growth | - A minimum of 30 subsistence oriented, 30 business-oriented and 2 central processing facilities owned by smallholders or community groups are supported by targeted investment, technical assistance and capacity building adopting business-oriented cocoa practices, enabling consistent higher sales, improving cashflow, and growth plans. - The establishment of the solar dryer maintenance and service enterprise will create new jobs (estimated around 10). |
|  | Export revenue and market access | - Traceability and certification are aimed to yield ca. 50t annual cocoa exports as a result of the project interventions. - Increase percentage of high-value cocoa to high end markets (currently 1 %) |
|  | Access to finance | - Strengthened or established payment track records, quality compliance, higher sales and targeted capacity building will enhance access to finance for vulnerable smallholder farmers. |
|  | Fuel cost savings | - Annual firewood reduction of benefitting communities of ca. 600t will decrease drying operating costs and free up time for other economic and community activities. |
| Social | Women’s workload and time use | - Smoke-free solar drying reduces fuel collection and tending time decreasing women’s labor burden, freeing time for other income activities and care. - At least 35% of trainees under this project will be women |
|  | Skills and local capacity | - Practical training in value addition, market access, business development etc. upgrades skills of cocoa producers and processers. |
|  | Community reinvestment | - Higher prices, sales and farmers income will free capital for community reinvestment such as for education, repairs etc. |
| Environmental | Firewood reduction | - Annual firewood reduction of ca. 600t will reduce pressure on forests. |
|  | Biodiversity | - Improved farming and processing skills and technologies will lead to higher returns per hectare and reduce incentives to expand agricultural activities into forests. - Promotion of cocoa agroforestry systems that shift cocoa from being a driver of deforestation to a contributor for conservation and restoration. |
|  | Climate Change | - The annual avoidance of 600t of firewood for combustion will lead to estimated annual direct GHG emission reductions of ca. 1,080 t Co2e |

Resources Required to Achieve the Expected Results

- Describe what resources are required to achieve the expected results. Thinking about the change pathway in your theory of change, state the key inputs (people, purchases, partnerships, etc.) that are required to deliver the outputs. This should include UNDP staff time from the country, region or HQ level, which must be adequately estimated, costed, and included in the project budget.

Partnerships

The project will be delivered through a coordinated partnership led by the Conservation and Environment Protection Authority (CEPA) working together with UNDP as lead implementing agency of this project and the Cocoa Board of PNG as a technical partner. Leveraging its catalytic financing expertise for mobilizing and unlocking capital for investments for sustainable and inclusive growth, the cocoa investment facility under this project will be established in partnership with UNCDF and other partners such as Credit Guarantee Corporation and a licensed financial institution. UNCDF and UNDP will convene all partners to co-develop the design of the facility during the baseline and inspection report of the project. A cocoa producer and fermenter registry, coordinated by CEPA and implemented by the Cocoa Board of PNG and supported under this project, will inform validation of the borrower pipeline. The selected financial institution will handle origination, underwriting, disbursement and collections using tailored loan products for vulnerable smallholders, women-led groups and centralized cocoa processing facilities, with repayments designed at higher income streams from lower operating and higher product costs (quality premiums). UNCDF will structure the de-risking instruments (e.g. first loss guarantee) and provide finance, investment and risk analytics. UNDP will lead and co-deliver technical assistance and capacity building activities under Act. 4 and 5 in close collaboration with technical agencies, producer groups, and local NGOs. The project will also closely collaborate with relevant provincial administrations to facilitate site access and landowner engagement and monitoring.

The project will also establish partnerships with financing institutions (domestic commercial banks and MFIs, regional and global development finance (such as the Asian Development Bank (ADB), World Bank) to mobilize and channel capital to biodiversity and climate finance in PNG, either as additional co-finance to the cocoa investment facility under this project or to other, complementary financing vehicles in PNG such as the Biodiversity and Climate Fund (BCF).

Activities will be closely implemented in partnership with existing ongoing relevant projects including  the UNDP-implemented, GEF-financed FOLUR project, EU-funded initiatives (e.g., EU Forestry-Climate Change-Biodiversity national component supporting EUDR readiness and sustainable commodity policy) and Australian-funded programmes (e.g. Australia–Papua New Guinea Economic Partnership (APEP), to avoid duplication and leverage existing technical assistance, experience from successful demonstration pilots, and certification activities. The project will also coordinate with ongoing buyer partnerships (e.g. supply-chain platforms connecting PNG producers to premium markets) to ensure that solar-dried, traceable cocoa can be marketed in stable contracts and higher price segments. Specifically, the project will build on the scaling-up of successes achieved under the FOLUR-IP project to scale-up investment in deforestation-free cocoa value chains.

Risks and Assumptions

Table 3: Risks and mitigation measures of the project

| Risk Categories | Ratings | Assessment and Mitigation Measures |
| --- | --- | --- |
| Climate | Substantial | PNG is one of the most climate vulnerable countries. Tropical cyclones, floods, landslides and droughts already disrupt generation and the long radial lines that cross rugged terrain. The project will increase vulnerable farmer incomes via high quality cocoa strengthening household adaptive capacity and resilience. By establishing a self-sustainable financing mechanism, the project aims to also support additional mobilization of climate and biodiversity finance allowing vulnerable cocoa farmers to invest in nature-positive, climate adaptation and livelihood supporting activities in the long term. Particular attention will be given to the design and assessing the location of system installations to reduce the risk of climate shocks and disasters on the infrastructure provided through the project. |
| Environment and Social | Moderate | Risks include land/tenure sensitivities (97% of land is customary managed and owned), potential pressure to expand agricultural activities into forests, and potential impacts from construction and small e-waste streams from solar PV and batteries supplied. As implementing agency, UNDP will apply its relevant environment and social safeguards policies and tools and conduct inclusive consultations to avoid misunderstanding and conflicts. |
| Political and Governance | Moderate | PNG faces issues with public‑sector corruption and governance reforms are still maturing. Governance and coordination risks across public departments and provinces exist. The project will mitigate this risk by establishing a Project Steering Committee, shared and transparent information sharing among the key entities, and alignment with other key initiatives such as EU/Australia/GEF funded initiatives. |
| Technological, Financial and Business Model | Moderate | The project involves the deployment of new technologies, which presents a degree of technological risk, particularly in terms of local capacity for operation, maintenance, and integration into existing systems. Financial risks include price volatility, cash-flow gaps, and working-capital needs that can constrain smallholders, as well as buyer-concentration risk. Given the limited expertise and resources of smallholder farmers, there is a potential risk of underutilization or system failure if technologies are not appropriately matched to local conditions. To mitigate this risk, the project will provide targeted capacity building, hands-on training and technical assistance for smallholder farmers on business development and improving farming and processing techniques. |
| Capacity for Implementation | Moderate | The country faces moderate risks related to capacity for implementation. Limited absorption capacity within government institutions, coupled with staffing constraints, can hinder the timely execution of project activities. The project will therefore be implemented by UNDP in close coordination and country-owned implementation plans which will ensure that implementation is grounded in national priorities and planning. |
| Fiduciary | Substantial | There is a risk of weak financial management, procurement, and oversight systems within national institutions, particularly given PNG’s limited institutional capacity. The project will therefore be implemented by UNDP in close coordination with relevant Government counterparts. |
| Other | Moderate | PNG’s rugged topography, limited road network, and recurrent port congestion frequently slow equipment deliveries and increase project costs, while incomplete grid‑performance data hinder effective planning. Building on the experience of past projects and applying lessons learned, the project will streamline implementation processes, reduce delays, and shorten overall project timelines such as by using pre-qualified vendors and leveraging established institutional procedures. |

Stakeholder Engagement

Primary beneficiaries of this project are smallholder cocoa farmers and fermenters in PNG’s New Britain Island (East New Britain and West New Britain Provinces) explicitly targeting women-led producers, vulnerable/low-income smallholder households, and producer groups and farmer cooperations. Target groups will be identified through an initial mapping as part of the baseline study during project inception followed by a detailed producer and fermenter mapping to be conducted by the Cocoa Board under Act. 2. To the extend possible, key information will be collected such as on vulnerability, income, remoteness, land tenure etc. The project will engage with the main beneficiaries regularly, such as through village meetings and beneficiary consultations. Training and advocacy material will be translated.

Other key project stakeholders include CEPA (as main Government lead), the Cocoa Board (as key technical counterpart), and other relevant ministries and provincial administrations. The project will establish partnerships with domestic and international financing institutions to mobilize and channel capital to biodiversity and climate finance in PNG, either as additional co-finance to the cocoa investment facility under this project or to other, complementary financing vehicles in PNG such as the BCF. Linkages of producers and fermenters with key market actors such as exporters, off-takers, buyers and certification bodies will be established. Civil-society partners (local NGOs/CBOs) will be partnered with to mobilize producer groups and co-deliver training.

People living near processing sites, customary landowners, and non-participant farmers may be indirectly affected by site selection, traffic, noise, or perceived distributional inequities. The project will apply UNDP Social & Environmental Standards and disclose information early (eligibility, site criteria, benefit-sharing etc.). Continuous engagement will be maintained via regular site visits.

Digital Solutions

The project will deploy simple, fit-for-purpose digital tools. As identified feasible, the investment facility will use digital application and appraisal process and offer digital repayment options, with a dashboard for the facility and partners to track progress. Digital tools will also help to analyze and optimize dryer performance and assist in planning maintenance. Training and capacity building will utilize digital tools where appropriate, aligned with UNDP data safety policies.

Knowledge

The project will generate practical, reusable knowledge assets and make them widely accessible. Planned products include:

- Cocoa post-harvest standard operating procedures (SOPs) and toolkits on fermentation, smoke-free drying, etc. and O&M manuals for solar/hybrid dryers;

- a producer/fermenter registry;

- training curricula (on various topics including on agroforestry, business/financial literacy, export readiness) and training facilitator guides;

- case studies on income increase, firewood/CO₂e reductions, and gender outcomes

- policy briefs and media products (short videos, photo stories, local newspaper articles, infographics).

Sustainability and Scaling Up

The project is designed so that benefits persist after the end of the project. By blending donor capital with commercial finance through the investment facility anchored in a licensed financial institution, and by recycling repayments into new financing to cocoa producers and processers, the facility converts one-off grants into a self-sustaining finance mechanism that will endure beyond the project. Combining the investment with technical assistance and capacity building will help protect asset repayment performance, while higher, more stable farmer incomes from high quality cocoa products will promote and enable continuous reinvestment into cocoa farming activities, enhance business management, and increase resilience to price shocks. Engaging MFIs, banks, and other investors will de-risk lending, expand borrower access to working capital, creating an evidence base that can help attract follow-on finance for replication in additional provinces and commodities.

The establishment of a solar dryer service and maintenance enterprise will ensure that the solar dryers and their key components (such as the solar PV panels; sensors; control box etc.) are maintained, serviced and replaced in the long term. Careful technology selection, including lessons learnt from other projects in the country and the region will prioritize durable technology choices with a long lifetime. Through its capacity building components, the project will provide comprehensive training programs for smallholder farmers, enhancing local capacity on nature-positive farming and processing of cocoa. This enhanced capacity will contribute to the sustainability of the project and empower communities to balance agricultural and nature conservation trade-offs effectively. By fostering community ownership and involvement, the project will also enhance social cohesion and resilience.

# Project Management (1/2 pages - 2 pages recommended)

Cost Efficiency and Effectiveness

- To maximize efficiency and continuity, the Project Management Unit (PMU) will be embedded within the existing PMU of the on-going UNDP and CEPA implemented -GEF FOLURproject benefitting from UNDP’s existing Country Office project management platforms, leveraging existing technical and managerial expertise and networks, and using established procedures, shared services, and procurement, finance, safeguards, and M&E. This integration reduces time for project inception, operationalization, and overhead costs, and enables joint operations. The PMU will draw on the Country Office’s portfolio of active projects for coordination and data sharing while maintaining a compact core team for day-to-day delivery and using targeted short-term experts for specialized tasks. Governance will adhere through the Country Office’s standard controls and biannual Project Steering Committee meetings, ensuring timely workplan/budget approvals, transparent reporting, and rapid problem-solving without duplicating structures.

Project Management

The project will be implemented primarily on New Britain Island (East andWest New Britain), with implementation support delivered through a PMU embedded in ongoing UNDP and CEPA implemented GEF-FOLUR project.  UNDP Direct Country Office Support Services (GMS/DES) and direct project costing are budgeted in the proposal to cover fiduciary management, procurement, contract administration, oversight, and M&E/MRV, ensuring compliant delivery and implementation.

# Results Framework

Intended Outcome as stated in the UNSDCF/Country Programme Results and Resource Framework: #5: Environment and climate change

Outcome indicators as stated in the Country Programme Results and Resources Framework, including baseline and targets: By 2028, people in Papua New Guinea, especially the most marginalized and vulnerable, benefit from equitable and participatory access to climate resilient services that improve livelihoods and protect natural resources

Applicable Output(s) from the UNDP Strategic Plan: Natural resources protected and managed to enhance sustainable productivity and livelihoods

Project title and Quantum Project Number: Leveraging enhanced climate and biodiversity financing for nature positive investment in PNG’s cocoa value chain

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | ## TARGETS (by frequency of data collection) |  |  |  | ## DATA COLLECTION METHODS & RISKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year | Year 1 | Year 2 | Year 3 | ## FINAL |  |
| Output 1 Sustainable livelihoods of local and indigenous communities in New Britain Island enhanced through establishing and increasing access to deforestation-free value chains | 1.1 Number of people directly benefitting from initiatives to protect nature and promote sustainable use of resources (male/female) | Assuming 60 subsidence and business oriented farmers with a household size of 5 people on average (300 people) and and 180 farmers with an household size of 5 people on average (900 people) benefiting from the investment in the centralized processing plants. | 0 | 2026 | 150 (75/75) | 300 (150/150) | 750 (375/375) | 1,200 (600/600) | Houeshold and farmer surveys including M&E Reports |
|  | 1.2 Areas of landscapes under improved practices, excluding protected areas (hectares) | Assuming 30 smallholders (1 hectar each) and 30 business-orientied farmers (0.75 hectars each) benefit from project activities (Lescuyer et al. 2018, Value Chain Analysis of the cocoa industry in Papua New Guinea). | 0 | 2026 | 10 | 20 | 20 | 50 | MRV Worksheets |
|  | 1.3 Average net annual income from cocoa of participating smallholders increased (PGK) | Assuming project facilitated investment to annual drying capacity of 245t and current sales prices of 1 PGK/kg which will increase to 1.5 PGK/kg as a result of quality increase. | 245,000 | 2026 | - | - | 367,500 | 367,500 | Houeshold and farmer surveys and spot checks |
|  | 1.4 Reduction in annual firewood use in benefitting communities (tonnes) | Assuming a reduction of 2.5t in firewood use per ton of cocoa produced | 0 | 2026 | - | - | 600 | 600 | Houeshold and farmer surveys and spot checks |
|  | 1.5 Reduction in annual direct greenhouse gas emissions (tCO₂e) | Assuming annual avoidance of 600t of firewood for combustion. | 0 | 2026 | - | - | 1,080 | 1,080 | MRV Worksheets |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans: [Note: monitoring and evaluation plans should be adapted to project context, as needed]

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. |  |  |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. |  |  |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. |  |  |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. |  |  |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. |  |  |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) |  |  |  |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Specify frequency (i.e., at least annually) | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. |  |  |

Evaluation Plan

| Evaluation Title | Partners (if joint) | Related Strategic Plan Output | UNSDCF/CPD Outcome | Planned Completion Date | Key Evaluation Stakeholders | Cost and Source of Funding |
| --- | --- | --- | --- | --- | --- | --- |
| e.g., Mid-Term Evaluation |  |  |  |  |  |  |

# Multi-Year Work Plan

All anticipated programmatic and operational costs to support the project, including development effectiveness and implementation support arrangements, need to be identified, estimated and fully costed in the project budget under the relevant output(s). This includes activities that directly support the project, such as communication, human resources, procurement, finance, audit, policy advisory, quality assurance, reporting, management, etc. All services which are directly related to the project need to be disclosed transparently in the project document.

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year |  |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Y1 | Y2 | Y3 |  |  |  | Funding Source |  | Budget Description |  | Amount |  |
| Output: Sustainable livelihoods of local and indigenous communities in New Britain Island enhanced through establishing and increasing access to deforestation-free value chains Gender marker: GEN2 | 1. Programme Setup, Coordination and Management | 50,000 |  |  |  |  | UNDP |  |  |  |  | 50,000 |  |
|  | 2. Establish a cocoa investment facility with a financial partner | 225,750 | - | - |  |  | UNDP/UNCDF |  |  |  |  | 225,750 |  |
|  | 3. Targeted investment into nature-positive cocoa post-harvesting equipment enhancing product quality and rural livelihoods | - | 245,000 | 155,000 |  |  | UNCDF |  |  |  |  | 400,000 |  |
|  | 4. Targeted technical assistance to smallholder cocoa farmers to enhance cocoa products and sales |  | 70,000 | 35,000 |  |  | UNDP |  |  |  |  | 105,000 |  |
|  | 5. Targeted capacity building for smallholder cocoa farmers to improve farming and post-harvesting processing techniques and business development |  | 70,000 | 35,000 |  |  | UNDP |  |  |  |  | 105,000 |  |
|  | 6. Supporting the establishment of solar dryer service and maintenance enterprise | 15,000 | 40,000 | 50,000 |  |  | UNDP |  |  |  |  | 105,000 |  |
|  | Project Management Cost | 92,812 | 92,812 | 46,407 |  |  | UNDP |  |  |  |  | 232,031 |  |
|  | Sub-Total for Output |  |  |  |  |  |  |  |  |  |  |  |  |
| General Management Support (5%) |  | 19,178 | 25,891 | 16,070 |  |  | UNDP |  |  |  |  | 61,139 |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  | 1,283,920 |  |

# Governance and Management Arrangements

CEPA will serve as a Proponent of this project. The Cocoa Board of Papua New Guinea will serve as the a technical partner of this project, leveraging its statutory mandate under the Cocoa Act 1981 and Regulations 1982 to regulate the industry, set/enforce quality standards, coordinate extension and R&D, and facilitate export procedures. The project will be implemented under Direct Implementation Modality (DIM) by UNDP. A Cost-Sharing Agreement between CEPA and UNDP will enable the transfer of project funds to UNDP for execution. UNDP will enter a dedicated partnership with UNCDF to design, operationalize and finance the cocoa investment facility.

UNDP will assume overall management responsibility and accountability for timely delivery, fiduciary oversight, procurement, environmental and social safeguards, financial reporting, and audit. The project will be housed in UNDP’s PNG Country Office with day-to-day operations supported by UNDP’s Operations Team and strategic oversight by the Deputy Resident Representative. A dedicated Project Management Unit (PMU) within UNDP will be established (or expanded from existing capacities), involving project management, finance, admin, operations M&E, MRV tasks, social safeguards and gender and relevant technical responsibilities.

A Project Steering Committee will provide strategic direction and approve annual workplans and budgets. The Steering Committee will be chaired by the Cocoa Board with membership from other relevant public, private-sector representatives and civil society representatives as needed. The PSC will meet biannually and endorse key instruments and milestones of this project (refer to section 9 for details on the milestones).

# Legal Context

[NOTE: Please choose one of the following options, as applicable. Delete all other options from the document]

# Option a. Where the country has signed the Standard Basic Assistance Agreement (SBAA)

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of (country) and UNDP, signed on (date).   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by [name of entity] (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Option b. Where the country has NOT signed the Standard Basic Assistance Agreement (SBAA)

The project document shall be the instrument envisaged and defined in the Supplemental Provisions to the Project Document, attached hereto and forming an integral part hereof, as “the Project Document”.

This project will be implemented by [name of entity] (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Option c. For Global and Regional Projects

This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions to the Project Document attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by [name of entity] (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

[NOTE: Please choose one of the following options that corresponds to the implementation modality of the Project. Delete all other options.]

Option a. Government Entity (NIM)

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

- a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4 have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and its sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

b) The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.

- In the implementation of the activities under this Project Document, UNDP places reasonable reliance upon the Implementing Partner for it to apply its laws, regulations and processes, and applicable international laws regarding anti money laundering and countering the financing of terrorism, to ensure consistency with the principles of then in force the UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy.

- The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes in accordance with UNDP’s regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, credible allegation of fraud or corruption or other financial irregularities with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- Choose one of the three following options:

Option 1: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

Option 2: The Implementing Partner agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors, and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

Option b. UNDP (DIM)

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism , that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Project Document, UNDP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor, and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - Each responsible party, subcontractor and sub-recipient (each a “sub-party” and together “sub-parties”) acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the sub-parties, and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, each sub-party shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, each sub-party, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

  - In the performance of the activities under this Project Document, each sub-party shall (with respect to its own activities), and shall require from its sub-parties (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, sub-parties will and will require that their respective sub-parties will take all appropriate measures to:

(i) Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

(ii) Offer employees and associated personnel training on prevention and response to SH and SEA, where sub-parties have not put in place its own training regarding the prevention of SH and SEA, sub-parties may use the training material available at UNDP;

(iii) Report and monitor allegations of SH and SEA of which any of the sub-parties have been informed or have otherwise become aware, and status thereof;

(iv) Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

(v) Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. Each sub-party shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the relevant sub-party shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

  - Each sub-party shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the relevant sub-party to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

  - Each responsible party, subcontractor and sub-recipient will ensure that any project activities undertaken by them will be implemented in a manner consistent with the UNDP Social and Environmental Standards and shall ensure that any incidents or issues of non-compliance shall be reported to UNDP in accordance with UNDP Social and Environmental Standards.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud, corruption or other financial irregularities, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption other financial irregularities with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - Choose one of the three following options:

Option 1: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption, other financial irregularities or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Option 2: Each responsible party, subcontractor or sub-recipient agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud corruption or other financial irregularities or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

Option c. CSO/NGO/Non-UN or other IGO with no signed SBEAA with UNDP

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document and the Project Cooperation Agreement between UNDP and the Implementing Partner.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Sanctions Consolidated Sanctions  List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Sanctions Consolidated Sanctions  List  can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

- a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will, and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4, have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and such sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

b) The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP is committed to the highest ethical standards and will not tolerate the diversion of the resources entrusted to it through Money Laundering or Terrorist Financing and will not partner with entities that tolerate the diversion of resources through Money Laundering or Terrorist Financing. To that effect, the Implementing Partner represents and warrants that it has not, and it shall not, at any time in the implementation of the Project engage in Terrorism Financing or Money Laundering.  The Implementing Partner shall communicate the restriction of this paragraph to its and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Documents and shall take all reasonable measures to ensure that such persons do not engage in Terrorism Financing or Money Laundering.

- The Implementing Partner shall immediately disclose to UNDP any actual, apparent, potential or attempted Terrorism Financing or Money Laundering activity that it becomes aware of. The Implementing Partner shall fully cooperate with any investigation or review of Terrorism Financing or Money Laundering activity by UNDP.

- The Implementing Partner acknowledges and agrees that Terrorism Financing or Money Laundering constitute financial irregulates and that if the Implementing Partner or any of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document engages in Terrorism Financing or Money Laundering activity  that would constitute a material breach of this Project Document, which entitles UNDP to immediately terminate the Project without incurring any liability or penalty.

- Furthermore, the Implementing Partner expressly acknowledges and agrees that, in the event that UNDP were to determine through an investigation or otherwise that Terrorism Financing or Money Laundering occurred, UNDP shall have, in addition to its right to immediately terminate the Project, the rights to:

- apply and enforce the relevant sanctions in accordance with UNDP internal regulations, rules, procedures, practices, policies and guidelines, including referral of the matter to national authorities when appropriate; and

- recover all losses, financial or otherwise, suffered by UNDP in connection with such Terrorism Financing or Money Laundering activity.

- For the purpose of this Project Document the following terms shall have the definition ascribed to the below:

- “Money Laundering” is generally considered as concealment of the origins of money obtained illegally, typically by passing it through a complex sequence of financial or commercial transactions. ML usually involves three stages: (i) introducing the proceeds of crime into the financial system (placement); (ii) transactions to convert or transfer the funds to other locations or financial institutions (layering); and (iii) reintroducing the funds into the legitimate economy as "clean" money and investing it in various assets or business ventures (reintegration) appearing to have been legally obtained. The FATF recommends that ML be criminalized by every country on the basis of article 3(1)(b) and (c) of the Vienna Convention and article 6(1) of the Palermo Convention.

- “Terrorist Financing” means providing support to individuals or entities that appear on the United Nations Security Council Consolidated Sanctions List accessible at https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using the UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP programmes and projects in accordance with UNDP regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors‘ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The Implementing Partner will promptly inform UNDP in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption or other financial irregularity with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption or other financial irregularity, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- Choose one of the three following options:

Option 1: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud,  corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

Option 2: The Implementing Partner agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud. corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with the Implementing Partner, responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management Standard Clauses” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

Option d. UN Agency other than UNDP, and IGO with signed SBEAA with UNDP

- [Name of UN Agency/IGO] as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- In the implementation of the activities under this Project Document, [Name of UN Agency/IGO] as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures. The Implementing Partner will ensure that its regulations, rules, policies and procedures are consistent with the principles of UNDP relating to SEA and SH requirements. Notwithstanding the foregoing, the [Name of UN Agency/IGO], as the Implementing Partner, will notify UNDP of any such allegations and investigations it may conduct further to such allegations.

- [Name of UN Agency/IGO] as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor and sub-recipient that is not a UN entity:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of [Name of UN Agency/IGO]’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - [Name of UN Agency/IGO]  reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - In the performance of the activities under this Project, [Name of UN Agency/IGO] as the Implementing Partner shall ensure, with respect to the activities of any of its responsible parties, sub-recipients and other entities engaged under the Project, either as contractors or subcontractors, their personnel and any individuals performing services for them, that those entities have in place adequate and proper procedures, processes and policies to prevent and/or handle SEA and SH.

- [Name of UN Agency/IGO] agrees to undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Sanctions Consolidated Sanctions  List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Sanctions Consolidated Sanctions  List  can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm ).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- In the implementation of the activities under this Project Document, [Name of UN Agency/IGO] as the Implementing Partner will ensure that its regulations, rules, policies and procedures are consistent with the principles of then in force UNDP’s Anti-Money Laundering and Countering the Financing of Terrorism Policy.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud, or corruption, by its officials, consultants, responsible parties, subcontractors, and sub-recipients in implementing the project or programme or using the UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- [This text should be included when the Implementing Partner is a non-UN IGO: The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.]

- [This text should be included when the Implementing Partner is a non-UN IGO: In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects or programmes. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors‘ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.]

- The Implementing Partner and UNDP will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption or other financial irregularity, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- Choose one of the three following options:

Option 1: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

Option 2: The Implementing Partner agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management Standard Clauses” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

Special Clauses. In case of government cost-sharing through the project, the following clauses should be included:

- The schedule of payments and UNDP bank account details.

- The value of the payment, if made in a currency other than United States dollars, shall be determined by applying the United Nations operational rate of exchange in effect on the date of payment.  Should there be a change in the United Nations operational rate of exchange prior to the full utilization by the UNDP of the payment, the value of the balance of funds still held at that time will be adjusted accordingly.  If, in such a case, a loss in the value of the balance of funds is recorded, UNDP shall inform the Government with a view to determining whether any further financing could be provided by the Government.  Should such further financing not be available, the assistance to be provided to the project may be reduced, suspended or terminated by UNDP.

- The above schedule of payments takes into account the requirement that the payments shall be made in advance of the implementation of planned activities.  It may be amended to be consistent with the progress of project delivery.

- UNDP shall receive and administer the payment in accordance with the regulations, rules and directives of UNDP.

- All financial accounts and statements shall be expressed in United States dollars.

- If unforeseen increases in expenditures or commitments are expected or realized (whether owing to inflationary factors, fluctuation in exchange rates or unforeseen contingencies), UNDP shall submit to the government on a timely basis a supplementary estimate showing the further financing that will be necessary. The Government shall use its best endeavours to obtain the additional funds required.

- If the payments referred above are not received in accordance with the payment schedule, or if the additional financing required in accordance with paragraph 6 above is not forthcoming from the Government or other sources, the assistance to be provided to the project under this Agreement may be reduced, suspended or terminated by UNDP.

- Any interest income attributable to the contribution shall be credited to UNDP Account and shall be utilized in accordance with established UNDP procedures.

In accordance with the decisions and directives of UNDP's Executive Board:

The contribution shall be charged:

- […%] cost recovery for the provision of general management support (GMS) by UNDP headquarters and country offices

- Direct cost for implementation support services (ISS) provided by UNDP and/or an executing entity/implementing partner.

- Ownership of equipment, supplies and other properties financed from the contribution shall vest in UNDP.  Matters relating to the transfer of ownership by UNDP shall be determined in accordance with the relevant policies and procedures of UNDP.

- The contribution shall be subject exclusively to the internal and external auditing procedures provided for in the financial regulations, rules and directives of UNDP.”

# ANNEXES

- Project Quality Assurance Report

- Social and Environmental Screening Template [English] [French] [Spanish], including additional Social and Environmental Assessments or Management Plans as relevant. (NOTE: The SES Screening is not required for projects in which UNDP is Administrative Agent only and/or projects comprised solely of reports, coordination of events, trainings, workshops, meetings, conferences, preparation of communication materials, strengthening capacities of partners to participate in international negotiations and conferences, partnership coordination and management of networks, or global/regional projects with no country level activities).

- Risk Analysis. Use the standard Risk Register template. Please refer to the Deliverable Description of the Risk Register for instructions

- Capacity Assessment: Results of capacity assessments of Implementing Partner (including Partner Capacity Assessment Tool (PCAT) and HACT Micro Assessment)

- Project Board Terms of Reference and TORs of key management positions. The standard Project Board TOR can be found here.

- On-Granting Provisions Applicable to the Implementing Partner. On-granting clauses for non-UNDP Implementing Partners can be found here.

The Gender Marker measures how much a project invests in gender equality and women’s empowerment. Select one for each output: GEN3 (Gender equality as a principle objective); GEN2 (Gender equality as a significant objective); GEN1 (Limited contribution to gender equality); GEN0 (No contribution to gender quality)

Note: Adjust signatures as needed

https://www.postcourier.com.pg/solar-cocoa-dryer-to-cut-cost-enhance-production/

https://www.abtglobal.com/insights/impact-briefs/2025/smoke-free-cocoa-opens-premium-export-opportunities-for-png

Assuming 60 subsidence and business oriented farmers with a household size of 5 people on average (300 people), and 180 farmers with an household size of 5 people on average (900 people) benefiting from the investment in the centralized processing plants.

Assuming the investment of Table 1 (245 t an annual drying capacity supported under this project) and current sales prices of 1 PGK/kg which will increase to 1.5 PGK/kg as a result of quality increase

20% of annual cocoa production of project beneficiaries (245 t/yr).

Assuming a reduction of 2.5t in firewood use per ton of cocoa produced

Please see the Guideline “Embedding Digital in Project Design”.

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards.  Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.

Optional, if needed

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a project budget affecting the scope (outputs), completion date, or total estimated project costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner

Use bracketed text only when IP is an NGO/IGO

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner

Applicable for non-UNDP Implementing Partner as Grant Making Institution facilitating on-granting.