Project Title: Challenging Harmful Attitudes and Norms for Gender Equality (CHANGE)

Project Number:  01005597

Implementing Partner: UNDP

Start Date: 2026			End Date: 2028		PAC Meeting date: 	18.02.2026

Brief Description

In Central Asia, gender inequality remains deeply entrenched, with all five countries lagging on the Global Gender Gap Index and showing persistent disparities in women’s political representation, economic participation, and access to resources and opportunities. Against this backdrop, the 2026–2028 Multi-Country Programme (MCP) will apply a holistic, gender-transformative approach to address root causes of GBV and systemic gender inequality in all five Central Asian countries. UNDP component contributes to Outcome 3 across five Central Asian countries – Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan and Uzbekistan. It addresses the structural economic inequalities that increase women’s vulnerability to gender-based violence (GBV), including limited access to decent work, unequal labour market participation, and the disproportionate burden of unpaid care work. Through a regional approach led by UNDP Kazakhstan, the project will strengthen evidence-based policymaking and expand women’s economic opportunities. It will support gender-responsive data collection and analysis to inform policies addressing women’s economic vulnerabilities, while promoting women’s access to employment, entrepreneurship and sustainable livelihoods through partnerships with governments, civil society, academia and the private sector.

| Contributing Outcome (CPD): UNDP Kazakhstan - STRATEGIC OUTCOME 2: By 2029, governance systems are more effective, inclusive, and accountable, enabling people, societies and economies to thrive. UNDP Kyrgyzstan – STRATEGIC OUTCOME 4: By 2027, all people in the Kyrgyz Republic enjoy the benefits of fair and accountable democratic institutions that are free from corruption and apply innovative solutions that promote respect for human rights and strengthen peace and cohesion. UNDP Tajikistan – STRATEGIC OUTCOME 2: Sustainable, inclusive and green economic growth. By 2026, public institutions and the private sector collaborate to implement innovative and gender-responsive policy frameworks and actions to green the economy and strengthen inclusion of vulnerable groups inclusive, accessible, high-quality and future-ready learning, skills and diverse income opportunities. UNDP Turkmenistan – STRATEGIC OUTCOME 2: By 2030, Turkmenistan will have improved conditions and opportunities for inclusive and sustainable economic diversification and growth. UNDP Uzbekistan – STRATEGIC OUTCOME 2: By 2030, all people in Uzbekistan achieve an adequate standard of living and have resilience to socio-economic and climate-related shocks through decent work, an effective social protection system and inclusive, innovative, and sustainable economic growth. Indicative Output(s) with gender marker: Output 3.1. Data collection and analysis inform policies and legislation addressing women's vulnerabilities Output 3.2. Enhanced access to employment and income generation opportunities for women Gender Marker: GEN 3 |  | Total resources required: | $2,417,612 |  |
| --- | --- | --- | --- | --- |
|  |  | Total resources allocated: | Donor: | $2,417,612 |
|  |  |  | Government: | n/a |
|  |  |  | UNDP: | $239,305 |
|  |  | Unfunded: | n/a |  |

Agreed by UNDP:

Mr. Sukhrob Khojimatov UNDP Kazakhstan Resident Representative a.i.

# Development Challenge

Despite some progress, countries in Central Asia continue to grapple with deep-seated gender inequalities, making gender-based violence (GBV) one of the most pressing and persistent development challenges. All five countries in the region face structural and systemic barriers to achieving gender equality, which is reflected in their rankings in the 2025 Global Gender Gap Index: Tajikistan (129th), Uzbekistan (110th), Kyrgyzstan (95th), Kazakhstan (92nd), with Turkmenistan lacking comprehensive data but showing comparable disparities.

Across the region, women are underrepresented in decision-making, carry the bulk of unpaid care and domestic work, and face persistent gender wage gaps and limited access to resources and economic opportunities. The COVID-19 pandemic has deepened existing gender inequalities. Also, in several regions, movements opposing gender equality and human rights have gained traction, leading to setbacks in the advancement of women's rights. Compounding these challenges is a human development crisis in Central Asia, marked by the unprecedented decline in HDI values in 2020 and 2021, followed by only partial recovery by 2025, with most countries yet to return to their pre-pandemic trajectories (UNDP, 2025). Against this backdrop, progress toward SDG 5 in Central Asia remains uneven and limited, with only a few countries meeting half of the gender equality targets (UN, 2025).

GBV in Central Asia remains both a cause and consequence of inequality. The Spotlight Initiative's transformative strategy recognised violence against women and girls (VAWG) as a systemic issue, targeting both root causes and intersecting issues,. It is sustained by discriminatory norms, unequal power dynamics, and structural inequalities. Harmful traditions, such as early and forced marriages and bride kidnapping, further entrench women’s exclusion. The normalisation of violence, insufficient legal protections, and lack of access to services exacerbate vulnerability, especially among rural women, ethnic minorities, and women with disabilities. Consequently, while digital tools offer innovative pathways for preventing and responding to GBV and supporting survivors, the rise of online gender-based violence underscores their double-edged nature.

According to the UN data, 1 in 3 women and girls in Central Asia have experienced violence at some point in their lives. GBV take various forms, including domestic and psychological violence, sexual harassment, economic exploitation. Many disturbing incidents of violence against women occur in their homes, perpetrated by intimate partners, highlighting a significant regional issue. Official statistics reveal alarming trends. Kazakhstan reported a tripling of domestic violence (DV) complaints over five years, reaching in 2023 some 100,000 domestic violence cases officially registered. In Tajikistan in the first half of 2023 alone, the Committee on Women and Family Affairs under the Government received 1,075 complaints. In Uzbekistan, in 2023, a total of 40,055 cases of violence and harassment against women identified and 39,263 women were issued with protection orders. In Kyrgyzstan, repeatedly rated as the most dangerous for women in Central Asia, at year-end 2023, the number of registered victims of domestic violence amounted to 13,104 people, of which at least 95 percent are women. In Turkmenistan existing evidence shows that 12% of women aged 18-59 have been subjected to physical and/or sexual violence by a spouse or partner. However, the true extent remains unknown due to underreporting, social stigma, and weak enforcement mechanisms. At the same time, high-profile cases of femicide and assault have recently heightened public awareness, igniting calls for urgent reforms, yet systemic barriers persist.

Civil society organisations and women’s rights groups remain important actors in advancing gender equality and combating GBV, often filling critical service and advocacy gaps. However, their operational space is shrinking due to restrictive legislation, funding constraints, and political pressure, threatening the continuity and expansion of their work. In Kyrgyzstan, the adoption of a law targeting foreign-funded CSOs restricts their operations, while in Tajikistan, the closure of over 700 CSOs, many focused on human rights and gender equality, raises concerns. Repression against civil society, especially those advocating for women's rights, exacerbate the challenges for activism in the region. The increasing hostility towards CSOs limits innovation, outreach, and the scaling of effective interventions.

While national governments in Central Asia have enacted laws and policies aligned with international standards to address gender equality and GBV, enforcement remains weak and uneven. Institutional coordination is often fragmented, and national data collection systems are insufficiently developed to track progress comprehensively or inform policy effectively.

Kazakhstan has made legislative progress against GBV, including empowering law enforcement to intervene in domestic violence cases without a survivor’s statement (2023) and criminalising domestic abuse (2024). However, further efforts are needed to ensure the effective implementation of the latter law to protect survivors and hold perpetrators accountable. Women remain underrepresented politically, holding 18.4% of parliamentary seats in 2024 and less than 12% of executive roles. Women’s labor force participation is 66% compared to 75.9% for men, with a gender pay gap around 25–30%. GBV remains pervasive: 17% of women report partner violence, and about 80 women are killed annually by intimate partners. Domestic violence reports average 300 daily but are widely underreported. Deep-seated gender biases persist, with 93.23% of the population holding prejudiced views, including acceptance of violence and male dominance in leadership. Women disproportionately shoulder unpaid domestic and care work - 19.9% of their time versus 6.3% for men, worsening economic inequality and affecting vulnerable single-parent families.

Kyrgyzstan has made legal progress on GBV with updates to its Domestic Violence Law, Criminal Codes, and ratification of ILO Convention No. 190. The 2024 law strengthens protections for women and children, but gaps remain in alignment with international standards and enforcement, especially regarding harmful practices like underage and forced marriages. Domestic violence cases rose 37% in 2024, and practices like bride kidnapping affect over 20% of marriages. Gender bias is widespread, with 98.2% holding discriminatory views and high tolerance for spousal violence. Women’s labor participation is 53% versus 78.6% for men, limited by caregiving burdens and reinforced by religious extremism. Despite an active civil society, restrictive laws and funding shortages hinder progress. Women hold 22.2% of parliamentary seats and 14.3% of cabinet positions but remain underrepresented in senior public roles.

Tajikistan’s National Programme (2025–2030) and a Multisectoral Council coordinate efforts to eliminate domestic violence, but key legal gaps remain, including the pending criminalisation of domestic violence and weak protections against workplace harassment. The 2022 Law on Equality faces low public awareness and needs amendments. Civil society actively advocates despite funding and staffing challenges. Women hold 28.6% of parliamentary seats and 13.6% of ministerial positions, with low workforce participation (31.8%) and a significant gender pay gap. Domestic violence affects 30–50% of women, with early marriage at 14.3%.

Turkmenistan’s National Action Plans on Gender Equality (2015–2025) emphasise addressing GBV, legislative reform, and women’s rights, but key gaps persist. The legal framework lacks explicit definitions of gender discrimination and GBV, and sectoral GBV standards remain unapproved due to missing legislation. Data availability on gender indicators is limited, with only 20.6% of necessary SDG gender metrics reported. Surveys reveal that 12% of women aged 18–59 experience partner violence, and 58.4% justify violence against women based on traditional gender roles. Women hold 25.6% of parliamentary seats and 22.2% of ministerial roles, but no gender quotas exist. Women’s labour force participation (48.7%) slightly exceeds men’s (46.5%), and community safety perceptions are high. Maternal mortality has improved, yet challenges remain, including low financial inclusion (35.5%), poor access to justice, low female schooling (10.9 years), and high adolescent birth rates.

Uzbekistan’s 2019 Law on Guarantees of Equal Rights addresses gender discrimination, supported by a 2030 Gender Equality Strategy, though final approval of sectoral SOPs and cross-sector coordination remain incomplete. Amendments in 2023-2024 established criminal liability for domestic violence and strengthened protections for women and children, resulting in nearly 16,000 offenders sentenced in early 2024 - a 50% increase. However, challenges persist, including vague domestic violence definitions and pressures on victims within the justice system. Only 40.2% of gender-related SDG indicators are available, with gaps in violence prevention, unpaid care work, and labor market data. Women hold 38% of parliamentary seats after a 40% candidate quota was introduced in 2024. Despite labor reforms banning gender discrimination, women’s labor force participation is low (39.9% vs. 72.3% for men), and the gender pay gap stands at 34%.

While there is growing recognition of the need for gender-transformative approaches, implementation remains uneven and often symbolic. There is an urgent need for integrated, evidence-based, and gender-transformative approaches that address root causes, engage all societal actors, including men, boys, faith leaders, and youth, and foster regional cooperation to leverage shared learning and scale successful models.

# Strategy

Spanning from 2026 to 2028, this EU-funded programme is implemented collaboratively by UNDP, UNFPA, and UN Women across all five Central Asian countries. This initiative not only complements national efforts but also enhances cross-border cooperation, reflecting the EU’s value in promoting sustainable, inclusive development in a complex and diverse regional landscape.

The MCP approach is in line with the Gender Equality Action Plan (GAP) III for 2021-2027, reflecting the EU's commitment to advancing gender equality in its external actions and accelerating global efforts in line with international and SDG commitments. In addition, by prioritizing social norms change and gender equality, this programme also aligns closely with the objectives of the 2030 Agenda for Sustainable Development.

The intervention logic of the MCP is rooted in a comprehensive understanding of the multifaceted nature of GBV and the underlying structural inequalities that perpetuate it. As such, the programme aims to address the pervasive issue of GBV in Central Asia, which is perpetuated by systemic inequalities, power imbalances and discriminatory social and gender norms. These create an environment where violence against women is used by men and tolerated by society and where women are denied equal rights and opportunities.

The MCP is grounded in the understanding that GBV is a multidimensional issue rooted in unequal power relations, discriminatory social norms, and institutional limitations. Effectively addressing GBV requires a comprehensive, intersectional, and sustained approach. The proposed Theory of Change posits that by achieving three interrelated and mutually reinforcing outcomes, GBV can be sustainably reduced in Central Asia:

IF social norms increasingly reflect zero tolerance for gender-based violence...

Transforming harmful social norms that normalise, or excuse violence is essential. In Central Asia, entrenched gender roles and patriarchal beliefs contribute to the persistence of GBV, reinforced by stigma, silence, and impunity. Evidence from global and regional studies (e.g. UN Women, UNICEF, UNFPA) shows that targeted interventions, especially those engaging men and boys, can effectively shift attitudes and behaviours. For example:

- In Kyrgyzstan, school-based curricula and public awareness campaigns have led to measurable changes in attitudes toward bride kidnapping and domestic violence.

- In countries such as Georgia and Moldova, strong zero-tolerance campaigns combined with legal enforcement have increased awareness and reduced social acceptance of GBV, as shown in DHS and MICS data.

Fostering zero-tolerance norms also strengthens the enabling environment for the other two outcomes by mitigating backlash and increasing public and institutional support for reforms.

...AND civil society organisations more effectively prevent and respond to GBV through strengthened coordination, capacity, and advocacy...

CSOs play a central role in prevention, protection, service delivery, and policy change. However, in Central Asia, women’s rights organisations often face limited funding, shrinking civic space, and fragmentation. By building CSO capacity, promoting shared platforms (e.g. the Spotlight Virtual Platform), and enhancing coordination, the programme will:

- Amplify survivor voices and community engagement

- Improve service delivery and outreach

- Enhance advocacy and accountability mechanisms

Evidence from similar efforts (e.g. the Spotlight Initiative in other regions) confirms that well-coordinated civil society leads to more responsive policies and greater resilience in communities.

…AND women have increased economic empowerment and access to sustainable livelihoods...

Economic empowerment is both a pathway to reducing vulnerability and a driver of systemic change. Women with financial independence are more likely to leave abusive situations, access services, and engage in collective action. This is especially relevant in Central Asia, where many women:

- Have limited awareness of their rights

- Face institutional and cultural barriers to employment, including the disproportionate burden of unpaid care work and the lack of accessible, affordable, and quality care services

- Are at greater risk of GBV due to economic dependency

Evidence shows that when women gain economic autonomy, they also gain greater agency, safety, and influence in both household and community decisions.

THEN a more equitable and violence-free environment will be enabled, LEADING TO a reduction in GBV.

The diagram below provides an illustration of the Theory of Change:

This approach aligns with global best practices, including the Spotlight Initiative's global Theory of Change and the INSPIRE framework (WHO, UNICEF, UNODC), maximising the likelihood of sustainable GBV reduction across the region.

The ToC is underpinned by following key assumptions, validated by regional evaluations and stakeholder consultations:

- Sustained political will at national and sub-national levels to prioritise GBV prevention, allocate resources, and support reforms;

- Formal endorsement and alignment with national strategies, enabling programme ownership and sustainability;

- Stable security and political context to allow safe and consistent implementation;

- Active participation and leadership from CSOs and communities, particularly marginalised groups;

- Availability and use of disaggregated GBV data to inform, adapt, and monitor interventions;

- Adequate infrastructure and digital access to facilitate outreach and service delivery;

- Effective interagency coordination, enabling coherence, efficiency, and collective accountability;

- Cultural adaptability and local ownership to ensure interventions are relevant and accepted in diverse contexts.

Recent evaluations, including the UN Women Independent Evaluation Service’s Global Evaluation Report Oversight System (GEROS) Meta-Analysis (2017–2022) and the Spotlight Initiative (2020–2023) in Central Asia and Afghanistan, identify that the most effective gender equality and GBV interventions combine institutional capacity-building with targeted advocacy grounded in national policy commitments, sustained government engagement, survivor-centred service models, and robust multi-sectoral coordination. Community-driven prevention initiatives engaging men and boys, tailored to local social norms and delivered via evidence-based messaging and peer-led approaches, are critical. Best practices include institutionalising multi-sectoral coordination mechanisms, legal and policy reform supported by implementation capacity, and meaningful participation of CSOs, especially representing marginalised groups. Rigorous monitoring, disaggregated data collection, and feedback loops enhance programme adaptability and equity. Women’s economic empowerment and strengthening gender-responsive care systems are key strategies for GBV prevention.

Lessons from the Spotlight Initiative emphasise the importance of formal government endorsements (e.g., MenEngage and HeForShe campaigns in Kazakhstan and Kyrgyzstan), geographic inclusivity reaching underserved populations (notably in Tajikistan), strengthening NGO-state collaboration (notably in Uzbekistan), data-driven decision-making integrating GBV topics into national surveys (e.g., MICS in Turkmenistan and Kazakhstan), and addressing sustainability challenges in psychosocial services (notably in Kyrgyzstan). Additionally, the lack of national experts on positive masculinity was identified, with Kyrgyzstan developing a comprehensive engagement strategy. Best practices include the regional adaptation of the kNOwVAWdata online training to build capacity in GBV data analysis (Uzbekistan), the Spotlight Digital Challenge engaging youth with ICT-based SGBV solutions, youth-led organisation mobilization for peer engagement (Kyrgyzstan), large-scale MenEngage and HeForShe campaigns reaching millions (Kazakhstan), intersectional research involving CSOs on marginalised groups (Tajikistan), and effective offline networking complementing digital efforts (Kyrgyzstan). These lessons and practices, consolidated through consultations among UN agencies and key stakeholders, inform the design of the current Multi-Country Programme to reflect evolving needs and priorities.

# Results and Partnerships

Guided by the Theory of Change and strategic approach, the MCP will deliver transformative, measurable change in gender equality and GBV prevention across Central Asia. To achieve this, the programme engages a wide spectrum of target groups, each playing an important and complementary role in advancing gender equality and preventing GBV, specifically:

- Women and girls are the primary beneficiaries, also empowered as active agents of change leading advocacy, shaping solutions, and contributing to gender equality.

- Men and boys will play a critical role in challenging harmful gender norms through education and mentorship.

- Adolescents and youth will be extensively engaged, receiving life skills education, peer support, and targeted programmes promoting positive masculinity and violence prevention, with special focus on marginalised groups.

- Public authorities at all levels, including parliament, central and local government, and Child Rights Ombudspersons will be a key stakeholder with a role in legislating, implementing policies, allocating resources, coordinating services, and ensuring accountability to create an environment that prevents GBV, supports survivors, and advances gender equality.

- Mass media and influencers will shape societal attitudes by promoting accurate information, raising awareness, combating misinformation, destigmatizing survivors, and encouraging victims to seek support and justice.

- CSOs and WROs will be engaged through capacity-building, data strengthening, advocacy support, and efforts to overcome pushback, enabling them to deliver services and influence policy effectively.

- Faith-based Organisations will be engaged via collaboration on education, advocacy, and community outreach aligned with government frameworks, ensuring inclusive and context-sensitive participation.

- Service providers will receive specialised training and support to enhance survivor-centered care and coordinate holistic services across traditional and digital platforms.

- Private sector will be involved through promotion of family-friendly policies, CSR initiatives, and providing paid apprenticeships to empower women economically.

- Academia and research will be engaged by collaborating on data sharing, producing evidence-based research, and informing effective GBV interventions and policies.

The programme’s strategy will be translated into interventions that are both context-specific and evidence-based, targeting structural barriers to gender equality and engaging all target groups. Stakeholders’ engagement will integrate capacity-building, advocacy, multi-stakeholder dialogue, and policy support, each carefully adapted to the roles, needs, and influence of different stakeholder groups.

The Overall Objective (Impact) of the MCP is to contribute to the reduction of GBV across Central Asia, aligned with SDG 5 and, specifically, Target 5.2 on eliminating all forms of violence against women and girls. While this long-term goal provides a clear strategic direction, it is important to recognise that reduction in GBV prevalence is influenced by a complex interplay of structural, behavioural, and systemic factors that extend beyond the direct scope and timeframe of the programme. Consequently, observable changes in GBV prevalence may not be immediately measurable or directly attributable to programme interventions within the three-year implementation period. Moreover, the limited availability of recent, comparable, and regularly updated data across the region, particularly for SDG Indicator 5.2.1: Percentage of women and girls aged 15-49 who have experienced physical and/or sexual violence by a current or former intimate partner in the previous 12 months, presents challenges for setting specific, time-bound targets related to GBV reduction at this stage. To address these limitations, the programme has set a directional impact target to contribute to a reduction in reported rates of GBV, using various proxy indicators where data is available, while simultaneously strengthening national systems for data collection, measurement, and response mechanisms.

To achieve this overarching aim, the programme pursues three interlinked Specific Objectives (Outcomes) that together address the structural, behavioural, and institutional drivers of gender-based violence. These objectives reflect a comprehensive approach rooted in prevention, empowerment, and systems strengthening and are the following:

- Social norms increasingly reflect zero tolerance for GBV

- Civil society organisations more effectively prevent and respond to GBV through strengthened coordination, capacity, and advocacy

- Women have increased economic empowerment and access to sustainable livelihoods

Each of the specific objectives is operationalised through a set of strategically defined eight Outputs and corresponding activities. These are designed to translate the programme’s vision into measurable results, ensuring coherence between the overarching impact and the interventions at national and regional levels. The outputs serve as the building blocks of change, addressing normative, institutional, and individual dimensions of GBV prevention and response, while the activities reflect context-specific approaches tailored to the diverse realities across the five Central Asian countries.

Output 3.1. Data collection and analysis inform policies and legislation addressing women's vulnerabilities

Output 3.1 strengthens data collection and analysis to inform policies and legislation addressing women’s vulnerabilities across Central Asia. Activity 3.1.1 conducts a national assessment in Kazakhstan to develop a detailed social portrait of women from vulnerable groups, informing targeted interventions and evidence-based policymaking. Activity 3.1.2 focuses on unpaid care work in Kazakhstan, Kyrgyzstan, Turkmenistan, and Uzbekistan through policy and legislative analysis, stakeholder workshops, and the development of training and certification programmes for domestic workers in Kazakhstan and Uzbekistan alongside awareness-raising efforts targeting both workers and employers to promote formal employment. Activity 3.1.3 supports Kazakhstan and Kyrgyzstan in implementing ILO Convention 190 by reviewing policies, building institutional capacities, raising awareness, and establishing monitoring and enforcement mechanisms to prevent workplace violence and harassment. Activity 3.1.4 enhances digital tools and data systems in Kazakhstan, Turkmenistan, and Uzbekistan, including a domestic employment contracts registration module and a gender-disaggregated digital dashboard to improve visibility and protection for women in the informal economy. Activity 3.1.5 conducts a gender-sensitive labour market needs assessment in Turkmenistan to identify barriers and opportunities for women’s workforce participation, guiding the development of responsive employment policies and programmes.

Output 3.2. Enhanced access to employment and income generation opportunities for women

Output 3.2 enhances women’s access to employment and income generation opportunities across Central Asia through comprehensive support to CSOs and women entrepreneurs. Activity 3.2.1 provides grants, capacity-building, and mentorship to CSOs in Kazakhstan, Turkmenistan and Uzbekistan to establish or expand sustainable economic empowerment centres, prioritizing existing institutional platforms to reduce startup costs and focusing on entrepreneurship in creative industries. Activity 3.2.2 supports the design, implementation, and promotion of paid apprenticeship programmes in Kazakhstan and Turkmenistan through partnerships with local businesses, academic institutions, NGOs, and municipalities, formalized by Memoranda of Understanding; it ensures a transparent selection process and ongoing mentorship to equip women with practical skills and work experience. Activity 3.2.3 promotes gender-responsive vocational education and training (TVET) in Kyrgyzstan by addressing structural barriers, including legal restrictions on women’s employment, and integrating gender-sensitive curricula to increase women’s participation in non-traditional, high-growth, and emerging sectors. Activity 3.2.4 targets economic empowerment of women in three regions of Tajikistan by providing orientation training, mentorship by experienced entrepreneurs, capacity building, technical assistance, and support for business plan development and implementation, including components on financial literacy and psychological health to foster sustainable income generation.

Achieving the MCP’s results depends on the strategic coordination and mobilisation of human, financial, technological, and institutional resources across various sectors and governance levels. This entails harnessing the expertise of participating UN agencies, government institutions, civil society, and other actors to deliver complementary and efficient support. Financial resources will be directed to priority interventions while ensuring sustainability and grassroots reach. Technological investments will facilitate data-driven decision-making, service delivery, and regional collaboration. Digital technologies will be integral to all programme components, enabling broader reach and active participation. Institutional engagement will promote policy alignment, capacity strengthening, and effective governance. The MCP’s; results will be monitored through a robust framework capturing both quantitative and qualitative indicators, disaggregated by age, gender, disability, and geography.

The programme will produce a range of knowledge products including comprehensive policy reports (e.g., social portrait of vulnerable women in Kazakhstan, unpaid care work policy recommendations across multiple countries), specialised training curricula and manuals for faith-based organisations, educators, CSOs, youth, and men on gender equality, GBV prevention, positive masculinities, and survivor-centred approaches; digital platforms and tools such as online learning portals, data dashboards, and domestic employment registration modules; labour market gender assessments (e.g., in Turkmenistan); advocacy materials including storybooks and media campaign toolkits; and frameworks supporting CSO capacity-building, economic empowerment centres, apprenticeship programs, and mentorship initiatives. These products aim to strengthen evidence-based policy, enhance capacities, facilitate regional knowledge sharing, and support sustainable, inclusive GBV prevention and gender equality efforts across Central Asia. These resources will be widely disseminated through the Spotlight Virtual Knowledge Platform, regional forums, and national channels to ensure effective uptake by governments, civil society organisations, and development partners.

The MCP adopts a proactive and structured approach to risk assessment and mitigation in line with EU standards, recognising that achieving transformative results in addressing GBV in Central Asia requires navigating a complex and often volatile environment. The programme prioritises early identification and continuous monitoring of risks throughout implementation, coupled with adaptive management strategies to ensure responsiveness to emerging threats. A strong emphasis is placed on community consultations, stakeholder coordination, and capacity development as integral components of risk mitigation, with special attention to the protection of women's rights actors and ensuring the programme's operational continuity and integrity. The MCP risks and mitigation measure include the following:

- Resistance from individuals and state bodies with traditional gender norms; addressed through targeted community consultations and identifying institutional change agents.

- Limited buy-in from government officials and community leaders; mitigated by early, ongoing stakeholder engagement aligned with national priorities.

- Pushback and harassment of women’s rights organisations; managed by enhancing legal protections, building alliances, and diversifying funding sources.

- Difficulty accessing marginalized or remote communities; overcome through mobile outreach and partnerships with trusted local organisations.

- Political instability and shifting government priorities; handled via adaptable programming and multi-stakeholder governance for continuity.

- Staff turnover and shortage of qualified personnel; reduced by investing in training, knowledge management, and competitive retention strategies.

- Misinterpretation or misrepresentation of programme goals; prevented through clear, transparent, and context-sensitive communication.

The programme’s design ensures both sustainability and scaling up by fostering local ownership, embedding gender equality and GBV prevention within cultural, institutional, and policy frameworks across Central Asia. Sustainability is promoted through capacity-building of community and faith-based leaders, youth empowerment, engagement of men and boys as key partners, and strengthening civil society organisations to continue advocacy and service delivery independently. Economic empowerment initiatives and digital tools are structured for long-term operation beyond external funding. Simultaneously, the programme facilitates scaling up by promoting regional cooperation and knowledge sharing through sub-regional learning forums, virtual exchanges, and cross-country advocacy campaigns, enabling replication and adaptation of best practices. Policy integration efforts support institutionalization at national and regional levels, while phased exit strategies and stakeholder consultations guide the responsible transition of roles and resources.

The MCP is designed to complement existing regional and national initiatives addressing GBV and women’s empowerment in Central Asia, funded by the EU and other donors, to enhance coherence, avoid duplication, and maximise impact. It will align with ongoing EU programmes under the 2021–2027 Multiannual Indicative Programme and the EU-Central Asia Joint Roadmap to enhance regional cooperation on gender and governance. The programme will coordinate with UNFPA’s UK-funded GBV prevention project to improve multi-sectoral responses and emergency systems. It will complement the EU Civil Society Facility by boosting civil society capacity and youth engagement across the region. At the country level, MCP will reinforce national efforts including UN Women’s GBV prevention grants in Kazakhstan, the “Action Now” project in Kyrgyzstan, judicial capacity building in Tajikistan, and youth and media projects in Uzbekistan. Collaboration with the Central Asian Alliance to End GBV will amplify advocacy and knowledge exchange. MCP will also synchronize with the forthcoming UN Sustainable Development Cooperation Framework (UNSDCF) 2026-2030 to ensure integrated, sustainable impact across sectors and borders.

The MCP aims to promote South-South and Triangular Cooperation by facilitating regional learning exchanges and policy dialogues among Central Asian countries to share experiences on GBV prevention and gender equality. It will also seek opportunities to exchange best practices with neighbouring regions such as Eastern Europe, South Caucasus, and South Asia. Additionally, the programme plans to engage with global platforms like MenEngage and the EU Gender Platform to increase the visibility of regional efforts and foster broader collaboration. These activities are intended to enhance knowledge sharing, regional solidarity, and the potential for scaling up effective approaches.

# Project Management

The MCP will be implemented in all five Central Asian countries – Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan, and Uzbekistan. Implementation will follow a decentralised but coordinated structure, with clear lines of responsibility, consistent with the pass-through fund management modality administered by the UNDP Multi-Partner Trust Fund Office (MPTFO) as the Administrative Agent. UNDP Kazakhstan will act as both the Participating UN Organisation (PUNO) and Convening Agent (CA) for the MCP, with key regional staff, including a full-time Regional Task Force Coordinator. The Steering Committee, co-chaired by a national government representative and a UN Country Team member, will provide strategic oversight, ensuring alignment with national priorities, UN mandates, and EU expectations. The EU Delegation Coordination Team, comprising representatives from all participating countries, will collaborate closely with UNDP country offices to ensure alignment with EU priorities, support visibility, and monitor progress throughout implementation.

Country-level implementation will be led by the respective UNDP Country Offices, each with dedicated staff for coordination and management, supported by regular inter-agency meetings to align activities and share progress. UNFPA’s regional oversight will be managed from its Central Asia Sub-Regional Office in Almaty, with country offices supported by gender focal points and consultancies. UN Women will assign regional and country-level teams responsible for managing and coordinating interventions, with focal points in each country for reporting and oversight. UNDP, UNFPA, and UN Women will hold regular coordination meetings at country and regional levels, ensuring coherence, synchronisation of activities, and consistent engagement with stakeholders.

The MCP is structured to maximise results through a regionally integrated, evidence-informed, and partnership-driven approach. Drawing on the Theory of Change, the programme was deliberately designed to achieve maximum impact with available resources by leveraging the comparative advantages of each UN agency and fostering complementarities across country contexts.

Overall, the MCP’s design integrates a decentralised but coordinated implementation model, sound financial stewardship, rigorous Monitoring, Evaluation and Reporting (MER) systems, and strategic communication to maximise cost-efficiency, foster transparency, and enhance accountability. This approach ensures the programme delivers coherent, impactful, and sustainable results across Central Asia, reinforcing regional cooperation and advancing the prevention and response to gender-based violence in line with EU priorities. Key elements that underpin its cost-efficiency include:

- Strategic Division of Labour Across Agencies. Each PUNO - UNDP, UNFPA, and UN Women, implements outputs aligned with its mandate and comparative advantage. This allows for specialisation and operational efficiency, reducing duplication and ensuring the most capable agency leads each component.

- Joint Planning and Coordination. Through the UNDP-led Regional Task Force and Steering Committee, the programme ensures strategic oversight and harmonisation of operations. Regular joint planning meetings enable adaptive management, shared resource planning, and operational synergies across the region.

- Leveraging Existing Structures and Initiatives. Where possible, the MCP builds on existing national systems, programme platforms, and institutional partnerships (e.g., MenEngage networks, Creative Industry Centres, and EU-UN projects), which ensures sustainability and cost avoidance in establishing parallel systems.

- Joint Operations and Learning. Coordination across UN agencies and programmes – including joint monitoring, procurement synergies, co-hosted learning events, and shared platforms such as the Spotlight Virtual Knowledge Platform – drives efficiency while fostering mutual accountability and learning.

- Strategic Resource Allocation. The budget distribution across countries was determined using a catalytic approach, prioritising strategic use of funds to amplify existing initiatives and institutional capacities rather than allocating resources strictly based on demographic size.

- Scalable Regional Model. The MCP's regional design enables cost-effective cross-border knowledge exchange, peer learning, and standardised tools (e.g., manuals, digital content, capacity-building resources), which can be replicated across contexts without additional development costs.

This structure is informed by lessons from previous regional initiatives, including the EU-UN Spotlight Initiative in Central Asia, which demonstrates the value of integrated multi-country models in leveraging economies of scale, reducing transaction costs, and enhancing coherence across donors and partners.

# Results Framework

Project title and Quantum Project Number: Challenging Harmful Attitudes and Norms for Gender Equality (CHANGE) Quantum Project Number: 01005597

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  |  | ## TARGETS (by frequency of data collection) |  |  |  | ## Data collection method and Risks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Country | Value | Year | Year 1 (2026) | Year 2 (2027) | Year 3 (2028) | ## FINAL |  |
| Outcome 3. Women have increased economic empowerment and access to sustainable livelihoods | % of women reporting enhanced economic independence and empowerment | Baseline and endline survey | Kazakhstan | 0 | 2026 | Baseline established | n/a | Endline survey | At least 60% of women report enhanced economic independence by the end of the program | Data collection method: Baseline survey (2026, Q2) and endline survey (2028, Q4) per country. Survey instruments to be harmonised across COs by regional M&E. Risk: Inconsistent interpretation of "enhanced economic independence and empowerment" across countries; weak baseline/endline comparability if survey tools differ; small or biased samples; risk of incorrectly aggregating country results. |
|  |  |  | Kyrgyzstan |  | 2026 | Baseline established | n/a | Endline survey |  |  |
|  |  |  | Tajikistan |  | 2026 | Baseline established | n/a | Endline survey |  |  |
|  |  |  | Turkmenistan |  | 2026 | Baseline established | n/a | Endline survey |  |  |
|  |  |  | Uzbekistan |  | 2026 | Baseline established | n/a | Endline survey |  |  |
| 3.1. Data collection and analysis inform policies and legislation addressing women's vulnerabilities | Number of policy recommendations on unpaid care work developed and formally submitted to government stakeholders | Documentation of policy recommendations, formal submission records, meeting minutes | Kazakhstan | 0 | 2025 | 1 recommendation drafted | 1 recommendation submitted | 1 recommendation formally adopted or under review | At least 1 new policy recommendation per country formally submitted to government by programme end | Data collection method: Review of submission records, meeting minutes and government acknowledgement letters. Risk: Policy processes may stall; recommendations submitted but not formally acknowledged by government. |
|  |  |  | Kyrgyzstan | 0 | 2025 | 1 recommendation drafted | 1 recommendation submitted | 1 recommendation formally adopted or under review |  |  |
|  |  |  | Turkmenistan | 0 | 2025 | 1 recommendation drafted | 1 recommendation submitted | 1 recommendation formally adopted or under review |  |  |
|  |  |  | Uzbekistan | 0 | 2025 | 1 recommendation drafted | 1 recommendation submitted | 1 recommendation formally adopted or under review |  |  |
|  | Number of legal or regulatory documents developed, formally submitted and adopted by government stakeholders to improve the protection and formalisation of labour standards - including domestic work and violence- and harassment-free workplaces | Official records of legal and regulatory documents, meeting minutes, and endorsements from relevant government bodies | Kazakhstan | 0 | 2025 | 1–2 documents in development | 2–3 documents submitted | 4 documents submitted and at least 2 adopted | At least four new per country | Data collection method: Legal document tracking log maintained by CO. Risk: Legislative processes are slow and may extend beyond the programme period; political priorities may shift. |
|  |  |  | Kyrgyzstan | 0 | 2025 | 1–2 documents in development | 2–3 documents submitted | 4 documents submitted and at least 2 adopted |  |  |
|  |  |  | Uzbekistan | 0 | 2025 | 1–2 documents in development | 2–3 documents submitted | 4 documents submitted and at least 2 adopted |  |  |
|  | Number of awareness-raising products to inform domestic workers and their employers about legislative changes, certification programmes and the benefits of formal delivered employment | Reports on the development and distribution of awareness-raising products, including copies of materials (brochures, posters, etc.) and distribution logs | Kazakhstan | 0 | 2025 | 0 | 2–3 products developed and distributed | 4 products developed and widely distributed | At least four new per country by the end of programme | Data collection method: CO maintains a product inventory with distribution logs. Risk: Reach and uptake of products may be limited; quality of materials not standardised across countries |
|  |  |  | Uzbekistan | 0 | 2025 | 0 | 2–3 products developed and distributed | 4 products developed and widely distributed |  |  |
|  | Number of standardised training initiatives and skills certification programmes developed for domestic workers to recognise and validate their skills | Documentation of developed training curricula, certification programme materials | Kazakhstan | 0 | 2025 | 1 training curriculum drafted | 2 training programmes developed; 1 certification programme launched | 2 training programmes operational; 2 certification programmes operational | At least two comprehensive training programmes/ curricula and two skills certification programmes per country | Data collection method: Review of training documentation, certification records. Risk: Certification may require government accreditation which can be delayed; institutional capacity to sustain programmes post-project. |
|  |  |  | Kyrgyzstan | 0 | 2025 | 1 training curriculum drafted | 2 training programmes developed; 1 certification programme launched | 2 training programmes operational; 2 certification programmes operational |  |  |
|  |  |  | Uzbekistan | 0 | 2025 | 2 standardized training initiatives and 2 certification programmes developed | 2 standardized training initiatives and 2 certification programmes launched | standardized training initiatives and 2 certification programmes operational |  |  |
|  | Functioning digital system improved or created to collect data on women in the informal economy, with data disaggregated by sex and sector | System development or upgrade records, data reports from the digital system | Kazakhstan | Lack of inclusive functional digital system | 2025 | System requirements and design specifications completed | System developed or upgraded and piloted; initial data collected | Fully functioning system operational with disaggregated data by sex and sector | A fully functioning digital system by 2027 | Data collection method: IT validation reports, system audit by CO M&E officer and ICT team. Annual data quality review. Risk: Technical infrastructure limitations; government buy-in required for sustainability; data privacy and protection concerns. |
|  |  |  | Uzbekistan |  | 2025 | System requirements and design specifications completed | System developed or upgraded and piloted; initial data collected | Fully functioning system operational with disaggregated data by sex and sector |  |  |
|  | Number of evidence-based employment support measures for women piloted based on gender-responsive labour market analysis | Documentation of designed employment support measures, pilot reports, and gender-responsive labour market analysis data | Turkmenistan | 0 | 2025 | Gender-responsive labour market analysis completed; 1 measure in design | 1 measures piloted and documented | 1 measures piloted, documented and evaluated | At least two evidence-based employment support measures designed and piloted in Turkmenistan | Data collection method: Review of pilot reports and labour market analysis documentation. Risk: Limited data on informal female employment in Turkmenistan; restricted access to some target groups. |
| 3.2. Enhanced access to employment and income generation opportunities for women | Number of individuals who accessed services and programmes offered | Records of individuals accessing services, program participation logs, registration forms, or database reports | Kazakhstan | 0 | 2025 | 0 | ≥175 individuals (70% women) | ≥300 individuals (70% women) | At least 300 individuals, with 70% women in each country, access services and programmes by programme end | Data collection method: Collect and verify service usage records, program participation logs, mentorship reports, and feedback surveys with implementing partners Risk: Limited access to programmes due to social, economic, or geographic barriers reduces women’s participation |
|  |  |  | Turkmenistan | 0 | 2025 | 0 | ≥175 individuals (70% women) | ≥300 individuals (70% women) |  |  |
|  |  |  | Uzbekistan | 0 | 2025 | 0 | ≥175 individuals (70% women) | ≥300 individuals (70% women) |  |  |
|  | Number of women participating in paid apprenticeship programmes | Apprenticeship programme records, tracking data, feedback surveys from both women participants and businesses, and programme evaluation reports | Kazakhstan | 0 | 2025 | 0 | 0 | ≥10 women completed apprenticeships | At least ten women participate in paid apprenticeship programmes per country by the end of programme |  |
|  |  |  | Turkmenistan | 0 | 2025 | 0 | 0 | ≥10 women completed apprenticeships |  |  |
|  | Number of women in target regions of Tajikistan who complete mentorship and capacity-building programmes and develop viable business plans | Programme reports and attendance records (disaggregated by region); Copies or summaries of developed business plans; Technical support logs or follow-up documentation; Mentor feedback and participant satisfaction surveys | Tajikistan | 0 | 2025 | 75 women complete orientation training; 45 women begin business plan development with mentor support | 150 women complete orientation training; 90 women develop business plans; 15 receive tailored technical support | 225 women complete orientation training; 135 women develop business plans; 30 women receive tailored technical support to implement business initiatives | 225 women complete orientation training to increase awareness of launching businesses; 135 women develop business plans through the mentorship programme; 30 women with business plans receive tailored technical support to implement their initiatives |  |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans: [Note: monitoring and evaluation plans should be adapted to project context, as needed]

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be flagged to project management and Steering Committee for course correction. | UNDP, UNFPA, UN Women | n/a |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Active risk log maintained; risks escalated to the Steering Committee when necessary; mitigation measures implemented promptly. | UNDP, UNFPA, UN Women | n/a |
| Learn | Capture knowledge, lessons learned, and good practices across countries and agencies. Promote adaptive programming and cross-country exchange. | At least annually; also after key learning events | Insights fed into programme planning and reflected in annual reports; shared with national counterparts and donor. | UNDP, UNFPA, UN Women | n/a |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | Results used by project management to improve implementation and decision-making. | UNDP Quality Assurance mechanisms | n/a |
| Review and Make Course Corrections | Review M&E data, risks, and lessons to inform adaptations in programme strategy, RRF updates, and budget reallocations. | At least annually | Recommendations are discussed in Steering Committee meetings and integrated into revised workplans and RRF. | Steering Committee, EUD and UNDP Kazakhstan | n/a |
| Project Report | Provide consolidated narrative and financial progress to donor, Steering Committee, and partners, including achievements, risks, compliance, and lessons. | Semi-annually; annually; final report at end | Inform EU and Steering Committee decision-making; ensure accountability and transparency; support learning and visibility requirements. | UNDP, UNFPA, UN Women, MPTF | n/a |
| Project Review (Project Steering Committee) | Regular oversight of programme performance and alignment with strategic goals; review Multi-Year Work Plan and approve course corrections. End-of-project review to extract lessons and assess sustainability. | Annual Steering Committee meetings | Steering Committe provides strategic guidance, assesses implementation challenges, and approves changes in RRF, workplans, and budgets as needed. | Steering Committee | n/a |

Evaluation Plan

| Evaluation Title | Partners (if joint) | Related Strategic Plan Outcome | UNSDCF/CPD Outcome | Planned Completion Date | Key Evaluation Stakeholders | Cost and Source of Funding |
| --- | --- | --- | --- | --- | --- | --- |
| Final External Independent Evaluation | UNDP, UNFPA, UN Women | Outcome 2 | Will depend on each country’s UNSDCF outcome, e.g. “Empowered People and Strong Institutions” (UNSDCF KAZ) | Q4 2028 | EUD, National Governments, UNDP, UNFPA, UN Women, CSOs, Regional Task Force | USD 30,000 Cost-shared by UNDP, UNFPA, and UN Women as per programme budget |

# Multi-Year Work Plan

All anticipated programmatic and operational costs to support the project, including development effectiveness and implementation support arrangements, need to be identified, estimated and fully costed in the project budget under the relevant output(s). This includes activities that directly support the project, such as communication, human resources, procurement, finance, audit, policy advisory, quality assurance, reporting, management, etc. All services which are directly related to the project need to be disclosed transparently in the project document.

| Expected Outputs | Planned Activities | Responsible Party | Planned Budget By Year |  |  | PLANNED BUDGET |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Y1 2026 | Y2 2027 | Y3 2028 | Funding Source | Budget description |  | Amount |
| Output 3.1. Data collection and analysis inform policies and legislation addressing women's vulnerabilities Gender marker: 3 | 3.1.1. Conduct a national assessment to develop the social portrait of women from vulnerable categories, including methodology design, data analysis, and preparation of a comprehensive report. | UNDP Kazakhstan CO | $30,000 | $0 | $0 | MPTFO | 72100 | Contractual Services - Companies | $30,000 |
|  |  |  | $1,500 | $1,000 | $500 |  | 74500 | Miscellaneous Expenses ? | $3,000 |
|  |  |  | $55,000 | $71,000 | $71,000 |  | 71400 | Contractual Services - Individuals | $197,000 |
|  |  |  | $5,600 | $5,100 | $5,100 |  | 73125 | Common Services-Premises | $15,800 |
|  |  |  | $5,750 | $1,666 | $1,666 |  | 72805 | Acquis of Computer Hardware | $9,082 |
|  |  |  | $400 | $400 | $400 |  | 72505 | Stationery & other Office Supp | $1,200 |
|  |  |  | $2,250 | $1,868 | $0 |  | 72220 | Furniture | $4,118 |
|  |  |  | $221 | $221 | $221 |  | 74325 | LCSSB charge | $662 |
|  |  |  | $6,465 | $6,200 | $6,200 |  | 67300 | GS Staff / NO Staff 67200 | $18,865 |
|  |  |  | $1,000 | $1,500 | $2,000 |  | 74500 | Bank commission | $4,500 |
|  |  |  | $2,500 | $2,500 | $2,500 |  | 72810 | Acquis of Computer Software | $7,500 |
|  | 3.1.2. Develop and disseminate policy recommendations on unpaid care | UNDP Kazakhstan CO | $36,600 | $10,000 | $15,000 | MPTFO | 72100 | Contractual Services - Companies | $61,600 |
|  |  |  | $4,800 | $12,000 | $3,000 |  | 71300 | Individual Consultant | $19,800 |
|  |  |  | $34,050 | $40,050 | $28,000 |  | 71600 | Travel | $102,100 |
|  |  |  | $7,500 | $7,500 | $2,500 |  | 72135 | Svc Co-Communications Service | $17,500 |
|  |  |  | $5,000 | $5,000 | $5,000 |  | 71400 | Contractual Services - Individuals | $15,000 |
|  |  | UNDP Kyrgyzstan CO | $23,000 | $15,022 | $0 | MPTFO | 72100 | Contractual Services - Companies | $38,022 |
|  |  |  | $0 | $4,000 | $4,000 |  | 71300 | Individual Consultant | $8,000 |
|  |  |  | $5,000 | $2,000 | $1,000 |  | 74500 | Miscellaneous Expenses | $8,000 |
|  |  | UNDP Turkmenistan CO | $16,000 | $0 | $1,000 | MPTFO | 71200 | International Consultant | $17,000 |
|  |  |  | $1,500 | $0 | $0 |  | 71600 | Transport expenses (for national and international consultants) | $1,500 |
|  |  |  | $0 | $0 | $2,000 |  | 75700 | Training expenses (catering and other services) | $2,000 |
|  |  |  | $5,000 | $6,000 | $0 |  | 71300 | Individual Consultant (national and international) | $11,000 |
|  |  | UNDP Uzbekistan CO | $24,426 | $10,520 | $4,900 | MPTFO | 72100 | Contractual Services - Companies | $39,846 |
|  |  |  | $7,800 | $1,950 | $1,950 |  | 71300 | Individual Consultant | $11,700 |
|  |  |  | $15,389 | $22,058 | $24,109 |  | 71400 | Contractual Services - Individuals | $61,556 |
|  |  |  | $2,381 | $1,726 | $1,548 |  | 67300 | DPC | $5,655 |
|  | 3.1.3. Support the Government in advancing the implementation of ILO Convention 190 through policy review, institutional capacity-building, awareness-raising, and the development of monitoring and enforcement mechanisms to prevent violence and harassment in the world of work. | UNDP Kazakhstan CO | $30,000 | $25,000 | $5,000 | MPTFO | 72100 | Contractual Services - Companies | $60,000 |
|  |  |  | $6,000 | $6,000 | $4,000 |  | 71300 | Individual Consultant | $16,000 |
|  |  |  | $5,580 | $6,000 | $6,000 |  | 72135 | Svc Co-Communications Service | $17,580 |
|  |  |  | $5,500 | $3,500 | $3,500 |  | 72515 | Print Media | $12,500 |
|  |  |  | $7,800 | $8,000 | $8,000 |  | 72315 | Food & Textile Products | $23,800 |
|  |  | UNDP Kyrgyzstan CO | $47,897 | $50,963 | $7,330 | MPTFO | 72100 | Contractual Services - Companies | $106,190 |
|  |  |  | $9,000 | $9,000 |  |  | 71300 | Individual Consultant | $18,000 |
|  |  |  | $2,500 | $2,500 | $1,000 |  | 74500 | Miscellaneous Expenses | $6,000 |
|  |  |  | $28,090 | $28,090 | $28,090 |  | 71400 | Contractual Services - Individuals | $84,269 |
|  |  |  | $671 | $671 | $671 |  | 74325 | LCSSB charge | $2,013 |
|  |  |  | $3,830 | $3,830 | $3,830 |  | 73100 | Rent | $11,490 |
|  |  |  | $300 | $300 | $300 |  | 72440 | Connectivity Charges | $900 |
|  | 3.1.4. Strengthen digital tools and data systems to enhance visibility, monitoring, and formalization of women’s work in the informal economy, with a focus on domestic employment. | UNDP Kazakhstan CO | $0 | $40,000 | $25,000 | MPTFO | 72100 | Contractual Services - Companies | $65,000 |
|  |  |  | $0 | $5,000 | $20,000 |  | 71300 | Individual Consultant | $25,000 |
|  |  |  | $5,000 | $5,000 | $5,000 |  | 67205 | Labour Cost - NO Staff | $15,000 |
|  |  | UNDP Turkmenistan CO | $17,000 | $0 | $0 | MPTFO | 71200 | International Consultant | $17,000 |
|  |  |  | $0 | $0 | $2,000 |  | 75700 | Training expenses | $2,000 |
|  |  |  | $7,000 | $20,000 | $7,000 |  | 71300 | Individual Consultant | $34,000 |
|  |  | UNDP Uzbekistan CO | $20,000 | $8,000 | $0 | MPTFO | 72100 | Contractual Services - Companies | $28,000 |
|  |  |  | $3,308 | $3,600 | $0 |  | 71300 | Individual Consultant | $6,908 |
|  |  |  | $15,389 | $22,058 | $24,110 |  | 71400 | Contractual Services - Individuals | $61,556 |
|  |  |  | $1,935 | $1,683 | $1,206 |  | 67300 | DPC | $4,824 |
|  | 3.1.5. Conduct labour market needs assessment through gender lenses in Turkmenistan | UNDP Turkmenistan CO | $11,330 | $8,670 | $0 | MPTFO | 71200 | International Consultant | $20,000 |
|  |  |  | $1,500 | $1,500 | $1,500 |  | 75700 | Training expenses (catering and other services) | $4,500 |
|  |  |  | $300 | $0 | $300 |  | 72500 | Stationery | $600 |
|  |  |  | $10,000 | $5,593 | $7,535 |  | 71300 | National Consultant | $23,128 |
|  |  |  | $1,200 | $1,200 | $1,200 |  | 73100 | Office rent | $3,600 |
|  |  |  | $20,272 | $20,391 | $20,543 |  | 71400 | Project management | $61,206 |
|  | Sub-Total for Output 3.1 - Kazakhstan |  | $258,516 | $264,505 | $219,587 |  |  |  | $742,607 |
|  | Sub-Total for Output 3.1 - Kyrgyzstan |  | $120,288 | $116,376 | $46,221 |  |  |  | $282,884 |
|  | Sub-Total for Output 3.1 - Turkmenistan |  | $91,102 | $63,354 | $43,078 |  |  |  | $197,534 |
|  | Sub-Total for Output 3.1 - Uzbekistan |  | $90,627 | $71,594 | $57,823 |  |  |  | $220,045 |
|  | Sub-Total for Output 3.1 |  | $560,533 | $515,829 | $366,709 |  |  |  | $1,443,070 |
|  | GMS (7%) | UNDP Kazakhstan CO | $18,096 | $18,515 | $15,371 | MPTFO | 75100 | GMS (7%) | $51,983 |
|  |  | UNDP Kyrgyzstan CO | $8,420 | $8,146 | $3,235 | MPTFO |  |  | $19,802 |
|  |  | UNDP Turkmenistan CO | $6,377 | $4,435 | $3,015 | MPTFO |  |  | $13,827 |
|  |  | UNDP Uzbekistan CO | $6,344 | $5,012 | $4,048 | MPTFO |  |  | $15,403 |
|  | Total by activity - Kazakhstan |  | $276,612 | $283,020 | $234,958 |  |  |  | $794,590 |
|  | Total by activity - Kyrgyzstan |  | $128,708 | $124,522 | $49,456 |  |  |  | $302,686 |
|  | Total by activity - Turkmenistan |  | $97,479 | $67,789 | $46,093 |  |  |  | $211,361 |
|  | Total by activity - Uzbekistan |  | $96,971 | $76,606 | $61,871 |  |  |  | $235,448 |
|  | Total by activity for Output 3.1 |  | $599,770 | $551,937 | $392,378 |  |  |  | $1,544,085 |
| Output 3.2. Enhanced access to employment and income generation opportunities for women Gender marker: 3 | 3.2.1. Support CSOs through grants, capacity-building, and mentorship to enhance sustainable economic opportunities for vulnerable women | UNDP Kazakhstan CO | $0 | $100,000 | $0 | MPTFO | 72100 | Contractual Services - Companies | $100,000 |
|  |  |  | $0 | $5,000 | $0 |  | 71300 | Individual Consultant | $5,000 |
|  |  |  |  | $10,000 | $0 |  | 72135 | Svc Co-Communications Service | $10,000 |
|  |  | UNDP Turkmenistan CO | $0 | $10,000 | $20,000 | MPTFO | 72605 | Grant provision | $70,000 |
|  |  | UNDP Uzbekistan CO | $20,000 | $20,000 | $0 | MPTFO | 72600 | Grants | $101,556 |
|  |  |  | $15,389 | $22,058 | $24,110 |  | 71400 | Contractual Services - Individuals | $63,656 |
|  |  |  | $700 | $700 | $700 |  | 73100 | Travel | $7,283 |
|  |  |  | $1,804 | $2,138 | $1,241 |  | 67300 | DPC | $70,183 |
|  |  | UNDP Tajikistan CO | $24,000 | $20,500 | $20,500 | MPTFO | 72100 | Contractual Services - Companies | $123,249 |
|  |  |  | $20,000 | $20,000 | $18,249 |  | 71400 | Contractual Services - Individuals | $59,549 |
|  |  |  | $0 | $650 | $650 |  | 73100 | Travel | $4,300 |
|  |  |  | $0 | $1,500 | $1,500 |  | 67300 | DPC | $23,000 |
|  | 3.2.2. Support the design, implementation, and promotion of paid apprenticeship programmes that provide women with practical skills and work experience, through partnerships with local businesses, academia, NGOs, and municipalities. | UNDP Kazakhstan CO | $0 | $10,000 | $10,000 | MPTFO | 72100 | Contractual Services - Companies | $20,000 |
|  |  |  | $0 | $5,000 | $5,000 |  | 71300 | Individual Consultant | $10,000 |
|  |  | UNDP Turkmenistan CO | $3,000 | $5,000 | $5,000 | MPTFO | 75700 | Training expenses (catering and other services) | $47,350 |
|  |  |  | $8,250 | $11,100 | $15,000 |  | 71300 | National Consultant | $88,350 |
|  |  |  | $17,000 | $18,000 | $19,000 |  | 71400 | Project management | $92,000 |
|  | 3.2.3. Promote equal access to economic opportunities through the removal of structural barriers and gender-responsive vocational education and training in Kyrgyzstan | UNDP Kyrgyzstan CO | $0 | $32,000 | $6,000 | MPTFO | 72100 | Contractual Services - Companies | $46,000 |
|  |  |  | $0 | $8,000 |  |  | 71300 | Individual Consultant | $208,000 |
|  | 3.2.4. Support for economic empowerment of women in target areas in Tajikistan through mentorship by entrepreneurs, capacity building and technical assistance | UNDP Tajikistan CO | $70,000 | $65,000 | $65,000 | MPTFO | 72100 | Contractual Services - Companies | $201,336 |
|  |  |  | $0 | $600 | $736 |  | 74500 | Miscellaneous Expenses | $146,336 |
|  | Sub-Total for Output 3.2 - Kazakhstan |  | $0 | $130,000 | $15,000 |  |  |  | $145,000 |
|  | Sub-Total for Output 3.2 - Kyrgyzstan |  | $0 | $40,000 | $6,000 |  |  |  | $46,000 |
|  | Sub-Total for Output 3.2 - Tajikistan |  | $114,000 | $108,250 | $106,635 |  |  |  | $328,885 |
|  | Sub-Total for Output 3.2 - Turkmenistan |  | $28,250 | $44,100 | $59,000 |  |  |  | $131,350 |
|  | Sub-Total for Output 3.2 - Uzbekistan |  | $37,893 | $44,895 | $26,051 |  |  |  | $108,840 |
|  | Sub-Total for Output 3.2 |  | $180,143 | $367,245 | $212,685 |  |  |  | $760,074 |
|  | GMS (7%) | UNDP Kazakhstan CO | $0 | $9,100 | $1,050 | MPTFO | 75100 | GMS (7%) | $10,150 |
|  |  | UNDP Kyrgyzstan CO | $0 | $2,800 | $420 |  |  |  | $3,220 |
|  |  | UNDP Tajikistan CO | $7,980 | $7,578 | $7,464 |  |  |  | $23,022 |
|  |  | UNDP Turkmenistan CO | $1,978 | $3,087 | $4,130 |  |  |  | $9,195 |
|  |  | UNDP Uzbekistan CO | $2,653 | $3,143 | $1,824 |  |  |  | $7,619 |
|  | Total by activity - Kazakhstan |  | $0 | $139,100 | $16,050 |  |  |  | $155,150 |
|  | Total by activity - Kyrgyzstan |  | $0 | $42,800 | $6,420 |  |  |  | $49,220 |
|  | Total by activity - Tajikistan |  | $121,980 | $115,828 | $114,099 |  |  |  | $351,906 |
|  | Total by activity - Turkmenistan |  | $30,228 | $47,187 | $63,130 |  |  |  | $140,545 |
|  | Total by activity - Uzbekistan |  | $40,546 | $48,038 | $27,874 |  |  |  | $116,459 |
|  | Total by activity for Output 3.2 |  | $192,753 | $392,953 | $227,573 |  |  |  | $813,279 |
|  | Total by project - Kazakhstan |  | $276,612 | $422,120 | $251,008 |  |  |  | $949,740 |
|  | Total by project - Kyrgyzstan |  | $128,708 | $167,322 | $55,876 |  |  |  | $351,906 |
|  | Total by project - Tajikistan |  | $121,980 | $115,828 | $114,099 |  |  |  | $351,906 |
|  | Total by project - Turkmenistan |  | $127,707 | $114,976 | $109,223 |  |  |  | $351,906 |
|  | Total by project - Uzbekistan |  | $137,517 | $124,644 | $89,745 |  |  |  | $351,906 |
|  | GRAND TOTAL |  | $792,524 | $944,889 | $619,952 |  |  |  | $2,357,365 |

# Governance and Management Arrangements

The governance and management of the MCP are structured to ensure inclusive decision-making, accountability, and coordination among all implementing and oversight entities. The arrangements are aligned with UN system standards and EU requirements and are designed to promote coherence across the five participating Central Asian countries.

UNDP, UNFPA, and UN Women will be each responsible for implementing the specific programme’s outputs and activities and delivering the results as per the programme Theory of Change and Results and Resources Framework (RRF).

UNDP Kazakhstan will act as both the Participating United Nations Organization (PUNO) and the Convening Agent (CA) for the MCP and will be responsible for facilitating coordination among all PUNOs and for consolidating programme-level narrative and financial reports based on inputs received from each participating agency in Kazakhstan. UNDP Kazakhstan will oversee the day-to-day implementation of the MCP, ensuring achievement of its objectives, targWQ ets, and results, including activities that span across the five Central Asian countries. The Country Office will recruit and host a full-time Regional Task Force Coordinator (NPSA-9) and a full-time Project Associate (NPSA-7). Additional technical and support staff will be engaged, as appropriate, to ensure effective programme monitoring, visibility, and stakeholder engagement across all countries.

The Steering Committee (SC) serves as the primary governance body of the MCP, providing strategic direction, oversight, and high-level decision-making throughout its implementation. The SC ensures that the MCP aligns with the priorities of the participating Central Asian governments, the mandates of the UN agencies involved, and the expectations of the European Union. Co-chaired by a representative of the national government and a member of the UN Country Team (or the UN Resident Coordinator), the SC includes all PUNOs, as well as representative of the European Union Delegation in Kazakhstan. Where relevant, non-UN implementing partners or stakeholders may also be invited to SC meetings. The SC will meet at least twice a year to:

- Review and endorse the RRF, annual work plans, and budgets;

- Examine consolidated narrative and financial reports;

- Approve any substantive changes to expected results or budget reallocations;

- Address strategic challenges or external risks affecting the programme;

- Ensure coherence, complementarity, and coordination across countries and agencies.

UNDP Kazakhstan will serve as the Secretariat to the Steering Committee. In this role, UNDP Kazakhstan is responsible for preparing and distributing meeting materials, documenting decisions, coordinating across PUNOs, and consolidating programme-level reporting.

UNDP CO in Central Asia will lead their respective country-level components within the programme. Each CO will designate focal staff for coordination, reporting, and oversight. UNDP Kyrgyzstan will engage a Project Specialist, Project Analyst, and Administrative & Finance Assistant to manage and implement programme activities. In Tajikistan, a National Project Officer and a Project Administrative Associate will oversee implementation. UNDP Turkmenistan will deploy a full-time Project Manager, a Project Assistant, and a Communications support role. In Uzbekistan, staffing will include a Project Analyst and a Project Associate.

Collaboration mechanisms within the MCP will be anchored by regular coordination meetings convened by the UNDP Country Offices, bringing together programme staff from UNDP, UNFPA, and UN Women at the country level to ensure alignment of activities, information exchange, and timely problem-solving. These meetings will review programme progress, adapt activities to the specific country context, and foster strong collaboration on the ground. Key updates and issues will be communicated to the Regional Task Force Manager to inform regional coordination and upward to the Steering Committee to support strategic decision-making.

UNFPA will act as Participating UN Organisation. At the regional level, oversight of UNFPA activities will be under the guidance of the Head of the Sub-Regional Office (SRO) for Central Asia in Almaty, P4 level. Additionally, a Programme Manager will offer management, administrative and financial support, stationed at UNFPA's SRO in Almaty. In-country operations will be conducted and managed by existing gender focal points/gender officers. Each of the 5 country offices will also receive support for in-country activities, with additional assistance provided through consultancies.

UN Women as the PUNO within the programme will assign a Regional Programme Manager and Programme Expert based in Kazakhstan and reporting to the UN Women Country Office Kazakhstan providing overall management, coordination and technical coherence to UN Women Country Offices. Programme teams in each UN Women Country Office will be responsible for the overall accountability and quality implementation of programme interventions at the country level. Each Country Office will designate focal staff for coordination, reporting, and oversight to ensure efficient implementation and alignment with regional objectives under UN Women’s leadership. In Kyrgyzstan, UN Women will engage a Project Coordinator and a Project Assistant to support implementation. In Uzbekistan, the team will include a Project Coordinator, a Country Programme Manager, and a Project Assistant. UN Women Tajikistan will deploy a Project Coordinator and a Finance/Administrative Support Officer to oversee national-level activities.

The MCP will be using a pass-through fund management modality where UNDP Multi-Partner Trust Fund Office will act as the Administrative Agent (AA) under which the funds will be channelled for the MCP through the AA. Each participating UN organization receiving funds through the pass-through would have to sign a standardized Memorandum of Understanding with the AA.

In addition to the EUD in Kazakhstan, represented on the Steering Committee, the EUD Coordination Team (EUD-CT) will comprise EUDs or designated EU representatives from other participating countries. Each member of the EUD-CT will work in close collaboration with the respective UNDP Country Office, which leads the implementation of the MCP at the national level. Through this partnership, the EUD-CT will facilitate strategic and operational alignment of programme activities with overarching EU priorities, will support visibility and communication initiatives, and will engage in regular exchanges to monitor progress and proactively address emerging challenges.

The diagram below presents the tentative governance structure of the programme:

UNDP, UNFPA and UN Women will ensure close coordination with other UN Agencies during the implementation of this MCP, including with UNICEF who plays a critical complementary role in this collaboration, addressing the intersection of violence against women and      children by supporting legal and policy reforms, focusing on prevention programming from early childhood through adolescence, and strengthening social services to ensure coordinated responses for both child protection and violence against women.

# Legal Context

For Global and Regional Projects

This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions to the Project Document attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by UNDP, UNFPA and UN Women in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

Option b. UNDP (DIM)

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism , that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Project Document, UNDP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor, and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - Each responsible party, subcontractor and sub-recipient (each a “sub-party” and together “sub-parties”) acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the sub-parties, and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, each sub-party shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, each sub-party, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

  - In the performance of the activities under this Project Document, each sub-party shall (with respect to its own activities), and shall require from its sub-parties (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, sub-parties will and will require that their respective sub-parties will take all appropriate measures to:

(i) Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

(ii) Offer employees and associated personnel training on prevention and response to SH and SEA, where sub-parties have not put in place its own training regarding the prevention of SH and SEA, sub-parties may use the training material available at UNDP;

(iii) Report and monitor allegations of SH and SEA of which any of the sub-parties have been informed or have otherwise become aware, and status thereof;

(iv) Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

(v) Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. Each sub-party shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the relevant sub-party shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

  - Each sub-party shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the relevant sub-party to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

  - Each responsible party, subcontractor and sub-recipient will ensure that any project activities undertaken by them will be implemented in a manner consistent with the UNDP Social and Environmental Standards and shall ensure that any incidents or issues of non-compliance shall be reported to UNDP in accordance with UNDP Social and Environmental Standards.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud, corruption or other financial irregularities, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption other financial irregularities with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - Choose one of the three following options:

Option 1: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption, other financial irregularities or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Option 2: Each responsible party, subcontractor or sub-recipient agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud corruption or other financial irregularities or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

Special Clauses. In case of government cost-sharing through the project, the following clauses should be included:

- The schedule of payments and UNDP bank account details.

- The value of the payment, if made in a currency other than United States dollars, shall be determined by applying the United Nations operational rate of exchange in effect on the date of payment.  Should there be a change in the United Nations operational rate of exchange prior to the full utilization by the UNDP of the payment, the value of the balance of funds still held at that time will be adjusted accordingly.  If, in such a case, a loss in the value of the balance of funds is recorded, UNDP shall inform the Government with a view to determining whether any further financing could be provided by the Government.  Should such further financing not be available, the assistance to be provided to the project may be reduced, suspended or terminated by UNDP.

- The above schedule of payments takes into account the requirement that the payments shall be made in advance of the implementation of planned activities.  It may be amended to be consistent with the progress of project delivery.

- UNDP shall receive and administer the payment in accordance with the regulations, rules and directives of UNDP.

- All financial accounts and statements shall be expressed in United States dollars.

- If unforeseen increases in expenditures or commitments are expected or realized (whether owing to inflationary factors, fluctuation in exchange rates or unforeseen contingencies), UNDP shall submit to the government on a timely basis a supplementary estimate showing the further financing that will be necessary. The Government shall use its best endeavours to obtain the additional funds required.

- If the payments referred above are not received in accordance with the payment schedule, or if the additional financing required in accordance with paragraph 6 above is not forthcoming from the Government or other sources, the assistance to be provided to the project under this Agreement may be reduced, suspended or terminated by UNDP.

- Any interest income attributable to the contribution shall be credited to UNDP Account and shall be utilized in accordance with established UNDP procedures.

In accordance with the decisions and directives of UNDP's Executive Board:

The contribution shall be charged:

- 7 % cost recovery for the provision of general management support (GMS) by UNDP headquarters and country offices

- Direct cost for implementation support services (ISS) provided by UNDP and/or an executing entity/implementing partner.

- Ownership of equipment, supplies and other properties financed from the contribution shall vest in UNDP.  Matters relating to the transfer of ownership by UNDP shall be determined in accordance with the relevant policies and procedures of UNDP.

- The contribution shall be subject exclusively to the internal and external auditing procedures provided for in the financial regulations, rules and directives of UNDP.”

# ANNEXES

- CPD Outcomes Contributing to Programme by Country

- Project Quality Assurance Report

- Social and Environmental Screening Template

- Risk Analysis. Use the standard Risk Register template. Please refer to the Deliverable Description of the Risk Register for instructions

- Steering Committee Terms of Reference.

| Annex 1. CPD Outcomes Contributing to Programme by Country |  |
| --- | --- |
| Applicable Outcome from the UNDP Strategic Plan 2026-2029: |  |
| STRATEGIC OUTCOME 2: By 2029, governance systems are more effective, inclusive, and accountable, enabling people, societies and economies to thrive. |  |
| Country | UNSDCF/Country Programme Results and Resource Framework Information |
| Kazakhstan | Intended Outcome as stated in UNDP Kazakhstan CPD 2026-2030: |
|  | Outcome 4: By 2030, all people in Kazakhstan, especially the most vulnerable, have equal access to fair justice and the rule of law in line with international human rights standards, and the inclusive, meaningful and gender-balanced participation in decision-making for all, as well as civic engagement is enhanced. |
|  | Outcome indicators as stated in UNDP Kazakhstan CPD 2026-2030, including baseline and targets: |
|  | Indicator 4.2.1: Number national and subnational policies, strategies, and institutional mechanisms promoting women and youth leadership and participation, including through volunteerism, in political, economic, and social decision-making. Baseline (2024): 0 Target (2030): 4 Indicator 4.2.3: Number of public and private institutions implementing international standards, including for the care economy, to respond to needs of women and youth Baseline (2024): 0 Target (2030): 15 |
| Kyrgyzstan | Intended Outcome as stated in UNDP Kyrgyzstan CPD 2023-2027: |
|  | Outcome 4: By 2027, all people in the Kyrgyz Republic enjoy the benefits of fair and accountable democratic institutions that are free from corruption and apply innovative solutions that promote respect for human rights and strengthen peace and cohesion. |
|  | Outcome indicators as stated in UNDP Kyrgyzstan CPD 2023-2027, including baseline and targets: |
|  | Indicator 4.3.1: Number of inclusive policies and mechanisms for pre-emptive governance and risk-informed development, civic participation, and social dialogue with focus on most vulnerable women and youth, to strengthen social contract at national and local levels Baseline (2020): 0 Target (2027): 1 policy, 3 mechanisms |
| Tajikistan | Intended Outcome as stated in UNDP Tajikistan CPD 2023-2026: |
|  | Outcome 2: By 2026, public institutions and the private sector collaborate to implement innovative and gender-responsive policy frameworks and actions to green the economy and strengthen inclusion of vulnerable groups. |
|  | Outcome indicators as stated in UNDP Tajikistan CPD 2023-2026, including baseline and targets: |
|  | Indicator #: Number of [measures] implemented with UN support to: b) increase women’s (and young girls) access to and use of digital technologies, digital finance, e-commerce and digital value chains; c) ensure women’s (and young girls) economic security and empowerment; Baseline (year): b) (2021) 2; c) (2021) 2; Target (year): b) 1; c) 2 |
| Turkmenistan | Intended Outcome as stated in UNDP Turkmenistan CPD {pls insert years}2026-2030: |
|  | Outcome 2: By 2030, Turkmenistan will have improved conditions and opportunities for inclusive and sustainable economic diversification and growth. |
|  | Outcome indicators as stated in UNDP Turkmenistan CPD {pls insert years}, including baseline and targets: |
|  | Indicator 2.2: Number of people who gained access to decent, formal, and safe employment opportunities in economic sectors with high employment potential, with a focus on women, youth, and persons with disabilities. 2.2.1. Number of initiatives aimed at improving formal and informal vocational education, including those focused on skills for “green” jobs. Baseline (2025): 1 Target (year): 6 2.2.2. Number of women, youth, and persons with disabilities who have acquired practical skills in cooperation with local companies and academic institutions, including skills related to “green” professions. Baseline (2024): None Target (2028): 700 (Women: 300; Youth: 200; Persons with disabilities: 200; Source/Frequency: Project reports / Annual) |
| Uzbekistan | Intended Outcome as stated in UNDP Uzbekistan CPD {pls insert years}: |
|  | Outcome 2: By 2030, all people in Uzbekistan achieve an adequate standard of living and have resilience to socio-economic and climate-related shocks through decent work, an effective social protection system and inclusive, innovative, and sustainable economic growth. |
|  | Outcome indicators as stated in UNDP Uzbekistan CPD {pls insert years}, including baseline and targets: |
|  | Indicator 2.1.3: Number of new or strengthened policies, legislations and regulations or investment in national care systems in place (current) Baseline (2026): 0 Target (2028): 4 Indicator 2.1.2: Number of entities with strengthened capacities to design and implement legislation, policies, action plans and initiatives to deliver quality, inclusive, and gender-responsive social benefits and services, including responses to GBV and environmental factors. a) CSOs b) Ministry of Labour and Poverty Reduction c) NASP Baseline (2026): 0 Target (2028): 4 Indicator 2.3.2: Number of improved skills development programmes, including apprenticeship programmes, implemented to promote women’s empowerment to develop qualifications required by the labour markets, including a distinct focus on green jobs with UNDP support. Baseline (2026): 0 Target (2028): 2 |

Annex 2. Project Quality Assurance Report

https://undp.lightning.force.com/lightning/r/Procedure__c/a37aA0000057YQHQA2/view

Annex 3. Social and Environmental Screening Template

https://undp.lightning.force.com/lightning/r/Procedure__c/a37aA0000057YZxQAM/view

Detailed Social and Environmental Screening Report

| ASM-20403 - SESP (Social and Environmental Screening Procedure) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Procedure Year: 2026 | Procedure Rating: Low |  |  |
| Procedure Status: Approved | Procedure Name: ASM-20403 |  |  |
| Procedure Type: Design | Procedure Department: CO - Kazakhstan - Astana |  |  |
| Record Owner: Aliya Seitzhan |  |  |  |  |  |
| Created by: Aliya Seitzhan,4/22/2026, 4:54 AM | Last Modified by: Sukhrob Khojimatov, 4/26/2026, 9:50 PM |  |  |  |  |

Portofolio/Project Type: Project

| Related Portfolio MYWPs/Projects (1) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Name | Portofolio/Project Name | Department | Status | ATLAS Project Number | Start Date | End Date |
| 01005597 | CHANGE - Challenging Harmful Attitudes and Norms for Gender Equality_MPTF | CO - Kazakhstan - Astana | On Going |  | 12/18/2025 | 12/31/2028 |

| Related QAs (1) |  |  |
| --- | --- | --- |
| Parent Procedure | Procedure Type | Procedure Year |
| ASM-20402 | Quality Assurance - Design | 2026 |

Triggered Requirements

Number of Identified Risks: 0

The Social and Environmental Screening Procedure (SESP) has indicated that, from a risk perspective, the following SES Principles and Standards are triggered for the project:

No Triggered Principles

| Assessment | Status: Complete |
| --- | --- |

Is assessment required? (Question only required for Moderate, Substantial and High Risk portfolio MYWPs/projects)

| Targeted assessment(s) required? |  | No |
| --- | --- | --- |
| If yes, please indicate the status of required assessment(s)? |  |  |

Comments (for instance, please indicate the assessment type) (20000 Characters maximum)

| Environmental and Social Impact Assessment (ESIA) required? |  | No |
| --- | --- | --- |
| If yes, please indicate the status? |  |  |

Comments (20000 Characters maximum)

| Strategic Environmental and Social Assessment (SESA) required? |  | No |
| --- | --- | --- |
| If yes, please indicate the status? |  |  |

Comments (20000 Characters maximum)

| Management Plans | Status: Complete |
| --- | --- |

Are management plans required? (Question only required for Moderate, Substantial and High Risk portfolio MYWPs/projects)

| Targeted management plan(s) required? |  | No |
| --- | --- | --- |
| If yes, please indicate the status of required management plan(s)? |  |  |

Comments (for instance, please indicate the type of management plan) (20000 Characters maximum)

| Environmental and Social Management Plan (ESMP) required? |  | No |
| --- | --- | --- |
| If yes, please indicate the status? |  |  |

Comments (20000 Characters maximum)

| Environmental and Social Management Framework (ESMF) required? |  | No |
| --- | --- | --- |
| If yes, please indicate the status? |  |  |

Comments (20000 Characters maximum)

Approval Information

| Approval Date: April 26, 2026 | Approved By: Sukhrob Khojimatov <sukhrob.khojimatov@undp.org> |
| --- | --- |
| Confirmed Date: | Confirmed By: |
| PAC/Board Date: | PAC/Board Meeting minutes uploaded: |

| Approval History |  |  |  |
| --- | --- | --- | --- |
| Step Name | Date | Status | Assigned To |
| Cleared for PAC/Board | 2026-04-26 21:50:37 | Approved | Sukhrob Khojimatov |
| Confirmed by PAC/Board | 2026-04-26 21:50:37 | Pending | Sukhrob Khojimatov |
| Approval Request Submitted | 2026-04-23 00:07:19 | Started | Aliya Seitzhan |

Questionnaire

| Step 1 - Integrate the SES Programming Principles | Status: Complete |
| --- | --- |

QUESTION 1: How Does the Portfolio MYWP/Project Integrate the Programming Principles in Order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the portfolio MYWP/project mainstreams the human rights-based approach (32000 Characters maximum)

The CHANGE project mainstreams the human rights-based approach by promoting equal access to opportunities, participation, and decision-making for women, particularly those in vulnerable situations. It supports evidence-based policymaking through disaggregated data on women’s needs and ensures inclusive stakeholder engagement, including civil society and marginalized groups, in project design and implementation. The project also strengthens duty bearers’ capacity to apply gender equality and human rights commitments in practice, while addressing resistance to change through awareness-raising, dialogue, and engagement of institutional change agents.

Briefly describe in the space below how the portfolio MYWP/project is likely to improve gender equality and women’s empowerment (32000 Characters maximum)

The project directly promotes gender equality and women’s empowerment by improving women’s access to employment and income-generating opportunities and addressing structural and social barriers to economic participation. It works with government and community stakeholders to strengthen buy-in for gender-responsive approaches and integrates awareness-raising and tailored messaging to address traditional gender norms. Through capacity-building and targeted interventions, the project enhances women’s economic inclusion, agency, and long-term empowerment.

Briefly describe in the space below how the portfolio MYWP/project mainstreams sustainability and resilience (32000 Characters maximum)

The CHANGE project strengthens sustainability and resilience by aligning interventions with national development priorities and building institutional capacity for long-term implementation. It adopts flexible programming to respond to potential political or contextual changes and ensures continuity through multi-stakeholder engagement mechanisms. By enhancing women’s economic opportunities and livelihoods, the project also contributes to greater household and community resilience to economic and social shocks.

Briefly describe in the space below how the portfolio MYWP/project strengthens accountability to stakeholders (32000 Characters maximum)

The project strengthens accountability through continuous and transparent engagement with government counterparts, civil society, and beneficiaries across all stages of implementation. It promotes clear communication of objectives, participatory planning, and regular coordination to ensure alignment and shared understanding. Feedback and collaboration mechanisms help prevent misinterpretation of goals and reinforce trust, ownership, and mutual accountability among stakeholders.

| Step 2.1 - SES Risk Screening Checklist (Programming Principles) | Status: Complete |
| --- | --- |

Human Rights

| P.1 Have local communities or individuals raised human rights concerns regarding the portfolio MYWP/project (e.g. during the stakeholder engagement process, grievance processes, public statements)? |  | No |
| --- | --- | --- |
| P.2 Is there a risk that duty-bearers (e.g. government agencies) do not have the capacity to meet their obligations in the portfolio MYWP/project? |  | No |
| P.3 Is there a risk that rights-holders (e.g. persons affected by programming activities) do not have the capacity to claim their rights? | No |  |

Would the portfolio MYWP/project potentially involve or lead to:

| P.4 Adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |  |  |  |
| --- | --- | --- | --- | --- |
| P.5 Inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities? |  | No |  |  |
| P.6 Restrictions in availability, quality of and/or access to resources or basic services, in particular to marginalized individuals or groups, including persons with disabilities? |  |  | No |  |
| P.7 Exacerbation of conflicts among and/or the risk of violence to affected communities and individuals? |  |  |  | No |

Gender Equality and Women's Empowerment

| P.8 Have women’s groups/leaders raised gender equality concerns regarding the portfolio MYWP/project, (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| --- | --- |

Would the portfolio MYWP/project potentially involve or lead to:

| P.9 Adverse impacts on gender equality and/or the situation of women and girls? | No |  |
| --- | --- | --- |
| P.10 Reproducing discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? |  | No |
| P.11 Limitations on women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? |  | No |
| P.12 Exacerbation of risks of gender-based violence, including sexual exploitation and abuse of women and children? |  | No |

Accountability

Would the portfolio MYWP/project potentially involve or lead to:

| P.13 Exclusion of any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them? | No |  |
| --- | --- | --- |
| P.14 Grievances or objections from potentially affected stakeholders? |  | No |
| P.15 Risks of retaliation or reprisals against stakeholders who express concerns or grievances, or who seek to participate in or to obtain information on the project/portfolio? |  | No |

Sustainability and Resilience

| P.16 Does the portfolio MYWP/project include activities with unknown design parameters for which potential SES risks cannot yet be determined and will require further activity-level screening and potential assessment for risks associated with sustainability and resilience? |  | No |
| --- | --- | --- |
| Step 2.2 - SES Risk Screening Checklist (Standards) | Status: Complete |  |

Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management

Would the portfolio MYWP/project potentially involve or lead to:

| 1.1 Adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? |  |  | No |  |
| --- | --- | --- | --- | --- |
| 1.2 Activities within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? |  |  | No |  |
| 1.3 Changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? | No |  |  |  |
| 1.4 Risks to endangered species? |  | No |  |  |
| 1.5 Exacerbation of illegal wildlife trade? |  |  |  | No |
| 1.6 Introduction of invasive alien species? |  |  |  | No |
| 1.7 Adverse impacts on soil? |  |  |  | No |
| 1.8 Harvesting of natural forests, plantation development, or reforestation? |  |  |  | No |
| 1.9 Significant agricultural production? |  |  |  | No |
| 1.10 Animal husbandry or harvesting of fish populations or other aquatic species? |  |  |  | No |
| 1.11 Significant extraction, diversion or containment of surface or ground water? |  |  |  | No |
| 1.12 Handling or utilization of genetically modified organisms/living modified organisms? |  |  |  | No |
| 1.13 Utilization of genetic resources? |  |  |  | No |
| 1.14 Adverse transboundary or global environmental concerns? |  |  |  | No |

Standard 2: Climate Change and Disaster Risks

Would the portfolio MYWP/project potentially involve or lead to:

| 2.1 Areas subject to hazards such as earthquakes, floods, landslides, severe winds, storm surges, tsunami or volcanic eruptions? |  |  | No |
| --- | --- | --- | --- |
| 2.2 Outputs and outcomes sensitive or vulnerable to potential impacts of climate change or disasters |  | No |  |
| 2.3 Direct or indirect increases in vulnerability to climate change impacts or disaster risks now or in the future (also known as maladaptive or negative coping practices)? |  | No |  |
| 2.4 Increases of greenhouse gas emissions, black carbon emissions or other drivers of climate change? | No |  |  |

Standard 3: Community Health, Safety and Security

Would the portfolio MYWP/project potentially involve or lead to:

| 3.1 Construction and/or infrastructure development (e.g. roads, buildings, dams)? |  |  |  | No |
| --- | --- | --- | --- | --- |
| 3.2 Air pollution, noise, vibration, traffic, injuries, physical hazards, poor surface water quality due to runoff, erosion, sanitation? |  |  | No |  |
| 3.3 Harm or losses due to failure of structural elements of the programming activities (e.g. collapse of buildings or infrastructure)? |  | No |  |  |
| 3.4 Risks of water-borne or other vector-borne diseases (e.g. temporary breeding habitats), communicable and noncommunicable diseases, nutritional disorders, mental health? | No |  |  |  |
| 3.5 Transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? |  | No |  |  |
| 3.6 Adverse impacts on ecosystems and ecosystem services relevant to communities' health (e.g. food, water purification, natural buffers, nutrient cycling, spiritual values, etc.)? | No |  |  |  |
| 3.7 Influx of portfolio MYWP/project workers to targeted areas? |  | No |  |  |
| 3.8 Engagement of security personnel to protect facilities and property or to support portfolio MYWP/project activities? |  |  | No |  |

Standard 4: Cultural Heritage

Would the portfolio MYWP/project potentially involve or lead to:

| 4.1 Activities adjacent to or within a Cultural Heritage site? | No |  |  |
| --- | --- | --- | --- |
| 4.2 Significant excavations, demolitions, movement of earth, flooding or other environmental changes? | No |  |  |
| 4.3 Adverse impacts to sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: portfolio MYWPs/projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) |  | No |  |
| 4.4 Alterations to landscapes and natural features with cultural significance? |  | No |  |
| 4.5 Utilization of tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes? |  |  | No |

Standard 5: Displacement and Resettlement

Would the portfolio MYWP/project potentially involve or lead to:

| 5.1 Temporary or permanent and full or partial physical displacement (including people without legally recognizable claims to land)? | No |
| --- | --- |
| 5.2 Economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions - even in the absence of physical relocation)? | No |
| 5.3 Risk of forced evictions? | No |
| 5.4 Impacts on or changes to land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | No |

Standard 6: Indigenous Peoples

Would the portfolio MYWP/project potentially involve or lead to:

| 6.1 Areas where indigenous peoples are present (including project area of influence)? | No |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 6.2 Activities located on lands and territories claimed by indigenous peoples? | No |  |  |  |  |
| 6.3 Impacts (positive or negative) to the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the programming activities are located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? | No |  |  |  |  |
| 6.4 The absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? |  | No |  |  |  |
| 6.5 The utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? |  |  | No |  |  |
| 6.6 Forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? |  |  | No |  |  |
| 6.7 Adverse impacts on the development priorities of indigenous peoples as defined by them? |  |  |  | No |  |
| 6.8 Risks to the physical and cultural survival of indigenous peoples? |  |  |  |  | No |
| 6.9 Impacts on the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? |  |  |  |  | No |

Standard 7: Labour and Working Conditions

Would the portfolio MYWP/project potentially involve or lead to: (note: applies to portfolio MYWP, project and contractor workers)

| 7.1 Working conditions that do not meet national labour laws and international commitments? |  | No |
| --- | --- | --- |
| 7.2 Working conditions that may deny freedom of association and collective bargaining? | No |  |
| 7.3 Use of child labour? |  | No |
| 7.4 Use of forced labour? |  | No |
| 7.5 Discriminatory working conditions and/or lack of equal opportunity? | No |  |
| 7.6 Occupational health and safety risks due to physical, chemical, biological and psychosocial hazards (including violence and harassment) throughout the portfolio MYWP/project life-cycle? | No |  |

Standard 8: Pollution Prevention and Resource Efficiency

Would the portfolio MYWP/project potentially involve or lead to:

| 8.1 The release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? |  | No |
| --- | --- | --- |
| 8.2 The generation of waste (both hazardous and non-hazardous)? |  | No |
| 8.3 The manufacture, trade, release, and/or use of hazardous materials and/or chemicals? | No |  |
| 8.4 The use of chemicals or materials subject to international bans or phase-outs? | No |  |
| 8.5 The application of pesticides that may have a negative effect on the environment or human health? | No |  |
| 8.6 Significant consumption of raw materials, energy, and/or water? | No |  |

Annex 4. Offline Portfolio/Project Risk Register by Country Office

| Portfolio/Project Title: “Challenging Harmful Attitudes and Norms for Gender Equality” (CHANGE) |  |  |  |  |  | Portfolio/Project Number: 01005597 |  | Date: 26.05.2026 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KAZAKHSTAN |  |  |  |  |  |  |  |  |
| # | Event | Cause | Impact(s) | Risk Category and Sub-category including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (team accountable for managing the risk) | Risk Treatment and Treatment Owner |
| 1 | There is a risk of resistance to change from individuals or groups, including representatives from the state bodies entrenched in traditional gender norms. | As a result of entrenched patriarchal attitudes and lack of awareness of gender equality benefits | Which will impact in delays or limits adoption of gender-responsive policies and practices | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 4 - Highly likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 To: 31-Dec-28 | Gaukhar Nursha, Ainur Moldakassimova | Risk Treatment 1.1: Engage in robust community consultations and awareness campaigns to build support and address resistance; identify and support change agents within institutions; use tailored messaging to resonate with different audiences Risk Treatment Owner: Gaukhar Nursha, Ainur Moldakassimova |
| 2 | There is a risk of a lack of support or buy-in from key stakeholders, including government officials and community leaders. | As a result of limited awareness of project objectives, competing priorities, and varying levels of institutional capacity among government officials and community leaders | Which will impact in lower levels of engagement may slow decision-making, reduce coordination, and affect the effectiveness and sustainability of project activities | 3. OPERATIONAL (3.5. Partners’ engagement) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 To: 31-Dec-28 | Gaukhar Nursha, Ainur Moldakassimova | Risk Treatment 2.3: Build strong relationships with key stakeholders through ongoing communication and collaboration; align programme objectives with national priorities; involve stakeholders early and consistently in planning and implementation; build on findings already validated and agreed upon by national stakeholders. Risk Treatment Owner: Gaukhar Nursha, Ainur Moldakassimova Risk Treatment Owner: Gaukhar Nursha, Ainur Moldakassimova |
| 3 | There is a risk of political instability or changes in government priorities affecting funding or support. | As a result of changes in the political context, leadership transitions, or shifts in policy priorities that influence resource allocation and institutional focus | Which will impact in reduced or delayed funding and support may affect implementation timelines, stakeholder engagement, and the sustainability of project outcomes | 7. STRATEGIC (7.6. Change/turnover in government) - UNDP Risk Appetite: OPEN TO SEEKING | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 To: 31-Dec-28 | Gaukhar Nursha, Ainur Moldakassimova | Risk Treatment 3.3: Maintain flexibility and adaptability in programme design; ensure alignment with longer-term development plans; establish multi-stakeholder governance mechanisms that ensure continuity beyond political cycles. Risk Treatment Owner: Gaukhar Nursha, Ainur Moldakassimova |
| 4 | There is a risk of misinterpretation or misrepresentation of programme goals leading to misunderstandings or conflicts. | As a result of varying interpretations among stakeholders and differences in local contexts | Which will impact in reduced stakeholder trust, coordination challenges, and delays or conflicts affecting smooth implementation and achievement of results | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Jan-26 To: 31-Dec-28 | Gaukhar Nursha, Ainur Moldakassimova | Risk Treatment 4.3: Ensure clear and transparent communication about programme goals and objectives; adapt messages to local contexts; use participatory methods to foster understanding and trust among stakeholders. Risk Treatment Owner: Gaukhar Nursha, Ainur Moldakassimova |

| Portfolio/Project Title: “Challenging Harmful Attitudes and Norms for Gender Equality” (CHANGE) | Portfolio/Project Number: 01005986 | Date: 01.06.2026 |
| --- | --- | --- |
| Kyrgyzstan |  |  |

| # | Event | Cause | Impact(s) | Risk Category and Sub-category (including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (team accountable for managing the risk) | Risk Treatment and Treatment Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | There is a risk of resistance to change from individuals or groups, including representatives from the GBV, GEWE authorized state bodies entrenched in traditional gender norms. | As a result of entrenched patriarchal attitudes, existing gender discrimination and lack of awareness of gender equality benefits | Which will impact in delays or limits adoption of gender-responsive policies and practices | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 4 - Highly likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 To: 31-Dec-28 | Nurlan Bakirov, Bermet Ubaidillaeva | Risk Treatment 1.1: Engage in robust community consultations, Multidisciplinary Working Groups and wider awareness campaigns to build support and address resistance; identify and support change agents and gender champions within institutions; use tailored messaging to resonate with different audiences Risk Treatment Owner: Nurlan Bakirov, Bermet Ubaidillaeva |
| 2 | There is a risk of a lack of support or buy-in from key stakeholders, including government officials and community leaders. | As a result of limited awareness of project objectives, competing priorities, and varying levels of institutional capacity among government officials and community leaders | Which will impact in lower levels of engagement may slow decision-making, reduce coordination, and affect the effectiveness and sustainability of project activities | 3. OPERATIONAL (3.5. Partners’ engagement) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 To: 31-Dec-28 | Nurlan Bakirov, Bermet Ubaidillaeva | Risk Treatment 2.3: Build strong relationships with key stakeholders through ongoing communication and collaboration; regarding to national partners to ensure aligning with state procedures of partnership, and in line to programme objectives with national priorities; involve stakeholders early and consistently in planning and implementation; co-establish joint platforms for communication and partnership, and building on findings already validated and agreed upon by national stakeholders. Risk Treatment Owner: Nurlan Bakirov, Bermet Ubaidillaeva |
| 3 | There is a risk of political instability or changes in government priorities affecting funding or support. | As a result of changes in the political context, leadership transitions, or shifts in policy priorities that influence resource allocation and institutional focus | Which will impact in reduced or delayed funding and support may affect implementation timelines, stakeholder engagement, and the sustainability of project outcomes | 7. STRATEGIC (7.6. Change/turnover in government) - UNDP Risk Appetite: OPEN TO SEEKING | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 ToTo: 31-Dec-28 | Nurlan Bakirov, Bermet Ubaidillaeva | Risk Treatment 3.3: Maintain flexibility and adaptability in programme design; ensure alignment with longer-term development plans; establish multi-stakeholder governance mechanisms that ensure continuity beyond political cycles. Risk Treatment Owner: Nurlan Bakirov, Bermet Ubaidillaeva |
| 4 | There is a risk of misinterpretation or misrepresentation of programme goals leading to misunderstandings or conflicts. | As a result of varying interpretations among stakeholders and differences in local contexts | Which will impact in reduced stakeholder trust, coordination challenges, and delays or conflicts affecting smooth implementation and achievement of results | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Jan-26 To: 31-Dec-28 | Nurlan Bakirov, Bermet Ubaidillaeva | Risk Treatment 4.3: Ensure clear and transparent communication about programme goals and objectives; adapt messages to local contexts; use participatory methods to foster understanding and trust among stakeholders. Actively inform and engage GTG, national networks addressing GBV, gender community for open dialogues on mitigate misinterpretations. Risk Treatment Owner: Nurlan Bakirov, Bermet Ubaidillaeva |

| Portfolio/Project Title: “Challenging Harmful Attitudes and Norms for Gender Equality” (CHANGE) | Portfolio/Project Number: 01006004 | Date: 01.06.2026 |
| --- | --- | --- |
| Tajikistan |  |  |

| # | Event | Cause | Impact(s) | Risk Category and Sub-category (including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (team accountable for managing the risk) | Risk Treatment and Treatment Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | There is a risk of a lack of support or buy-in from key stakeholders, including government officials and community leaders. | As a result of limited awareness of project objectives, competing priorities, and varying levels of institutional capacity among government officials and community leaders | Which will impact in lower levels of engagement may slow decision-making, reduce coordination, and affect the effectiveness and sustainability of project activities | 3. OPERATIONAL (3.5. Partners’ engagement) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 To: 31-Dec-28 | Zarina Juraeva | Risk Treatment 2.3: Build strong relationships with key stakeholders through ongoing communication and collaboration; align programme objectives with national priorities; involve stakeholders early and consistently in planning and implementation; build on findings already validated and agreed upon by national stakeholders. Risk Treatment Owner: Zarina Juraeva Risk Treatment Owner: Zarina Juraeva |
| 2 | There is a risk of political instability or changes in government priorities affecting funding or support. | As a result of changes in the political context, leadership transitions, or shifts in policy priorities that influence resource allocation and institutional focus | Which will impact in reduced or delayed funding and support may affect implementation timelines, stakeholder engagement, and the sustainability of project outcomes | 7. STRATEGIC (7.6. Change/turnover in government) - UNDP Risk Appetite: OPEN TO SEEKING | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 To: 31-Dec-28 | Zarina Juraeva | Risk Treatment 3.3: Maintain flexibility and adaptability in programme design; ensure alignment with longer-term development plans; establish multi-stakeholder governance mechanisms that ensure continuity beyond political cycles. Risk Treatment Owner: Zarina Juraeva |
| 3 | There is a risk of misinterpretation or misrepresentation of programme goals leading to misunderstandings or conflicts. | As a result of varying interpretations among stakeholders and differences in local contexts | Which will impact in reduced stakeholder trust, coordination challenges, and delays or conflicts affecting smooth implementation and achievement of results | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Jan-26 To: 31-Dec-28 | Zarina Juraeva | Risk Treatment 4.3: Ensure clear and transparent communication about programme goals and objectives; adapt messages to local contexts; use participatory methods to foster understanding and trust among stakeholders. Risk Treatment Owner: Zarina Juraeva |

| Project Title: “Challenging Harmful Attitudes and Norms for Gender Equality” (CHANGE) | Project Number: | Date: May 2, 2026 |
| --- | --- | --- |
| Turkmenistan |  |  |

| # | Event | Cause | Impact(s) | Risk Category and Sub-category (including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (team accountable for managing the risk) | Risk Treatment and Treatment Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | There is a risk of resistance to change from individuals or groups, including representatives from the state bodies entrenched in traditional gender norms. | Lack of understanding of gender norms, and readiness to make changes | When influential stakeholders resist change, project components—especially those related to gender equality—may face delays, reduced cooperation, or even active obstruction. This can limit the project’s ability to meet its objectives within planned timelines. | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | 4 - Highly likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 To: 31-Dec-28 | Lachin Artykova | Engage in robust community consultations and awareness campaigns to build support and address resistance; identify and support change agents within institutions resonate with different audiences.; use tailored messaging to |

| Portfolio/Project Title: “Challenging Harmful Attitudes and Norms for Gender Equality” (CHANGE) |  |  |  |  |  | Portfolio/Project Number: 01005958 |  | Date: 01.06.2026 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UZBEKISTAN |  |  |  |  |  |  |  |  |
| # | Event | Cause | Impact(s) | Risk Category and Sub-category including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (team accountable for managing the risk) | Risk Treatment and Treatment Owner |
| 1 | There is a risk of resistance to change from individuals or groups, including representatives from the state bodies entrenched in traditional gender norms. | As a result of entrenched patriarchal attitudes and lack of awareness of gender equality benefits | Which will impact in delays or limits adoption of gender-responsive policies and practices | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 4 - Highly likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 To: 31-Dec-28 | Gulnoza Akhmedova | Risk Treatment 1.1: Engage in robust community consultations and awareness campaigns to build support and address resistance; identify and support change agents within institutions; use tailored messaging to resonate with different audiences. Risk Treatment Owner: Gulnoza Akhmedova |
| 2 | There is a risk of a lack of support or buy-in from key stakeholders, including government officials and community leaders. | As a result of misalignment between programme objectives and national priorities, insufficient early engagement and consultation, weak communication, competing institutional interests, and limited awareness or ownership of the project’s goals among government officials and community leaders. | Lack of stakeholder buy-in can lead to delayed or weakened implementation of activities, limited policy uptake, and reduced overall effectiveness and sustainability of the CHANGE Project’s interventions. | 3. OPERATIONAL (3.5. Partners’ engagement) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 To: 31-Dec-28 | Gulnoza Akhmedova | Risk Treatment 2.1: Ensure regular stakeholder engagement, consultation, and communication with government counterparts and community leaders to strengthen ownership and support for project activities. Risk Treatment 2.2: Build strong relationships with key stakeholders through ongoing communication and collaboration; align programme objectives with national priorities; involve stakeholders early and consistently in planning and implementation; build on findings already validated and agreed upon by national stakeholders. Risk Treatment Owner: Gulnoza Akhmedova |
| 3 | There is a risk of political instability or changes in government priorities affecting funding or support. | As a result of changes in the political context, shifts in political leadership, evolving policy agendas, economic pressures, and external or regional factors that redirect government focus and resources away from gender equality initiatives. | Which will lead to disruptions in programme implementation, reduced funding or support, weakened policy commitment, and delays in achieving the project’s intended results. | 7. STRATEGIC (7.6. Change/turnover in government) - UNDP Risk Appetite: OPEN TO SEEKING | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jan-26 To: 31-Dec-28 | Gulnoza Akhmedova | Risk Treatment 3.1: Maintain regular engagement with government stakeholders, align project activities with national priorities, and diversify partnerships to sustain institutional support despite political or policy changes. Risk Treatment 3.2: Maintain flexibility and adaptability in programme design; ensure alignment with longer-term development plans; establish multi-stakeholder governance mechanisms that ensure continuity beyond political cycles. Risk Treatment Owner: Gulnoza Akhmedova |
| 4 | Pushback against women's rights organisations and activists, including harassment, defamation, or legal challenges aimed at impeding their advocacy efforts and stifling progress towards gender equality. Lack of funding for CSOs and CSO-run crisis centres affects regularity and consistency in their work supporting victims of violence. | As a result of varying entrenched gender norms and backlash against equality efforts, restrictive civic space and legal environments, competing political priorities, and low or unstable financial support for civil society initiatives. | Pushback and underfunding of women’s rights organisations can weaken service delivery for survivors, disrupt advocacy efforts, and significantly slow progress in preventing and responding to gender-based violence under the CHANGE Project. | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Highly likely Impact: 3 - Extreme Risk level: Extreme (equates to a risk appetite of EXPLORATORY) | From: 01-Jan-26 To: 31-Dec-28 | Gulnoza Akhmedova | Risk Treatment 4.1: Mitigation requires strengthening stakeholder engagement, coalition-building, and culturally sensitive advocacy to counter backlash and shift harmful gender norms, while supporting CSOs to operate effectively within restrictive environments through adaptive and risk-informed approaches. It also involves diversifying and stabilizing funding, investing in organizational capacity, and applying flexible, context-sensitive programming to enhance resilience and sustainability. Risk Treatment 4.2: Advocate robust security measures to protect activists and organisations; build alliances with supportive stakeholders; strengthen legal and institutional protection mechanisms; diversify funding sources and promote pooled funding modalities for CSOs. Risk Treatment Owner: Gulnoza Akhmedova |
| 5 | Limited access to marginalised or remote communities, hindering outreach efforts. | Limited access to marginalised or remote communities is caused by geographic isolation, weak infrastructure and service networks, limited local partnerships, and sociocultural barriers that restrict engagement and outreach | Limited access to marginalised or remote communities can lead to reduced outreach and participation, leaving vulnerable groups underserved and decreasing the overall effectiveness and inclusiveness of the CHANGE Project’s interventions. | 3. OPERATIONAL (3.5. Partners’ engagement) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 3 - Highly likely Impact: 3 - Extreme Risk level: Extreme (equates to a risk appetite of EXPLORATORY) | From: 01-Jan-26 To: 31-Dec-28 | Gulnoza Akhmedova | Risk Treatment 5.1: Implement innovative strategies such as mobile outreach teams or community liaisons; partner with local organisations that have established trust; ensure logistical planning is tailored to reach the most remote areas. |

Annex 5. Steering Committee Terms of Reference

EU–UN Multi-Country Programme

“Challenging Harmful Attitudes and Norms for Gender Equality (CHANGE)”

Overall responsibilities:

The SC serves as the primary governance body of the EU–UN Multi-Country Programme (MCP), providing strategic direction, oversight, and high-level decision-making throughout its implementation. The SC ensures that the MCP aligns with the priorities of the participating Central Asian governments, the mandates of the UN agencies involved, and the expectations of the European Union.

Permanent members of the SC include:

- Representative of the European Union Delegation in Kazakhstan (co-chair)

- Representative of the European Union Delegation in the Kyrgyz Republic

- Representative of the European Union Delegation in Tajikistan

- Representative of the European Union Delegation in Turkmenistan

- Representative of the European Union Delegation in Uzbekistan

- Representative of the Ministry of Foreign Affairs of the Republic of Kazakhstan (co-chair)

- Representative of the UN Resident Coordinator Office in Kazakhstan (co-chair)

- Representative of UNDP Kazakhstan

- Representative of UNFPA Kazakhstan

- Representative of UN Women Kazakhstan

Non-permanent members of the SC, to be invited on an ad-hoc basis, when relevant:

- Non-UN implementing partners or stakeholders

The SC will meet at least once a year.

In case a consensus cannot be reached, final decision shall rest with the Steering Committee co-chairs, the Representative of the European Union Delegation in Kazakhstan, the UN Resident Coordinator in Kazakhstan and the representative of the Ministry of Foreign Affairs of the Republic of Kazakhstan.

Specific responsibilities of the SC:

- Review and endorse the RRF, annual work plans, and budgets;

- Assess overall programme progress against planned results, ensure alignment with strategic priorities, and monitor compliance with donor requirements;

- Examine consolidated narrative and financial reports;

- Address strategic implementation challenges or external risks affecting the programme, assess risk management measures, and provide direction on necessary adjustments;

- Ensure coherence, complementarity, and coordination across countries and agencies;

- Endorse any substantive modifications to the RRF, work plan, and budget allocations to ensure continued relevance and effectiveness of the programme;

- Oversee the final end or project evaluation process, approve its terms of reference, and review its findings;

- Endorse disbursements to PUNOs, in line with the budget set forth in the Joint Programme Document.

UNDP Kazakhstan will serve as the Secretariat to the Steering Committee. In this role, UNDP Kazakhstan is responsible for preparing and distributing meeting materials, documenting decisions, coordinating across PUNOs, and consolidating programme-level reporting.

The Gender Marker measures how much a project invests in gender equality and women’s empowerment. Select one for each output: GEN3 (Gender equality as a principle objective); GEN2 (Gender equality as a significant objective); GEN1 (Limited contribution to gender equality); GEN0 (No contribution to gender quality)

2025 Global Gender Gap Report, World Economic Forum; https://reports.weforum.org/docs/WEF_GGGR_2025.pdf

Situational Analysis of Men and Gender Equality in the Central Asia Region, a report prepared in 2022 for the UNFPA Country Office in the Republic of Kazakhstan under the Spotlight Initiative Regional Programme for Central Asia and Afghanistan.

Progress at risk: gender equality in COVID-19 response in Europe and Central Asia, UNDP, 2022

https://www.unicef.org/kazakhstan/en/reports/knowledge-attitudes-and-practices-survey-violence-against-children-families-kazakhstan

https://www.unicef.org/media/92376/file/Child-Protection-Gender-Dimensions-of-VACAG-2021.pdf

UN data, 2023: https://kazakhstan.un.org/en/238825-uniting-progress-eu-and-un-support-launch-central-asian-alliance-end-gender-based-violence.

https://www.gov.kz/memleket/entities/qriim/press/news/details/544741?lang=ru.

https://www.hrw.org/ru/world-report/2024/country-chapters/tajikista.

https://documents.un.org/api/symbol/access?s=CEDAW%2FC%2FUZB%2FFCO%2F6&l=E.

Women, Peace and Security Index, 2023/2024, Georgetown Institute for Women, Peace and Security.

Data from Ministry of Internal Affairs of the Kyrgyz Republic.

National Survey on the Health and Status of a Woman in the Family, 2022.

https://www.aljazeera.com/features/2024/5/1/in-kazakstan-a-storm-over-domestic-violence-after-minister-killed-wife

https://www.reuters.com/world/europe/kyrgyzstan-adopts-law-targeting-foreign-funded-ngos-2024-04-02/.

https://www.ohchr.org/en/press-releases/2024/03/tajikistan-un-expert-criticises-dissolution-700-ngos.

Turning a Blind Eye: Are women represented in politics in Kazakhstan? UN Women

World Bank Gender Data Portal: https://genderdata.worldbank.org/en/economies/kazakhstan

Sample survey on violence against women in Kazakhstan, UN Women, 2018

Data from General Prosecutors Office of the Republic of Kazakhstan

2023 Social Gender Norms Index, UNDP

UN Women Data Hub: https://data.unwomen.org/country/kazakhstan

Country Gender Equality Profile Kyrgyzstan, UN Women, 2025

2023 Social Gender Norms Index, UNDP

World Bank Gender Data Portal: https://genderdata.worldbank.org/en/economies/kyrgyz-republic

https://www.equalfuture-eurasia.org/womens-representation-in-politics-and-public-administration/kyrgyzstan

https://www.weforum.org/stories/2024/06/gender-equality-women-hold-cabinet-positions-2024/

World Bank Gender Data Portal: https://liveprod.worldbank.org/en/economies/tajikistan

https://www.adb.org/sites/default/files/institutional-document/185615/tajikistan-cga.pdf

https://data.unwomen.org/country/turkmenistan.

https://turkmenistan.unfpa.org/sites/default/files/pub-pdf/report_health_and_status_of_a_woman_in_the_family_in_turkmenistan.pdf.

https://www.equalfuture-eurasia.org/womens-representation-in-politics-and-public-administration/turkmenistan

World Bank Gender Data Portal: https://genderdata.worldbank.org/en/economies/turkmenistan.

https://www.gazeta.uz/en/2024/11/26/domestic-violence/

World Bank, Gender Data Portal: https://genderdata.worldbank.org/en/economies/uzbekistan

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards.  Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.

Optional, if needed

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a project budget affecting the scope (outputs), completion date, or total estimated project costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner