Building an Inclusive and Resilient Economy for All in the Gambia

Portfolio Document

Please use the

Document GUIDANCE

for instructions on how to complete this document.

UNDP’s Effectiveness Group (BPPS) is mandated to serve as the custodian of UNDP’s prescriptive content on Programme, Portfolio and Project Management. Any changes to policies or procedures which fall within PPM, are updated by BPPS/EfG.

December 19, 2023

PORTFOLIO DOCUMENT

[Country name, or Global/Regional Portfolio]

Portfolio Title: Building an Inclusive and Resilient Economy for All in the Gambia

Portfolio Number:

Start Date: 1st January 2026  End Date: 31st December 2030LPAC Meeting date: 9 December 2025

Summary Description (500 characters limit)

The UNDP Gambia Inclusive Growth Portfolio is designed to catalyze a shift toward an economy that is inclusive, diversified, and climate-resilient; one which creates decent work, empowers women and youth, and strengthens institutions for sustainable prosperity. This portfolio is designed as a sequenced and adaptive system of change that deliberately prioritizes, tests, and scales a small number of catalytic interventions over time, using learning and evidence to guide course correction and investment decisions. The portfolio acknowledges that The Gambia’s development challenges including low productivity, high informality, limited fiscal space, and growing climate stress are profoundly interconnected. Addressing them with individual, siloed projects is no longer an option. Rather these development challenges require a systems approach that links economic, governance, and environmental transformations into one integrated framework. Through stakeholders’ coordination, learning, and co-creation, the portfolio helps national and local actors test new solutions, scale what works, and build a more responsive development system. At the heart of the portfolio is a commitment to bridging the macro–meso–micro layers of transformation. This entails integrating national policy and financing frameworks (macro) with institutional delivery systems and local economic development (meso), while empowering MSMEs, cooperatives, and households to participate in inclusive markets (micro). This alignment aims to strengthen feedback between local innovation and national policy learning, ensuring that transformation is both grounded and scalable. The portfolio is co-created and co-led by the Government of The Gambia, under the leadership of the Ministry of Trade, Industry, Regional; Integration and Employment (MoTIE) in partnership with the UNDP Country Office and the UNDP Regional Service Centre for Africa. Core collaborators include the Ministries of Youth and Sports (MoYS); Higher Education (MOHERST); Public Service (MoPS); Finance and Economic Affairs (MOFEA); Environment, Climate Change and Natural Resources (MECCNAR); Agriculture (MoA); and Gender, Children, and Social Welfare (MoGCSW); the Gambia Chamber of Commerce and Industry (GCCI); women’s business and youth networks; and UN partners contributing to the UNSDCF outcomes on Green, Resilient and Inclusive Livelihoods and Good Governance and Human Development. By connecting national ambitions with local action and international partnerships, the portfolio seeks to not only accelerate growth but make it more inclusive, greener, and resilient for generations of Gambians to come.

PORTFOLIO OVERVIEW

| Contributing UNSDCF/CPD or RPD or SP Outcome(s): Deliver Portfolio Output(s): |  | Total resources required: |  |  |
| --- | --- | --- | --- | --- |
|  |  | Total resources allocated: |  |  |
|  |  |  | UNDP TRAC: |  |
|  |  |  | Donor 1: |  |
|  |  |  | Donor 2: |  |
|  |  |  | Government: |  |
|  |  |  | In-Kind: |  |
|  |  | Unfunded: |  |  |

| Strategic Partners Implementing Partner(s) Name of Organizations Name Organization UNDP : Name Country Office SIGNATORIES |  |
| --- | --- |
| Implementing Partner(s) per Multiyear Work Plan (MYWP) 1 signature here Print Name: Date | Government Development Coordination Authority signature here Print Name: Date |
| Implementing Partner for MYWP 2 signature here Print Name: Date | UNDP signature here Print Name: Date |
| Implementing Partner for MYWP 3 signature here Print Name: Date |  |

1. Theory of Change

This section presents a summary of the justification, the hypothesis, and underlying logic of portfolio design and outlines what UNDP (together with its partners) will do to address the development challenge(s). It is divided into three discrete parts that work together to provide a comprehensive summary.

Development Challenge (500 characters limit) Growth in The Gambia has largely been positive in recent years. Since the transition to democrtatic rule in 2016/17, GDP growth has averaged above 5% except during the Covid-19 Pandemic. This compares favorably with the period 2007-2016, when growth averaged 3.6% annually, as well as with the 3-4% average growth for Sub-Saharan Africa. Yet, this growth has not translated into broad-based opportunity. In 2020, poverty stood at 53.4% with significant rural (76%) and urban (34%) disparities. With a Gini Coefficient of 38.78%, The Gambia ranks among the highest in terms of inequality in the region. For Gambia, this reflects unequal access to services and opportunities – especially among the youth, women, and marginalized regions. Job creation in the dominant sectors—agriculture, tourism, and trade—remains limited due to persistently low productivity and weak value addition. The country has experienced significant deindustrialization over three decades: manufacturing share of GDP declined from 8.5% in 1995 to 4.8% by 2024, exacerbating unemployment. Micro, small and medium-sized enterprises contribute approximately 20% of Gambia’s GDP, and are key drivers of job creation, business innovation, and inclusive growth, but are constrained by geographic reach, infrastructure, technology, regulatory environment, etc. This narrow growth base leaves the economy highly exposed to external and climatic shocks. To unlock its manufacturing potential, The Gambia needs systematic reforms in education, finance, governance, and digital ecosystems. Data shows that four out of every five Gambians work in informal or subsistence activities with little access to credit, skills, technology, or markets. The informal economy—equal to almost 40 percent of GDP—provides livelihoods but few pathways toward mobility as well as limiting tax revenue, access to finance, and innovation uptake. Youth face particularly acute barriers: only 38 percent participate in the labour market, while 40 percent are not in employment, education, or training (NEET), and vocational and technical qualifications remain scarce. This mismatch between skills and labour-demand in productive sectors feeds high unemployment, low earnings, and migration pressures. Women continue to be largely limited to agriculture and the informal sector and face significant barriers in access to land, finances and other productive assets. These vulnerabilities cut across the macro–meso–micro levels of the system. At the macro level, fiscal constraints, debt servicing, and policy overlaps and duplications restrict the ability to invest in long-term transformation. At the meso level, gaps between national and local governance weaken coordination, distort resource allocation, and limit coherent delivery, while TVET and financial services are insufficiently matching market demands. At the micro level, informality, under-skilling, limited finance trap people in a cycle of low productivity and reduced resilience. Together, these dynamics reinforce a high-risk, low-opportunity equilibrium. Climate and environmental stress amplify this fragility and compounded structural vulnerabilities of the economy and livelihoods. Farming and fishing communities face increasingly frequent floods, droughts, and coastal erosion that erode income, assets, and natural capital. Forest loss—from 4,100 square km in 1990 to about 2,400 in 2021—signals unsustainable resource use and rising ecological vulnerability. The combined pressures of climate change, economic precarity, unsustainable practices and demographic growth threaten both livelihoods and national stability. Gambian policymakers therefore recognize the need for new pathways that reconcile economic growth with environmental stewardship. Yet the foundations for transformation are emerging. The country’s strengths are: Strategic location on trans-Sahara logistics corridor; membership of ECOWAS and AfCFTA; youthful population (65% under 25); macroeconomic stability (inflation <5% in 2024). The Recovery-focused National Development Plan (2023–2027) prioritizes green recovery, economic diversification, and youth and women’s empowerment. The UNSDCF (2024–2028) advances green and inclusive livelihoods alongside governance and human development, while the UNDP Country Programme (2024–2028) aligns these priorities through its pillars on inclusive growth, accountable governance, and climate resilience. The challenge, therefore, is not only to grow faster but to grow differently by expanding productivity in job-rich sectors, strengthening value chains, equipping people with the skills to participate in a changing economy, and aligning national policy with local innovation and climate-resilient systems in a holistic and integrated manner.

Description of Change (500 characters limit) UNDP The Gambia’s Inclusive Growth Portfolio drives a structural shift from fragmented and vulnerability-prone systems toward an inclusive, diversified, and climate-resilient economy. It reframes how growth is generated by linking productivity, resilience, and inclusion so that economic opportunities expand for the bottom 40 percent of Gambians, especially youth and women. The core premise is that transformation occurs when value chains become more competitive, institutions more predictable, and communities more resilient to shocks. Only by linking macroeconomic stability, institutional capability, enterprise development, and resilient ecosystems can The Gambia transition from vulnerability to an inclusive, diversified, and climate-resilient economy. It is envisaged that The Gambia will have evolved from a narrowly focused economy into a regional hub for agro-processing, light manufacturing, fisheries and ICT services, underpinned by advanced productivity, strengthened value-chain linkages, diversified markets, empowered human capital and a green, digitally enabled infrastructure. The portfolio’s Theory of Change is built around three interconnected systems: inclusive economic development, accountable governance, and economic and environmental resilience. These systems reinforce one another: inclusive value chains require effective institutions; governance is enhanced in conditions when livelihoods improve; and resilience depends on both institutional capability and diversified economic activity. The portfolio activates these feedback loops to shift the economy from low-productivity informality toward higher-value, job-rich sectors compatible with green and blue transformation. Systems Outcomes: Change is initiated by strengthening linkages across macro, meso, and micro levels: • Macro: national policy relevance and effectiveness, and regional trade integration (including AfCFTA) that create predictable rules and expand market opportunities. • Meso: institutional delivery systems, local governments, and economic infrastructure that translate national ambition into functioning markets and services at the local level. • Micro: MSMEs, cooperatives, youth and women entrepreneurs, and households whose innovation drives productivity and value addition. The portfolio acts as an integrator that connects these layers through adaptive experimentation, continuous learning, and co-creation. By operating as a learning system, it generates real-time evidence that informs policy reform, public investment choices, and the scaling of successful local solutions. Mechanisms of Change: Transformation materializes through three mutually reinforcing shifts: - Inclusive Value Chains & Green Jobs — upgrading agrifood, tourism, light manufacturing, blue, and circular-economy value chains; improving access to finance, skills, markets, and digital infrastructure; and linking MSMEs to domestic and regional opportunities under AfCFTA, underpinned by large-scale skilling and re-skilling. - Governance & Enabling Systems for MSME development — strengthening enabling environment for private sector development, data-driven planning, decentralization and accountability mechanisms that make growth more inclusive and predictable. - Resilient Livelihoods & Sustainable Infrastructure — expanding renewable energy and affordable and reliable energy, nature-based solutions; enabling climate resilience; strengthening social protection; and building local systems that protect livelihoods and ecosystems. These shifts generate portfolio momentum: as enterprises adopt green and digital practices, they stimulate market demand and fiscal space; as institutions coordinate more effectively, they enable investment; as communities build resilience, they unlock new green and blue-economy opportunities. Each shift amplifies the others, accelerating system transformation faster than isolated projects. Sustaining Transformation The approach assumes sustained government commitment, private-sector engagement, and donor support for integrated and adaptive financing models. Key risks ranging from fiscal pressures and coordination gaps to climate shocks are mitigated through continuous sensemaking, a live risk register, and UNDP’s convening role as systems integrator across national and local actors.

UNDP portfolio contribution (500 characters limit) The UNDP Gambia Inclusive Growth Portfolio turns UNDP’s global commitment to “connected systems for connected lives” into action. It directly contributes to the UNSDCF’s two national priorities: Green, Resilient, and Inclusive Livelihoods and Good Governance, Human Development, and Rule of Law. Within UNDP’s Country Programme (2024–2028), the portfolio brings together three outcomes, namely, climate and environmental resilience, accountable governance, and inclusive and sustainable growth into one adaptive framework that learns and adapts as it delivers. At the regional and global level, the portfolio advances the goals of the Regional Programme for Africa and the UNDP Strategic Plan (2026–2029): to foster resilient economies, empower people, and strengthen governance systems that can adapt to uncertainty. Also relevant are the SDGs and Agenda 2063. It embodies UNDP’s shift from managing projects to managing systems of change. UNDP’s distinctive value lies in its ability to connect what was previously done in silos. It bridges policy and finance at the national level, institutional delivery at the local level, and enterprise innovation at the community level. This integrator role - part convener, part catalyst, part translator - turns fragmented interventions into a coherent platform for transformation. By linking governance reform, economic diversification, and environmental sustainability, UNDP helps partners work as one system rather than as parallel efforts. In The Gambia, this means aligning investments and policies around a simple but powerful idea: that every young person, every small business, and every community should have the chance to take part in and benefit from the transition to a green, inclusive, and regionally connected economy. The portfolio complements and amplifies partner initiatives such as the AfDB’s Youth Employment and Entrepreneurship Programme, the EU’s GREAT Initiative, and the World Bank’s Climate-Smart Agriculture and MSME Resilience Projects. What UNDP adds is the connection logic: the learning architecture that allows these interventions to reinforce one another and plug into regional opportunities like the AfCFTA. Through its adaptive design, the portfolio turns UNDP’s Country Programme into a dynamic system of learning and transformation. Insights from local pilots, quarterly sensemaking sessions, and annual reflection cycles flow directly into national policy dialogue, budget priorities, and programme design. The result is a dynamic feedback loop between experimentation and action, between local innovation and national reform. To deepen this contribution, the portfolio focuses on four key learning questions: - How can The Gambia shift from fragmented, short-term interventions to sustained, inclusive, and climate-smart value chains linked to regional trade under the AfCFTA? - What policies and institutional arrangements best connect governance reform, social protection, and private-sector growth? - How can digital and green innovation be designed to genuinely reach and empower women, youth, and informal enterprises? - What collaborative models can sustain adaptive management and inter-cluster learning in the Gambian context? The answers will inform future iterations of the Portfolio and Country Programmes, feed into regional portfolio learning across Africa, and enrich UNDP’s global agenda on structural transformation and systems approaches. In this way, The Gambia’s experience will not only drive national progress, it will also help UNDP refine how it learns to navigate complexity worldwide.

Please use Annex 8 “Theory of Change” for the full narrative and diagram (as needed).

2.	Portfolio Results Framework

This section defines the portfolio’s expected results and how they help achieve UNSDCF/CPD outcomes or the Regional Programme Development outcomes of the SP outputs/outcomes.

PORTFOLIO RESULTS FRAMEWORK

| Portfolio Name: One Gambia: Building an Inclusive and Resilient Economy for All | Quantum Portfolio No. : |
| --- | --- |

| Portfolio Intent (What is the portfolio working towards; what is its “North Star” statement?) max.100 characters By 2035, The Gambia will have evolved from a narrowly focused economy into a regional hub for agro-processing, light manufacturing, fisheries and ICT services, underpinned by advanced productivity, strengthened value-chain linkages, diversified markets, empowered human capital and a green, digitally enabled infrastructure. |  | Portfolio Contribution to CPD (incl. UNSCDF/CPD Outcome & CPD Output, to be updated as portfolio evolves) max. 100 characters |
| --- | --- | --- |
| Transforming The Gambia’s systems for inclusive, sustainable, and resilient growth. |  | Contributes to CPD Outcomes 1.1, 2.1 & 2.2 on resilience, governance, and inclusive growth. |

| Portfolio Results | Are we seeing progress, where and how? | Indicator | Baseline |  | End Target |  | Means of Verification |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year | Value | Year |  |
| System Change: By 2030, The Gambia transitions from unequal, fragmented, and climate-vulnerable systems to an inclusive, diversified, and climate-resilient economy powered by productive enterprises, credible institutions, and expanded opportunities for the bottom 40 percent. The shift is from a low-productivity equilibrium characterized by informality, weak value chains, and limited public investment to a coordinated system where economic, governance, and climate subsystems reinforce one another. Sustained transformation begins locally, where communities, MSMEs, cooperatives, and local governments drive innovation in agrifood, blue, and emerging green value chains. These locally anchored changes scale nationally when supported by coherent policy, predictable regulation, climate-smart investment, and strengthened public finance systems. By intentionally bridging macro–meso–micro layers, the portfolio improves the flows of knowledge, finance, and accountability that enable enterprises to upgrade, diversify, and participate in higher-value markets including through AfCFTA. The mechanism of change is rooted in strengthening feedback loops: local experimentation generates insights that inform national policy; institutional reforms expand market access and reduce transaction costs; and climate-resilient infrastructure enables communities and value chains to adapt, invest, and grow. As governance systems become more responsive and enterprises more competitive, new economic opportunities emerge for youth and women, creating a virtuous cycle of productivity, resilience, and inclusion. Together, these dynamics transform The Gambia from a vulnerability-prone economy into an adaptive, opportunity-rich system capable of sustaining green, inclusive, and climate-resilient growth. . (As observed in shifts that the Theory of Change has identified as keys to systemic transformation.) | - Shift (Output): From fragmented, informal, and low-productivity livelihoods that remain disconnected from skills, finance, markets, and value addition, limiting youth and women to subsistence activities vulnerable to shocks To diversified, competitive, and climate-smart value chains where MSMEs, cooperatives, youth, and women entrepreneurs upgrade their capabilities, access finance and technology, and participate in higher-value production and trade—generating decent work and driving green and blue economic transformation. | - Percentage increase in total factor productivity (TFP) among supported MSMEs and producer groups in agriculture, manufacturing, and fisheries, disaggregated by sector, sex, and age. - Percentage increase in domestic value retention within priority value chains supported - Percentage increase in the export earnings of supported priority value chains. - Percentage of youth- and women-led enterprises in priority value chains with improved skills and profitability.. - # of youth- and women-led enterprises in priority value chains benefitting from improved storage, processing, quality assurance, and market-facilitation infrastructure enabling value addition and competitive market participation. - # of supported MSMEs, cooperatives, and small producers within selected value chains integrated into domestic, regional (AfCFTA), or global value chains (disaggregated by sex and age) | 0 30 TBD TBD 0 0 | 2025 2025 2025 2025 2025 2025 | 25% 50 TBD TBD TBD TBD | 2030 2030 2030 2030 2030 2030 |  |
|  |  | - % increase in the number of youth and women employed in priority value chains (formal or semi-formal). | TBD | 2026 | TBD | 2030 |  |
|  |  |  | TBD | 2026 | TBD | 2030 |  |
|  |  | - % increase in the number of MSMEs and cooperatives participating in higher-value segments of priority value chains (agri-food, fisheries, blue/circular economy). |  |  |  |  |  |
|  | - Shift (Output): From siloed, under-resourced, and weakly coordinated institutions that limit participation, accountability, market connectivity, creating high transaction costs for citizens and enterprises To accountable, data-driven, and participatory governance systems across national and local levels that coordinate policy, planning, and service delivery; enable inclusive markets; strengthen decentralization; and create predictable, transparent conditions for investment, enterprise growth, and social protection. | - Number of policies, strategies, or regulatory frameworks revised, developed,, adopted, and implemented to support inclusive value chain and MSME development. - # of operational digital governance systems and data platforms, particularly at decentralized level, that improve licensing, compliance, trade facilitation, MSME data availability, or aid coordination. - # of functioning institutional mechanisms, stakeholder platforms and systems, that support inclusive private sector development. - Percentage of Local Government Authorities (LGAs) supported to integrate value chains and MSME development into local development planning and budgets). | 4 1 2 0 | 2025 2025 2025 2025 | 7 3 TBD 50 | 2030 2030 2030 2030 |  |
|  | - Shift (Output): From vulnerable communities and degraded ecosystems exposed to recurrent climate shocks, lacking the sustainable infrastructure, clean energy, and risk-management systems needed to protect livelihoods, food systems, and local economies To resilient, adaptive communities and ecosystems supported by renewable energy, climate-smart infrastructure, early warning and risk-finance systems, and national–local institutions that mobilize and manage climate finance . | - Percentage of supported households, MSMEs and producer groups adopting climate-smart production, processing, or livelihood practices in priority value chains, disaggregated by sex, age, and disability status. - # of MSMEs benefitting from green credit / climate-finance instruments to adopt climate-smart, efficient technologies and sustainable practices. - Percentage of enterpreneurs covered by resilience strengthening social protection mechanisms (e.g., insurance coverage or anticipatory early‑warning payouts) that mitigate climate-related risks. - Percentage of communities with reliable access to basic socio-economic services (water, electricity, and community facilities) by 2028. | TBD TBD (NEA) 0 0 | 2026 2025 2025 2025 | 20 TBD TBD 75 | 2030 2030 2030 2028 |  |
|  |  | - # of climate-resilient and sustainable community-managed infrastructure assets (e.g., water systems, coastal protection, eco-processing facilities) built or rehabilitated under integrated resilience plans | TBD | 2025 | TBD | 2030 |  |
|  |  |  | TBD | 2026 | TBD | 2030 |  |
| Portfolio Momentum: Portfolio momentum emerges from the reinforcing feedback among local innovation, accountable governance, and climate resilience. As communities and MSMEs generate inclusive growth, they expand the fiscal and political space for responsive governance; stronger institutions, in turn, channel resources and trust back into local systems that invest in green and resilient livelihoods. Climate finance and digital innovation act as accelerators, converting adaptation and inclusion into new investment opportunities. Together, these dynamics create a self-sustaining cycle of trust, investment, and learning, driving transformation faster than any single intervention could achieve. Momentum is reinforced across the macro–meso–micro linkages, as national reforms unlock local investment, local innovation informs policy adaptation, and communities demonstrate resilience that attracts broader financing and export growth. (Underlying momentum on key dynamics central to the success of the portfolio.) | - Momentum: Increased policy coherence, institutional alignment and coordination/collaboration, transparent data driven governance to strengthen accountability in support of youth and women led MSME/Value Chain development. | - # of joint policy, planning, coordination mechanisms/ platforms established/ activated / strengthened that align policy, economic, and climate resilience priorities across public sectors in support of MSMEs / Value Chains at centralized and decentralized levels of governance. | 0 | 2025 | TBD | 2030 | semi-annual Portfolio Momentum Report approved by the Portfolio Board |
|  | - Momentum: Youth- and women-led MSMEs innovate, expand adoption of green and digital practices, leverage financing and build partnerships contributing to decent job and sustained incomes thus reducing exclusion. | - Number of women- and youth-led enterprises actively engaged in value chain partnerships, innovation ecosystems, or business alliances that mobilize finance, knowledge, and market opportunities. | TBD | 2026 | TBD | 2030 | semi-annual Portfolio Momentum Report approved by the Portfolio Board |
|  | - Momentum: Confidence and resilience grow as climate investments, sustainable infrastructure, and adaptive practices reinforce livelihoods, attract funding, and strengthen ecosystem services. |  |  |  |  |  | semi-annual Portfolio Momentum Report approved by the Portfolio Board |
|  |  | - Volume of additional public and private finance leveraged for value chain/ MSME development (beyond baseline ODA) | TBD | 2026 | TBD | 2030 |  |
|  |  | - % of MSMEs adopting green/digital technologies that report increased profitability or market access after two years | 0 | 2025 | 25 | 2030 |  |
|  |  | - % of communities reporting improved resilience to climate and economic shocks (measured through household income stability or reduced losses) | 0 | 2025 | 20 | 2030 |  |
| Portfolio Learning2: Building actionable know-how in enterprise innovation, participatory governance, and climate resilience by embedding continuous sensemaking, reflection, and adaptation across teams and partners ensuring decisions, investments, and policies evolve in real time to sustain inclusive, diversified, and climate-resilient growth. (New know how instrumental to the success of the portfolio.) | In policy area Learning how integrated policy design, evidence, and real-time experimentation can align economic, governance, and climate objectives, accelerating inclusive growth and resilience through adaptive policy and investment decisions. | semi-annual Portfolio Momentum Report approved by the Portfolio Board | 0 | 2026 | 10 | 2030 |  |
|  | System transformation Learning how inclusive value chains, accountable governance, and green infrastructure interact across macro, meso, and micro levels to generate reinforcing feedback loops that sustain jobs, trust, and resilience, transforming isolated successes into system-wide change. | semi-annual Portfolio Momentum Report approved by the Portfolio Board | 0 | 2026 | 10 | 2030 |  |
|  | Portfolio adaptation Strengthening collective capability to sense, interpret, and respond to emerging trends through regular sensemaking cycles, adaptive workplans, and continuous partner learning ensuring that insights translate swiftly into course correction and innovation across the portfolio. | semi-annual Portfolio Momentum Report approved by the Portfolio Board | 0 | 2026 | 10 | 2030 |  |

3.	Monitoring, Evaluation & Learning

This section outlines the monitoring, evaluation, and learning (MEL) processes applicable to the portfolio that help support real-time course correction and portfolio impact.

MEL activities: The portfolio MEL process is structured around these key activities:

| Activity | Purpose & summary | Expected Outcomes |
| --- | --- | --- |
| Inception Phase (6 months) | - Aligns actors, maps ongoing initiatives, establishes baselines, and develops the first learning and resource mobilization cycle. - Identifies priority value chains based on detailed assessments of existing and potential value chains. - The inception phase will establish the portfolio’s governance, learning systems, and intervention prioritisation, creating the foundation for adaptive delivery and evidence-based scaling. | - Inception Report with baselines, risk matrix, and learning agenda - Socialized and co-owned portfolio architecture |
| Sensemaking workshop (1-3 days) | - Biannual strategic reflection sessions reviewing system change signals, testing ToC assumptions, and integrating evidence from national and local partners. | - Updated ToC and Results Framework - Adjusted workplans and learning questions - Policy feedback synthesized |
| Portfolio review (Quarterly, 2 - 4 hours) | - Structured internal reviews to assess alignment of projects and clusters, identify synergies, and strengthen adaptive implementation. | - Updated progress reports - Cross-team learning captured - Risks addressed promptly |
| Team check-in (Biweekly, 1-2 hours) | - Informal management meetings to review operations, track bottlenecks, and maintain communication and morale | - Timely decisions - Smooth coordination |
| Adaptation | - Follow each MEL activity to ensure learnings inform revisions to strategy, partnerships, and implementation. - Documented in a “Change Log”. | - Recorded adaptive actions - Living documentation of portfolio evolution |

MEL frequencies: The portfolio MEL key activities operate at these frequencies:

| Activity | Frequency | Who |
| --- | --- | --- |
| Inception Phase | One time (6 months) | Portfolio Management Team with RSCA & Partners |
| Sensemaking workshop | Every 6 months | Portfolio Board, Management team, Stakeholders. |
| Portfolio review | Quarterly | Portfolio Management Team, Portfolio Shared Results Committee |
| Team check-ins | Weekly of Biweekly | Core Portfolio Team |
| Adaptation | Integrated across all MEL activities | MEL Focal Points and relevant leads |

Evaluation Plan

| Evaluation Title | Partners (if joint) | Related Portfolio Output | UNSDCF/CPD Outcome | Planned Completion Date | Key Evaluation Stakeholders | Cost and Source of Funding |
| --- | --- | --- | --- | --- | --- | --- |
| Portfolio Evaluation | Government of The Gambia; UNDP RSCA | Outputs 1–3 (Value Chains, Governance, Climate Resilience) | Green, Resilient and Inclusive Livelihoods; Good Governance and Rule of Law | 2030 | UNDP, Government, Private Sector, Civil Society, Academia | USD 150,000 (TRAC + Partner Funds) |

| 4. Partnerships & Stakeholders |  |  |  |  |
| --- | --- | --- | --- | --- |
| This section refers to the portfolio’s Partnership & Stakeholder approach. |  |  |  |  |
| Partnerships (500 characters limit) |  |  |  |  |
| The success of the UNDP Gambia Inclusive Growth Portfolio will depend on the strength and trust of its partnerships. It is now well understood that inclusive and climate-resilient growth cannot be achieved by any single actor; it demands a community of practice that learns, adapts, and acts together. This portfolio therefore serves as a shared platform where government, business, civil society, and development partners co-create, test, and scale solutions that connect people’s livelihoods to systemic transformation. Working with Government: The portfolio will be jointly led by the Government of The Gambia, building on close collaboration with the Ministry of Finance and Economic Affairs, Ministry of Trade, Industry, Regional Integration and Employment, Ministry of Youths and Sports, Ministry of Higher Education, Research and Science and Technology and Ministry of Environment, Climate Change and Natural Resources, Ministry of Agriculture, and Ministry of Lands, Regional Government and Religious Affairs. These partnerships turn national ambitions into practical, people-centered outcomes. Engagement with the National Enterprise Development Initiative (NEDI), National Youth Council, National Youth Service Scheme, and Women’s Bureau makes sure that women and youth remain central to local economic transformation, while local governments connect policy to communities and keep development grounded in real needs. During the inception phase, a Portfolio Task Team made up of these ministries and agencies will guide portfolio socialization and early alignment, anchoring national ownership and coherence with the National Development Plan (2023–2027). Engaging Business and Financial Partners: The portfolio understands that entrepreneurs, cooperatives, and financial institutions are the engine of inclusive growth. It therefore engages MSME networks, banks, mobile operators, and fintech innovators to expand access to finance, digital services, and markets, especially for women- and youth-led enterprises. Partnerships with chambers of commerce and industry associations in agriculture, fisheries, tourism, and digital trade help green value chains and make them more competitive. At the macro level, collaboration with the AfCFTA Secretariat, ECOWAS, and national trade agencies creates entry points for Gambian MSMEs to participate in regional markets turning local innovation into cross-border opportunity. Collaborating with Development Partners: The portfolio builds complementarity with ongoing programmes of the African Development Bank, European Union, World Bank, UNCTAD, and FAO, ensuring that investments synergize one another rather than overlap. Regional institutions such as the African Union Commission, AfCFTA Secretariat, and ECOWAS serve as amplifiers of learning linking The Gambia’s experience to Africa’s broader transformation agenda. Development partners will also be engaged through an annual Portfolio Socialization and Resource Mobilization Roundtable, reinforcing the idea that the portfolio is both a delivery instrument and a learning platform for joint, flexible financing. Partnering with Communities, Academia, and Civil Society: Real change begins at the local level. Civil-society organizations, community-based groups, and youth and women’s associations are essential partners in shaping and testing solutions that reflect lived realities. Partnering with TVET institutions translates market-ready technical and entrepreneurship skills into employment opportunities. Collaboration with the University of The Gambia, local think tanks, and research networks supports applied research, data generation, and policy experimentation—ensuring that local innovation informs national decision-making. UNDP’s Role: UNDP’s comparative advantage lies in its ability to connect systems and people. Through its convening power and integrated approaches, UNDP provides the neutral space where government priorities, private-sector energy, and community innovation converge. As a catalyst and facilitator, UNDP sustains coherence between the macro (policy and finance), meso (institutions and delivery systems), and micro (enterprises and communities) levels ensuring that collective effort leads to lasting, scalable impact. This collaborative, adaptive, and learning-driven partnership model is what should carry the portfolio forward toward its 2030 vision: a Gambia where economic opportunity, social inclusion, and climate resilience reinforce one another. |  |  |  |  |
| Co-creation (500 characters limit) |  |  |  |  |
| Co-creation is the fundamental principle of the UNDP Gambia Inclusive Growth Portfolio. The country’s transition toward inclusive and climate-resilient growth will be a collective effort that is built on diverse perspectives, lived experience, and shared learning. The portfolio aims to provide the space, structure, and relationships through which this effort takes place, transforming collaboration into a way of working rather than a single event. Co-creation as Foundation: From its inception, the portfolio has been shaped through co-creation. The August 2025 Portfolio Retreat brought together government institutions, local authorities, civil-society organizations, private-sector actors, youth and women’s networks, and UNDP teams from Inclusive Growth (Country Office and Regional Service Center for Africa), Governance, and Environment. Over four days, participants mapped system challenges, tested assumptions, and co-designed the first iteration of the Theory of Change. That process established both the analytical basis and the co-creation working culture of the portfolio. The upcoming inception phase will deepen this approach through the formation of a cross-thematic Portfolio Task Team and a series of socialization and learning sessions with government partners, donors, and local actors. In this way, co-creation develops from a starting exercise into a sustained governance mechanism that keeps the portfolio open, responsive, and grounded in collective intelligence. Co-creation in Practice: Co-creation is embedded throughout the portfolio’s implementation and learning cycles: - Local level (micro): community groups, MSMEs, and local governments jointly design and test value-chain, governance, and resilience solutions using participatory planning, rapid learning loops, and adaptive prototyping. - Institutional level (meso): local governments, ministries, agencies and other actors collaborate with the Portfolio Team to align policies, financing, and delivery systems with field-level evidence, maintaining active feedback between practice and reform. - National and regional level (macro): development partners and donors co-shape programme design, pilot investments, and blended-finance mechanisms that link The Gambia’s local innovations to AfCFTA and regional value-chain opportunities. Tools for Collaborative Action: Joint design exercises, learning labs, and adaptive planning sessions serve as the portfolio’s practical instruments for co-creation, turning ideas into prototypes, testing them in real contexts, and scaling what works. Each partner’s contribution, whether policy leadership, technical expertise, funding, or community insight feeds directly into a living system of experimentation and sensemaking. In this way, co-creation becomes both the method and mindset of the portfolio: a disciplined process of learning together, where participation outweighs perfection, discovery precedes design, and progress is measured not only by results but by the relationships of trust that make systems change possible. |  |  |  |  |
| Stakeholder Engagement Identify key stakeholders and outline a strategy to ensure stakeholders are engaged throughout |  |  |  |  |
| Target group(s) |  | Engagement strategy (100 characters limit) |  |  |
| groups that are the intended beneficiaries of the portfolio. |  | strategy to engage these targeted groups |  |  |
| Government Ministries, Departments and Agencies (Finance, Trade, Environment) |  | Policy co-creation, alignment of national frameworks with portfolio |  |  |
| Local Government / Councils |  | Joint planning, local LED pilots, and participatory decision-making |  |  |
| Youth and Women Entrepreneurs / MSMEs |  | Co-design value-chain solutions, digital and finance inclusion pilots |  |  |
| Community-Based Organizations (CBOs) & Cooperatives |  | Livelihood pilots, community dialogues, joint learning sessions and knowledge exchange |  |  |
| Farmers, Fishers & Small Producers |  | Capacity building, market access, and climate-smart production support |  |  |
| Private Sector Associations & Financial Institutions |  | Innovation labs, green finance, and mentoring for inclusive MSMEs |  |  |
| Youth and Women Networks (e.g. Gambia Youth Council, Women’s Bureau) |  | Joint advocacy and inclusive policy dialogue |  |  |
| Academic & Research Institutions (e.g. University of The Gambia) |  | Applied research, evidence generation, and knowledge sharing |  |  |
| Other Potentially Affected Groups |  |  |  |  |
| Informal sector workers at risk of exclusion |  | Participatory mapping and inclusion in value-chain pilots |  |  |
| Traditional & Religious Leaders |  | Dialogue facilitation and community sensitization |  |  |
| Natural resource user (land, water, fisheries) |  | Consultations on sustainable resource use and access rights |  |  |
| Small Traders & Cross-Border Market Actors |  | Market forums and regional trade coordination sessions |  |  |
| Local Civil Society Organizations & NGOs |  | Feedback loops, social accountability, and advocacy partnerships |  |  |
| Engaging social & environmental concerns (500 characters limit) |  |  |  |  |
| The Gambia Inclusive Growth Portfolio is designed to ensure that every intervention contributes positively to people’s well-being and to the planet’s sustainability. The approach to safeguards goes beyond compliance; it treats environmental and social standards as a framework for learning and accountability. The portfolio fully aligns with UNDP’s Social and Environmental Standards (SES) and applies the Social and Environmental Screening Procedure (SESP) across all activities; not as a checklist, but as an essential part of adaptive management and co-creation. Embedding Safeguards in the Portfolio Cycle: Social and environmental safeguards are integrated into every stage of the portfolio, from inception and planning to sensemaking and evaluation. The Portfolio Task Team and implementing partners will systematically apply UNDP’s SESP to all new or realigned initiatives. This will ensure that potential risks are identified early, managed transparently, and mitigated collaboratively through dialogue and co-design with affected communities. All findings will be tracked in a Risk and Safeguards Register, reviewed during quarterly portfolio reviews and biannual sensemaking workshops. These reviews will close the loop between social and environmental insights and decision-making ensuring that feedback directly informs adaptation, policy dialogue, and institutional learning. Access to Concerns and Grievances: Communities and partners will have clear, accessible channels for raising concerns or grievances about potential social or environmental impacts. These include: - Local-level grievance mechanisms managed by implementing partners and local authorities, supported by UNDP for consistency and responsiveness. - Direct access to UNDP’s Social and Environmental Compliance Unit (SECU) and Stakeholder Response Mechanism (SRM), with communication materials and contacts available in national and local languages. - Transparent follow-up on actions taken to address reported issues, feeding back into portfolio adaptation and learning cycles. Inclusive Safeguards and Participatory Monitoring: The portfolio adopts a participatory approach, ensuring that communities, women’s organizations, and youth networks play an active role in monitoring environmental and social impacts. Findings from these participatory reviews will inform Portfolio Learning Notes, programme design adjustments, and engagement with national policies, making accountability part of the system’s intelligence, not a reactive measure. In this way, social and environmental engagement becomes both an ethical foundation and a learning instrument. It builds trust between citizens, institutions, and partners while reinforcing the portfolio’s vision of inclusive, climate-resilient prosperity where people and nature flourish together. . |  |  |  |  |
| 5. Resources |  |  |  |
| This section outlines the resources required to implement the portfolio. |  |  |  |
| Resources Required to Achieve the Expected Results |  |  |  |
| Overall budget | # Implementing Partner (1) |  | Implementing Partner 2 |
| - USD | - Number |  | - number |
| Tangible resources (500 characters limit) |  |  |  |
| The portfolio will coordinate investments in people, infrastructure, and tools to drive its three system shifts. Tangible resources include dedicated technical specialists in inclusive growth, governance, and climate resilience; data and monitoring systems that enable real-time learning and adaptive management; and seed financing and investment in production spaces and equipment for MSME and value-chain pilots that demonstrate models of inclusive enterprise which can be scaled-up. Investments will also support digital and training platforms for women and youth, local innovation hubs that connect communities and entrepreneurs to national institutions, and facilities for sensemaking workshops, co-creation labs, and adaptive planning sessions. Together, these resources create support for the portfolio, enabling collaboration, experimentation, and evidence generation across all levels of the system. |  |  |  |
| Intangible resources (500 characters limit) |  |  |  |
| Success will depend on more than just financial inputs. It rests on shared purpose, trust, and a culture of collaboration among partners. The portfolio draws on UNDP’s convening power, its long-standing relationships with government, business, and civil society, and the adaptive learning principles that connect insights to actions across sectors. These intangible resources such as knowledge networks, policy credibility, social capital, and collective commitment to co-creation and experimentation form the intangible resources that sustains system change. They enable alignment where mandates differ, foster mutual accountability, and transform partnerships into engines of innovation. Together these human and institutional capabilities are what allow the portfolio to behave as a dynamic system: sensing, learning, and adapting continuously toward inclusive and resilient growth. |  |  |  |

6. Implementing Partner(s) Role(s) & Multiyear Work Plan

The Implementing Partner(s) (IP) will work closely with the Portfolio Management Team. A separate, MYWP and budget must be prepared for each Implementing Partner. Implementing Partner(s) for achieving the portfolio outputs

| Implementing Partner(s) | Portfolio Outputs | Other responsibilities |
| --- | --- | --- |
| UNDP | Portfolio Outputs 1, 2 and 3, as well the pilot phase | Contributing to portfolio momentum and learning results |
| Ministry of Trade, Industry, Regional Integration and Employment (MOTIE) | Portfolio Outputs 1, 2 and 3 | Contributing to portfolio momentum and learning results |

Implementing Partner multiyear work plan & budget

This plan shall have a detailed MYWP and budget for the next phase of work, and a higher- level schematic plan and budget for all subsequent phases. MYWPs can be developed and approved per implementing partner. The IP’s work will be based on a rolling budgeting and MYWP approach. At the end of each phase, a rapid portfolio adjustment assessment will determine the exact MYWP and budget for the next phase based on portfolio learnings. This will happen within the confines of the total available budget and the IP’s scope of work.

All MYWPs together will yield the joint results framework.

7 Governance & Management

This section refers to the Governance and Management of all portfolio assets including tangible and intangible resources, learning, opportunities, and risks. There is one Portfolio Board, one Portfolio Management Team, Portfolio Assurance and one Portfolio Shared Results Committee (PSRC).

Standard Text for Portfolio Board

There is one Portfolio Board. It provides high-level oversight of the portfolio, risk management and portfolio assurance. It approves the inclusion of new implementing partners at the time of portfolio approval as well as during the implementation, for contributing to portfolio results. The portfolio board enjoys the authority to fold in ongoing projects with their respective implementing partners under the portfolio in consultation with concerned stakeholders.  In this regard, the Board:

- approves the multiyear partner work plan containing milestones. Portfolio milestones are approved yearly by the board, for each subsequent 12-month period of work.

- assesses any major risks to the portfolio and related decisions/agreements on any management actions and adjustments. Also, the Portfolio Board assesses the results achieved at the portfolio level and contribution to country programme outcomes and the portfolio objective.

- reviews how integration and intersectionality are pursued in achieving greater impact to the portfolio's objectives and the CPD outcomes.

- identifies new partnerships for the portfolio based on the identified new policy spaces resulting from the portfolio implementation and to ensure sustainability, identify new resource mobilization opportunities.

- makes decision on suspension of and extension of the portfolio (not the individual multiyear work plans under the portfolio delegated to the Implementing Partners) subject to partner commitment and funding.

The Portfolio Board will meet at the minimum once a year, but as necessary, will meet more frequently. The timing of board meetings will be agreed upon in advance and shall correspond to key portfolio reporting.

There are three categories of Portfolio Board members are the following:

  - The Executive is:  Ministry of Trade, Industry, Regional Integration and Employment (MoTIE), UNDP/RR, Ministry of Finance, and Ministry of Public Services

  - Beneficiary Representative(s) is: GCCI

  - Development Partner(s) representative(s) is: EU

  - Portfolio Assurance representative(s) is: UNDP/PMSU:

  - Portfolio Management Team (draft): Team Leaders for IGP, Governance and Environment, Head of PMSU, Deputy RR/UNDP

  - Portfolio Shared Results Committee (PSRC): MoTIE, MoYS, MECCNAR, MoHERST, MoFEA, MoLRG, MoJ, MoTAC, MoA , GCCI, GWCCI, GYCC, GSCC

Governance Diagram

While there is a clear hierarchy between the Portfolio Board and the Portfolio Shared Results Committee as per their respective mandates, the visual conveys a way of working that is premised on a continous dialogue, in line with the dynamic management of a portfolio.

For more details about roles and responsibilities, refer to:

Annex 5.	“Portfolio Board Terms of Reference and ToRs of key management positions UNDP Standard 			Terms of Reference for the Portfolio Board of [Insert Portfolio Title and Portfolio Number]”

Portfolio Board Terms of Reference

There is one Portfolio Board which meets at least once a year.

The Portfolio Board provides high-level oversight of the portfolio, risk management and portfolio assurance. Key areas of focus for the Board are as follows:

- Approves the inclusion of new implementing partners at the time of portfolio approval as well as during the implementation, for contributing to portfolio results.

- The Portfolio Board enjoys the authority to fold in ongoing projects with their respective implementing partners under the portfolio provided;

  - the projects are aligned and integrated to the portfolio Theory of Change,

  - they share a common portfolio Results Framework,

  - they are integrated into an updated multiyear work plan approved by the respective implementing partner(s)

  - and they have secure agreements from the implementing partners on convening a Portfolio Board and the Portfolio Shared Results Committee

- Assess major risks to the portfolio and related decisions/agreements on management actions and adjustments at the portfolio level.

- Assess the results achieved at the portfolio level and contribution to CPD Outcomes and the portfolio objective.

- Reviews how integration and intersectionality are pursued in achieving greater impact to the portfolio's objectives and the CPD outcomes.

- Identify new partnerships for the portfolio based on the identified new policy spaces resulting from the portfolio implementation and to ensure sustainability,

- Identify and facilitate new resource mobilization opportunities.

- Take decision on suspension of and extension of the portfolio (not the individual multiyear work plans under the portfolio delegated to the Implementing Partners) subject to partner commitment and funding.

- LEGAL CONTEXT

NOTE: Please choose one of the following options in the Multiyear Work-Plan

Each Implementing Partner will be bound by the Option selected in the Multiyear Work Plan:

Option a. Where the country has signed the Standard Basic Assistance Agreement (SBAA)

This portfolio document shall be the instrument referred to as “Project Document” in Article 1 of the Standard Basic Assistance Agreement between the Government of (country) and UNDP, signed on (date). Consequently, all references in the SBAA to “Project Document “shall be deemed to refer to this “Portfolio Document”.  All references in the SBAA to “Executing Agency” shall be deemed to refer to the “Implementing Partner”.

Section 6 (Implementing Partner(s) Role(s) & Multiyear Work Plan) above and Annex 7 (Implementing Partners) identify the implementing partners for each of the workplans in this Portfolio (each, an “Implementing Partner”). The Implementing Partner will implement the programme activities in the multiyear work plan applicable to such Implementing Partner  in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Option b. Where the country has NOT signed the Standard Basic Assistance Agreement (SBAA)

The portfolio document shall be the instrument envisaged and defined as “Project Document” in the Supplemental Provisions, attached hereto and forming an integral part hereof.

Section 6 (Implementing Partner(s) Role(s) & Multiyear Work Plan) above and Annex 7 (Implementing Partners) identify the implementing partners for each of the workplans in this Portfolio( (each, an “Implementing Partner”). The Implementing Partner will implement the programme activities in the multiyear work plan applicable to such Implementing Partner in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Option c. For Global and Regional Portfolios

This portfolio forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this portfolio to the associated country level activities, this document shall be the “Project   Document” instrument referred to in: (i) the respective signed Standard Basic Assistance Agreement (SBAA) (for the specific countries); or (ii) in the Supplemental Provisions attached to the Portfolio Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner”.

Section 6 (Implementing Partner(s) Role(s) & Multiyear Work Plan) above and Annex 7 (Implementing Partners)  identify the implementing partners for each of the workplans in this Portfolio (each, an “Implementing Partner”). The Implementing Partner will implement the portfolio outputs assigned   to such Implementing Partner in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

- RISK MANAGEMENT

# Risk Management

a. Government Entity (NIM): Ministry of Trade, Industry, Regional Integration and Employment

- Consistent with the Article III of the SBAA [or the Supplemental Provisions], the responsibility for the safety and security of the relevant Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the portfolio is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Portfolio Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Portfolio Document are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Portfolio Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in the implementation of this Portfolio, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Portfolio Document.

(a) In the implementation of the activities under this Portfolio Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Portfolio Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

- a) In the performance of the activities under this Portfolio Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Portfolio Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4 have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and its sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Portfolio Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

b) The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Portfolio.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct portfolio and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the portfolio/programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other portfolio stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Portfolio Document shall cooperate in good faith with any exercise to evaluate any programme or portfolio -related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to Portfolio sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the portfolio or using UNDP funds.

- In the implementation of the activities under this Portfolio Document, UNDP places reasonable reliance upon the Implementing Partner for it to apply its laws, regulations and processes, and applicable international laws regarding anti money laundering and countering the financing of terrorism, to ensure consistency with the principles of then in force the UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy.

- The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Portfolio Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Portfolio Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP Portfolios and programmes in accordance with UNDP’s regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Portfolio Document will promptly inform one another in case of any incidence of inappropriate use of funds, credible allegations of fraud or corruption or other financial irregularities with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP Portfolio or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- Indicate in the Multiyear Work Plan of each Implementing Partner the applicable option:

Option 1: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Portfolio Document.

Option 2: The Implementing Partner agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of this Portfolio Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.

Option 3: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Portfolio Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.

Note:  The term “Portfolio Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Portfolio Document, including those with responsible parties, subcontractors, and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Portfolio Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the Portfolio, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Portfolio Document.

b. The following provisions will apply when implementation is done by UNDP (DIM)

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the Portfolio funds are used to provide support to individuals or entities associated with terrorism , that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Portfolio Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list. This provision must be included in all sub-contracts or sub-agreements entered into under this Portfolio Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct Portfolio and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the Portfolio or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other Portfolio stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Portfolio Document, UNDP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Portfolio Document shall cooperate in good faith with any exercise to evaluate any programme or Portfolio-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to Portfolio sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor, and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Portfolio Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the Portfolio is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Portfolio Document.

  - Each responsible party, subcontractor and sub-recipient (each a “sub-party” and together “sub-parties”) acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the sub-parties, and other entities involved in Portfolio implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Portfolio Document.

(a)	In the implementation of the activities under this Portfolio Document, each sub-party shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) 	Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Portfolio Document, in the implementation of activities, each sub-party, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

  - In the performance of the activities under this Portfolio Document, each sub-party shall (with respect to its own activities), and shall require from its sub-parties (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, sub-parties will and will require that their respective sub-parties will take all appropriate measures to:

(i) Prevent its employees, agents or any other persons engaged to perform any services under this Portfolio Document, from engaging in SH or SEA;

(ii) Offer employees and associated personnel training on prevention and response to SH and SEA, where sub-parties have not put in place its own training regarding the prevention of SH and SEA, sub-parties may use the training material available at UNDP;

(iii) Report and monitor allegations of SH and SEA of which any of the sub-parties have been informed or have otherwise become aware, and status thereof;

(iv) Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

(v) Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. Each sub-party shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties with respect to their activities under the Portfolio Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the relevant sub-party shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

  - Each sub-party shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the relevant sub-party to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Portfolio.

  - Each responsible party, subcontractor and sub-recipient will ensure that any Portfolio activities undertaken by them will be implemented in a manner consistent with the UNDP Social and Environmental Standards and shall ensure that any incidents or issues of non-compliance shall be reported to UNDP in accordance with UNDP Social and Environmental Standards.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud, corruption or other financial irregularities, by its officials, consultants, subcontractors and sub-recipients in implementing the Portfolio or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Portfolio Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Portfolio Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and Portfolios. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption other financial irregularities with due confidentiality.

Where it becomes aware that a UNDP Portfolio or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - Choose one of the three following options:

Indicate in the Multiyear Work Plan of each Implementing Partner the applicable option:

Option 1: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption, other financial irregularities or otherwise paid other than in accordance with the terms and conditions of this Portfolio Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Portfolio Document.

Option 2: Each responsible party, subcontractor or sub-recipient agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Portfolio Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud corruption or other financial irregularities or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.

Option 3: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Portfolio Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.

Note:  The term “Portfolio Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Portfolio Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Portfolio Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the Portfolio or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Portfolio Document.

c. The following provisions will apply when implementation is done by a CSO/NGO/Non-UN or other IGO with no signed SBEAA with UNDP

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Portfolio Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the Portfolio is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Portfolio Document [and the Project/Portfolio Cooperation Agreement between UNDP and the Implementing Partner].

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Portfolio Document are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Sanctions Consolidated Sanctions  List, and that no UNDP funds received pursuant to the Portfolio Document are used for money laundering activities. The United Nations Security Council Sanctions Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Portfolio implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Portfolio Document.

(a) In the implementation of the activities under this Portfolio Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Portfolio Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

- a) In the performance of the activities under this Portfolio Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will, and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Portfolio Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4, have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and such sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Portfolio Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

b) The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Portfolio.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct Portfolio and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the Portfolio or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other Portfolio stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Portfolio Document shall cooperate in good faith with any exercise to evaluate any programme or Portfolio-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to Portfolio sites, relevant personnel, information, and documentation.

- UNDP is committed to the highest ethical standards and will not tolerate the diversion of the resources entrusted to it through Money Laundering or Terrorist Financing and will not partner with entities that tolerate the diversion of resources through Money Laundering or Terrorist Financing. To that effect, the Implementing Partner represents and warrants that it has not, and it shall not, at any time in the implementation of the Portfolio engage in Terrorism Financing or Money Laundering.  The Implementing Partner shall communicate the restriction of this paragraph to its and each of its responsible parties, their respective sub-recipients and other entities involved in Portfolio implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Portfolio Documents and shall take all reasonable measures to ensure that such persons do not engage in Terrorism Financing or Money Laundering.

- The Implementing Partner shall immediately disclose to UNDP any actual, apparent, potential or attempted Terrorism Financing or Money Laundering activity that it becomes aware of. The Implementing Partner shall fully cooperate with any investigation or review of Terrorism Financing or Money Laundering activity by UNDP.

- The Implementing Partner acknowledges and agrees that Terrorism Financing or Money Laundering constitute financial irregulates and that if the Implementing Partner or any of its responsible parties, their respective sub-recipients and other entities involved in Portfolio implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Portfolio Document engages in Terrorism Financing or Money Laundering activity  that would constitute a material breach of this Portfolio Document, which entitles UNDP to immediately terminate the Portfolio without incurring any liability or penalty.

- Furthermore, the Implementing Partner expressly acknowledges and agrees that, in the event that UNDP were to determine through an investigation or otherwise that Terrorism Financing or Money Laundering occurred, UNDP shall have, in addition to its right to immediately terminate the Portfolio, the rights to:

- apply and enforce the relevant sanctions in accordance with UNDP internal regulations, rules, procedures, practices, policies and guidelines, including referral of the matter to national authorities when appropriate; and

- recover all losses, financial or otherwise, suffered by UNDP in connection with such Terrorism Financing or Money Laundering activity.

- For the purpose of this Portfolio Document the following terms shall have the definition ascribed to the below:

- “Money Laundering” is generally considered as concealment of the origins of money obtained illegally, typically by passing it through a complex sequence of financial or commercial transactions. ML usually involves three stages: (i) introducing the proceeds of crime into the financial system (placement); (ii) transactions to convert or transfer the funds to other locations or financial institutions (layering); and (iii) reintroducing the funds into the legitimate economy as "clean" money and investing it in various assets or business ventures (reintegration) appearing to have been legally obtained. The FATF recommends that ML be criminalized by every country on the basis of article 3(1)(b) and (c) of the Vienna Convention and article 6(1) of the Palermo Convention.

- “Terrorist Financing” means providing support to individuals or entities that appear on the United Nations Security Council Consolidated Sanctions List accessible at https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the Portfolio or using the UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Portfolio Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Portfolio Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP programmes and Portfolios in accordance with UNDP regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors‘ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The Implementing Partner will promptly inform UNDP in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption or other financial irregularity with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP Portfolio or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption or other financial irregularity, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- Indicate in the Multiyear Work Plan of each Implementing Partner the applicable option:

Option 1: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud,  corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of this Portfolio Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Portfolio Document.

Option 2: The Implementing Partner agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Portfolio Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.

Option 3: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud. corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Portfolio Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.

Note:  The term “Portfolio Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Portfolio Document, including those with the Implementing Partner, responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Portfolio Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the Portfolio, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management Standard Clauses” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Portfolio Document.

d. The following provisions will apply when implementation is done by a UN Agency other than UNDP, and IGO with signed SBEAA with UNDP

- The Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- In the implementation of the activities under this Portfolio Document, the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures. The Implementing Partner will ensure that its regulations, rules, policies and procedures are consistent with the principles of UNDP relating to SEA and SH requirements. Notwithstanding the foregoing, the Implementing Partner, will notify UNDP of any such allegations and investigations it may conduct further to such allegations.

- The Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor and sub-recipient that is not a UN entity:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Portfolio Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and the Implementing Partner property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the Portfolio is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - The Implementing Partner reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Portfolio Document.

  - In the performance of the activities under this Portfolio, the Implementing Partner shall ensure, with respect to the activities of any of its responsible parties, sub-recipients and other entities engaged under the Portfolio, either as contractors or subcontractors, their personnel and any individuals performing services for them, that those entities have in place adequate and proper procedures, processes and policies to prevent and/or handle SEA and SH.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that none of the [Portfolio funds] [UNDP funds received pursuant to the Portfolio Document] are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Sanctions Consolidated Sanctions  List, and that no UNDP funds received pursuant to the Portfolio Document are used for money laundering activities. The United Nations Security Council Sanctions Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct Portfolio and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the Portfolio or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other Portfolio stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Portfolio Document shall cooperate in good faith with any exercise to evaluate any programme or Portfolio-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to Portfolio sites, relevant personnel, information, and documentation.

- In the implementation of the activities under this Portfolio Document, the Implementing Partner will ensure that its regulations, rules, policies and procedures are consistent with the principles of then in force UNDP’s Anti-Money Laundering and Countering the Financing of Terrorism Policy.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud, or corruption, by its officials, consultants, responsible parties, subcontractors, and sub-recipients in implementing the Portfolio or programme or using the UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- This text applies when the Implementing Partner is a non-UN IGO: The requirements of the following documents, then in force at the time of signature of the Portfolio Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Portfolio Document and are available online at www.undp.org.]

- This text applies if the Implementing Partner is a non-UN IGO: In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP Portfolios or programmes. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors‘ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The Implementing Partner and UNDP will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP Portfolio or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption or other financial irregularity, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- Indicate in the Multiyear Work Plan of each Implementing Partner the applicable option:

Option 1: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of this Portfolio Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Portfolio Document.

Option 2: The Implementing Partner agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Portfolio Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.

Option 3: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Portfolio Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Portfolio Document.

Note:  The term “Portfolio Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Portfolio Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Portfolio Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the Portfolio, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management Standard Clauses” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Portfolio Document.

Special Clauses. In case of government cost-sharing through the Portfolio, the following clauses should be included:

- The schedule of payments and UNDP bank account details.

- The value of the payment, if made in a currency other than United States dollars, shall be determined by applying the United Nations operational rate of exchange in effect on the date of payment.  Should there be a change in the United Nations operational rate of exchange prior to the full utilization by the UNDP of the payment, the value of the balance of funds still held at that time will be adjusted accordingly.  If, in such a case, a loss in the value of the balance of funds is recorded, UNDP shall inform the Government with a view to determining whether any further financing could be provided by the Government.  Should such further financing not be available, the assistance to be provided to the Portfolio may be reduced, suspended or terminated by UNDP.

- The above schedule of payments takes into account the requirement that the payments shall be made in advance of the implementation of planned activities.  It may be amended to be consistent with the progress of Portfolio delivery.

- UNDP shall receive and administer the payment in accordance with the regulations, rules and directives of UNDP.

- All financial accounts and statements shall be expressed in United States dollars.

- If unforeseen increases in expenditures or commitments are expected or realized (whether owing to inflationary factors, fluctuation in exchange rates or unforeseen contingencies), UNDP shall submit to the government on a timely basis a supplementary estimate showing the further financing that will be necessary. The Government shall use its best endeavours to obtain the additional funds required.

- If the payments referred above are not received in accordance with the payment schedule, or if the additional financing required in accordance with paragraph 6 above is not forthcoming from the Government or other sources, the assistance to be provided to the Portfolio under this Agreement may be reduced, suspended or terminated by UNDP.

- Any interest income attributable to the contribution shall be credited to UNDP Account and shall be utilized in accordance with established UNDP procedures.

In accordance with the decisions and directives of UNDP's Executive Board:

The contribution shall be charged:

- […%] cost recovery for the provision of general management support (GMS) by UNDP headquarters and country offices

- Direct cost for implementation support services (ISS) provided by UNDP and/or an executing entity/implementing partner.

- Ownership of equipment, supplies and other properties financed from the contribution shall vest in UNDP.  Matters relating to the transfer of ownership by UNDP shall be determined in accordance with the relevant policies and procedures of UNDP.

- The contribution shall be subject exclusively to the internal and external auditing procedures provided for in the financial regulations, rules and directives of UNDP.”

ANNEXES

Annex 1	Portfolio Quality Assurance Report (per the Quality Assurance (Projects) procedure)

Annex 2	Social and Environmental Screening Procedure (SESP) in Quantum+ (per the UNDP Online Social and Environmental Screening Procedure)

Annex 3	Portfolio Risk Register

Annex 4	Capacity Assessment. Results of capacity assessments of Implementing Partner(s) (including Partner Capacity Assessment Tool (PCAT) and HACT Micro Assessment)

Annex 5	Portfolio Board Terms of Reference and TORs of key management positions

Annex 6	On-Granting Provisions Applicable to the Implementing Partner(s)

Annex 7	Implementing Partner(s) detailed Multiyear Work Plan

PORTFOLIO MULTIYEAR WORK PLAN (MYWP) 1

| Portfolio Name : Building an Inclusive and Resilient Economy for All in the Gambia / One Gambia: Building an Inclusive and Resilient Economy for All | Quantum Portfolio No. : |
| --- | --- |
| Implementing Partner (1) : UNDP | Quantum MYWP No. : |
| Implementation Modality : Direct Implementation Modality (DIM)Direct Implementation Modality (DIM)Direct Implementation Modality (DIM) |  |
| Risk Management (Refund Clause) : [SELECT THE REFUND CLAUSE (Please see Risk Management Section for Government Entity (NIM) in para.15, UNDP (DIM) in para.7, CSO/NGO/Non-UN or other IGO with no signed SBEAA in para.18), or UN Agency other than UNDP and IGO with signed SBEAA in para.13.][SELECT THE REFUND CLAUSE (Please see Risk Management Section for Government Entity (NIM) in para.15, UNDP (DIM) in para.7, CSO/NGO/Non-UN or other IGO with no signed SBEAA in para.18), or UN Agency other than UNDP and IGO with signed SBEAA in para.13.]LECT THE REFUND CLAUSE (Please see Risk Management Section for Government Entity (NIM) in para.15, UNDP (DIM) in para.7, CSO/NGO/Non-UN or other IGO with no signed SBEAA in para.18), or UN Agency other than UNDP and IGO with signed SBEAA in para.13.][SE |  |
| Portfolio Results : (System Change statement copied verbatim from the Portfolio Results Framework) |  |

| Portfolio Outputs (shift statement, including contribution to Portfolio Momentum & Portfolio Learning) | Planned Interventions | Planned Y1 Budget (USD) | Indicative Yearly budget allocation (USD) |  |  |  | Responsible Party | Total Budget |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Y2 | Y3 | Y4 | Y5 |  | Funding Source | Budget Description | Amount (USD) in Millions |
| Inception and Alignment Phase (2026 – 6 months) | Establish, sensitize and capacitate Portfolio Board (MoTIE, UNDP, MoPS, MoFEA, EU) Task Team (Secretariat) and Shared Results Committee (technical committee) under MOTIE and UNDP. | 15,000 | 15,000 | 15,000 | 16,050 | 16,050 | UNDP | UNDP |  | 77,100 |
|  | Launch the 2026 Portfolio Annual Work Plan (LPAC, LoAs FACE & ICE, Implementation Plans) | 1,000 |  |  |  | 2,000 | UNDP | UNDP |  | 3,000 |
|  | Conduct inception and socialization workshops with government, donors, and civil society. | 12,000 |  |  |  |  | UNDP |  |  | 12,000 |
|  | Conduct assessment and selection of priority Value Chains for the Portfolio | 25,000 |  |  |  |  | UNDP | UNDP |  | 25,000 |
|  | Define criteria, conduct assessment and select LGAs for piloting portfolio interventions. | PM |  |  |  |  | UNDP / MOLRG | UNDP |  | PM |
|  | Sub-total Inception Phase | 53,000 |  |  |  |  |  |  |  | 117,100 |
| Output 1: Inclusive, market-aligned and climate-smart value chains strengthened, enabling MSMEs, women and youth to access skills, finance and markets, and create decent green jobs contributing to climate-resilient economic growth. (Inclusive Value Chains and Green Jobs) | Results Area #1.2: Innovation & Entrepreneurship |  |  |  |  |  |  |  |  |  |
|  | 1.1.1: Promote entrepreneurship, networking and innovation by operationalizing UNIPOD and regional innovation hubs, and strengthening platforms like the YouthConnekt. | 400,000 | 115,000 | 123,050 | 131,664 | 140,880 | UNDP / MoHERST / MoYS / LGAs | UNDP | 75700 Conferencing 72500 Supplies (technical materials) 72600 Grants (Innovation challenge) | 910,593 |
|  | Results Area #1.3: Finance & Investment |  |  |  |  |  |  |  |  |  |
|  | 1.3.1: Support the design and implementation of innovative mechanisms to enhance financial access for MSMEs – including tailored credit lines, and foreign & diaspora investments. | 114,000 | 225,000 | 350,000 | 350,000 | 350,000 | UNDP / CBG / MoFEA / MOFA / GIEPA | UNDP | 71600 grants (Seed money) | 1,389,000 |
|  | 1.3.2: Promote mobilization and channeling of underutilized financial resources toward MSME investment, by mapping of national assets (pension funds, insurance funds, CBG funds, etc.). | 25,000 | 10,000 | 5,000 |  |  | UNDP | UNDP |  | 40,000 |
|  | Sub-total Output 1 | 539,000 | 365,000 | 478,050 | 481,663.5 | 490,879.7 |  |  |  | 2,354,593.2 |
| Output 2: Governance frameworks, institutional capacities and digital systems strengthened to deliver coherent, data-driven policies, efficient services, and inclusive market conditions supporting enterprise growth and social protection (Governance & Enabling Systems) Contribution to Portfolio Learnings Gender Marker: [SELECT GENDER MARKER] | Results Area # 2.3 Data, Digital Tools & Services |  |  |  |  |  |  |  |  |  |
|  | 2.3.5: Pilot and scale up the use of Artificial Intelligence (AI) tools for MSMEs development | 5,000 | 0 | 50,000 | 2,500 | 2,500 | UNDP | UNDP | 75700 conferencing, 71400 technical supports, 71300 local consultants | 60,000 |
|  | Sub-total Output 2 | 5,000 | 0 | 50,000 | 2,500 | 2,500 |  |  |  | 60,000 |
| Output 3: Climate-resilient infrastructure, livelihoods and social protection systems strengthened to reduce vulnerability and enhance adaptive capacity of communities to climate-related shocks and stresses. (Resilient Livelihoods & Sustainable Infrastructure) Contribution to Portfolio Momentum Contribution to Portfolio Learnings Gender Marker: [SELECT GENDER MARKER] | Results Area # 3.1: Sustainable & Resilient Energy, Infrastructure & Livelihoods (Building Community Resilience) |  |  |  |  |  |  |  |  |  |
|  | 3.1.1: Support the implementation of the Programme for Accelerated Community Development (PACD) | 3,055,556 | 9,715,872 | 10,941,104 | 8,259,765 | 3,237,905.94 | UNDP/MoPS/LGAs | UNDP | 72200 Equipment, 75700 Training & Conferencing 71600 Travel 72500 Goods & Services, 72100 Contractual Services Companies ( construction) | 35,210,202.94 |
|  | Results Area # 3.3: Social Protection |  |  |  |  |  |  |  |  |  |
|  | 3.3.1: Strengthen social protection by expanding coverage to informal sector and digitizing the registration process. | 50,000 |  |  |  |  | UNDP/NSPA | UNDP | 75700 Conferencing 71300 Local Consultant 71600 Travel | 50,000 |
|  | 3.3.2: Design and implement innovative social protection mechanisms for mitigating risks against climate hazards – e.g. flooding (insurance, anticipatory action- early warning), protecting livelihoods and economic activities. | 15,000 |  | 80,000 | 70,000 |  | UNDP/ MECNAR / NDMA / GRCS |  |  | 165,000 |
|  | Sub-total Output 3 | 3,120,556 | 9,715,872 | 11,021.104 | 8,329,765 | 3,237,905.94 |  |  |  | 35,425,202.94 |
| Cross-Cutting 4 – Monitoring, Evaluation, Accountability & Learning (MEAL) | - Conduct bi-annual sense-making workshops. | 4,000 | 4,000 | 4,000 | 4000 | 4,000 | UNDP | UNDP |  | 20,000 |
|  | - Run quarterly portfolio reviews and reflection cycles. | 2,500 | 2,500 | 2,500 | 2,500 | 2,500 | UNDP | UNDP |  | 12.500 |
|  | - Operationalize MEL dashboard and baseline system. | 15,000 | 15,000 | 15,000 | 15,000 | 15,000 | UNDP | UNDP |  | 75,000 |
|  | - Undertake mid-term and final evaluations. | - | - | 28,000 | - | 50,000 | UNDP | UNDP |  | 78,000 |
|  | 4.5 Produce learning briefs and knowledge products. | - | 10,000 | 25,000 | 15,000 | - | UNDP | UNDP |  | 50,000 |
|  | Sub-total Cross-cutting 4 | 21,500 | 31,500 | 74,500 | 36,500 | 71,500 |  | UNDP |  | 235,500 |
| Cross-Cutting 5 – Resource Mobilization & Partnerships | - Develop and implement Joint Resource Mobilization Plan. | 55,000 | - |  |  | 25,000 | UNDP | UNDP |  | 80,000 |
|  | - Hold annual donor coordination and co-financing dialogues. |  | 25,000 | 50,000 | 50,000 |  | UNDP | UNDP |  | 125,000 |
|  | - Expand PACD pooled fund and blended-finance partnerships (AfDB, EU, GCF). | 50,000 | 75,000 | 100,000 | 100,000 | 75,000 | UNDP | UNDP |  | 400,000 |
|  | - Design Private-Sector Engagement Framework and Partnership Compacts. | 25,000 | 75,000 | 75,000 | 100,000 | 100,000 | UNDP | UNDP |  | 375,000 |
|  | Sub-total Cross-cutting 5 | 105,000 | 175,000 | 225,000 | 250,000 | 200,000 |  |  |  | 955,000 |
|  | Grand Total IP 1 UNDP | 3,844,056 | 10,287,372 | 11,848,654 | 9,100,428.5 | 4,000,285.6 |  |  |  | 39,080,796.1 |
|  | Grand Total IP 2 MOTIE | 892,625 | 1,452,624 | 1,452,625 | 1,567,625 | 1,447,625 |  |  |  | 6,813,125 |
|  | Total of IP 1 and IP 2 | 4,841,681 | 11,914,996 | 13,526,279 | 10,918,053.5 | 5,647,910.6 |  |  |  | 45,893,921.1 |
| Project Management | Communications Cost (1%) | 48,416.81 | 119,149.96 | 135,262.8 | 109,180.5 | 56,479.1 | UNDP |  |  | 468,489 |
|  | Delivery Enabling Services |  |  |  |  |  | UNDP |  |  |  |
|  | Project Staff (salaries) | 107,016 | 107,016 | 107,016 | 107,016 | 107,016 | UNDP |  |  | 535,080 |
|  | Facilities and Administration (GMS - 8%) | 366,724.5 | 948,989.8 | 1,051,492 | 873,444.3 | 451,832.8 | UNDP |  |  | 3,692,483.4 |
|  | Audits and HACT (1%) | 48,416.81 | 119,149.96 | 135,262.8 | 109,180.5 | 56,479.1 | UNDP |  |  | 468,489 |
|  | M&E (2%) | 96,833.62 | 238,299.9 | 270,525.6 | 218,361 | 112,958.2 | UNDP |  |  | 936,978 |
|  | TOTAL | 5,509,088 | 13,447,601.5 | 15,225,838 | 12,335,235.8 | 6,432,675.8 |  |  |  | 52,950,439.1 |

This MYWP is an integral part of the Portfolio Document and is subject to all the provisions in the Portfolio Document, including the Legal Context and the Risk Management Sections. The implementation modality selected in the MYWP will determine which specific legal provisions in the Risk Management Section will apply to each Implementing Partner. The option selected here will also determine the option in the Legal Context section that will apply to the Implementing Partner. The MYWP contributes to the portfolio results. Risks emerging from the implementation of the MYWP will be reflected in the portfolio risk register.

Agreed by:

| UNDP |  |
| --- | --- |
| <Name> |  |

PORTFOLIO MULTIYEAR WORK PLAN (MYWP) 2

| Portfolio Name : Building an Inclusive and Resilient Economy for All in the Gambia / One Gambia: Building an Inclusive and Resilient Economy for All | Quantum Portfolio No. : |
| --- | --- |
| Implementing Partner (2) : Ministry of Trade , Industry, Regional Integration & Employment (MoTIE) | Quantum MYWP No. : |
| Implementation Modality : National Implementation Modality (NIM)National Implementation Modality (NIM)National Implementation Modality (NIM) |  |
| Risk Management (Refund Clause) : [SELECT THE REFUND CLAUSE (Please see Risk Management Section for Government Entity (NIM) in para.15, UNDP (DIM) in para.7, CSO/NGO/Non-UN or other IGO with no signed SBEAA in para.18), or UN Agency other than UNDP and IGO with signed SBEAA in para.13.][SELECT THE REFUND CLAUSE (Please see Risk Management Section for Government Entity (NIM) in para.15, UNDP (DIM) in para.7, CSO/NGO/Non-UN or other IGO with no signed SBEAA in para.18), or UN Agency other than UNDP and IGO with signed SBEAA in para.13.]LECT THE REFUND CLAUSE (Please see Risk Management Section for Government Entity (NIM) in para.15, UNDP (DIM) in para.7, CSO/NGO/Non-UN or other IGO with no signed SBEAA in para.18), or UN Agency other than UNDP and IGO with signed SBEAA in para.13.][SE |  |
| Portfolio Results : (System Change statement copied verbatim from the Portfolio Results Framework) |  |

| Portfolio Outputs (shift statement, including contribution to Portfolio Momentum & Portfolio Learning) | Planned Interventions | Planned Y1 Budget (USD) | Indicative Yearly budget allocation (USD) |  |  |  | Responsible Party | Total Budget |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Y2 | Y3 | Y4 | Y5 |  | Funding Source | Budget Description | Amount (USD) in Millions |
| Output 1: Inclusive, market-aligned and climate-smart value chains strengthened, enabling MSMEs, women and youth to access skills, finance and markets, and create decent green jobs contributing to climate-resilient economic growth. (Inclusive Value Chains and Green Jobs) | Results Area #1.1: Skills and Capacities for Value Chain Development |  |  |  |  |  |  |  |  |  |
|  | 1.1.1: Strengthen market-responsive skills and capacities for youth, women and entrepreneurs, including through upgrading of TVET centers and curricula, specialized skills for value-addition and SEZs, coding bootcamps, internship and apprenticeship programmes. | 150,000 | 300,000 | 325,000 | 325,000 | 325,000 | MoHERST / MOCDE / MoTIE / MoYS / LGAs |  | 75700 Training & Conferencing 71500 Stipends 72200 Equipment, 72100 Contractual Services Companies (construction) | 1,125,000 |
|  | 1.1.2: Enhance and modernize MSME digital skills for online market access and digital services, including at 2-3 LGA levels. | 25,000 | 50,000 | 50,000 | 50,000 | 50,000 | MoCDE / MOHERST / LGAs | 0 | 75700 conferencing, 71400 technical supports, 71300 local consultants | 225,000 |
|  | Results Area #1.2: Innovation & Entrepreneurship |  |  |  |  |  |  |  |  |  |
|  | 1.2.1: Expand and strengthen MSMEs exchange and connections through networking platforms and mentorship programmes to spur exchange of ideas and innovation at all levels. | 25,000 | 25,000 | 25,000 | 25,000 | 25,000 | MoTIE / LGAs |  |  | 125,000 |
|  | 1.2.2: Support and nurture innovation by strengthening Patents and Intellectual Property Rights for private sector development. |  | 20,000 | 20,000 | 20,000 | - | MoJ |  |  | 60,000 |
|  | Results Area #1.3: Access to Finance & Investment |  |  |  |  |  |  |  |  |  |
|  | 1.3.1: Improve MSME access to finance and financial services through MSME support funds, and promotion on non-traditional collateral. |  |  |  |  |  | MOTIE |  |  |  |
|  | 1.3.2: Strengthen traditional credit and saving schemes/structures (including cooperatives) to promote joint business investment for MSME growth. |  |  |  |  |  | DCD / ? |  |  |  |
|  | Results Area # 1.4: Infrastructure, Logistics and Facilitation |  |  |  |  |  |  |  |  |  |
|  | 1.4.1: Invest in production inputs, infrastructure, logistics and services for value-addition and value chain facilitation, including cold-storage and processing facilities, quality equipment and packaging, and Lumo upgrading. | 50,000 | 180,000 | 180,000 | 180,000 | 180,000 | MoA / MoFWR / DCD / MoTIE (GCCI / GWCC / GYCC / GSCC / CGI) / LGAs |  | 75600 Conferencing 71300 Local Consultant 72100 Contractual Services Companies (Construction) | 770,000 |
|  | Results Area # 1.5: Market Access & Expansion |  |  |  |  |  |  |  |  |  |
|  | 1.5.1: Promote domestic, AfCFTA and international market access, expansion and scaling by smallholder/producer agglomeration, connections to domestic hospitality industry, “Made in Gambia” initiatives, export readiness programmes, and third-party product testing and certification for priority value chains. | 100,000 | 180,000 | 155,000 | 290,000 | 190,000 | MOTIE / GIEPA / MOFA / MOTAC / LGAs |  | 75700 Conferencing 71400 technical supports, 71600 Travel & 72500 Supplies (trade fairs ) | 715,000 |
|  | Sub-total Output 1 |  |  |  |  |  |  |  |  |  |
| Output 2: Governance frameworks, institutional capacities and digital systems strengthened to deliver coherent, data-driven policies, efficient services, and inclusive market conditions supporting enterprise growth and social protection. ￼￼) Contribution to Portfolio Momentum Contribution to Portfolio Learnings Gender Marker: [SELECT GENDER MARKER] | Results Area #2.1: Policy, Strategy & Regulation |  |  |  |  |  |  |  |  |  |
|  | 2.1. Enhance sector policy relevance and effectiveness to support inclusive growth by review and implementation of the MSME Policy, Employment policy, Formalization Policy, TVET Policy, Land Policy, Social Protection Policy, and Lumo Modernization Strategy. | 25,000 | 100,000 | 75,000 | 70,000 | 70,000 | MOTIE / MOHERST / MOLRG / NSPA / LGAs |  | 75600 Conferencing 71300 Local Consultant 72100 Contractual Services Companies (Construction) | 315,000 |
|  | 2.2 Strengthen macro-policy framework for inclusive growth by support for the operationalization of the Integrated Financing Framework, establishment of a centralized Aid Management Platform, formulation of the Human Development Report, review of the RF-NDP (2023-2027) and the National Voluntary Review of SDGs. | 200,000 | 257,625 | 157,625 | 167,625 | 167,625 | UNDP / MOTIE / MOFEA |  | 71400 Technical assistance, 75700 Conferencing, 71300 Local Consultant (System development) | 903,125 |
|  | Results Area # 2.2: Institutional Capacities |  |  |  |  |  |  |  |  |  |
|  | 2.2.1: Strengthen capacity of MoTIE for value chain facilitation, industry development and coordination, and AfCFTA negotiations and market participation. | 50,000 | 175,000 | 110,000 | 110,000 | 110,000 | MOTIE / (GSB/FSQA/ GCCPC) |  | 75700 Conferencing 71600 Travel | 555,000 |
|  | 2.2.2: Strengthen local government capacity, systems and processes to provide businesses facilitating services (registration, licencing, tax administration, investment facilitation, land allocation) in 2-3 LGAs. |  |  |  |  |  | MOTIE / GIEPA / MOFEA / MOLRG / LGAs |  |  |  |
|  | 2.2.1: Enhance key/relevant government capacities for youth employment creation through institutional support to the Gambia Songhai Initiative and the National Youth Service Scheme. | 190,000 | 150,000 | 150,000 | 150,000 | 150,000 | MOYS | UNDP | 75700 Training 72200 equipment 71300 Local Consultants 71600 Conferencing | 790,000 |
|  | Results Area # 2.3 Data, Digital Tools & Services |  |  |  |  |  |  |  |  |  |
|  | 2.3.1: Develop and expand digital tools and data capacities to strengthen public service delivery and evidence-based decision-making, including the Single Window Portal, , an MSME data portal and annual census, and trade related R&D capacities. | 0 | 200,000 | 125,000 | 100,000 | 100,000 | MoTIE / MOFEA (GBOS)/ LGAs | UNDP | 75700 Training 71300 Consultancy | 525,000 |
|  | Sub-total Output 2 |  |  |  |  |  |  |  |  |  |
| Output 3: Climate-resilient infrastructure, livelihoods and social protection systems strengthened to reduce vulnerability and enhance adaptive capacity of communities to climate-related shocks and stresses. (Resilient Livelihoods & Sustainable Infrastructure) Contribution to Portfolio Momentum Contribution to Portfolio Learnings Gender Marker: [SELECT GENDER MARKER] | Results Area # 3.2: Climate Adaptation |  |  |  |  |  |  |  |  |  |
|  | 3.2.1: Promote the expansion of climate-smart value chains through needs assessment, sensitization, capacity building and incentives mechanisms. |  | 30,000 | 15,000 | 15,000 | 15,000 | MECCNAR / MoA / MoTIE / LGAs |  |  | 75,000 |
|  | 3.2.2: Develop and pilot a green credit scheme for rural businesses to adopt smart climate technologies and sustainable practices. |  | 10,000 | 10,000 | 10,000 | 10,000 | MECCNAR / LGAs |  |  | 40,000 |
|  | Results Area # 3.3: Social Protection |  |  |  |  |  |  |  |  |  |
|  | 3.3.2: Ensure inclusion and expand opportunities for Women with Disabilities, through Talent & Innovation, and Institutional Support in MSME and value chain development | 50,000 | 50,000 | 50,000 | 50,000 | 50,000 | MoGCSW | UNDP | 71600 travel & 72500 Printing (Trade Fairs) 75700 Training & Conferencing | 250,000 |
|  | Sub-total Output 3 |  |  |  |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  |  |  |  |  |

This MYWP is an integral part of the Portfolio Document and is subject to all the provisions in the Portfolio Document, including the Legal Context and the Risk Management Sections. The implementation modality selected in the MYWP will determine which specific legal provisions in the Risk Management Section will apply to each Implementing Partner. The option selected here will also determine the option in the Legal Context section that will apply to the Implementing Partner. The MYWP contributes to the portfolio results. Risks emerging from the implementation of the MYWP will be reflected in the portfolio risk register.

Agreed by:

| UNDP |  | Ministry of Trade , Industry, Regional Integration & Employment (MoTIE) |
| --- | --- | --- |
| <Name> |  | <Name> |

Annex 8. Portfolio Theory of Change

Vision and Intent

By 2030, The Gambia stands as a connected, inclusive, and climate-resilient economy, one that expands opportunity for the bottom 40 percent, especially women and young people, while safeguarding the nation’s natural and social capital.
The portfolio envisages local economies as engines of transformation, powered by people and enterprises that innovate, produce, and trade, and anchored by institutions that are transparent, responsive, and trusted. Together, these local and national systems form the foundation of a resilient and inclusive society. The ultimate benefit for people is a future where livelihoods are secure, governance is credible, ecosystems are thriving, and every Gambian can live with dignity in the face of economic and climatic uncertainty.

Core Hypothesis

Systemic transformation happens when inclusion, accountability, and resilience progress together across three interdependent levels: local (micro), institutional (meso), and national/regional (macro). The portfolio’s fundamental hypothesis is that inclusive economic opportunities, accountable governance, and climate resilience reinforce one another through feedback loops of trust, innovation, and investment. Transformation is therefore not a product of isolated projects but of integrated change: a dynamic system where small shifts accumulate into structural transformation.

Pathways of Change

- Inclusive and Green Value Chains for Decent Work (Linking Micro to Meso to Macro): Empowering MSMEs, cooperatives, and producers to participate in green and blue value chains diversifies the economy and generates decent work. When national trade, finance, and skills policies align with local innovation, productivity and inclusion rise together. The AfCFTA serves as the continental platform for scaling Gambian value chains and exports, linking national transformation to regional opportunity.

- Accountable Governance and Enabling Systems for Inclusion (Linking Macro to Meso): Transparent, participatory, and data-driven governance builds trust between citizens, markets, and the state. Improved coordination among ministries, local governments, and communities ensures policy coherence from the capital to the community level. Accountability becomes tangible when citizens shape the services and policies that affect their daily lives.

- Climate and Resilience Infrastructure for Sustainable Prosperity (Linking Meso to Micro): Integrating climate adaptation, renewable energy, and sustainable infrastructure into community livelihoods turns resilience into a productive asset rather than a defensive measure. When climate investments are locally driven but nationally enabled, they unlock green finance, regenerate ecosystems, and expand the adaptive capacity of people and institutions alike.

Dynamic Interactions and Feedback Loops

Change in one domain will accelerate progress in the others:

- Local innovations in value chains and adaptation generate visible results that influence national policy and attract finance.

- Stronger governance creates enabling conditions for local solutions to scale equitably and efficiently.

- Climate-smart investments safeguard gains and catalyze new opportunities for inclusive growth.

- Continuous feedback between local experience and national learning sustains portfolio momentum; the self-reinforcing cycle of trust, innovation, and institutional responsiveness that underpins sustainable transformation.

Assumptions

- Political and partner commitment to inclusive, climate-resilient growth remains strong.

- Fiscal stability, policy coherence, and institutional capability improve progressively.

- Women and youth remain active participants in shaping markets and policies.

- Regional trade and integration opportunities under AfCFTA continue to expand.

Risks

- Fiscal shocks or macroeconomic instability could constrain public investment.

- Institutional fragmentation or policy inertia may slow implementation.

- Climate disasters or global crises could disrupt progress.

- Digital and green transitions risk deepening inequality if not designed inclusively.

Opportunities

- Regional momentum through AfCFTA and the AU–UNDP Blue and Green Transition Programmes.

- Growing donor and private-sector appetite for blended finance and impact investment.

- A dynamic generation of Gambian youth and entrepreneurs driving digital, social, and green innovation.

Partnerships as Enablers

Transformation depends on a broad coalition of actors:

- Government partners (Finance, Trade, Environment, Gender, Youth) ensure national policy coherence and reform.

- Local governments link policy to people through participatory planning and local economic development.

- Private sector and financial institutions drive innovation, investment, and employment creation.

- Civil society, youth, and women’s networks co-create and monitor solutions for inclusion and accountability.

- Development partners and regional bodies (AfDB, UNCTAD, AU, ECOWAS, AfCFTA Secretariat) provide finance, knowledge, and South-South learning.

- UNDP serves as a systems integrator, connecting actors, aligning incentives, and turning local innovation into policy reform and regional learning.

Theory of Change Hypothesis

If local economies are empowered to innovate and link to markets; and if governance systems are transparent, participatory, and evidence-based; and if climate investments protect ecosystems and strengthen livelihoods;
then The Gambia will shift from fragmented and vulnerable systems to a self-reinforcing cycle of inclusive, diversified, and climate-resilient growth enabling prosperity that is both sustainable and inclusive.

Note: Adjust signature as needed. Endorsement of the government development coordination authority may be satisfied in one of four ways. Please see the PPM Appraise and Approve Policy.

By comparison: Mali 35.7%; Niger 32.9%; Benin 34.4%; Senegal 36.2%; Sierra Leone 35.7%; 35.3%; Ghana 51.1%; Nigeria 35.1% - Average for 11 SSA countries 37.01.

In setting Results Framework indicators please note: UNDP publishes its portfolio/project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards. Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audiences clearly understand the results of the portfolio.

This shift links MSMEs and cooperatives (micro) with emerging local clusters and municipal value chains (meso), supported by national trade and investment frameworks (macro) that unlock regional opportunities under the AfCFTA. It focuses on expanding productive inclusion by connecting small producers to sustainable markets, promoting value addition in agribusiness, fisheries, tourism, and digital trade, and ensuring that youth- and women-led enterprises are positioned as central actors in The Gambia’s green and blue transition.

At the meso level, decentralized institutions and local councils act as integrators, translating national policies into inclusive services and enabling community enterprises to thrive within formal systems.

This shift focuses on strengthening The Gambia’s resilience architecture by expanding access to renewable energy, promoting sustainable land and coastal management, and improving the flow of climate finance to the local level. It advances nature-based and community-driven solutions that reduce vulnerability while supporting livelihoods and productivity. This shift ensures that infrastructure investments and climate finance operate coherently across levels (national frameworks (macro) guiding investments, local governments (meso) coordinating delivery, and communities and enterprises (micro) adapting and innovating for resilience).

IP will need to demonstrate, through the multi-year work-plan and budget, that they have sufficient resourcing and capacity to manage and capture their contributions to the Portfolio Momentum and Portfolio Learning results categories of the Portfolio Results Framework.

These learning loops operationalize the Theory of Change, translating its assumptions, causal pathways, and evidence feedback into adaptive portfolio management and real-time decision learning.

Optional, if needed

Additional implementing partners may be included in the portfolio during its implementation.

Use bracketed text only when IP is an NGO/IGO

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner

Applicable for non-UNDP Implementing Partners that act as grant making Institution facilitating on-granting.