Country/Region/Global: Nigeria

Initiation Plan

Project Title	:	Accelerating Community Development & Local Governance Performance in Nigeria

Expected UNSDCF/CPD Outcome(s)	:	By 2027, more inclusive, participatory, transparent, and gender-sensitive governance, justice, and human rights systems are in place at all levels to promote acceleration in achieving the 2030 Agenda and SDGs for a peaceful, inclusive, and cohesive society.

Expected CPD Output(s)	:	Output 3.4: Strengthened System Institutions and Capacities for Transitioning to Development Solutions and for Inclusive and Gender Response Peace Building.

Initiation Plan Start/End Dates	:	January – December 2026

Implementing Partner	:	_____________________________________

The Accelerating Community Development & Local Governance Performance (ACD–LGP) is a catalytic TRAC-2 investment designed to strengthen Nigeria’s local governance and ward-level capacity for effective governance performance and service delivery. Aligned with the UNDP Strategic Plan 2026–2029, the ACD-LGP targets the nation’s "weakest link" by strengthening the functional and service-delivery capacity of LGAs across eight states. With a focus on effective governance and prosperity for all, the ACD-LGP activates sustainable finance as a primary accelerator, promising to unlock domestic co-financing through state budgets, private investors, and development finance institutions. A central pillar of focus is the development of investment-ready delivery packages to modernize community infrastructure, ensuring that macro-reforms translate into tangible livelihood improvements and development outcomes for LGAs. Critical interventions include creating a toolkit for implementing the Renewed Hope Ward Development Project (RHWDP) as a national execution framework and introducing digital dashboards to monitor budget execution and shorten procurement cycle times. The geographical focus of ACD-LGP corresponds with the ISSP target states to ensure a comprehensive rural transformation. Partnerships are structured as multi-level delivery compacts involving federal ministries, state governors, and institutions such as the African Development Bank. Ultimately, the ACD–LGP model seeks to create a self-reinforcing cycle of performance and finance that restores citizen trust through visible development results at scale.

The Accelerating Community Development & Local Governance Performance (ACD–LGP) is a catalytic TRAC-2 investment designed to strengthen Nigeria’s local governance and ward-level capacity for effective governance performance and service delivery. Aligned with the UNDP Strategic Plan 2026–2029, the ACD-LGP targets the nation’s "weakest link" by strengthening the functional and service-delivery capacity of LGAs across eight states. With a focus on effective governance and prosperity for all, the ACD-LGP activates sustainable finance as a primary accelerator, promising to unlock domestic co-financing through state budgets, private investors, and development finance institutions. A central pillar of focus is the development of investment-ready delivery packages to modernize community infrastructure, ensuring that macro-reforms translate into tangible livelihood improvements and development outcomes for LGAs. Critical interventions include creating a toolkit for implementing the Renewed Hope Ward Development Project (RHWDP) as a national execution framework and introducing digital dashboards to monitor budget execution and shorten procurement cycle times. The geographical focus of ACD-LGP corresponds with the ISSP target states to ensure a comprehensive rural transformation. Partnerships are structured as multi-level delivery compacts involving federal ministries, state governors, and institutions such as the African Development Bank. Ultimately, the ACD–LGP model seeks to create a self-reinforcing cycle of performance and finance that restores citizen trust through visible development results at scale.

Total resources required           	$ 1000,000

Total allocated resources:	_________

- Regular			_________

- Other:

  - Donor		_________

  - Donor		_________

  - Government	_________

Unfunded budget:		_________

In-kind Contributions		_________

Total resources required           	$ 1000,000

Total allocated resources:	_________

- Regular			_________

- Other:

  - Donor		_________

  - Donor		_________

  - Government	_________

Unfunded budget:		_________

In-kind Contributions		_________

Programme Period:		Jan – Dec 2026

Quantum Project Number:	______________

Quantum Output Number:	______________

Gender Marker:			2

Programme Period:		Jan – Dec 2026

Quantum Project Number:	______________

Quantum Output Number:	______________

Gender Marker:			2

Agreed by UNDP:

# ABBREVIATION

ACD–LGP 	Accelerating Community Development & Local Governance Performance

AfDB 		African Development Bank

BoA 		Bank of Agriculture

BoI 		Bank of Industry

DBN 		Development Bank of Nigeria

DFIs, 		Development Finance Institutions

FMBEP 	Federal Ministry of Budget and Economic Planning

GBV 		Gender-Based Violence

IsDB 		Islamic Development Bank

ISSP 		Integrated Smart States Programme

LED 		Local Economic Development

LGA		Local Government Area

MoF 		Ministry of Finance

MSME 	Micro, Small, and Medium Enterprises

MTEF		Medium-Term Expenditure Framework

PFM		Public Financial Management

PPPs 		Public-Private Partnerships

PPPs 		Public–Private Partnerships

RHWDP 	Renewed Hope Ward Development Project

SOP 		Standard Operating Procedures

UN		United Nations

UNDP		United Nations Development Programme

# Purpose and Expected Output

The Accelerating Community Development & Local Governance Performance in Nigeria (ACD–LGP) is a catalytic TRAC-2 investment that tackles Nigeria’s most binding development constraint: weak local governance and ward-level execution, the point where political ambition, public finance, service delivery, and citizen trust converge.

Nigeria stands at a critical inflection point. Far-reaching macroeconomic reforms are underway; domestic fiscal space is tightening; multilateral financing is contracting; and demand for visible, people-centred results is intensifying as the country approaches the 2027 electoral cycle. In this environment, the government's credibility increasingly depends on whether national reforms translate into tangible improvements in livelihoods and basic services at the community level. While reform momentum at the federal and state levels is significant, Nigeria’s federal structure makes states and local governments the primary execution frontier. The weakest link in the delivery chain remains LGAs and wards, where execution failure most often undermines reform impact.

UNDP Nigeria has already responded through a decisive institutional transformation. In 2025, the Country Office pivoted from fragmented projects to a portfolio-based operating model anchored on the Integrated Smart States Programme (ISSP), linking federal reforms, state leadership and financing, local delivery systems, and community innovation ecosystems. This shift has unlocked USD 50–80 million in state co-financing by end-2025, with a trajectory toward USD 200 million by 2027, demonstrating a clear lesson: when UNDP brings speed, credible delivery systems, and investment-ready portfolios, governments invest their own resources at scale.

However, sustaining and scaling this momentum now depends on strengthening the most politically sensitive and operationally fragile layer of the system: LGAs and wards. Without reliable delivery routines, financial discipline, performance management, and citizen accountability at this level, state-level reforms cannot translate into durable development outcomes.

At the same time, the Federal Government has launched the Renewed Hope Ward Development Project (RHWDP) as a national flagship forward-level transformation, but it currently lacks the delivery architecture, results systems, and investment packaging required to function as a true execution engine. This TRAC-2 proposal directly addresses both challenges.

With USD 1 million (Feb–Dec 2026), ACD–LGP deploys catalytic capital to:

- Fortify the local governance delivery frontier across 15–20 LGAs in 8 states through performance systems, Public Financial Management (PFM) and procurement routines, accountability and grievance mechanisms, and basic digital workflows.

- Convert political ambition into costed, sequenced, investment-ready pipelines by producing 30+ ward/LGA delivery packages, supported by energy audits and facility readiness diagnostics;

- De-risk and accelerate Government Development Finance, unlock USD 10–20 million in domestic and blended co-financing through state/LGA budgets, DFIs, PPPs, and Energy-as-a-Service models; and

- Operationalize RHWDP through a federal delivery toolkit, results framework, alignment clinics, and a national replication pathway under ISSP for 2027–2028 scale.

By end-2026, the initiative is expected to deliver measurable improvements in local execution, service reliability, economic opportunity, and citizen trust, creating a self-reinforcing cycle of systems → performance → finance → scale → impact that positions UNDP as the system integrator and investment catalyst for Nigeria’s next phase of transformation.

2. Strategic Alignment

2.1 Strategic Alignment with UNDP Strategic Plan 2026–2029

The ACD–LGP initiative is fully aligned with the UNDP Strategic Plan 2026–2029, advancing all four Strategic Objectives and activating the three Accelerators of Progress through an integrated, systems-level approach anchored in Nigeria’s national reform agenda and sub-national delivery architecture.

- UNDP Strategic Plan 2026–2029: The UNDP Strategic Plan 2026-2029 marks a bold evolution in the organization's approach, focusing on four primary objectives: prosperity for all, effective governance, crisis resilience, and a healthy planet. This new cycle is powered by three high-impact "accelerators" digital and AI transformation, gender equality, and sustainable finance to drive systemic change. By moving beyond the minimum poverty line, the UNDP aims to help countries build dynamic, resilient economies that can withstand global shocks.

- UN 2030 Agenda for Sustainable Development: Adopted by all United Nations Member States in 2015, the 2030 Agenda provides a shared global vision for peace and prosperity for people and the planet. At its heart are the 17 Sustainable Development Goals (SDGs), which constitute an urgent call to action for all countries in a global partnership. These goals recognize that ending poverty must go hand in hand with strategies that improve health and education, reduce inequality, and spur economic growth. The agenda is unique in its "indivisible" nature, meaning that the economic, social, and environmental dimensions of development must be balanced.

- Renewed Hope Ward Development Programme (RHWDP): The Renewed Hope Ward Development Programme (RHWDP) is a grassroots socio-economic initiative launched under President Bola Tinubu’s administration in Nigeria. Designed to be highly data-driven, it targets poverty at the most granular level, the ward, to ensure that federal interventions reach the "poorest of the poor" directly. By decentralizing development, the programme aims to bypass bureaucratic bottlenecks and foster economic growth from the bottom up. It focuses on empowering small-scale businesses, supporting the elderly, and creating inclusive opportunities regardless of political or religious affiliation.

The RHWDP aligns seamlessly with the UNDP’s mission by localizing the "Leaving No One Behind" principle through direct ward-level interventions. It mirrors the UNDP Strategic Plan’s focus on structural transformation by shifting development power to subnational authorities and local communities. Similarly, the programme supports the Accelerated Community Development and Local Governance Programme (ACD-LGP) by strengthening the capacity of local institutions to manage resources and deliver basic services.

Alignment with the Four Strategic Objectives

Prosperity for All. The project expands inclusive economic opportunity by converting ward and LGA priorities into investment-ready Local Economic Development (LED) packages, modernizing markets, strengthening Micro, Small, and Medium Enterprises (MSMEs), and unlocking domestic and private finance. These interventions directly raise productivity, incomes, and local revenue, with strong benefits for women and youth.

Effective Governance. ACD–LGP tackles Nigeria’s core execution constraint by institutionalizing credible local governance and delivery systems, including public financial management routines, procurement reform, performance dashboards, accountability mechanisms, and grievance redress. This strengthens state capacity, transparency, and citizen trust while ensuring public resources translate into visible development results.

Crisis Resilience. By embedding risk-informed planning, climate and disaster screening, conflict sensitivity, and people-centred accountability platforms into local delivery systems, the project strengthens community resilience to economic, social, climate, and security shocks, particularly in fragile and politically sensitive regions.

Healthy Planet. The project integrates sustainable energy access, productive-use energy solutions, climate-resilient infrastructure standards, and environmental risk screening into community development and service delivery packages, supporting climate adaptation, emissions reduction, and sustainable management of natural resources.

Activation of the Strategic Accelerators

The ACD-LGP is a catalytic initiative designed to unlock USD 10–20 million in domestic co-financing, structure blended finance pipelines, and crowd in private investment, transforming political ambition into bankable delivery at scale. Gender equality is embedded as a design requirement and performance measure, with quantified commitments for women’s participation, leadership in accountability systems, access to economic opportunities, and gender-responsive service delivery, strengthening both development impact and institutional legitimacy. The project will deploy digital public financial management workflows, performance dashboards, asset registries, service-tracking systems, and delivery intelligence platforms that will improve transparency, speed, accountability, and evidence-based decision-making at all levels of implementation.

Systems Transformation and Scale

By strengthening Nigeria’s most fragile delivery frontier, local governance and ward-level execution, and anchoring these reforms within the ISSP and the national RHWDP, ACD–LGP operationalizes UNDP’s 2026–2029 systems-based development approach: connecting institutions, finance, services, communities, and markets into a coherent, scalable national transformation model.

3. Project Objective and Value Proposition

Project Objective

To strengthen local governance delivery systems and generate investment-ready community development packages across strategically selected pilot states, while providing federal enablement to operationalize the RHWDP as a scalable national platform for ward-level delivery under the ISSP.

Value Proposition

The catalytic investment positions UNDP as the preferred partner for the government(?) in navigating the challenges of diminishing multilateral financing, serving as a systems integrator to translate reforms into tangible results, and acting as an investment catalyst that transforms public ambitions into achievable outcomes. TRAC-2 funding is leveraged not for isolated activities but as catalytic capital to institutionalize scalable local governance models, generate essential delivery intelligence such as energy audits and facility diagnostics, unlock and structure domestic public financing, and facilitate national replication through initiatives like RHWDP and ISSP.

4. Theory of Change and Delivery Logic

If UNDP Nigeria, through the ISSP, strengthens local governance delivery systems, professionalizes LGA performance management, installs financial discipline and accountability mechanisms, and generates investment-grade community delivery packages—while simultaneously equipping the Federal Government with the tools to operationalize RHWDP—then:

- State and LGA political ambition will convert into executable, costed, and financed delivery pipelines;

- Community-level service reliability and local economic activity will improve;

- Domestic public financing will crowd-in private and development finance;

- Citizen trust in public institutions will strengthen; and

- Nigeria will achieve visible development results at scale before the 2027 elections.

This creates a self-reinforcing cycle: Systems → Performance → Finance/Investment → Scale → Impact → Trust → Stronger Systems. This underpins sustainable national transformation.

Operational Delivery Logic

The ACD-LGP aims to operationalize a transformative programme by equipping Local Government Areas (LGAs) with five interlocking delivery capabilities. These include bottom-up, ward-anchored planning; integrated digital public financial management and revenue systems with safeguards for autonomy; modernized community economic infrastructure (such as markets, cold chains, productive-use energy, and service billing); people-centered platforms for peace, justice, and accountability; and climate-resilient investment planning and infrastructure. By implementing these capabilities together, LGAs can translate political commitments and public spending into tangible improvements in services, livelihoods, and local economic activity, thereby fostering citizen trust and enabling large-scale Government Development Finance.

5. Implementation Design

5.1  Spatial Targeting

Spatial targeting principle: Select states and LGAs where (i) ISSP momentum and reform interest exist, (ii) co-financing prospects are credible, and (iii) pilots can generate demonstration effects for national replication through RHWDP.

South-East Cluster

- Ebonyi (flagship pilot): Align with Ebonyi development agenda (e.g., EB-REDI / People’s Charter). Pilot LGAs focus on integrated rural transformation, governance and performance systems, and energy audits for schools/PHCs and productive clusters.

- Abia: 2–3 LGAs adopt ACD–LGP package, aligned to ISSP pipeline and co-financing pathways.

South-South Cluster

- Akwa Ibom and Bayelsa: 2–3 LGAs each; adaptation to coastal/climate realities and energy-linked livelihoods; LED platforms; accountability and performance systems; investment packaging for modernized markets and community services.

- Other Regional Pilots (for national demonstration and political economy balance)

- North-Central: Plateau (leverage strong reform and co-financing momentum; LGA performance routines and visible service reliability packages).

- North-East: Taraba (service reliability and delivery packages, adapted to fragility and access constraints).

- North-West: Katsina (delivery frontier focus; systems strengthening; resilience-informed packages).

- South-West: Ogun & Lagos (demonstration of digital enablement, market systems, and scalable dashboards; link to innovation ecosystems where relevant).

Federal Enablement

- FMBEP/MoF and national RHWDP architecture: Development of RHWDP operationalization toolkit, results framework, prioritization logic, package templates, accountability/performance monitoring instruments, and integration pathway to ISSP ACD–LGP replication.

5.2 Sustainable Finance Accelerator

The ACD–LGP TRAC-2 investment is designed as catalytic capital. Each USD 1 of TRAC-2 funding targets USD 10–20 in leveraged financing from:

- State & LGA budget allocations

- Performance-linked grants and fiscal transfers

- Development Finance Institutions (DFIs)

- Public–Private Partnerships (PPPs) and private investors

- Energy-as-a-Service and service-based financing models

Concrete Financing Pathways.  The project activates financing through five structured channels:

- State & LGA Budget Integration — formal co-financing commitments, budget tagging, MTEF alignment

- Performance-Linked Grants — tied to delivery benchmarks and governance reforms

- Energy-as-a-Service Models — off-balance-sheet service reliability investments for facilities and markets

- DFI Co-Financing & PPP Structuring — pipeline notes for blended finance and private participation

- ISSP Portfolio Scale Platform — national replication & investment packaging

Transition Logic: Diagnostics → Pipeline (through cocreation) → Financing → Execution → Scale. This transition logic converts political intent into executable investment pipelines and sustained delivery at scale.

5.3	Gender Equality & Women’s Empowerment

Gender Marker: GEN 2 – Gender-Responsive

Quantified Commitments

- ≥50% women representation in ward committees and grievance redress mechanisms

- ≥60% women beneficiaries of LED, market, and service delivery packages

- Dedicated Gender-Based Violence (GBV) referral & service safety indicators embedded in accountability platforms

These commitments are embedded in planning protocols, delivery packages, performance dashboards, and learning products.

Gender equality is treated as a performance multiplier in this initiative. By embedding women’s voice, leadership and economic participation into ward planning, delivery routines, accountability systems and investment packaging, the project strengthens the quality of local decision-making, reduces capture risks, improves service access and legitimacy, and expands the base of viable local enterprises—thereby reinforcing sustainable finance and the scale pathway under RHWDP.

5.4	Partnership Architecture for Scale

Given Nigeria’s federal structure and the delivery focus of this intervention, partnerships are structured as execution and financing instruments rather than coordination platforms. Partnership Strategy (Multi-Level, Delivery-First, Finance-Anchored). ACD–LGP is intentionally designed as a federal–state–local delivery and financing compact under UNDP Nigeria’s ISSP. Partnerships are structured to do three things simultaneously: (i) install credible local governance delivery systems, (ii) convert community priorities into investment-ready packages, and (iii) unlock domestic and blended finance at scale. Collaboration is not treated as coordination for its own sake; it is a deliberate division of labour across policy enablement, sub-national execution, financing mobilisation, and citizen accountability.

A. Federal Government Partnerships (National Enablement and Scale)

Federal Ministry of Budget and Economic Planning (FMBEP) and the Ministry of Finance (MoF) will be the primary federal counterparts for RHWDP operationalization, including endorsement and adoption of the RHWDP delivery toolkit, results framework, prioritization logic, and replication pathway. Federal technical working arrangements will ensure alignment between RHWDP’s national intent and ISSP’s delivery architecture so that RHWDP functions as a credible national execution platform rather than a standalone initiative. Other relevant national entities (as required by RHWDP operationalization) will be engaged through federal–state technical alignment sessions, ensuring coherence on targeting, safeguards, results reporting, and adoption protocols.

B. State Government Partnerships (Co-Financing, Enabling Environment, Scale Readiness)

The eight pilot states—Ebonyi (flagship), Abia, Akwa Ibom, Bayelsa, Plateau, Taraba, Katsina, Ogun and Lagos—are not just beneficiaries; they are co-investors and scale partners. Collaboration is anchored in:

- Formal co-financing commitments, budget tagging, and Medium-Term Expenditure Framework (MTEF) alignment;

- Enabling state-level support functions (planning, procurement oversight, audit response systems) that support LGA delivery without undermining LGA autonomy safeguards; and

- State convening power to align LGAs, sector MDAs, communities, and private actors around a single, sequenced delivery pipeline.

The partnership model builds on the ISSP breakthrough of mobilizing USD 50–80 million in state co-financing (with a trajectory toward USD 200 million by 2027) and extends this momentum into the ward/LGA execution frontier.

C. Local Government and Ward-Level Collaboration (Execution, Accountability, Citizen Trust)

Pilot LGAs and ward structures are the core implementation platform. Collaboration will focus on:

- Establishing delivery routines (planning–budget–procurement–service monitoring–feedback loops);

- Institutionalizing minimum PFM and procurement standards and transparent reporting as entry conditions;

- Operationalizing grievance redress and citizen feedback mechanisms, including safe and aggregated publication of trends and response tracking; and

- Ensuring inclusive participation, especially women, youth, and persons with disabilities, in ward committees and accountability platforms.

D. Development Finance Institutions and Financial Institutions (Pipeline Financing and Scale)

Partnerships with DFIs and domestic financial institutions are expected to shift from “interest” to bankable pipeline co-creation, leveraging the project’s investment-grade diagnostics and pipeline notes. Priority collaboration pathways include:

- African Development Bank (AfDB): potential co-creation of technical facilities for sub-national investment readiness (energy and service reliability cases);

- Islamic Development Bank (IsDB): alignment with Nigeria engagement pipelines that rely on investment readiness and scalable delivery systems;

- Bank of Industry (BoI): linkages to rural MSME inclusion and enterprise support; commercialization pathways for community and local clusters;

- Development Bank of Nigeria (DBN): structured pipeline notes to address investment-readiness bottlenecks, especially in underserved regions;

- Bank of Agriculture (BoA): support to local agribusiness value chains and community economic packages where relevant; and

- Afreximbank: engagement on trade, MSME, and cluster-based finance where pipeline notes mature.

These partnerships will be activated through bankable pipeline notes (energy, LED, service reliability), standardized investment packaging, and co-financing arrangements anchored in state/LGA budget credibility.

E. Private Sector and Service Providers (Execution Efficiency and Service-Based Financing)

Private sector collaboration will focus on:

- Energy-as-a-Service models for health facilities, schools, and markets (off-balance-sheet service reliability investments where feasible);

- PPP structuring support for market modernization, cold-chain systems, and service billing pilots;

- Vendor quality assurance protocols and streamlined procurement approaches to reduce cycle time and ensure value for money.

F. UNDP and UN System Collaboration

Within UNDP, the programme will leverage portfolio capabilities across Governance, Sustainable Finance, Digital Transformation, Crisis Prevention/Resilience, and Energy/Climate to deliver integrated systems strengthening. Where relevant, the UN system coordination will align on safeguards, inclusion, and risk management in fragile contexts, without creating parallel coordination burdens.

Partnership Outputs Expected

- Federal adoption of RHWDP toolkit and results framework;

- Co-financing agreements and budget tagging in pilot states/LGAs;

- DFI/private sector engagement through pipeline notes and structured financing pathways;

- Functioning citizen feedback and grievance redress systems that strengthen trust and reduce capture.

6. Risk Analysis and Mitigation Measures

The ACD–LGP design deliberately treats risk as a delivery variable: systems + routines + transparency + performance dashboards + investable packaging reduce leakage, improve credibility of spending, and accelerate co-financing. Risks are managed through a modular roll-out, strong safeguards, and “delivery labs” that troubleshoot execution bottlenecks in real time.

| No | Risk | Rating | Mitigation Measures |
| --- | --- | --- | --- |
| 1. | Fiscal stress / delayed releases and co-financing shortfalls | High | Phase implementation by readiness and fiscal calendar; prioritize “quick-win” investments and high-visibility service reliability improvements; secure written co-financing/commitment notes and budget tagging within MTEF/annual budgets; adopt modular delivery packages (can proceed with partial funding); link each package to realistic CAPEX/OPEX and maintenance assumptions to avoid unfunded liabilities. |
| 2. | Political economy capture/ leakage/diversion of local resources | High | Implement minimum safeguards as entry conditions (open reporting, basic procurement routines, audit response); deploy performance dashboards and monthly reporting; strengthen citizen feedback + grievance redress with escalation pathways; apply risk screening and integrity checks in investment packaging; promote ward-to-budget concordance and public disclosure of package selection criteria. |
| 3. | Weak LGA capacity (planning, PFM, procurement, data, delivery routines) | Medium–High | Provide surge technical assistance and embedded coaching; training-of-trainers for sustainability; simplified tools/templates; peer learning across LGAs; “delivery routine” playbooks (budget execution tracking, procurement workflow, facility uptime monitoring); leverage state-level support functions without undermining LGA autonomy safeguards. |
| 4. | Procurement delays and market availability constraints | Medium | Use framework/roster approaches where permissible; pre-agreed technical specifications for common goods/services; establish delivery lab troubleshooting (procurement clinics); vendor quality assurance protocols; phase pilots with items having shorter lead times; integrate a procurement cycle time indicator to drive behavior change. |
| 5. | Data quality, fragmented reporting, and dashboard credibility risk | Medium | Adopt standardized templates and minimum data standards; geotagging protocols for facilities/market assets; periodic data quality reviews; define “dashboard minimum viable dataset” (budget execution, procurement cycle time, service uptime proxies, grievance stats, gender disaggregation); align RHWDP results instruments with ISSP reporting logic. |
| 6. | Autonomy and intergovernmental coordination risks (state interference / LGA trust deficits) | Medium–High | Establish clear governance arrangements in the Framework: roles, decision rights, and safeguards; embed transparency provisions; use state convening for alignment while keeping ward/LGA prioritization logic visible and rules-based; utilize Governors Forum and State Ministries of Local Government as conveners and enablers, not controllers; apply jointly agreed protocols for fund flow and reporting. |
| 7. | Social tension/insecurity disrupting field delivery | Medium | Integrate people-centred peace, justice, and accountability platforms; coordinate with state security and justice actors using rights-compliant Standard Operating Procedures (SOPs); conflict sensitivity and do-no-harm screening in delivery packages; flexible scheduling and remote support options where needed. |
| 8. | Climate and disaster shocks (flooding, extreme weather) affecting assets and service continuity | Medium | Include risk-informed siting and design (elevated plinths, drainage buffers, resilient standards); integrate facility readiness and climate risk screening into packages; preparedness measures (community wardens, drills where applicable); include O&M planning to protect functionality. |
| 9. | Inclusion gaps (women, youth, persons with disabilities left behind) | Medium | Set participation and benefit targets; gender-responsive consultation design; track benefits with sex/age disaggregation; ensure women’s representation in accountability and market governance structures; integrate GBV referral considerations where relevant; apply safeguards to ensure vulnerable groups are not excluded from upgraded services or market opportunities. |
| 10. | Reputational risk (high expectations vs. visible results timeline) | Medium | Maintain disciplined scope: focus on functionality and results reliability; sequence for early visible wins; proactive communications grounded in verified results; publish progress through dashboards and learning products; manage partner expectations via milestone-based delivery plans. |

# Management Arrangements

UNDP Country Office envisions a transformed portfolio that prioritizes innovative quality assurance, proactive risk management, and seamless partner coordination to enhance results reporting and learning. In partnership with the Federal Ministry of Finance and Economic Planning (FMBEP), our efforts will turbocharge the Rural Health and Water Development Project (RHWDP) by aligning national strategies with cutting-edge technologies and promoting the adoption of advanced toolkits, dynamic results frameworks, and efficient replication pathways.

At the state level, the ACD-LGP will prioritize adaptive co-financing models and integrated budget strategies, foster robust political leadership, and create an enabling environment for scalable solutions. The LGAs will serve as execution hubs, implementing enhanced delivery processes while leveraging real-time monitoring of the transformation. The programme will establish comprehensive channels for citizen feedback and grievance redress, empowering communities to actively engage in governance.

To tackle design-to-execution challenges, Delivery Labs will evolve into innovation hubs that streamline processes and eliminate bottlenecks through advanced procurement clinics and strategic partner alignment. We will leverage state-of-the-art performance dashboards to continuously track results and ensure accountability, enhancing transparency and performance management. By harnessing data analytics and predictive modelling, we will drive data-driven decision-making, ensuring that budget allocations are closely tied to tangible results and community impact.

# Monitoring

In line with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans:

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action |
| --- | --- | --- | --- |
| Track the results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the project's progress toward achieving the agreed outputs. | Quarterly, or at the frequency required for each indicator. | Slower-than-expected progress will be addressed by the project management team. |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management, and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision-making. | At least annually | The project board will discuss performance data, risks, lessons, and quality, and use them to make course corrections. |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess project performance and to review the Multi-Year Work Plan, ensuring realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of-project review to capture lessons learned, discuss opportunities for scaling up, and socialize project results and lessons learned with relevant audiences. | Specify frequency (i.e., at least annually) | Any quality concerns or slower-than-expected progress should be discussed by the project board, and management actions should be agreed to address the identified issues. |

# WORK PLAN

Period: 2026

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount in USD |
| Outcome 1: Local Governance Delivery Systems Strengthened Baseline: 0 Indicators: LGAs using live performance dashboards linked to budget execution Targets: ≥80% of pilot LGAs Related CP outcome: | 1.1 Local Governance Systems Strengthening Framework & Modular Offer Developed |  |  |  |  |  |  |  |  |
|  | 1.1.1 Activity action: Develop the Local Governance Systems Strengthening Framework, including delivery sequencing, governance & autonomy safeguards, PFM, service delivery, LED, accountability & digital enablement modules | X | X |  |  | UNDP/LGAs | TRAC 2 |  | 90,000 |
|  | 1.1.2 Activity action: Design capacity development & coaching architecture; peer learning system | X | X | X |  | UNDP/LGAs | TRAC 2 |  | 70,000 |
|  | 1.1.3 Activity action: Deploy surge technical assistance (PFM, procurement, costing, risk screening, dashboard engineering) | X | X | X |  | UNDP/LGAs | TRAC 2 |  | 100,000 |
|  | Sub-total Output 1.1 |  |  |  |  |  |  |  | 360,000 |
|  | 1.2: LGA Performance Architecture Piloted in 15–20 LGAs |  |  |  |  |  |  |  |  |
|  | 1.2.1 Activity action: Establish State/LGA Delivery Labs; configure dashboards & minimum data standards |  | X | X |  | UNDP/LGAs | TRAC 2 |  | 160,000 |
|  | 1.2.2 Activity action: Monthly delivery & procurement clinics to reduce bottlenecks | X | X | X | X | UNDP/LGAs | TRAC 2 |  | 90,000 |
|  | 1.2.3 Activity action: Field coordination & peer learning exchanges | X | X | X | X | UNDP/LGAs | TRAC 2 |  | 90,000 |
|  | Sub-total Output 1.2 |  |  |  |  |  |  |  |  |
| Outcome 2: Community-level prosperity and sustainable finance. Baseline: 0 Indicators: Audit Issue Resolution Targets: 70\%$ Resolution Rate Related CP outcome: | 2.1 Evidence-Driven Community Delivery Packages Designed & Costed |  |  |  |  |  |  |  |  |
|  | 2.1.1 Conduct energy audits & facility diagnostics (schools, PHCs, markets, clusters) |  | X | X |  | UNDP/LGAs | TRAC 2 |  | 110,000 |
|  | 2.1.2 LED & service delivery diagnostics; design ≥30 ward/LGA delivery packages with gender-responsive planning |  | X | X | X | UNDP/LGAs | TRAC 2 |  | 50,000 |
|  | 2.2 Sustainable Finance & Co-Financing Pathways Established |  |  |  |  |  |  |  |  |
|  | 2.2.1 Operationalize Sustainable Finance Accelerator: apply transition logic Diagnostics → Pipeline → Financing → Execution → Scale; implement leverage mechanisms (state/LGA budget tagging, performance-linked grants, energy-as-a-service models, DFI co-financing & PPP structuring) | X | X | X | X | UNDP/LGAs | TRAC 2 |  |  |
| Outcome 3: The Federal Government is equipped to operationalize RHWDP as a national execution platform. Baseline: 0 Indicators: Investment Pipeline Targets: 12 Prospectus Notes | 3.1 RHWDP Delivery Enablement Package Provided |  |  |  |  |  |  |  |  |
|  | 3.1.1 Develop RHWDP toolkit: implementation guidance, results framework, costing, adoption package | X | X | X |  | UNDP/LGAs | TRAC 2 |  | 80,000 |
|  | 3.2 National Learning & Replication Pathway Established |  |  |  |  |  |  |  |  |
|  | 3.2.1 Conduct 4 federal–state alignment sessions; finalize national replication pathway |  |  | X | X | UNDP | TRAC 2 |  | 90,000 |
| Output 4: 4. Monitoring, Learning & Visibility Baseline: Indicators: Energy Assessments Targets: 200 Facilities Related CP outcome: | 4.1 Monitoring & Data Quality Systems |  |  |  |  |  |  |  |  |
|  | 4.1.1 Dashboard QA, geotagging protocols, quarterly data quality & performance reviews, including leverage & gender tracking | X | X | X | X | UNDP/States/LGAs | TRAC 2 |  | 30,000 |
|  | 4.2 Learning & Knowledge Products |  |  |  |  |  |  |  |  |
|  | 4.2.1 National learning clinic; synthesis & replication reports | X | X | X | X | UNDP/States/LGAs | TRAC 2 |  | 25,000 |
|  | 4.3 Results-Based Visibility |  |  |  |  |  |  |  |  |
|  | 4.3.1 Results documentation, communications & reporting | X | X | X | X |  | TRAC 2 |  | 15,000 |
| TOTAL |  |  |  |  |  |  |  |  |  |

Maximum 18 months