Project Title: Pre-stabilization in Gaza:

Project Number: TBD

Implementing Partner: UNDP PAPP (Direct Implementation Modality – DIM)

Start Date: 01 January 2026			End Date: 31 December 2026 (Phase 1)

PAC Meeting date: TBD

Brief Description

The Comprehensive Plan to End the Gaza Conflict of 08 October 2025, endorsed through United Nations Security Council Resolution 2803 (2025), put a halt to the conflict in Gaza that had started with the Hamas attack against Israel on 07 October 2023. In the wake of the Israeli military response to this armed attack that had resulted in around 1,200 people killed according to Israeli authorities, large parts of the Gaza Strip have been destroyed and the majority of its population has been displaced over the course of the two-year military campaign. The Comprehensive Plan combined with UNSCR 2803 (2025) represent a unique opportunity for putting Gaza on a trajectory for recovery, viable stability and reformed non-Hamas governance. Stabilization has proven to be the most effective approach to establishing, strengthening, and expanding legitimate governance in conflict environments. Whilst the political-security prerequisites for designing and launching a fully-fledged stabilization engagement are not yet in place, the emerging political environment shaped by the Comprehensive Plan and UNSCR 2803 (2025) allow for the initiation of a stabilization preparatory phase aimed at establishing the foundational building blocks for the re-building of key civilian (political-security) governance elements through a phased approach that aligns with and supports (political and operational) progress on the Comprehensive Plan and UNSC Resolution 2803 (2025) operationalisation. This pre-stabilization intervention is built around two complementary pillars: 1) Security (incl. UXO risk reduction, youth/vulnerable groups resilience, logistical and infrastructural enabling conditions for subsequent Palestinian Police forces deployment) and 2) Civil Governance & Services (incl. civil documentation services in cooperation with the Gaza Emergency Operations Room, One-Stop Shops as centralized physical/digital interface for multiple public services). Pre-stabilization efforts will cooperate and synchronize with ongoing humanitarian, early recovery, security, rule of law, and economic recovery initiatives, guaranteeing and facilitating a comprehensive approach to stability in Gaza.

| Contributing Outcome (UNSDCF, CPD, RPD ): Palestinian Programme Framework (2023-2027) Outcome 1 – Improved democratic governance based on the principles of human rights and rule of law, with equitable access to justice and quality public and basic services. Output 1.3: Capacities of service providers enhanced. Strategic Plan Output A.3.2. Indicative Output(s) with gender marker: |  | Total resources required: | USD 3,675,000 |  |
| --- | --- | --- | --- | --- |
|  |  | Total resources allocated: USD 3,500,000 (GFFO Funding Windows) |  |  |
|  |  |  | UNDP TRAC: | Crisis Bureau: USD 175,000 |
|  |  |  | Donor: | GFFO USD: 3,500,000 |
|  |  |  | Government: |  |
|  |  |  | In-Kind: |  |
|  |  | Unfunded: |  |  |

Agreed by (signatures):

| Government | UNDP | Implementing Partner |
| --- | --- | --- |
| Print Name: | Print Name: | Print Name: |
| Date: | Date: | Date: |

Content

I.	Strategy	4

II.	Results and Partnerships	8

III.	Project Management	18

IV.	Results Framework	20

V.	Monitoring And Evaluation	24

VI.	Work Plan 	26

VII.	Governance and Management Arrangements	28

VIII.	Legal Context	29

IX.	Risk Management	31

X.	ANNEXES	50

Development Challenge

Following the events of 07 October 2023 and subsequent conflict, Gaza has experienced a catastrophic humanitarian crisis with widespread destruction of homes and infrastructure, significant casualties, and displacement of the majority of the population. The ensuing war saw the destruction of around 70 percent of homes and infrastructure in Gaza, the death of several tens of thousands of Palestinians, and the displacement of around 85 percent of Gaza’s population.

The Comprehensive Plan to End the Gaza Conflict of 08 October 2025, formally agreed to by Israel and Hamas and endorsed through United Nations Security Council Resolution 2803 (2025), represents a timely and unique opportunity for putting Gaza on a trajectory for recovery, viable stability and enabling conditions for Palestinian governance transition. Together, the Comprehensive Plan and UNSCR 2803 foresee the creation of a political-security architecture as catalyst for a new phase in Gaza’s history and development. The key elements of this architecture consist of a “transitional administration” under the supervision of an international “Board of Peace” (BoP), a “technocratic, apolitical committee” of competent Palestinians, and an International Stabilization Force (ISF).

Stabilization has proven to be the most effective approach to establishing, strengthening, and expanding legitimate governance in conflict environments. Stabilization is therefore well-placed to support the transitional administration. With the establishment of the foreseen political-security architecture still pending, the key prerequisites for a full-scale stabilization intervention are however not present. A preparatory stabilisation engagement is therefore required aimed at pre-positioning structures and processes in support of the future transitional administration, thereby creating the enabling conditions for integrated stabilization programming at a subsequent stage.

Despite the current challenging situation in Gaza, there is a rudimentary operational presence of Palestinian governance in Gaza — including the Gaza Emergency Operations Room coordination mechanism, former PA personnel on payroll, and limited PA ministry presence in specific sectors — beyond the control of Hamas upon which the preparatory stabilization engagement can build. The project therefore addresses three interlinked development challenges:

- the absence of viable, PA-led security and civilian governance structures;

- the collapse of essential public service delivery systems, particularly civil documentation and administrative functions; and

- the risk that the window of opportunity created by the Comprehensive Plan and UNSCR 2803 will close without the necessary preparatory groundwork being established.

# Strategy

Stabilization rationale

The Comprehensive Plan and the United Nations Security Council Resolution 2803 (2025)represent the current international framework for Gaza recovery. Effective implementation of this framework is essential for Gaza's humanitarian and future political, security, economic and development trajectory. A failure of this initiative is likely to increase the suffering of people in Gaza and precludes a long-term peaceful and prosperous future of Palestinians in Gaza. Stabilization as proven device for establishing, strengthening, and expanding legitimate governance in conflict environments can offer meaningful interventions in support of the operationalisation of the “Comprehensive Plan” and UNSCR 2803.

The idiosyncrasies of the current context in Gaza however, require a deliberate contextual adaptation going beyond UNDP’s corporate stabilization approach rooted in a three-pillar logic (security in communities, service restoration, and income support) delivered through a stabilization compact and adaptive management. Whereas the formation of the Transitional Administration with its constitutive elements is currently proceeding, progress on the political preconditions for the continued implementation of the Comprehensive Plan, such as the demilitarization of Hamas and the decommissioning of its weaponry as well as Palestinian Authority (PA) reform, is likely to be subject to a prolonged timeline. Furthermore, the geographical scope of a future Gaza engagement remains unclear and the role of an international civilian presence in Gaza still being defined.

As a result, the political-security prerequisites for designing and launching a fully-fledged stabilization engagement are not yet in place.

Consequently, the intervention is a time-bound stabilisation effort to rebuild key civilian (political-security) governance , aligned with phased political and operational progress on the Comprehensive Plan and UNSC Resolution 2803 (2025), supporting Gaza’s territorial integrity under a transitional administration with a strong multilateral footprint. Pre-stabilization will therefore need to be prepared to expand and/or widen its engagement once certain trigger points are met, but also to conclude its engagement in case of missing progress under the Comprehensive Plan and UNSCR 2803 (2025) or deviation thereof. The pre-stabilization phase prioritizes coherent, low-profile measures that focus on three enabling building blocks for future stabilization. Firstly, pre-stabilization is to strengthen Palestinian governance and service delivery while avoiding reinforcement of parallel authority and delivery structures. While international legitimacy of the envisioned Palestinian Committee might be high and guaranteed, legitimacy and acceptance within Gaza remains to be built. Therefore, pre-stabilization will build upon and coordinate with the existing  operational presence of Palestinian governance in Gaza, such as the Gaza Emergency Operations Room (incl. direct or indirect links to the PA), with a view to strengthening the legitimacy of the transitional administration and advancing the development of a viable, locally accepted future Palestinian leadership of Gaza.

Secondly, the design and delivery of pre-stabilization interventions in selected locations will develop and establish delivery networks for the transitional administration to utilize for the operationalisation of its strategies/plans. This will reduce the time and resources for the transitional administration to become operational. Thirdly, pre-stabilization will support people in Gaza at the time of their greatest need, preventing further displacement.

This three-pronged pre-stabilization approach will be operationalised through two complementary pillars: 1) Security (incl. UXO risk reduction through assessment/mapping/sensitization, youth/vulnerable groups civic engagement and safe spaces programming, logistical and infrastructural enabling conditions for subsequent Palestinian Police forces deployment), 2) Civil Governance & Services (incl. Gaza Emergency Operations Room coordination support, civil documentation services, One-Stop Shops as centralized physical/digital interface for multiple public services, strategic communications capacity strengthening, and community perception monitoring). Pre-stabilization efforts will cooperate and synchronize with ongoing humanitarian, early recovery, security, rule of law, and economic recovery initiatives, ensuring a comprehensive approach to stability in Gaza.

Attribution

Stabilization can only be successful if the progress/success it generates is attributed to the Transitional Administration and locally-accepted Palestinian members. Therefore, the delivery of activities needs to be seen as Transitional Administration/Palestinian governance-initiated and -led, in close coordination with the Palestinian Authority. UNDP will refrain from using its own logos on signage and commemorative markers, opting instead to feature Transitional Administration/Palestinian governance to emphasize Palestinian ownership and visibility. Communicating that stabilization efforts are initiated and led by Transitional Administration/Palestinian governance, in close coordination with the Palestinian Authority, mitigates the risk of non-state groups taking undue credit for the stabilization benefits produced by this project.

Localized and integrated stabilization

Selected project locations are to benefit from the implementation of context-specific integrated pre-stabilization packages based on the two complementary pillars Security and Civil Governance & Service. The integrated pre-stabilization packages will be designed with Palestinian participation. Respecting the Whole of Palestine approach and in support of a coherent and effective Gaza engagement, pre-stabilization interventions will be coordinated with the Gaza Emergency Operations Room. This operational and technical anchoring will function as a unifying mechanism for joint and coherent planning and action in Gaza. Pre-stabilization will be complementary with existing programmes in Gaza, particularly the UNDP Transitional Community Neighbourhoods (ITCN) offer.

Selection criteria of stabilization locations

Site selection will ensure political relevance, be operationally viable, conflict sensitive, and feasibility for UNDP to plan and deliver integrated measures.

Political relevance: Transitional Administration - Alignment with Palestinian priorities and direct/indirect PA presence, including quick win potential by targeting sites where visible improvements feasible within Phase 1. Political red line: No support or attribution to non-state actors.

Population relevance: population cluster

Operational prerequisites: Minimum security; UNDP access; community willingness to engage with PA; PA-linked functional presence.

Conflict sensitivity: Transparent geographic prioritization to avoid inter-communal tension and geographic distribution to avoid a perception of favoritism

- Alignment: Synergy with UNDP Inclusive Transitional Community Neighbourhoods (ITCN) in the following initial candidate areas:

- Gaza City (Northern Gaza): Gaza City stands out as the most logical location for stabilization interventions. The city holds central political and institutional importance, with municipal structures that appear more readily reactivatable than in many other areas. Its existing administrative presence and strong symbolic value make it a strategically important setting for visible and credible actions. From a population perspective, Gaza City represents a major hub. The high concentration of residents and displacement dynamics make it a critical area for any efforts related to voluntary return and restoration of services. Interventions here would reach a significant number of beneficiaries. Operational conditions, while far from ideal, are comparatively more favorable. Certain infrastructure and essential services appear recoverable. Access constraints and unexploded ordnance risks remain real but seem manageable within a phased and carefully sequenced approach. In terms of conflict sensitivity, risks are present (particularly regarding perceptions of inequality) but interventions can be reasonably justified and defended if they are well-communicated and designed with balance and inclusivity.

- Khan Younis/Mawasi/Rafah (Southern Gaza): Khan Younis and the Al Mawasi area present clear relevance from both humanitarian and demographic perspectives. The region has experienced significant population movements and remains a key area in discussions surrounding return and resettlement. The institutional environment is more fragile. Governance mechanisms and administrative structures are less robust, which may complicate rapid implementation. Coordination is feasible but likely to require additional effort and support. The primary challenges are operational. Damage to housing and infrastructure is extensive, implying the need for substantial preparatory investments before large-scale programming can be effectively deployed. Access and technical safety considerations remain sensitive. Despite these constraints, risks related to social or territorial tensions appear manageable, provided that interventions adopt a cautious, inclusive, and context-sensitive approach.

- Deir el Balah/Nuseirat (Central Gaza): Deir el-Balah is distinguished mainly by relatively favorable operational conditions. Access appears easier, infrastructure less degraded, and the overall environment more stable compared to several other locations. This makes it a suitable candidate for activities requiring rapid implementation or pilot initiatives. However, its strategic weight in terms of return dynamics and displacement patterns is more limited. While the area currently hosts a large displaced population, it is not necessarily central to long-term return trajectories. Another important consideration is perception. The risk of political interpretation or perceptions of favoritism may be more pronounced here. Any intervention would therefore require particularly careful communication and stakeholder engagement.

Adaptive programming

Effective pre-stabilization interventions require an enabling organisational culture with appropriate leadership structures and management processes. Key elements in the UNDP management approach to stabilization comprise the use of the Direct Implementation Modality (DIM), Service Units and the targeted delegation of authority. UNDP PAPP will adopt a ‘business-as-usual is not an option’ mentality, and the UNDP PAPP senior management will ensure that all staff are aware a much-accelerated pace in implementing activities is urgently required. UNDP PAPP will also ensure that implementation occurs using these special measures.

The volatile context of stabilization requires regular programmatic and operational adaptations based on the analysis of evidence. UNDP PAPP senior management will set up and drive an adaptive management practice that integrates conflict sensitivity, risk management and a ‘finger-on-the-pulse’ monitoring and learning to meet this requirement.

Theory of Change

If…

- UXOs are removed.

- Safe spaces are created for youth and vulnerable groups.

- Former PCP/PCD and other state personnel still on payroll of PA structures are active

- Deployment of Palestinian Police is enabled.

- Access to documentation is improved.

- One-stop service hubs are created.

- Strategic communications attribute service improvements to PA coordination

- Conflict and political-economic analysis is conducted to ensure an adaptive approach to programming

And assuming that …

- The ceasefire endorsed by the Comprehensive Plan and United Nations Security Council Resolution 2803 (2025) holds, although remaining fragile and subject to localized violations.

- The anticipated transitional governance administration for Gaza will progressively emerge during Programme implementation, with pre-stabilization activities creating enabling conditions for eventual transition rather than assuming immediate operationalization.

- The envisaged International Stabilization Force will be established and support the training of Palestinian Police forces to be deployed to Gaza (as outlined in UNSCR 2803).

- UNDP can leverage its existing operational field presence, technical expertise and trusted partnerships in Gaza for the delivery of stabilisation activities.

- The pre-stabilization phase proceeds on the basis that immediate enabling actions are both necessary and feasible, while recognizing that transitional institutions are not yet in place and failure of the Comprehensive Plan may render pre-stabilization superfluous.

- Access to materials, equipment, and technical expertise is limited but sufficient to deliver carefully sequenced, integrated pre-stabilization packages in selected locations.

- Communities are open to the involvement in pre-stabilization.

- A critical mass of former personnel of the Palestinian Authority can be re-activated through existing systems accepted by competent authorities, enabling their reintegration into priority functions.

- Minimum security conditions exist in selected areas to allow safe implementation of pre-stabilization measures.

- PA authorities demonstrate willingness and capacity to engage in coordination and service delivery leadership roles

Then…

- Safety for rehabilitation of infrastructure will increase.

- Community perception of security will improve in pilot sites (measurable via perception surveys)

- Youth and vulnerable will be less inclined to join non-state armed groups.

- The Transitional Governance Authority will be facilitated.

- The way will pave the way for a Palestinian State to become legitimate and capable of delivering services.

# Results and Partnerships

Expected Results

Pre-stabilization in Gaza is intended to help maintain the window of opportunity created by the Comprehensive Plan and UNSCR 2803 and take advantage of the halt to major violence and the renewed but still limited international access to Gaza. By strengthening Palestinian governance, community security/safety and service delivery as well as community resilience to counter a Hamas resurgence, preventing further displacement (pressure) and maintaining a multilateral posture, pre-stabilization can help create the enabling conditions for the emergence of a governance alternative to the former de-facto government and maintain the territorial integrity of Gaza with a significant multilateral footprint under the umbrella of the transitional administration. Phase 1 pre-stabilization creates initial enabling conditions for potential future governance transition.

Success will be gauged by visible Palestinian ownership, functional delivery, and improved public perceptions.

- Palestinian ownership demonstrably embedded.

- No further displacement, potential IDP return

- Gaza Emergency Operations Room ensures coherent/coordinated PA-involved response.

- Transitional Administration delivery across the entirety of Gaza with support from existing PA-led structures

- Perception gains in Palestinian governance legitimacy and capacity among communities.

- Selected PA functions strengthened and performing.

In its first phase(2026-2027), pre-stabilization prioritizes immediately implementable activities within 3 selected sites/areas while conducting preparatory assessments and framework development for activities requiring transitional governance structures. It will be centred around bounded civilian “security-enabling” measures and minimum liveability packages taking into account equity monitoring, do-no-pull safeguards preparing for integration in transitional governance arrangements and, ultimately, anticipated PA reforms as and when possible and desirable (Phase 2). UNDP will leverage its existing operational footprint in Gaza (for example, rubble removal, water trucking, and solid waste management) as a platform for delivery.

Considering the geographical realities of Gaza being de facto split into a Green Zone (IDF-controlled) and Red Zone (where most civilians are concentrated), pre-stabilization has to follow the stabilization core principle of being population-centric. Whilst considering Gaza as a whole, pre-stabilization will initially focus on stabilizing selected Red Zone population centres creating the enabling conditions for Gaza-wide Palestinian (non-armed group) governance and return-enabling, community-owned solutions, complementing the ongoing Inclusive Transitional Community Neighborrod Programme (ITCN) as the initial delivery engine and applying UNCT/HCT parameters for transitional displacement sites (TDS) as binding safeguards. A Gaza-wide stabilization lens reduces additional displacement pressure by restoring minimum liveability thresholds in Red Zone population centers, to be expanded to the so-called Green Zone as soon as conditions will allow in line with the ceasefire plan, and mitigating Rafah-driven outflow risk through accelerated in-place stabilization—while keeping transitional governance and security arrangements oriented toward Gaza-wide civilian outcomes and a handover-ready pathway to PA-centered service systems.

Pillar 1: Strengthened Civilian Safety and Security Enabling Environment

In Gaza, where security reach and access are expected to remain variable while the 2803 architecture is implemented, Pillar 1 is operationalized as bounded, civilian security-enabling functions that (a) reduce civilian harm risks, (b) enable safe access for liveability restoration, and (c) avoid securitizing aid or creating enclave-protection logic. This aligns with UNDP’s guidance that liaison with security forces is integral and that stabilization requires a minimum security enabling environment. The security interventions will reduce immediate risks, enable PA-linked policing, and create safe community spaces that deter recruitment and violence, while building national capacities.

  - UXO risk reduction (UNMAS):

SRM establishes the security foundations enabling PA to establish territorial presence in pilot areas, creating the secure environment needed for both PA operations and ITCN construction activities. The project builds on UNDP PAPP's established UNMAS partnership and SOPs already operational under ITCN through the following activities:

- 1.1.1 UXO contamination assessment and mapping in pilot areas

- 1.1.2 Capacity building for Palestinian Mine Action Center (PMAC)

- 1.1.3 Community UXO risk sensitization campaigns

Phase 1 scope (12 months): Focus on UXO assessment and mapping, community sensitization campaigns, and PMAC capacity building. Coordination initiated for safe disposal area designation. Specialized demining equipment not yet authorized limits scope to preparatory interventions.

Phase 2 if conditions permit (6 months, complementary budget): Full-scale UXO clearance and disposal operations contingent on specialized demining equipment authorization obtained and safe disposal areas formally designated.

  - Youth and specific-needs groups: Establish community safe spaces to reach youth at risk of recruitment or disengaging from non-state armed groups,

With Gaza's education system collapsed, youth face heightened recruitment risks. Complementing ITCN and IPR programmes funded by Germany, SRM establishes community safe spaces as anchor points where PA can build visibility and trust while concentrating interventions from multiple partners. These spaces create the enabling environment for PA to establish presence and deliver services in coordination with civil society through the following activities:

- 1.2.1 Community safe space establishment and management (CSO-implemented, PA-supervised, UNDP-supported)

- 1.2.2 Civic education and electoral system sensitization for future local election participation, including Youth Councils elections1.2.3 Youth-led community activities (sports/games) and sensitization campaign engagement

These interventions focus on at-risk youth across pilot areas, creating community trust foundations that enable PA territorial presence. The programming complements ITCN's neighborhood-based social cohesion work while leveraging UNDP PAPP's proven psychosocial support and youth engagement frameworks to ensure coordinated, non-duplicative programming.

Phase 1 scope (12 months): Establishment and operationalization of community safe spaces in pilot sites, civic education programming, election of youth councils and youth-led activities. Safe spaces managed by selected CSOs with formal PA coordination mechanisms, ensuring interventions strengthen rather than bypass PA authority. Multi-partner programming (UNICEF, local NGOs) concentrated through these hubs to maximize impact and PA visibility.

Phase 2 if conditions permit (6 months, complementary budget): Based on evaluation and lessons learned, organize a new round of selected youth with improved skills curriculum developed in coordination with Ministry of Education, contingent on Ministry of Education engagement (and ideally on screening process for voluntary engagement of youth at risk in partnership with Ministry of Interior), curriculum accreditation pathways, and sustained security conditions.

  - Reintegration of former PCP/PCD:

SRM supports PA to prepare institutional foundations for eventual reintegration of former Palestinian Civil Police (PCP) and Palestinian Civil Defense (PCD) personnel currently on payroll and vetted by the PA. This preparatory work creates the conditions for PA to restore legitimate security and civil protection structures in pilot areas, building community confidence in PA service delivery capacity. While awaiting formal institutional arrangements, UNDP will develop frameworks and conduct assessments to ensure rapid implementation once conditions permit, through the following activities:

- 1.3.1 Feasibility assessment and consultation with Gaza Emergency Operations Room, the technocratic committee, and Ministry of Interior

- 1.3.2 Technical support and participation with international partners in development of reintegration frameworks and protocols (SOPs, procedures, coordination mechanisms)

- 1.3.3 Technical support to the PA and participation with international partners in design of vetting process architecture and institutional coordination structures

Phase 1 scope (12 months): Preparatory work exclusively—assessments, consultations with PA counterparts, technical support to framework development and protocol design in coordination with international partners. No actual personnel reintegration will occur in Phase 1, unless conditions allow.

Phase 2 if conditions permit (6 months, complementary budget): Support the PA to conduct vettingoperations for PCP/PCD personnel, facilitate reintegration into PA security structures, deploy vetted personnel to police posts in pilot areas, and provide on-the-job support. Contingent on PLO approval, PA technocratic committee operational, formal deployment protocols established, and security conditions permitting.

  - Enabling Palestinian Police deployment:

SRM creates the operational conditions for PA to establish visible presence in pilot areas, building community confidence in PA security provision. While awaiting security stabilization and ISF deployment conditions, UNDP will procure bureau equipment and prepare police infrastructure foundations to ensure rapid operationalization once conditions permit. Equipment support enables Palestinian Police to operate effectively, demonstrating PA capacity to provide legitimate law enforcement and public order through the following activities:

- 1.4.1 Procurement of essential police bureau equipment (communication devices, non-lethal operational materials, office furniture and supplies)

- 1.4.2 Identification of police post locations (with UXO clearance prioritization) and development of Bills of Quantity for rehabilitation or prefabricated infrastructure

Phase 1 scope (12 months): Focus on bureau equipment procurement and preparatory infrastructure planning. Police post sites identified and assessed (coordinated with UXO clearance priorities), Bills of Quantity developed for rehabilitation or prefab deployment. Equipment pre-positioned and sites ready to enable rapid deployment when security conditions stabilize.

Phase 2 if conditions permit (6 months, complementary budget): Provision of mobility assets (vehicles/motorbikes) and security infrastructure deployment/rehabilitation (hesco barriers, fencing, street lighting, police posts, courts) contingent on: (1) security conditions stabilized in pilot areas, (2) ISF deployment sustained and operational, (3) site access secured and UXO clearance completed, and (4) complementary resources secured.

Pillar 2:  Supported Civil Administrative Functions and Service Delivery

The civil package will restore core administrative functions, documentation, and service access, anchored in PA coordination and strategic communications to build trust and coherence.

  - Gaza Emergency Operations Room: PA-linked coordination for a coherent, prioritized response leveraging existing capacities and resources with potential connectivity with future transitional administration.

SRM strengthens PA's capacity to coordinate stabilization interventions across Gaza through support to the Gaza Emergency Operations Room (GEOR). In the short term, while awaiting more consolidated governance structures and legitimate PA institutional arrangements, the GEOR serves as the central technical coordination hub where PA establishes strategic oversight and operational visibility, enabling coherent prioritization of interventions and leveraging existing capacities and resources. This creates the institutional foundation for PA to manage the transition from humanitarian response to stabilization, with potential connectivity to future transitional administration structures, through the following activities:

- 2.1.1 GEOR operational infrastructure establishment (office space, equipment, IT systems, transportation, power supply)

- 2.1.2 GEOR staffing and technical capacity (coordinators, engineers, IT specialists, communications officers, administrative support)

- 2.1.3 GEOR operational systems strengthening (information management platforms, coordination protocols, stakeholder engagement mechanisms)

Phase 1 scope (12 months): Establish functional GEOR operations including office infrastructure, technical staffing, information management systems, and coordination protocols with UN agencies and partners. Focus on demonstrating PA capacity to manage complex multi-stakeholder interventions through operational GOR coordination hub.

Phase 2 if conditions permit (6 months, complementary budget): Assess whether to continue GEOR support or shift assistance to legitimate PA state institutions as they become operational (municipalities, sector ministries such as Ministry of Local Government, Ministry of Interior). Provide technical support to whichever institutional arrangement proves most effective for PA coordination and service delivery, contingent on PA transitional arrangements clarity and institutional capacity assessment.

  - Reintegration of former PA personnel: Preparatory process to mobilize  staff into functional civil roles

SRM supports PA to prepare the institutional foundations for mobilizing vetted former PA civil servants currently on payroll into functional civil roles. Current conditions do not permit actual vetting or deployment operations, so Phase 1 focuses exclusively on preparatory work to ensure rapid implementation once PA governance structures are operational. This preparatory framework creates the institutional foundations that will enable ITCN's work placement programme to transition from short-term employment to sustainable PA service delivery, ensuring personnel placements strengthen rather than bypass PA institutional authority, through the following activities:

- 2.2.1 Feasibility assessment and conditions analysis in coordination with Gaza Emergency Operations Room and technocratic committee

- 2.2.2 Development of SOPs,  deployment frameworks and protocols for civil servant reintegration

- 2.2.3 Technical support and participation with international partners to the Palestinian Authority in design of vetting process architecture

Phase 1 scope (12 months): Preparatory work exclusively such as feasibility assessments, conditions analysis with GEOR and technocratic committee, development of deployment frameworks and protocols in coordination with international partners. No actual personnel vetting or deployment will occur in Phase 1 due to the absence of formal PA institutional authority and approved vetting protocols.

Phase 2 if conditions permit (6 months, complementary budget): Support the PA to define and execute vetting operations for former PA civil servants, facilitate deployment to priority service delivery functions (education, health, municipalities), and provide on-the-job support and supervision. Contingent on PA operational, formal vetting protocols established, transitional governance structures clarified, and security conditions permitting.

  - Civil documentation services:  Restore civil registry functions

SRM supports PA to restore essential civil documentation services, enabling citizens to access birth/death certificates, identity documents, and passports through secure, accessible modalities. In the short term, while awaiting full restoration of PA institutional infrastructure, mobile units and digital interfaces create visible PA service delivery presence in pilot areas, building community trust and demonstrating PA capacity to provide legitimate administrative functions. These services create enabling conditions for ITCN beneficiary registration and service delivery (housing allocations, work placements require civil documentation), ensuring programme participants can access formal identification necessary for PA service provision, through the following activities:

- 2.3.1 Mobile civil registry units deployment and service delivery (equipment, staffing, secure data management)

- 2.3.2 Birth/death certificates and passport services provision through mobile and fixed-point modalities

- 2.3.3 Digital interface development and secure documentation systems

Phase 1 scope (12 months): Deploy mobile civil registry units in pilot areas, establish secure documentation processes, and provide birth/death certificates and identity services. Focus on demonstrating PA administrative capacity and building community confidence in PA legitimate service delivery. Digital systems development initiated for future scale-up.

Phase 2 if conditions permit (6 months, complementary budget): Expand to passport services provision, scale mobile units to additional areas, and transition to fixed-point PA administrative centers as infrastructure permits. Contingent on PA Ministry of Interior coordination formalized, secure documentation protocols established.

  - One-Stop Shop: Centralized physical/digital interface for multiple public services

SRM builds on UNDP PAPP's existing one-stop service center concept to establish PA-coordinated service delivery hubs in pilot areas. While UNDP's emergency service centers focus on immediate post-conflict service access (IDs, certificates, health cards), SRM creates the enabling conditions for PA to institutionalize these services with strategic coordination and digital integration. This demonstrates PA capacity to provide multi-sector administrative functions through legitimate channels, building community trust in PA governance. SRM supports transition from emergency service provision to sustainable PA-led service delivery infrastructure, through the following activities:

- 2.4.1 Physical service center establishment in pilot sites (building on UNDP emergency center model with PA institutional anchoring)

- 2.4.2 Digital service platforms and ID systems integration for secure, accessible service delivery

- 2.4.3 PA coordination mechanisms and service provider partnerships (Ministries, CSOs, utilities)

Phase 1 scope (12 months): Establish physical service centers in pilot sites leveraging UNDP's proven emergency center model, focusing on PA institutional coordination and digital platform development. Support Ministry of Interior, Ministry of Social Development, and other PA service providers to establish presence. Digital systems architecture designed for future integration.

Phase 2 if conditions permit (6 months, complementary budget): Full digital ID systems integration, expansion to additional service categories (land registration, business licensing), and scale-up to additional sites. Contingent on PA institutional capacity to manage expanded services, digital infrastructure operational, and inter-ministerial coordination formalized.

  - Strategic communications: Continuous messaging to build trust, manage expectations, and secure stakeholder buy-in.

SRM strengthens PA Gaza Emergency Operations Room and technocratic committee capacity to communicate stabilization progress and manage citizen expectations through strategic, coordinated messaging. In the short term, while awaiting full PA governance restoration, effective communications demonstrate PA responsiveness and build community trust through visibility of tangible service delivery improvements. This creates the narrative foundation that enables PA to consolidate legitimacy and secure stakeholder buy-in for transitional arrangements. Strategic communications complement ITCN's community engagement (social cohesion) by providing Gaza-wide PA messaging that frames ITCN neighborhood-level improvements within broader PA stabilization strategy, through the following activities:

- 2.5.1 PA GEOR/technocratic committee communications systems development (media capacity, messaging protocols, spokespersons training)

- 2.5.2 PA-led messaging campaigns and quick wins visibility (tangible service delivery achievements, expectation management)

Phase 1 scope (12 months): Establish PA communications capacity within GEOR/technocratic committee, develop strategic messaging frameworks, and launch PA-led campaigns highlighting early stabilization achievements (UXO clearance, youth programming, civil documentation access). Focus on building PA credibility through transparent communication of progress and challenges.

Phase 2 if conditions permit (6 months, complementary budget): Expand to transitional administration communications, scale messaging to emerging PA institutional structures (municipalities, sector ministries), and develop comprehensive PA governance narrative. Contingent on PA transitional arrangements clarity, demonstrated GOR communications effectiveness in Phase 1, and sustained security conditions enabling field reporting.

  - Data for stabilization: Community perception monitoring and conflict-sensitive analysis

SRM establishes systematic data collection and analysis mechanisms that enable PA and UNDP to measure stabilization progress through community lens and adapt programming to conflict dynamics. In the short term, while awaiting PA institutional monitoring capacity, these systems provide the evidence base demonstrating whether interventions are building trust in PA governance or creating unintended tensions. This enables adaptive management that strengthens rather than undermines PA legitimacy. The monitoring framework complements ITCN's site-level community engagement and accountability mechanisms by providing Gaza-wide perception data that contextualizes neighborhood-level feedback within broader stabilization trends, informing both SRM and ITCN adaptive programming, through the following activities:

- 2.6.1 Community perception monitoring system establishment (trust in PA, safety perception, service satisfaction, tension indicators, early warning system)

- 2.6.2 Political Economy Analysis (PEA) for conflict-sensitive programming and risk mitigation

- 2.6.3 Data collection, analysis, M&E frameworks, and feedback mechanisms for adaptive management and PA decision-making support

Phase 1 scope (12 months): Establish community perception monitoring systems in pilot sites, conduct baseline and regular perception surveys measuring PA trust and service satisfaction, execute comprehensive PEA to inform programming adaptations, and develop M&E frameworks. Early warning system operational to identify emerging tensions. Feedback loops connect community data to GEOR/PA decision-making and SRM/ITCN programming adjustments.

Phase 2 if conditions permit (6 months, complementary budget): Establish structured community consultation mechanisms for joint Joint Action Plans as full stabilization operations approach, expand perception monitoring to additional sites, develop PA institutional capacity to manage monitoring independently, and integrate early warning systems with PA security coordination.

Partnerships

The project engages exclusively with Palestinian Authority institutions and structures linked to legitimate Palestinian governance, in full alignment with UNSCR 2803 (2025) and the Comprehensive Plan framework. Primary institutional partners include the PA Gaza Emergency Operations Room as the central coordination mechanism, and relevant PA ministries for service delivery through One-Stop Shop centers.

Coordination with international frameworks occurs through: the Board of Peace mechanisms; UN agencies including UNMAS (UXO operations), UNICEF, and UNCT/HCT; the International Stabilization Force (ISF) once deployed; EUBAM (for PCP vetting support); and UNSCO (on political messaging and compliance with international legal standards). All interventions are designed to strengthen PA institutional presence and legitimacy, avoiding creation of parallel authority structures.

Board of Peace, Technocratic Palestinian Committee, International Stabilization Force: UNDP will collaborate closely with the transitional governance authorities to ensure the security conditions necessary for effective program implementation. This partnership will help create a safe and stable environment for pre-stabilization efforts.

EUBAM Rafah und EUPOL COPPS/OSC: EUBAM Rafah (border-coordination functions) and EUPOL COPPS/OSC (policing): XXX

UNMAS: UNMAS will serve as the technical implementation partner for UXO Risk Reduction under Pillar 1 (Security) of the UNDP pre-stabilization project in Gaza. It will provide (a) technical assessment and mapping through systematic UXO contamination identification and risk mapping across selected pilot sites, with coordination with ITCN Programme and relevant authorities to inform safe rubble removal sequencing and identify requirements for safe disposal area designation. In parallel, UNMAS will lead (b) capacity building through technical training and equipment provision for the Palestinian Mine Action Center (PMAC) in assessment methodologies, alongside institutional strengthening to build sustainable national UXO risk management capacity. UNMAS will also deliver (c) large-scale community sensitization campaigns on UXO risks and safe behaviors in pilot sites, and (d) contribute to project governance by serving as technical advisor to the SRM Project Technical Committee on UXO risk management.

UNSCO: UNDP PAPP will engage with UNSCO to align pre-stabilization efforts with broader humanitarian, political and diplomatic strategies. Regular coordination will ensure that UNDP’s pre-stabilization in Gaza complement UNSCOL’s work, reinforcing a coherent and strategic approach to humanitarian assistance.

AFPs (UN Agencies, Funds, and Programmes): UNDP will collaborate with other UN agencies to open the space for their engagement, including by maximizing impact through future joint planning and implementation. UNDP’s pre-stabilization is at the heart of the humanitarian-development-peace (HDP) nexus, addressing immediate needs while laying the foundation for recovery and development. Coordination with specialized agencies in areas will ensure an integrated response that leverages the expertise and resources of the UN system.

Risks and Assumptions

Criteria-led sequenced implementation of the Comprehensive Plan to be assessed and agreed upon by the relevant stakeholders creates significant uncertainties regarding the political and security environment as well as the geographic scope in which pre-stabilization is to operate. As a result, the realities of key political, security and legal risks being taken on by the pre-stabilization engagement cannot be adequately assessed and will need to be continually monitored. Ultimately, the level of risk appetite regarding the political and legal risks will be continually discussed in the technical committee between UNDP and GFFO (incl. potential subsequent donors) requiring a political assessment and decision.

A central operational risk under the 2803 architecture is that phased security and governance reach, combined with access constraints, could concentrate early stabilization benefits in limited areas, creating ‘pull’ dynamics and incentivizing displacement. If early recovery and service restoration scale mainly where security control is most feasible, a Green-first trajectory can harden into Green-only recovery, increasing Red to Green population movements and reinforcing de facto partition. SRM programming should therefore adopt explicit ‘do-no-pull’ safeguards and equity monitoring from the outset, prioritizing liveability restoration where populations are concentrated and designing expansion triggers that do not make civilian liveability conditional on protracted political-security milestones.

The pre-stabilization engagement will be highly dependent on progress under the Comprehensive Plan and UNSCR 2803 (2025), the demobilisation/demilitarization of Hamas in particular.

| Risk description | Risk type | Risk assessment (Impact, Likelihood & Risk Level) | Mitigation measures |
| --- | --- | --- | --- |
| Hamas refusal to demilitarize/disarm results in the failure of the Comprehensive Plan. | 7. STRATEGIC (7.3. Stakeholder relations and partnerships) - UNDP Risk Appetite: OPEN TO SEEKING 3. OPERATIONAL (3.6. Transition and exit strategy) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 4 - Highly likely Impact: 5 - Extreme Risk level: HIGH RISK (equates to a risk appetite of SEEK) | - Continuous political monitoring via UNDP and PA liaison; - Design interventions as flexible enabling conditions adaptable to political evolution; - Coordinate with UNSCO on ceasefire compliance; - Maintain adaptive management allowing rapid suspension/resumption; - Escalation to Steering Committee if political conditions change. |
| Early recovery and service restoration scale mainly where security control is most effective resulting in a Green Zone-first trajectory hardening into Green Zone-only recovery, thereby forcing Red→Green population movements and reinforcing de facto partition. |  | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | - Intentional "oil spot" strategy: establish initial success in accessible areas demonstrating rapid wins and PA service delivery capacity; - Leverage early results to build momentum and political will for geographic expansion; - Explicit expansion roadmap communicated to communities in underserved areas showing phased timeline tied to security improvements and PA capacity growth; - Technical Committee tracks political-security evolution to identify expansion opportunities; - Steering Committee reviews quarterly expansion plans ensuring geographic equity over Programme lifetime; |
| Exclusive pre-stabilization support to Green Zone hardens and de facto legitimises the partition of Gaza. |  | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | - Site selection criteria deliberately include cross-geographic diversity (North: Gaza City, Central: Deir el-Balah/Nuseirat, South: Khan Younis/Mawasi/Rafah) avoiding concentration in single zone; - Clear programmatic commitment to Gaza-wide coverage over Programme lifetime, with pilot phase explicitly framed as "first sites" not "only sites"; - Transparent expansion roadmap communicated publicly showing intent to reach all geographic areas as security permits; - Regular public communications emphasizing temporary pilot nature and commitment to territorial integrity of Gaza; - Steering Committee quarterly reviews of expansion opportunities ensuring political message of non-acceptance of partition; |
| Cooperation with and/or supporting the Alternative Safe Community initiative creates legal liabilities for potential land rights violations. |  |  | - No direct cooperation with Alternative Safe Community initiative; - Transparent communication of PA leadership role ; - Programming focuses on PA-led coordination and legitimate authority mechanisms only; - Clear positioning under UNSCR 2803 mandate supporting PA governance; - Avoid any activities that could be perceived as legitimizing parallel governance structures; - Coordination with UNSCO on political messaging and positioning; - Coordinate with UNSCO and OHCHR on compliance with international legal standards; - All site selection and population movement support (IDP return) guided by voluntary return principles and international humanitarian law; |
| Persistent presence of informal security arrangements in competition with central government provided security. | 3. OPERATIONAL (3.5. Partners’ engagement) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | - Intensify community-based approach through systematic community consultations and engagement mechanisms creating direct citizen-PA linkages; - Deliver visible quick wins in both security and service delivery demonstrating tangible PA effectiveness; - Strategic communications highlighting PA coordination role in service improvements; - Community perception monitoring tracking trust in PA security and services relative to informal arrangements; rapid response to community feedback showing PA responsiveness; - Technical Committee ISF coordination ensuring security quick wins are attributed to legitimate authorities; - Incremental demonstration that PA-led coordination delivers concrete benefits, progressively reducing citizen reliance on informal security providers |
| Cooperation with or indirect reliance on non-state security actors / government-affiliated security actors creates legal liabilities for links to criminal actors. |  |  | - Strict policy: all security coordination exclusively through verified PA/ISF official channels; - Vetting activities by PA prevents infiltration by criminal-linked actors; - Youth safe community spaces with civic education provide alternatives to informal actor recruitment; - Legal due diligence and UNDSS security assessments identifying risk areas; - Site selection prioritizes clear PA/ISF control zones; - Suspend operations rather than engage with unverified actors; |
| Political instrumentalization of stabilization activities and progress by non-state actors, thereby undermining the attribution of the stabilization intervention to the transitional administration / Palestinian governance actors. | 5. REPUTATIONAL (5.5. Stakeholder management) - UNDP Risk Appetite: CAUTIOUS 7. STRATEGIC (7.7. Alignment with national priorities) - UNDP Risk Appetite: OPEN TO SEEKING | Likelihood: 4 - Highly likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | - Strategic pre-stabilization communications systematically attributing all stabilization achievements to PA coordination and legitimate governance; - PA branding and visibility on all infrastructure rehabilitation and service delivery; - Community consultations and engagement mechanisms creating direct citizen-PA linkages; - Gaza Emergency Operations Room serves as public face of coordination, reinforcing PA institutional presence; - Community perception monitoring tracking attribution perceptions and detecting misattribution early; - Rapid communications response if non-state actors attempt credit claiming; - Coordinate messaging with PA strategic communications unit ensuring consistent narrative; |
| Lack of willingness and capability amongst International Stabilization Force (ISF) for cooperation and participation in stabilization interventions. | 7. STRATEGIC (7.5. Government commitment) - UNDP Risk Appetite: OPEN TO SEEKING | Likelihood: 2 - Low likelihood Impact: 4 - Extensive Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | - Early liaison with International Stabilization Force establishing coordination protocols and security requirements through UNDP Gaza Sub-Office and UNDSS; - Align programming timeline with ISF deployment phases; - Site selection prioritizes ISF-secured areas; - Remote management and local implementation modalities reducing ISF dependence for daily operations; - Coordinate with UNSCO on ISF cooperation frameworks; - Contingency planning for limited ISF capacity scenarios; |
| Continued ISR military attacks (drone/fighter jets) and military presence in Gaza; | 3. OPERATIONAL (3.7. Occupational safety, health and well-being) - UNDP Risk Appetite: EXPLORATORY TO OPEN 8. SAFETY AND SECURITY (8.1. Armed conflict) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 4 - Highly likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | - Continuous security monitoring with suspension protocols if military operations resume; - Remote management procedures to protect personnel; - Flexible implementation timeline allowing suspension/resumption; - Site selection considering distance from military presence; - Advocacy through UNSCO for respect of civilian implementation space; |

Stakeholder and Beneficiary Engagement

State institutions/Government: The project engages exclusively with Palestinian Authority institutions and structures linked to legitimate Palestinian governance. Given the absence of formal governance structures in Gaza, the project operates through the PA Gaza Emergency Operations Room and prepares institutional frameworks for eventual engagement with the technocratic committee and transitional administration as foreseen under UNSCR 2803. All interventions avoid creation of parallel authority structures.

Communities: The project adopts a community-based approach targeting displaced populations, and residents including returness in the three pilot sites (Deir el-Balah/Nuseirat, Khan Younis/Mawasi/Rafah, Gaza city). Community engagement occurs through youth programming providing civic education and psychosocial support to at-risk youth; One-Stop Shop service centers delivering essential civil documentation and public services accessible to all population groups including elderly and persons with disabilities; and community perception monitoring through regular surveys measuring security perceptions, trust in PA institutions, and service satisfaction to inform adaptive programming.

South-South and Triangular Cooperation

Pre-stabilization efforts in Gaza will build on lessons from Iraq, the Lake Chad region, and Mozambique, leveraging their successful approaches to enhance impact and sustainability. UNDP PAPP will engage in knowledge exchanges through the stabilization academy and forum, joint study visits, and peer-to-peer learning sessions. UNDP PAPP will also contribute to global and regional workshops and technical exchanges on critical stabilization issues such as communications, ‘finger-on-the-pulse’ monitoring, efficient operations and use of special measures.

Sustainability and Scaling Up

In designing its immediate stabilization support, UNDP adheres to the following sustainability principles: national and local ownership and accountability (transitional governance authority facilitated through pre-stabilization efforts paving the way for Palestinian Authority’s ownership); an integrated approach (enhancing local governance accountability, citizen engagement, and self-reliance); speed and flexibility based on changing circumstances; and visibility and communication (all results branded as delivered by the transitional governance authorities and/or Palestinian Authority, with no local-level visibility for donors and UNDP).

# Project Management

UNDP will execute this project through Direct Implementation Modality (DIM). Leadership on the management and overall direction of the stabilization programme will be provided by the UNDP Special Representative of the Administrator. The programme will be implemented under the guidance of the Head of the Gaza Sub-Office.

A core technical team designated by UNDP Gaza Sub-Office provides comprehensive management and in-house substantive expertise. The team includes: the Governance Team Leader (international – P4), who will serve as the “project coordinator” and Programme Management Specialist International P3 (50%) ; Project Manager/Security NPSA-8 (100%); Community Mobilizer (100%); Results Based Management Support Services (10%); Business Solutions Service Centre Support Services (10%); Operational Support Services (HR, Finance, IT, Procurement, General Services) (30%); Risk Management Support Services (10%); and Communication Support Service (10%). The team will be supported by the UNDP Crisis Bureau Global Stabilization Advisor.

Cost efficiency measures include DIM modality enabling direct oversight of expenditures, leveraging UNDP’s existing operational infrastructure in Gaza (Sub-Office, partnerships, systems), maximizing impact through co-financing with Crisis Bureau and other donor contributions, and shared service models reducing overhead per activity.

The project will be governed through a three-level governance architecture: a Project Steering Committee (PSC) for strategic direction; a Project Technical Committee (PTC) for technical coordination and donor engagement; and Site-Level Committees for operational coordination at each of the three pilot sites.

# Results Framework

Intended Outcome as stated in the UNSDCF/Country [or Regional] Programme Results and Resource Framework: Linked SDG Goals and Targets: Goal 1 (No Poverty), SDG 5 - Gender equality (targets 5.2, 5.4, 5.5) SDG 8 - Decent work & economic growth (8.3, 8.6), SDG 16 - Peace, justice & strong institutions (target 16.3) SDG 9 (target 9.1) Linked SP Moonshot(s): End poverty: Lift 100 million people out of poverty Linked Strategic Plan Output: A.3.2 Stabilization, recovery, and reconstruction efforts resulted in improved access to essential services and infrastructure, revitalized local economies, successful reintegration of excombatants, and reduced social tensions among crisis-affected populations. Linked Strategic Plan Indicator: IRRF A.3.2.5 Number of people who received direct support through UNDP-supported stabilization programmes (new) a) Total b) Women c) Men d) Youth d1) Youth women d2) Youth men e) Persons with disabilities f) Internally displaced populations g) Refugees g1) Refugees women g2) Refugees men Linked Flagship target(s)*: 10 million conflict-impacted people access life-sustaining support resulting in significantly reduced humanitarian caseload

Outcome indicators as stated in the Country Programme [or Regional] Results and Resources Framework, including baseline and targets: Linked Palestinian Programme Framework (2023-2027), programmatic priority: Outcome 1: Improved democratic governance based on the principles of human rights and rule of law, with equitable access to justice and quality public and basic services

Applicable Output(s) from the UNDP Strategic Plan: Output 1.3: Capacities of service providers for effective, efficient and responsive public and basic social services enhanced Indicator 1.3.1 Number of public/private service providers who have improved infrastructure and/or technical capacity to provide better services, (disaggregated by type of service provider, sector, type of capacity and geographical area)

Project title and Quantum Project Number: Pre-stabilization in Gaza ¦ TBD

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | TARGETS |  |  |  |  | DATA COLLECTION METHODS & RISKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year | Q1 | Q2 | Q3 | Q4 | FINAL |  |
| Output 1 Output 1: Strengthened Civilian Safety and Security Enabling Environment | Indicator 1.1.1.: Area assessed for UXO contamination |  | 0 | 2026 |  |  |  |  | X square meters assessed across 3 pilot sites (pending UNMAS technical input) |  |
|  | Indicator 1.1.2: Personnel trained in UXO assessment |  | 0 | 2026 |  |  |  |  | 15-20 personnel trained and equipped in UXO assessment methodologies |  |
|  | Indicator 1.1.3: Community members reached through UXO sensitization |  | 0 | 2026 |  |  |  |  | 30,000+ individuals across 3 pilot sites (gender-disaggregated data) |  |
|  | Indicator 1.2.1: Number of at-risk youths participating in safe community spaces programming |  | 0 | 2026 |  |  |  |  | 100-150 youth (40% female minimum) across pilot sites |  |
|  | Indicator 1.4.1: Number of Office police equipment items procured |  | 0 | 2026 |  |  |  |  | Essential police equipment package procured |  |
| Output 2: Supported Civil Administrative Functions and Service Delivery | Indicator 2.1.1: Number of Operations Room personnel deployed, trained and equipped. |  | 0 | 2026 |  |  |  |  | 12 Operations Room staff trained in coordination systems and equipped with operational tools (IT equipment, coordination platforms, technical protocols) |  |
|  | Indicator 2.3.1: Number of mobile civil registry units operational |  | 0 | 2026 |  |  |  |  | 3 mobile civil registry units deployed across pilot sites providing regular services |  |
|  | Indicator 2.3.2: Number of people accessing civil documentation services through SRM-supported mechanisms |  | 0 | 2026 |  |  |  |  | Target: 10,000 people (disaggregated by sex) across pilot sites |  |
|  | Indicator 2.4.1: Number of one-stop centers established and operational |  | 0 | 2026 |  |  |  |  | 3 physical One-Stop Shop service centers operational (1 per pilot site) |  |
|  | Indicator 2.5.1: PA communications systems operational |  | 0 | 2026 |  |  |  |  | PA GOR/technocratic committee communications systems strengthened with technical equipment, training, and protocols delivered |  |
|  | Indicator 2.6.1: Community perception monitoring system operational and result survey available |  | 0 | 2026 |  |  |  |  | Community perception monitoring system established with baseline + minimum 2 monitoring rounds completed measuring PA trust, security perception, and service satisfaction |  |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans: [Note: monitoring and evaluation plans should be adapted to project context, as needed]

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. |  |  |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. |  |  |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. |  |  |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. |  |  |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. |  |  |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) |  |  |  |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Specify frequency (i.e., at least annually) | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. |  |  |

Evaluation Plan

| Evaluation Title | Partners (if joint) | Related Strategic Plan Output | UNSDCF/CPD Outcome | Planned Completion Date | Key Evaluation Stakeholders | Cost and Source of Funding |
| --- | --- | --- | --- | --- | --- | --- |
| e.g., Mid-Term Evaluation |  |  |  |  |  |  |

# Work Plan

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1: Strengthened Civilian Safety and Security Enabling Environment Gender Marker: Gen 2 | 1.1 Support to UXO risk reduction |  |  |  |  |  |  |  |  |
|  | 1.1.1 UXO contamination assessment and mapping |  |  |  |  |  |  | 72100-Contractual Services- Companies 71300-Local Consultants | $320 000 |
|  | 1.1.2 Capacity building for Palestinian Mine Action Center (PMAC) |  |  |  |  |  |  |  |  |
|  | 1.1.3 Community UXO risk sensitization campaigns |  |  |  |  |  |  |  |  |
|  | 1.2 Establish safe community spaces |  |  |  |  |  |  |  |  |
|  | 1.2.1 Community safe spaces establishment and management |  |  |  |  |  |  |  | $472 200 |
|  | 1.2.2 Civic education and electoral system sensitization for future participation |  |  |  |  |  |  |  |  |
|  | 1.2.3 Youth-led community activities and sensitization campaign engagement |  |  |  |  |  |  |  |  |
|  | 1.3 Support vetting of PCP/PCD: Preparatory assessment for PCP/PCD reintegration |  |  |  |  |  |  |  |  |
|  | 1.3.1 Feasibility assessment and consultation with GEOR/technocratic committee |  |  |  |  |  |  |  | $0 |
|  | 1.3.2 Support PA to develop of reintegration frameworks and vetting protocols |  |  |  |  |  |  |  |  |
|  | 1.4 Police equipment procurement |  |  |  |  |  |  |  |  |
|  | 1.4.1 Procurement of essential police equipment and materials |  |  |  |  |  |  |  | $45 000 |
|  | Sub-Total for Output 1 |  |  |  |  |  |  |  | $837 200 |
| Output 2: Supported Civil Administrative Functions and Service Delivery Gender marker: | 2.1 Support to Gaza Emergency Operations Room (GEOR) |  |  |  |  |  |  |  |  |
|  | 2.1.1 GEOR operational infrastructure establishment (office space, equipment, IT systems, transportation, power supply) |  |  |  |  |  |  |  | $680 500 |
|  | 2.1.2 GOR staffing and technical capacity (coordinators, engineers, IT specialists, communications officers, administrative support) |  |  |  |  |  |  |  |  |
|  | 2.1.3 GOR operational systems strengthening (information management platforms, coordination protocols, stakeholder engagement mechanisms) |  |  |  |  |  |  |  |  |
|  | 2.2 Vetting of PA payroll personnel: Preparatory assessment for PA personnel reintegration |  |  |  |  |  |  |  |  |
|  | 2.2.1 Feasibility assessment and conditions analysis with GEOR/technocratic committee |  |  |  |  |  |  |  | $0 |
|  | 2.2.2 Support to PA to develop of SOPs, vetting frameworks, and deployment protocols |  |  |  |  |  |  |  |  |
|  | 2.3 Increase access to civil documentation |  |  |  |  |  |  |  |  |
|  | 2.3.1 Mobile civil registry units deployment and service delivery |  |  |  |  |  |  |  | $400 100 |
|  | 2.3.2 Birth/death certificates and passport services provision |  |  |  |  |  |  |  |  |
|  | 2.4 Support the creation of one-stop services |  |  |  |  |  |  |  |  |
|  | 2.4.1 Physical service center establishment in pilot sites |  |  |  |  |  |  |  | $430 300 |
|  | 2.4.2 Digital service platforms and ID systems integration |  |  |  |  |  |  |  |  |
|  | 2.5 Strengthen strategic pre-stabilization communication |  |  |  |  |  |  |  |  |
|  | 2.5.1 PA GOR/technocratic committee communications systems development |  |  |  |  |  |  |  | $112 986 |
|  | 2.5.2 PA-led messaging campaigns and quick wins visibility |  |  |  |  |  |  |  |  |
|  | - Data for Stabilization |  |  |  |  |  |  |  |  |
|  | 2.6.1 Community perception monitoring system establishment |  |  |  |  |  |  |  | $132 000 |
|  | 2.6.2 Political Economy Analysis (PEA) for conflict-sensitive programming |  |  |  |  |  |  |  |  |
|  | 2.6.3 Data collection, analysis, and feedback mechanisms for adaptive management |  |  |  |  |  |  |  |  |
|  | Sub-Total for Output 2 |  |  |  |  |  |  |  | $1 755 886 |
| UNDP Staff/technical team |  |  |  |  |  |  |  |  | $446 542 |
| Operational costs (including rent, fuel, transport, armoured vehicle, security, IT equipment, supplies) |  |  |  |  |  |  |  |  | $179 400 |
| CB Technical Assistance (5%) |  |  |  |  |  |  |  |  | $183 750 |
| General Management Support |  |  |  |  |  |  |  |  | $272 222 |
| TOTAL |  |  |  |  |  |  |  |  | $3,675,000 |

# Governance and Management Arrangements

UNDP will execute this project through Direct Implementation Modality (DIM). The SRM Gaza pilot employs a three-level governance architecture to ensure PA ownership, multi-stakeholder coordination, and operational effectiveness.

Project Steering Committee (PSC)

The PSC provides strategic direction, validates site selection and intervention design, approves annual work plans and budgets, and ensures alignment with PA Gaza recovery priorities and UNSCR 2803 mandate. The PSC is chaired by the Head of the Palestinian Emergency Operations Room in Gaza, with the UNDP Head of the Gaza Sub-Office as co-chair and the Head of Stabilization as secretariat. Members include: 1 Representative from the PA Prime Minister Office, 1 Representative of UNSCO, GFFO, and representatives of potential future donors. The PSC meets at least once a year and may convene meetings anytime upon request by one of the co-chairs.

Project Technical Committee (PTC)

The PTC supports effective implementation and facilitates technical coordination between UNDP, GFFO/German Embassy/Representative Office, and where applicable, representatives of potential future donors. The committee meets on a quarterly basis and includes regular briefings from UNDP on progress, challenges, and upcoming priorities. It advises the PSC on technical matters and plays a key role in reviewing and endorsing activity packages for selected project locations.

Site-Level Committees

Site-Level Committees will be established in each of the three pilot sites (Deir el-Balah, Khan Younis Municipality/Mawasi area, and Gaza City), to coordinate implementation with relevant local stakeholders, One-Stop Shop service center staff, community safe space coordinators, local community-based organizations, and PA ministry service providers. In the absence of formal local government structures in Gaza, these committees serve as the primary coordination mechanism ensuring coherent service delivery and maintaining linkages with the PA Gaza Emergency Operations Room. Site-Level Committees meet monthly to coordinate schedules, address operational challenges, share community feedback, and ensure conflict-sensitive implementation.

Monitoring and Learning

Stabilization programming requires a constant ‘finger-on-the-pulse’ of programme implementation progress and conflict dynamics to ensure real-time data for adaptive programme management, conflict sensitivity application, and well-informed risk management. The project will obtain and analyse data through formal and informal channels including the GFFO-funded political context monitoring system, social media monitoring, and regular learning cycles where UNDP PAPP Senior Management and the Stabilization Team revisit the Theory of Change and agree on programmatic adaptations.

# Legal Context

[NOTE: Please choose one of the following options, as applicable. Delete all other options from the document]

Option a. Where the country has signed the Standard Basic Assistance Agreement (SBAA)

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Palestinian Authority and UNDP, as applicable.   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by UNDP (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Option b. Where the country has NOT signed the Standard Basic Assistance Agreement (SBAA)

The project document shall be the instrument envisaged and defined in the Supplemental Provisions to the Project Document, attached hereto and forming an integral part hereof, as “the Project Document”.

This project will be implemented by UNDP (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Option c. For Global and Regional Projects

This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions to the Project Document attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by UNDP (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the PAPP, signed on XXX   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by UNDP (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures.

# Risk Management

[NOTE: Please choose one of the following options that corresponds to the implementation modality of the Project. Delete all other options.]

Option a. Government Entity (NIM)

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

- a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4 have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and its sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

b) The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.

- In the implementation of the activities under this Project Document, UNDP places reasonable reliance upon the Implementing Partner for it to apply its laws, regulations and processes, and applicable international laws regarding anti money laundering and countering the financing of terrorism, to ensure consistency with the principles of then in force the UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy.

- The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes in accordance with UNDP’s regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, credible allegation of fraud or corruption or other financial irregularities with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- Choose one of the three following options:

Option 1: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

Option 2: The Implementing Partner agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors, and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

Option b. UNDP (DIM)

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism , that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Project Document, UNDP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor, and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - Each responsible party, subcontractor and sub-recipient (each a “sub-party” and together “sub-parties”) acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the sub-parties, and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, each sub-party shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, each sub-party, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

  - In the performance of the activities under this Project Document, each sub-party shall (with respect to its own activities), and shall require from its sub-parties (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, sub-parties will and will require that their respective sub-parties will take all appropriate measures to:

(i) Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

(ii) Offer employees and associated personnel training on prevention and response to SH and SEA, where sub-parties have not put in place its own training regarding the prevention of SH and SEA, sub-parties may use the training material available at UNDP;

(iii) Report and monitor allegations of SH and SEA of which any of the sub-parties have been informed or have otherwise become aware, and status thereof;

(iv) Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

(v) Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. Each sub-party shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the relevant sub-party shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

  - Each sub-party shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the relevant sub-party to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

  - Each responsible party, subcontractor and sub-recipient will ensure that any project activities undertaken by them will be implemented in a manner consistent with the UNDP Social and Environmental Standards and shall ensure that any incidents or issues of non-compliance shall be reported to UNDP in accordance with UNDP Social and Environmental Standards.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud, corruption or other financial irregularities, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption other financial irregularities with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - Choose one of the three following options:

Option 1: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption, other financial irregularities or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Option 2: Each responsible party, subcontractor or sub-recipient agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud corruption or other financial irregularities or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

Option c. CSO/NGO/Non-UN or other IGO with no signed SBEAA with UNDP

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document and the Project Cooperation Agreement between UNDP and the Implementing Partner.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Sanctions Consolidated Sanctions  List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Sanctions Consolidated Sanctions  List  can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

- a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will, and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4, have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and such sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

b) The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP is committed to the highest ethical standards and will not tolerate the diversion of the resources entrusted to it through Money Laundering or Terrorist Financing and will not partner with entities that tolerate the diversion of resources through Money Laundering or Terrorist Financing. To that effect, the Implementing Partner represents and warrants that it has not, and it shall not, at any time in the implementation of the Project engage in Terrorism Financing or Money Laundering.  The Implementing Partner shall communicate the restriction of this paragraph to its and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Documents and shall take all reasonable measures to ensure that such persons do not engage in Terrorism Financing or Money Laundering.

- The Implementing Partner shall immediately disclose to UNDP any actual, apparent, potential or attempted Terrorism Financing or Money Laundering activity that it becomes aware of. The Implementing Partner shall fully cooperate with any investigation or review of Terrorism Financing or Money Laundering activity by UNDP.

- The Implementing Partner acknowledges and agrees that Terrorism Financing or Money Laundering constitute financial irregulates and that if the Implementing Partner or any of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document engages in Terrorism Financing or Money Laundering activity  that would constitute a material breach of this Project Document, which entitles UNDP to immediately terminate the Project without incurring any liability or penalty.

- Furthermore, the Implementing Partner expressly acknowledges and agrees that, in the event that UNDP were to determine through an investigation or otherwise that Terrorism Financing or Money Laundering occurred, UNDP shall have, in addition to its right to immediately terminate the Project, the rights to:

- apply and enforce the relevant sanctions in accordance with UNDP internal regulations, rules, procedures, practices, policies and guidelines, including referral of the matter to national authorities when appropriate; and

- recover all losses, financial or otherwise, suffered by UNDP in connection with such Terrorism Financing or Money Laundering activity.

- For the purpose of this Project Document the following terms shall have the definition ascribed to the below:

- “Money Laundering” is generally considered as concealment of the origins of money obtained illegally, typically by passing it through a complex sequence of financial or commercial transactions. ML usually involves three stages: (i) introducing the proceeds of crime into the financial system (placement); (ii) transactions to convert or transfer the funds to other locations or financial institutions (layering); and (iii) reintroducing the funds into the legitimate economy as "clean" money and investing it in various assets or business ventures (reintegration) appearing to have been legally obtained. The FATF recommends that ML be criminalized by every country on the basis of article 3(1)(b) and (c) of the Vienna Convention and article 6(1) of the Palermo Convention.

- “Terrorist Financing” means providing support to individuals or entities that appear on the United Nations Security Council Consolidated Sanctions List accessible at https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using the UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP programmes and projects in accordance with UNDP regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors‘ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The Implementing Partner will promptly inform UNDP in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption or other financial irregularity with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption or other financial irregularity, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- Choose one of the three following options:

Option 1: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud,  corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

Option 2: The Implementing Partner agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud. corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with the Implementing Partner, responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management Standard Clauses” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

Option d. UN Agency other than UNDP, and IGO with signed SBEAA with UNDP

- [Name of UN Agency/IGO] as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- In the implementation of the activities under this Project Document, [Name of UN Agency/IGO] as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures. The Implementing Partner will ensure that its regulations, rules, policies and procedures are consistent with the principles of UNDP relating to SEA and SH requirements. Notwithstanding the foregoing, the [Name of UN Agency/IGO], as the Implementing Partner, will notify UNDP of any such allegations and investigations it may conduct further to such allegations.

- [Name of UN Agency/IGO] as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor and sub-recipient that is not a UN entity:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of [Name of UN Agency/IGO]’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - [Name of UN Agency/IGO]  reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - In the performance of the activities under this Project, [Name of UN Agency/IGO] as the Implementing Partner shall ensure, with respect to the activities of any of its responsible parties, sub-recipients and other entities engaged under the Project, either as contractors or subcontractors, their personnel and any individuals performing services for them, that those entities have in place adequate and proper procedures, processes and policies to prevent and/or handle SEA and SH.

- [Name of UN Agency/IGO] agrees to undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Sanctions Consolidated Sanctions  List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Sanctions Consolidated Sanctions  List  can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm ).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- In the implementation of the activities under this Project Document, [Name of UN Agency/IGO] as the Implementing Partner will ensure that its regulations, rules, policies and procedures are consistent with the principles of then in force UNDP’s Anti-Money Laundering and Countering the Financing of Terrorism Policy.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud, or corruption, by its officials, consultants, responsible parties, subcontractors, and sub-recipients in implementing the project or programme or using the UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- [This text should be included when the Implementing Partner is a non-UN IGO: The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.]

- [This text should be included when the Implementing Partner is a non-UN IGO: In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects or programmes. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors‘ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.]

- The Implementing Partner and UNDP will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption or other financial irregularity, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- Choose one of the three following options:

Option 1: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

Option 2: The Implementing Partner agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management Standard Clauses” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

Special Clauses. In case of government cost-sharing through the project, the following clauses should be included:

- The schedule of payments and UNDP bank account details.

- The value of the payment, if made in a currency other than United States dollars, shall be determined by applying the United Nations operational rate of exchange in effect on the date of payment.  Should there be a change in the United Nations operational rate of exchange prior to the full utilization by the UNDP of the payment, the value of the balance of funds still held at that time will be adjusted accordingly.  If, in such a case, a loss in the value of the balance of funds is recorded, UNDP shall inform the Government with a view to determining whether any further financing could be provided by the Government.  Should such further financing not be available, the assistance to be provided to the project may be reduced, suspended or terminated by UNDP.

- The above schedule of payments takes into account the requirement that the payments shall be made in advance of the implementation of planned activities.  It may be amended to be consistent with the progress of project delivery.

- UNDP shall receive and administer the payment in accordance with the regulations, rules and directives of UNDP.

- All financial accounts and statements shall be expressed in United States dollars.

- If unforeseen increases in expenditures or commitments are expected or realized (whether owing to inflationary factors, fluctuation in exchange rates or unforeseen contingencies), UNDP shall submit to the government on a timely basis a supplementary estimate showing the further financing that will be necessary. The Government shall use its best endeavours to obtain the additional funds required.

- If the payments referred above are not received in accordance with the payment schedule, or if the additional financing required in accordance with paragraph 6 above is not forthcoming from the Government or other sources, the assistance to be provided to the project under this Agreement may be reduced, suspended or terminated by UNDP.

- Any interest income attributable to the contribution shall be credited to UNDP Account and shall be utilized in accordance with established UNDP procedures.

In accordance with the decisions and directives of UNDP's Executive Board:

The contribution shall be charged:

- […%] cost recovery for the provision of general management support (GMS) by UNDP headquarters and country offices

- Direct cost for implementation support services (ISS) provided by UNDP and/or an executing entity/implementing partner.

- Ownership of equipment, supplies and other properties financed from the contribution shall vest in UNDP.  Matters relating to the transfer of ownership by UNDP shall be determined in accordance with the relevant policies and procedures of UNDP.

- The contribution shall be subject exclusively to the internal and external auditing procedures provided for in the financial regulations, rules and directives of UNDP.”

# ANNEXES

- Project Quality Assurance Report

- Social and Environmental Screening Template [English] [French] [Spanish], including additional Social and Environmental Assessments or Management Plans as relevant. (NOTE: The SES Screening is not required for projects in which UNDP is Administrative Agent only and/or projects comprised solely of reports, coordination of events, trainings, workshops, meetings, conferences, preparation of communication materials, strengthening capacities of partners to participate in international negotiations and conferences, partnership coordination and management of networks, or global/regional projects with no country level activities).

- Risk Analysis. Use the standard Risk Register template. Please refer to the Deliverable Description of the Risk Register for instructions

- Capacity Assessment: Results of capacity assessments of Implementing Partner (including Partner Capacity Assessment Tool (PCAT) and HACT Micro Assessment)

- Project Board Terms of Reference and TORs of key management positions. The standard Project Board TOR can be found here.

- On-Granting Provisions Applicable to the Implementing Partner. On-granting clauses for non-UNDP Implementing Partners can be found here.

The Gender Marker measures how much a project invests in gender equality and women’s empowerment. Select one for each output: GEN3 (Gender equality as a principle objective); GEN2 (Gender equality as a significant objective); GEN1 (Limited contribution to gender equality); GEN0 (No contribution to gender quality)

Note: Adjust signatures as needed

As per UNDP’s Enterprise Risk Management Policy

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards.  Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.

All proposals should align to at least one SP output and related indicator and include those in the workplan/result-framework below to show contribution to the SP IRRF. The linkage to the SP Output and indicator should also be reflected in Quantum.

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.

Optional, if needed

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a project budget affecting the scope (outputs), completion date, or total estimated project costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner

Use bracketed text only when IP is an NGO/IGO

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner

Applicable for non-UNDP Implementing Partner as Grant Making Institution facilitating on-granting.