GEF PPG TOTAL BUDGET WORK PLAN

PROJECT TITLE:  Promoting Sustainable Land Management to Achieve Land Degradation Neutrality (LDN), Enhance Livelihoods, and Strengthen the Farming Communities in the Aylagundet Watershed, Debub Region, Eritrea (PIMS# 10304)

COUNTRY / REGION / GLOBAL: Eritrea/RBA

BRIEF DESCRIPTION

The Project Preparation Grant (PPG) is a funding mechanism provided by the GEF to support the preparation of project proposals. It aims to develop the project concept into a full project by funding activities such as project development, stakeholder engagement, and risk management. The PPG is essential for ensuring that projects align with GEF policies and are effectively implemented. All GEF-specific project roles and responsibilities, including assurance and oversight functions, can be found in the GEF RACI.

Expected final outputs of the GEF PPG:

- UNDP-GEF Project Document and all mandatory annexes (in English).

- GEF CEO Endorsement Request and all mandatory annexes; and

- Validation Workshop report

| Programme Period: (18 months) | 04 May 2026—04 November 2027 |
| --- | --- |
| Alignment to UNSDCF / CPD (Outcomes & Outputs): CPD Outputs: Gender Marker: | By 2026, people in Eritrea have benefited from climate resilient, sustainable environment and natural resources management Output 3.1 Capacity of national, subnational and community-level institutions is strengthened to sustainably manage and use biodiversity, environmental and natural resources and reduce disaster risks and their impacts Output 3.2. Men, women and youth in rural areas are enabled to manage and utilize natural resources equitably and sustainably to improve livelihoods Output 3.3. Capacities of public institutions and communities are enhanced to mitigate, adapt to and mainstream climate change and disaster risks into development programmes Output 3.4. Access to modern, renewable and affordable clean energy sources and services increased GEN2 |

| PPG Management Arrangements: | UN Agency |
| --- | --- |
| PPG Implementing Partner: | Ministry of Land, Water & Environment (MOLWE)t |
| Expected Management Arrangements for full project: | NIM |

This document describes how the GEF Project Preparation Grant (PPG) resources will be programmed, over 18 months to produce the expected final outputs (see above) that are fully compliant with UNDP and GEF policies and ready for submission to the GEF for CEO endorsement.

This document must go through internal technical and financial clearance at the same time as the PIF before submission to the GEF.

When the PIF has been technically cleared by the GEF, indicating that the PPG resources have been approved by the GEF, this document will be included as annex to the PPG DOA letter issued to the Head of Office for signature. The signed DOA letter and its annexes constitute the UNDP Project Initiation Plan.  For Global projects, this document will be sent for signature by the BPPS Deputy Director, to constitute the equivalent of the project Initiation Plan for the PPG phase. For non-DIM PPGs, this file will be sent for signature by the Implementing Partner and UNDP Head of Office.

# PPG Total Budget Work Plan (TBWP)

| Quantum Output | Quantum Activity | Quantum Responsible Party (UNDP, IP, or RP) | Quantum Fund ID | Quantum Donor ID | Quantum Budgetary Account Code | Quantum Budget Account Description | Amount Year 1 (2026) (USD) | Amount Year 2 (2027) (USD) | Total (USD) | Budget Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project preparation grant (PPG) to finalize the UNDP-GEF project document for project title: Promoting Sustainable Land Management to Achieve Land Degradation Neutrality (LDN), Enhance Livelihoods, and Strengthen the Farming Communities in the Aylagundet Watershed, Debub Region, Eritrea (PIMS# 10304) } | Project Preparation Activity | UNDP | 62000 | 10003 | 71200 | International Consultants | $92,000.00 | $23,000.00 | $115,000.00 | Fund 62000 / Account 71200 – International Consultants |
|  |  |  |  |  |  |  |  |  |  | Covers fees for internationally recruited consultants providing specialized technical expertise required for PPG deliverables, including: |
|  |  |  |  |  |  |  |  |  |  | • International Lead Consultant (Team Leader) responsible for overall coordination, design, QA, and consolidation;(75 workdaysx$600=$45,000) |
|  |  |  |  |  |  |  |  |  |  | • International SES Specialist (screening, risk assessment, safeguards instruments) ;(70 daysx$550=$38,500) |
|  |  |  |  |  |  |  |  |  |  | • International Gender and Stakeholder Engagement Specialist (gender analysis, stakeholder analysis, and action plans); (63daysx$500=$31,500) |
|  |  |  |  |  |  |  |  |  |  | TOTAL= $115,500 |
|  |  |  |  |  |  |  |  |  |  | Costs are calculated based on daily professional fees × number of working days, aligned with delivery of: |
|  |  |  |  |  |  |  |  |  |  | • Component A: $46,000 (Preparatory Technical Studies & Reviews): |
|  |  |  |  |  |  |  |  |  |  | Covers baseline assessment, stakeholder consultations, field data collection, and analytical inputs. |
|  |  |  |  |  |  |  |  |  |  | • Component B: 63,250(Formulation of Technical Assessments and Plans): |
|  |  |  |  |  |  |  |  |  |  | Covers preparation of ProDoc, CEO Endorsement Request, SES instruments, Gender Action Plan, and Stakeholder Engagement Plan. |
|  |  |  |  |  |  |  |  |  |  | • Component C: $5,750 (Validation and Consultation Workshops): |
|  |  |  |  |  |  |  |  |  |  | Covers stakeholder validation, workshop implementation, and finalization of project documentation. |
|  |  |  |  |  |  |  |  |  |  | • Cross-cutting analytical outputs (SES, Gender Action Plan, Stakeholder Engagement Plan). |
|  |  |  | 62160 |  | 71200 | Contractual Services-Companies | $30,000.00 | $7,500.00 | $37,500.00 | Covers costs of national experts engaged to undertake in-country technical work, including: |
|  |  |  |  |  |  |  |  |  |  | · Preparation of baseline assessment (biophysical and socio-economic); |
|  |  |  |  |  |  |  |  |  |  | · Stakeholder consultations, field data collection, and validation; |
|  |  |  |  |  |  |  |  |  |  | · Preparation of Draft Stakeholder Engagement Report; |
|  |  |  |  |  |  |  |  |  |  | · Provision of datasets and evidence for SES and gender analyses. |
|  |  |  |  |  |  |  |  |  |  | Costs are based on daily rate × number of working days, i.e $250x150days. It linked primarily to: |
|  |  |  |  |  |  |  |  |  |  | · Component A=$27,500 (baseline, consultations, data collection); |
|  |  |  |  |  |  |  |  |  |  | · Component B=$7,500 (Supporting inputs to ProDoc sections and annexes). |
|  |  |  |  |  |  |  |  |  |  | · Component C=$2,500 (Supporting inputs to Validation Workshop). |
|  |  |  |  |  |  |  |  |  |  | TOTAL = $37,500 |
|  |  |  | 62181 |  | 71600 | Travel | $15,000.00 | $4,150.00 | $19,150.00 | Travel description (Costs for mission airfares, terminal expenses, and living allowances) |
|  |  |  |  |  |  |  |  |  |  | Fund 62181 / Account 71600 – Travel |
|  |  |  |  |  |  |  |  |  |  | Component A: $1,433: (Covers all official travel required for PPG implementation, including:) |
|  |  |  |  |  |  |  |  |  |  | • International consultant missions; |
|  |  |  |  |  |  |  |  |  |  | • National consultant and stakeholder field visits; |
|  |  |  |  |  |  |  |  |  |  | Component B: $14,920 (Travel to project sites (Debub Region and Aylagundet watershed); |
|  |  |  |  |  |  |  |  |  |  | •Component C: $2,797 (Participation in inception, technical, and validation workshops.) |
|  |  |  |  |  |  |  |  |  |  | Includes: |
|  |  |  |  |  |  |  |  |  |  | • Airfare, DSA, terminal expenses, and local transport; |
|  |  |  |  |  |  |  |  |  |  | • Travel of national stakeholders for consultations. |
|  |  |  |  |  |  |  |  |  |  | TOTAL = $19,150 |
|  |  |  |  |  | 72400 | Communications & Audio Visual Equip | $3,000.00 | $2,000.00 | $5,000.00 | Communication and connectivity charges description. No IT equipment is allowed to be budgeted. |
|  |  |  |  |  |  |  |  |  |  | Account 72400 – Communications & Audio-Visual Equipment |
|  |  |  |  |  |  |  |  |  |  | Covers communication and connectivity costs required for PPG execution, including: |
|  |  |  |  |  |  |  |  |  |  | • Internet and telecommunication services; |
|  |  |  |  |  |  |  |  |  |  | • Virtual meeting platforms and coordination tools; |
|  |  |  |  |  |  |  |  |  |  | • Audio-visual services for workshops and consultations. |
|  |  |  |  |  |  |  |  |  |  | Supports coordination across national and international stakeholders. |
|  |  |  |  |  |  |  |  |  |  | Component A=$250, Component B=4,000; Component C=$750 |
|  |  |  |  |  |  |  |  |  |  | TOTAL = $5,000 |
|  |  |  |  |  |  |  |  |  |  | (No capital IT equipment is included, in line with GEF rules prohibiting capital expenditure.) |
|  |  |  |  |  | 72500 | Supplies | $2,000.00 | $1,000.00 | $3,000.00 | Supplies, as office supplies, description |
|  |  |  |  |  |  |  |  |  |  | Account 72500 – Supplies |
|  |  |  |  |  |  |  |  |  |  | Covers consumable items directly required for PPG activities, including: |
|  |  |  |  |  |  |  |  |  |  | • Office supplies and data collection materials; Component A=$150 |
|  |  |  |  |  |  |  |  |  |  | Stationery and documentation materials for fieldwork Component B=$2,400 |
|  |  |  |  |  |  |  |  |  |  | * Workshops, Printing consumables: Component C=$450 |
|  |  |  |  |  |  |  |  |  |  | TOTAL = $3,000 |
|  |  |  |  |  | 74100 | Professional Services | $1,000.00 | $0.00 | $1,000.00 | For HACT Micro Assessments only - Assess capacity of the executing partner |
|  |  |  |  |  |  |  |  |  |  | Covers costs associated with the HACT (Harmonized Approach to Cash Transfers) Micro Assessment of the Implementing Partner (MOLWE) to assess financial management capacity, identify fiduciary risks, and determine appropriate assurance modalities in line with UNDP requirements. |
|  |  |  |  |  |  |  |  |  |  | Calculation basis: |
|  |  |  |  |  |  |  |  |  |  | HACT Micro Assessment conducted by an accredited firm (lump sum estimate: $1,000). |
|  |  |  |  |  |  |  |  |  |  | Inputs to institutional capacity assessment and implementation arrangement sections of the ProDoc and CEO Endorsement Request (Component B: $1,000). |
|  |  |  |  |  | 74200 | Audio Visual & Print Prod Cost | $0.00 | $2,750.00 | $2,750.00 | Printing, publication, translation cost description |
|  |  |  |  |  |  |  |  |  |  | Account 74200 – Audio-Visual & Print Production Costs |
|  |  |  |  |  |  |  |  |  |  | Covers preparation and dissemination of PPG outputs, including: |
|  |  |  |  |  |  |  |  |  |  | • Printing of reports (baseline, stakeholder report, ProDoc drafts); |
|  |  |  |  |  |  |  |  |  |  | • Translation of documents into/out of English; |
|  |  |  |  |  |  |  |  |  |  | • Editing, formatting, and layout of project documentation; |
|  |  |  |  |  |  |  |  |  |  | • Preparation of workshop materials. |
|  |  |  |  |  |  |  |  |  |  | Costs are calculated as unit cost × volume/pages, aligned with: |
|  |  |  |  |  |  |  |  |  |  | • Component B (ProDoc and annexes) =$2,200 |
|  |  |  |  |  |  |  |  |  |  | • Component C (validation workshop documentation) =$550 |
|  |  |  |  |  |  |  |  |  |  | TOTAL= $2,750. |
|  |  |  |  |  | 74500 | Miscellaneous Expenses | $500.00 | $100.00 | $600.00 | Miscellaneous items should be considered carefully and explained in detail. It cannot be detailed as “miscellaneous expenses” and should not be used as a contingency budget. To the greatest extent, all foreseen expenditures must be budgeted in other categories. |
|  |  |  |  |  |  |  |  |  |  | Account 74500 – Miscellaneous Expenses |
|  |  |  |  |  |  |  |  |  |  | Covers minor, fully specified costs not allocable to other categories, such as: |
|  |  |  |  |  |  |  |  |  |  | • Bank charges and transaction fees; |
|  |  |  |  |  |  |  |  |  |  | • Minor logistical expenses linked to consultations or missions. |
|  |  |  |  |  |  |  |  |  |  | Component B (ProDoc and annexes) =$600 |
|  |  |  |  |  | 75700 | Training, Workshops and Confer | $10,000.00 | $6,000.00 | $16,000.00 | Training, Workshops, Conferences, and Meetings costs description |
|  |  |  |  |  |  |  |  |  |  | Account 75700 – Training, Workshops, and Conferences |
|  |  |  |  |  |  |  |  |  |  | Covers organization and implementation of all PPG-related consultations and workshops, including: |
|  |  |  |  |  |  |  |  |  |  | Component A=$800 (Inception workshop, technical design consultations;) |
|  |  |  |  |  |  |  |  |  |  | Component B=$12,800 (Stakeholder engagement and workshops (national and local); |
|  |  |  |  |  |  |  |  |  |  | Component C= $2,400 (Validation workshop.) |
|  |  |  |  |  |  |  |  |  |  | Eligible costs include: |
|  |  |  |  |  |  |  |  |  |  | • Venue rental, catering, and workshop logistics; |
|  |  |  |  |  |  |  |  |  |  | • Participant travel and DSA; |
|  |  |  |  |  |  |  |  |  |  | • Facilitation, documentation, and materials. |
|  |  |  |  |  |  |  |  |  |  | TOTAL = $16,000 |
|  |  | Total Responsible Party UNDP (DIM) |  |  |  |  | $153,500.00 | $46,500.00 | $200,000.00 |  |
| Total PPG breakdown by Component | Component A: Preparatory Technical Studies & Reviews |  |  |  |  |  |  |  | $76,133 |  |
|  | Component B: Formulation of technical assessments and plans to integrate into PPG Outputs |  |  |  |  |  |  |  | $108,670 |  |
|  | Component C: Validation and consultation workshops |  |  |  |  |  |  |  | $15,197 |  |

Calculation Table

| Responsible Party | Cost Item | Quantum Budgetary Acc Code | Units | Unit cost (US$) | Budget (US$) |  |  | PPG COMPONENT |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | A | B | C |
|  |  |  |  |  | Total | Year 1 | Year 2 |  |  |  |
| Responsible Party UNDP | Project Preparation Grant (PPG) Team Leader | 71200 | 60 | 750 | 45,000 | 36,000 | 9,000 | 18,000 | 24,750 | 2,250 |
|  | Social and Environmental Standards (SES) Expert | 71200 | 55 | 700 | 38,500 | 30,800 | 7,700 | 15,400 | 21,175 | 1,925 |
|  | Gender and Stakeholder Engagement Specialist | 71200 | 45 | 700 | 31,500 | 25,200 | 6,300 | 12,600 | 17,325 | 1,575 |
|  | Sub-total |  |  |  | 115,000 | 92,000 | 23,000 | 46,000 | 63,250 | 5,750 |
|  | National Natural Resources & Socio-Economic Baseline Consultant | 71300 | 150 | 250 | 37,500 | 30,000 | 7,500 | 27,500 | 7,500 | 2,500 |
|  | Travel (consultants) | 71600 | 1 | 19,150 | 19,150 | 15,000 | 4,150 | 1,433 | 14,920 | 2,797 |
|  | Communications & Audio-Visual Equipment | 72400 | 1 | 5,000 | 5,000 | 3,000 | 2,000 | 250 | 4,000 | 750 |
|  | Supplies | 72500 | 1 | 3,000 | 3,000 | 2,000 | 1,000 | 150 | 2,400 | 450 |
|  | Professional Services | 74100 | 1 | 1,000 | 1,000 | 1,000 | - | - | 1,000 | - |
|  | Audio Visual & Print Prod Cost | 74200 | 1 | 2,750 | 2,750 | - | 2,750 | - | 2,200 | 550 |
|  | Miscellaneous | 74500 | 1 | 600 | 600 | 500 | 100 | - | 600 | - |
|  | training, Workshops and Conferences | 75700 | 1 | 16,000 | 16,000 | 10,000 | 6,000 | 800 | 12,800 | 2,400 |
|  | Sub-total |  |  |  | 85,000 | 61,500 | 23,500 | 30,133 | 45,420 | 9,447 |
|  | Total |  |  |  | 200,000 | 153,500 | 46,500 | 76,133 | 108,670 | 15,197 |
|  | Component A |  |  |  | 76,133 |  |  |  |  |  |
|  | Component B |  |  |  | 108,670 |  |  |  |  |  |
|  | Component C |  |  |  | 15,197 |  |  |  |  |  |

Annex: Guidance on completing the PPG TBWP section

Please note the following during the preparation of the PPG Budget:

- Maintain one single output and one activity as per the template above. This aligns with the PPG requirements in Quantum.

- Enter the Responsible Party(ies) that will implement the project. In case there are 2 Responsible Parties implementing the budget, each of them will have their budget.

- Select the Quantum Fund from the GEF Fund that will cover costs of the PPG.

- Quantum Donor is the same for all GEF funds.  Do not change.

- Only the Budget Accounts listed in the template can be budgeted.

- Budget notes should detail the use and purpose of the budget and include the cost breakdown and calculation basis (e.g., daily fee and number of days/weeks, unit cost and quantity). The outputs (deliverables) of the consultants must be clear. Please consult the below list of eligible and ineligible expenditures for what can and cannot be budgeted for the PPG. No UNDP staff costs can be budgeted.

- Terms of Reference (TORs) for key consultants and project personnel should follow UNDP procedures outlined in the POPP.

  - This includes the guidance in the POPP Procurement Chapter/Individual Contract section (refer to Individual Contract Policy); for project non-staff personnel, the IPSA or NPSA contract modality may be leveraged, which is an HR process (refer to the International Personnel Services Agreement and National Personnel Services Agreement policies).

  - See standard and sample TOR templates for Consultants financed by the GEF PPG.

- No “personnel” or project management costs can be charged to the Initiation Plan using GEF PPG resources; such costs should be borne by the requesting agency or co-financing. All technical support must be provided by local and/or international consultants, not by UNDP staff. Miscellaneous items should be considered very carefully and explained.

- No UNDP Support Services (DPC) is to be budgeted as this is against GEF policy

Per GEF Policy, the list of eligible and ineligible expenditure can be found in the Guidelines of Project and Program Cycle (table 1)

Eligible Expenditure Items for In-country Preparations of GEF project submission:

- Local consultations, national hearings and/or workshops to inform about GEF purposes and procedures or to discuss specific project and program ideas. This could include translation into local languages where appropriate and preparation of background papers that could facilitate discussion.

- Travel costs for local experts for consultations and discussions with interested parties and stakeholders, and local participation were warranted in project design.

- Local workshops to discuss a project concept and provide a platform for divergent views on its efficacy.

- Consultancies and contracts to develop program and/or project options. These may be national, regional or international, as appropriate and agreed among partners. This could include preparation of terms of reference for pre-feasibility studies, feasibility studies, basic costing, technical and scientific design parameters, financial plan, assessment of incremental cost, strategy papers and where possible, the preparation of such papers.

- Gender and Environmental and Social Safeguards analysis required at project preparation phase. Subject to discussion with and concurrence of GEF Secretariat during the review process, this could include documenting the project baseline conditions and evaluating safeguard risks, developing related action plans or equivalents.

- Free prior and informed consent and related consultations to ensure environmental and social safeguard standards are met.

- Assistance in preparing national and/or sectoral plans and programs (such as energy, industry or agriculture) that have direct bearing on project design, national policy analysis, and inventory and data analysis in support of the proposed project.

- Costs of translating documents into and out of English.

- Assessing capacity of executing partners. (including PCAT and HACT)

- In addition, for regional and global projects: In-country costs in eligible recipient countries, including travel and subsistence costs of recipient country experts to consultations associated with the development of a regional or global project or program.

Ineligible expenditures under Project Preparation Grants (PPGs)

- Costs associated with the work of government staff or regular project/program activities of a GEF Agency or a Project Executing Entity (EA).

- Non-project preparation costs including: project start-up costs (i.e. costs covered by Agency Fee such as pipeline management, operationalization of the project, internal appraisal, or covered by the project budget); demonstration and pilot projects; implementation of large-scale enabling activities, including detailed country-wide inventories and country studies, training activities other than where they are directly related to project and/or country preparation and major research.

- Capital goods (e.g. computers and engineering equipment) other than those directly required for project preparation.

- Purchase of motorized vehicles (such purchase, if required, should instead be covered by co financing amounts, not PPG).

Reporting by PPG Component:

Further details on standard PPG Components and Activities can be found in the guidance document for PPG Teams on the VF intranet. This breakdown (by Component only) must be used in the CEO Endorsement Request (Annex D) when reporting on the aggregate utilization of PPG Funds. Please do not report at Activity or Budget Account level.

| Component | Activity |
| --- | --- |
| Component A: Preparatory Technical Studies & Reviews | - Desktop and field-based studies and data collection - Gender Analysis - SES Screening and Assessments - Identification of project sites - Financial planning, co-financing, and investment mobilized - Stakeholder Analysis - Appraise and formulate the most appropriate implementation and execution modality - Other required studies |
| Component B: Formulation of technical assessments and plans to integrate into PPG Outputs | - Stakeholder Engagement Plan - Gender Action Plan and Budget - Social and Environmental Standards: Screening and Management Measures - GEF and LDCF/SCCF Core Indicators - Completion of the required official endorsement letters - Project Management Arrangements - Mandatory Annexes - Other activities |
| Component C: Validation and consultation workshops | - Local consultations and workshops - Other activities |