## Workplan
Improving Marine Monitoring Along the Aqaba Coastline - Phase II: Comprehensive Work Plan (June 2026 - May 2029)
OUTCOME: Enhanced institutional capacity for evidence-based marine management and pollution risk reduction in the Gulf of Aqaba
|  |  | Year 1 (Jun 2026 - May 2027) | [11 empty] | Year 2 (Jun 2027 - May 2028) | [11 empty] | Year 3 (Jun 2028 - May 2029)
Output / Work Package | Activity | Sub-Activities | M1 Jun | M2 Jul | M3 Aug | M4 Sep | M5 Oct | M6 Nov | M7 Dec | M8 Jan | M9 Feb | M10 Mar | M11 Apr | M12 May | M13 Jun | M14 Jul | M15 Aug | M16 Sep | M17 Oct | M18 Nov | M19 Dec | M20 Jan | M21 Feb | M22 Mar | M23 Apr | M24 May | M25 Jun | M26 Jul | M27 Aug | M28 Sep | M29 Oct | M30 Nov | M31 Dec | M32 Jan | M33 Feb | M34 Mar | M35 Apr | M36 May
OUTPUT 1: Comprehensive oceanographic, biological, and water quality data collected and analyzed (WP1) | 1.1 Conduct oceanographic and water quality monitoring surveys | 1.1.1 Procure and deploy oceanographic monitoring equipment, including CTD profiler sensors (2 units), water quality probes, and microplastic sampling gear (1 set), to support systematic marine data collection and analysis. | bar: Year 1 (Jun 2026 - May 2027) M3 Aug to Year 1 (Jun 2026 - May 2027) M6 Nov
1.1.2 Conduct monthly field surveys over a 30-month period to generate continuous, high-quality datasets on marine water quality and microplastic presence, informing evidence-based decision-making and environmental management. | bar: Year 1 (Jun 2026 - May 2027) M7 Dec to Year 3 (Jun 2028 - May 2029) M36 May
| 1.2 Strengthen biological and plankton sampling systems | 1.2.1 Procure and deploy plankton sampling equipment, including Bongo plankton nets (1 set), to support standardized collection and analysis of plankton communities as part of marine ecosystem monitoring activities. | bar: Year 1 (Jun 2026 - May 2027) M3 Aug to Year 1 (Jun 2026 - May 2027) M6 Nov
| 1.3 Establish advanced laboratory analysis and eDNA monitoring capacity | 1.3.1 Procure and install specialized laboratory equipment (1 set) to establish and operationalize environmental DNA (eDNA) analysis capacity. | bar: Year 1 (Jun 2026 - May 2027) M3 Aug to Year 1 (Jun 2026 - May 2027) M6 Nov
1.3.2 Conduct laboratory-based analyses over a 30-month period, including DNA and eDNA assessments alongside water quality testing, to generate robust datasets supporting marine ecosystem monitoring and evidence-based management. | bar: Year 1 (Jun 2026 - May 2027) M7 Dec to Year 3 (Jun 2028 - May 2029) M36 May
| 1.4 Deliver international capacity-building and knowledge exchange programmes | 1.4.1 Exchange Training program on eDNA metabarcoding in IMR and TRSC (for 6 Jordanian scientists in Norway and Switzerland) | bar: Year 1 (Jun 2026 - May 2027) M11 Apr to Year 1 (Jun 2026 - May 2027) M12 May
OUTPUT 2: Fisheries data collection modernized and fish stock health assessed (WP2) | 2.1 Strengthen participatory fisheries data systems and digital reporting mechanisms | 2.1.1 Deploy a UN Volunteer to support community-based fisheries monitoring and data analysis over a 30-month period, strengthening participatory data collection and evidence generation. | bar: Year 1 (Jun 2026 - May 2027) M7 Dec to Year 3 (Jun 2028 - May 2029) M36 May
2.1.2 Design, develop, and operationalize a mobile application (1 system) to enable standardized, real-time fisheries data collection by fishers. | bar: Year 1 (Jun 2026 - May 2027) M7 Dec to Year 2 (Jun 2027 - May 2028) M13 Jun
2.1.3 Implement a structured fisher engagement and capacity-building programme over 24 months to promote adoption and effective use of the digital data collection application. | bar: Year 1 (Jun 2026 - May 2027) M11 Apr to Year 3 (Jun 2028 - May 2029) M30 Nov
2.1.4 Organize and deliver three stakeholder workshops with the fishing community to enhance participation, validate data collection approaches, and strengthen collaborative fisheries management. | bar: Year 1 (Jun 2026 - May 2027) M10 Mar; Year 2 (Jun 2027 - May 2028) M22 Mar; Year 3 (Jun 2028 - May 2029) M34 Mar
| 2.2 Conduct fisheries-independent BRUVS surveys | 2.2.1 Procure and operationalize Baited Remote Underwater Video Systems (BRUVS) (3 units) to support standardized, fisheries-independent monitoring of marine biodiversity and fish stocks.) | bar: Year 1 (Jun 2026 - May 2027) M2 Jul to Year 1 (Jun 2026 - May 2027) M9 Feb
2.2.2 Implement quarterly BRUVS survey deployments (10 surveys) to generate consistent, high-quality datasets on species abundance, distribution, and ecosystem health, informing evidence-based fisheries management | bar: Year 1 (Jun 2026 - May 2027) M9 Feb to Year 3 (Jun 2028 - May 2029) M33 Feb
| 2.3 Enhance biological sampling and contaminant analysis capacity | 2.3.1 Procure and install specialized equipment (1 set) for fish tissue contaminant analysis to strengthen laboratory capacity for monitoring marine pollution and food safety. | bar: Year 1 (Jun 2026 - May 2027) M2 Jul to Year 1 (Jun 2026 - May 2027) M6 Nov
2.3.2 Conduct biological sampling and contaminant analysis over a 25-month period to generate reliable data on pollutant levels in marine species, supporting evidence-based environmental management and regulatory decision-making. | bar: Year 1 (Jun 2026 - May 2027) M5 Oct to Year 3 (Jun 2028 - May 2029) M29 Oct
OUTPUT 3: Benthic habitats and Vulnerable Marine Ecosystems (VMEs) mapped and assessed (WP3) | 3.1 Conduct deep-water habitat surveys and coral health assessments | 3.1.1 Procure and operationalize a Remotely Operated Vehicle (ROV) equipped with high-definition cameras (1 unit) to support deep-water habitat exploration and monitoring. | bar: Year 1 (Jun 2026 - May 2027) M6 Nov to Year 2 (Jun 2027 - May 2028) M15 Aug
3.1.2 Procure and utilize coral health assessment tools (1 set) to enable standardized evaluation of coral reef conditions and ecosystem health. | bar: Year 1 (Jun 2026 - May 2027) M3 Aug to Year 1 (Jun 2026 - May 2027) M6 Nov
3.1.3 Conduct bi-annual ROV-based video surveys (6 surveys) to generate high-resolution data on deep-water habitats and coral health, informing conservation planning and evidence-based marine management. | bar: Year 2 (Jun 2027 - May 2028) M17 Oct; Year 2 (Jun 2027 - May 2028) M20 Jan; Year 2 (Jun 2027 - May 2028) M23 Apr; Year 3 (Jun 2028 - May 2029) M26 Jul; Year 3 (Jun 2028 - May 2029) M29 Oct; Year 3 (Jun 2028 - May 2029) M32 Jan
| 3.2 Strengthen AI-driven habitat classification and geospatial analysis capacity | 3.2.1 Procure and deploy AI-based habitat classification software (1 license) to enable automated analysis and interpretation of marine habitat data. | bar: Year 1 (Jun 2026 - May 2027) M3 Aug to Year 1 (Jun 2026 - May 2027) M7 Dec
3.2.2 Procure and operationalize GIS software and associated workstations (3 units) to strengthen geospatial data processing, analysis, and visualization capacity. | bar: Year 1 (Jun 2026 - May 2027) M3 Aug to Year 1 (Jun 2026 - May 2027) M7 Dec
3.2.3 Conduct habitat mapping and geospatial analysis to generate high-resolution spatial datasets and decision-support tools, informing marine conservation planning and ecosystem management. | bar: Year 1 (Jun 2026 - May 2027) M11 Apr to Year 3 (Jun 2028 - May 2029) M34 Mar
| 3.3 Support identification of Vulnerable Marine Ecosystems (VMEs) and conservation planning | 3.3.1 Conduct identification and assessment of Vulnerable Marine Ecosystems (VMEs) and develop evidence-based conservation and management plans to support sustainable marine resource use and ecosystem protection. | bar: Year 2 (Jun 2027 - May 2028) M15 Aug to Year 3 (Jun 2028 - May 2029) M36 May
OUTPUT 4: Data management systems established and knowledge products disseminated (WP4) | 4.1 Establish an integrated marine data management system and infrastructure | 4.1.1 Design, develop, and operationalize an integrated marine database system (1 system) to consolidate, manage, and enable access to multi-source marine data. | bar: Year 1 (Jun 2026 - May 2027) M1 Jun to Year 1 (Jun 2026 - May 2027) M8 Jan
4.1.2 Upgrade data storage infrastructure (1 service) to ensure secure, scalable, and efficient storage, processing, and retrieval of marine datasets, supporting long-term data management and decision-making. | bar: Year 1 (Jun 2026 - May 2027) M1 Jun to Year 1 (Jun 2026 - May 2027) M6 Nov
| 4.2 Develop public data access platforms and visualization tools | 4.2.1 Design, develop, and operationalize a public data portal and website (1 system) to enhance access, transparency, and dissemination of marine data to stakeholders and the wider public. | bar: Year 1 (Jun 2026 - May 2027) M6 Nov to Year 1 (Jun 2026 - May 2027) M12 May
4.2.2 Procure and deploy data visualization software licenses to support the analysis, interpretation, and user-friendly presentation of marine datasets, enabling informed decision-making and knowledge sharing. | bar: Year 1 (Jun 2026 - May 2027) M1 Jun to Year 1 (Jun 2026 - May 2027) M8 Jan
| 4.3 Produce knowledge products and support scientific research dissemination | 4.3.1 Develop and disseminate policy briefs (6 briefs) to translate scientific findings into actionable recommendations for policymakers and stakeholders. | bar: Year 2 (Jun 2027 - May 2028) M14 Jul; Year 2 (Jun 2027 - May 2028) M18 Nov; Year 2 (Jun 2027 - May 2028) M22 Mar; Year 3 (Jun 2028 - May 2029) M26 Jul; Year 3 (Jun 2028 - May 2029) M30 Nov; Year 3 (Jun 2028 - May 2029) M34 Mar
4.3.2 Support the publication of scientific research (6 publications), including coverage of publication-related costs, to enhance knowledge dissemination and visibility of project-generated evidence. | bar: Year 2 (Jun 2027 - May 2028) M15 Aug; Year 2 (Jun 2027 - May 2028) M19 Dec; Year 2 (Jun 2027 - May 2028) M23 Apr; Year 3 (Jun 2028 - May 2029) M27 Aug; Year 3 (Jun 2028 - May 2029) M31 Dec; Year 3 (Jun 2028 - May 2029) M35 Apr
| 4.4 Strengthen stakeholder engagement, awareness, and technical capacity | 4.4.1 Organize and deliver stakeholder workshops and events (8 events) to strengthen coordination, knowledge exchange, and multi-stakeholder engagement in marine resource management. | bar: Year 1 (Jun 2026 - May 2027) M6 Nov; Year 1 (Jun 2026 - May 2027) M10 Mar; Year 2 (Jun 2027 - May 2028) M14 Jul; Year 2 (Jun 2027 - May 2028) M18 Nov; Year 2 (Jun 2027 - May 2028) M22 Mar; Year 3 (Jun 2028 - May 2029) M26 Jul; Year 3 (Jun 2028 - May 2029) M30 Nov; Year 3 (Jun 2028 - May 2029) M34 Mar
4.4.2 Design and implement public awareness campaigns (2 campaigns) to promote environmental stewardship, increase awareness of marine conservation issues, and encourage behavioral change. | bar: Year 2 (Jun 2027 - May 2028) M18 Nov; Year 3 (Jun 2028 - May 2029) M30 Nov
OUTPUT 5: Marine pollution early warning system piloted and institutional response capacity strengthened (WP5) | 5.1 Establish and operationalize a real-time pollution monitoring and early warning system | 5.1.1 Deploy a UN Volunteer Specialist on pollution monitoring and early warning over a 30-month period to coordinate system implementation, data management, and institutional integration. | bar: Year 1 (Jun 2026 - May 2027) M4 Sep to Year 3 (Jun 2028 - May 2029) M33 Feb
5.1.2 Procure, install, and operationalize real-time pollution monitoring infrastructure, including water quality, oil, and nutrient sensors (3 units), along with a data telemetry and communication system (1 system) to enable continuous data transmission and automated alerts | bar: Year 1 (Jun 2026 - May 2027) M1 Jun to Year 1 (Jun 2026 - May 2027) M7 Dec
5.1.3 Implement sensor deployment, calibration, and routine maintenance to ensure accuracy, reliability, and sustained functionality of the monitoring system | bar: Year 1 (Jun 2026 - May 2027) M4 Sep to Year 1 (Jun 2026 - May 2027) M9 Feb; Year 2 (Jun 2027 - May 2028) M20 Jan; Year 3 (Jun 2028 - May 2029) M33 Feb
| 5.2 Strengthen GIS-based pollution risk mapping and spatial analysis capacity | 5.2.1 Procure and deploy GIS-based pollution risk mapping software (1 license) to enable advanced spatial analysis and modeling of environmental risks. | bar: Year 1 (Jun 2026 - May 2027) M6 Nov to Year 2 (Jun 2027 - May 2028) M14 Jul
5.2.2 Conduct pollution risk mapping and geospatial analysis over a three-year period to generate dynamic risk profiles and decision-support tools, informing pollution prevention, preparedness, and response measures. | bar: Year 1 (Jun 2026 - May 2027) M8 Jan to Year 3 (Jun 2028 - May 2029) M36 May
| 5.3 Enhance institutional readiness and emergency response capacity | 5.3.1 Procure and deploy pollution response equipment and field kits (1 set) to strengthen operational capacity for rapid environmental emergency response. | bar: Year 1 (Jun 2026 - May 2027) M1 Jun to Year 1 (Jun 2026 - May 2027) M6 Nov
5.3.2 Develop and institutionalize Standard Operating Procedures (SOPs) for pollution detection and response, and deliver targeted institutional capacity-building through six training workshops. | bar: Year 1 (Jun 2026 - May 2027) M11 Apr; Year 2 (Jun 2027 - May 2028) M14 Jul; Year 2 (Jun 2027 - May 2028) M17 Oct; Year 2 (Jun 2027 - May 2028) M20 Jan; Year 2 (Jun 2027 - May 2028) M23 Apr; Year 3 (Jun 2028 - May 2029) M26 Jul
5.3.3 Design and conduct emergency response simulation exercises with ASEZA (3 drills) to test operational readiness, validate SOPs, and strengthen inter-agency coordination. | bar: Year 2 (Jun 2027 - May 2028) M18 Nov; Year 2 (Jun 2027 - May 2028) M24 May; Year 3 (Jun 2028 - May 2029) M33 Feb
| 5.4 Promote regional scaling and international capacity development | 5.4.1 Develop a scaling roadmap and sustainability plan (1 deliverable) to guide replication, long-term financing, and institutionalization of the pollution monitoring and early warning system. | bar: Year 3 (Jun 2028 - May 2029) M27 Aug to Year 3 (Jun 2028 - May 2029) M36 May
5.4.2 Capacity building program on Norway experience in Marine pollution early warning in IMR Bergen | bar: Year 2 (Jun 2027 - May 2028) M23 Apr to Year 3 (Jun 2028 - May 2029) M26 Jul
5.4.3 Project Closing Conference and Regional Stakeholder Engagement Event | bar: Year 3 (Jun 2028 - May 2029) M35 Apr to Year 3 (Jun 2028 - May 2029) M36 May
PROJECT MANAGEMENT & COORDINATION | Project Manager / NPSA 8 (36 months)
Operations Associate / NPSA 7 - Part Time 18% (36 months)
| Monitoring & Evaluation activities | HACT | bar: Year 1 (Jun 2026 - May 2027) M1 Jun to Year 1 (Jun 2026 - May 2027) M9 Feb
Final Evaluation | bar: Year 3 (Jun 2028 - May 2029) M32 Jan to Year 3 (Jun 2028 - May 2029) M36 May