## BUR Umbrella_FT (hidden)
Umbrella SB-001119 BUR Umbrella
| Objective | Outcome | Output | Activity
Root- Objective | SB-001119 Umbrella Programme for Biennial Update Report to the United National Framework Convention on Climate Change (UNFCCC)
Outcome 1 | SB-001119.01 SB-001119.02 SB-001119.n SB-001119.39 | To support thirty nine (39) Least Developed Countries (LDCs) and Small Islands Developing States (SIDS) prepare and submit good quality initial biennial update reports to the UNFCCC that comply with the convention's reporting obligation
Output 1.1 |  |  | 1.1 Enhanced national ownership and coordination of BUR and NCs preparation processes at the country level
| Activity 1.1.1 |  |  | 1.1.1 National stakeholders involvement and institutional roles and responsibilites in the BUR preparation clearly defined and outlined
Output 1.2 |  |  | 1.2 BUR PIPs are responsive to national development planning processes
| Activity 1.2.1 |  |  | 1.2.1 Thirty nine (39) BUR PIPs which include strategies aimed at enhancing integration of climate change mitigation issues into national development planning frameworks submitted to UNEP for approval
Output 2.1 |  |  | 2.1 Good quality BURs that meet the UNFCCC's reporting obligations and national development planning process requirements are prepared by LDCs and SIDS and submitted to the UNFCCC
| Activity 2.1.1 |  |  | 2.1.1 Thirty nine (39) BURs that meet the development planning needs of LDCs and SIDS and convention reporting requirement published and submitted to the UNFCCC
Output 3.1 |  |  | 3.1 BUR projects are effectively implemented, monitored and evaluated.
| Activity 3.1.1 |  |  | 3.1.1 Project inception workshop held
| Activity 3.1.2 |  |  | 3.1.2 Project financial and technical progress reports prepared and submitted promptly to UNEP
| Activity 3.1.3 |  |  | 3.1.3 Project is evaluated upon successful execution
Outcome 4 | SB-001119.40 |  | Project Management Cost (PMC)

## BUR Umbrella_AT (hidden)
Umbrella SB-001119 BUR Umbrella
|  | Objective | Outcome | Output
Root- Objective | SB-001119 | To support thirty nine (39) Least Developed Countries (LDCs) and Small Islands Developing States (SIDS) prepare and submit good quality initial biennial update reports to the UNFCCC that comply with the convention's reporting obligation
Outcome 1 |  | SB-001119.01 | 1.1 Enhanced national ownership and coordination of BUR and NCs preparation processes at the country level
|  |  | SB-001119.01.01 | 1.1.1 National stakeholders involvement and institutional roles and responsibilites in the BUR preparation clearly defined and outlined
Outcome 2 |  | SB-001119.02 | 1.2 BUR PIPs are responsive to national development planning processes
|  |  | SB-001119.02.01 SB-001119.02.02 SB-001119.02.n SB-001119.02.39 | Country 1 1.2.1 Thirty nine (39) BUR PIPs which include strategies aimed at enhancing integration of climate change mitigation issues into national development planning frameworks submitted to UNEP for approval Country 2 1.2.1 Thirty nine (39) BUR PIPs which include strategies aimed at enhancing integration of climate change mitigation issues into national development planning frameworks submitted to UNEP for approval Country n 1.2.1 Thirty nine (39) BUR PIPs which include strategies aimed at enhancing integration of climate change mitigation issues into national development planning frameworks submitted to UNEP for approval Country 39 1.2.1 Thirty nine (39) BUR PIPs which include strategies aimed at enhancing integration of climate change mitigation issues into national development planning frameworks submitted to UNEP for approval
Outcome 3 |  | SB-001119.03 | 2.1 Good quality BURs that meet the UNFCCC's reporting obligations and national development planning process requirements are prepared by LDCs and SIDS and submitted to the UNFCCC
|  |  | SB-001119.03.01 SB-001119.03.02 SB-001119.03.n SB-001119.03.39 | Country 1 2.1.1 Thirty nine (39) BURs that meet the development planning needs of LDCs and SIDS and convention reporting requirement published and submitted to the UNFCCC Country 2 2.1.1 Thirty nine (39) BURs that meet the development planning needs of LDCs and SIDS and convention reporting requirement published and submitted to the UNFCCC Country n 2.1.1 Thirty nine (39) BURs that meet the development planning needs of LDCs and SIDS and convention reporting requirement published and submitted to the UNFCCC Country 39 2.1.1 Thirty nine (39) BURs that meet the development planning needs of LDCs and SIDS and convention reporting requirement published and submitted to the UNFCCC
Outcome 4 |  | SB-001119.04 | 3.1 BUR projects are effectively implemented, monitored and evaluated.
|  |  | SB-001119.04.01 | 3.1.1 Project inception workshop held 3.1.2 Project financial and technical progress reports prepared and submitted promptly to UNEP 3.1.3 Project is evaluated upon successful execution
Outcome 5 |  | SB-001119.05 | Project Management Cost (PMC) - Execution Support

## BUR Umbrella_Hybrid (hidden)
Umbrella SB-001119 BUR Umbrella
|  | Objective | Outcome | Output
Root- Objective | SB-001119 | To support thirty nine (39) Least Developed Countries (LDCs) and Small Islands Developing States (SIDS) prepare and submit good quality initial biennial update reports to the UNFCCC that comply with the convention's reporting obligation
Outcome 1 |  |  | 1.1 Enhanced national ownership and coordination of BUR and NCs preparation processes at the country level
39 Countries 1.1.1 National stakeholders involvement and institutional roles and responsibilites in the BUR preparation clearly defined and outlined
Outcome 2 |  |  | 1.2 BUR PIPs are responsive to national development planning processes
39 Countries 1.2.1 Thirty nine (39) BUR PIPs which include strategies aimed at enhancing integration of climate change mitigation issues into national development planning frameworks submitted to UNEP for approval
Outcome 3 |  | SB-001119.01 SB-001119.02 SB-001119.n SB-001119.39 | 2.1 Good quality BURs that meet the UNFCCC's reporting obligations and national development planning process requirements are prepared by LDCs and SIDS and submitted to the UNFCCC
39 Countries 2.1.1 Thirty nine (39) BURs that meet the development planning needs of LDCs and SIDS and convention reporting requirement published and submitted to the UNFCCC
Outcome 4 |  |  | 3.1 BUR projects are effectively implemented, monitored and evaluated.
39 Countries 3.1.1 Project inception workshop held 3.1.2 Project financial and technical progress reports prepared and submitted promptly to UNEP 3.1.3 Project is evaluated upon successful execution
Outcome 5 |  |  | Project Management Cost (PMC) - Execution Support

## IPMR_ Structure_EA (hidden)
Umbrella SB-01473 BTRNC
Root | SB-01473 | Climate Change Mitigation EA Projects- Umbrella Name
Outcome 1 | SB-01473.01 | Country X Prepares a BTR/NC
Output 1.1 | SB-01473.01.01 | PIP Preparation
Output 1.2 | SB-01473.01.02 | BTR/NC Preparation
Output 1.3 | SB-01473.01.03 | Stocktaking
Outcome 2 | SB-01473.02 | Country Y Prepares a BTR/NC
Output 2.1 | SB-01473.02.01 | PIP Preparation
Output 2.2 | SB-01473.02.02 | BTR/NC Preparation
Output 2.3 | SB-01473.02.03 | Stocktaking
Stand-Alone SB-01473 BTRNC
Root | SB-01473 | Climate Change Mitigation EA Projects- Stand Alone
Outcome 1 | SB-01473.01 | Country X Prepares a BTR/NC
Output 1.1 | SB-01473.01.01 | PIP Preparation (if needed)
Output 1.2 | SB-01473.01.02 | BTR/NC Preparation
Output 1.3 | SB-01473.01.03 | Stocktaking

## Class Explanation (hidden)
UMOJA Commitment Class Explanation with matching IMIS object codes
No. | Commitment Class Name | Umoja Budget Class NEW | IMIS Object codes OLD | Explanation
1 | Staff and Other Personnel Costs | Class_010 | 1100/1200/1300/5500 | (i) All staff/ Admim and consultants costs, but excluding related e.g. travel (ii) Meeting facilitators, interpreters, Evaluation consultants all to be budgeted under this Class.
2 | Contractual Services | Class_120 | 2300, 3200, 3300 | (i) Works and services of a commercial nature contracted following procurement procedures. This could include contracts given to NGOs if they are more similar to procurement of services than a grant transfer. (ii) Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. (iii) Commercial printing/publication contracts to be budgeted here
3 | Operating and Other Direct Costs | Class_125 | 4300, 5100, 5300 | Communications, IT, maintenance, rental of premises and equipment, vehicle expenses, utilities, bank charges etc.
4 | Supplies Commodities and Materials | Class_130 | 4100 | (i) Consumable supplies e.g. office stationary/supplies etc.; (ii) Costs associated with the delivery, storage and distribution of consumable supplies procured such as transportation, freight, customs, insurance, warehousing and other logistical requirements;
5 | Equipment Vehicles and Furniture | Class_135 | 4200 | (i) Procurement of non-consumables e.g. IT equipment, vehicles, furniture etc. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. For those who do donor reports according to IPSAS this would equal depreciation for period.
6 | Transfers and Grants Issued to Implementing Partner (IP) | Class_140 |  | Transfers and Grants Issued to Implementing Partner (IP): Amounts expended through agreements with sub-partners which require periodical reporting to account for amounts advanced These are funds to be released to IP. When raising PO, the below noted 8 categories are budgeted for which follow the above noted Commitment Class and hence guidance. There were no matching IMIS object codes until late 2014 when advised to use xx61 codes. IP PO breakdown: (i) Staff and personnel (ii) Travel (iii) Contractual Services (iv) Vehicle & Furniture (v) Grants out (vi) General operating costs (vii) Supplies & commodities (viii) IP PSC
7 | Grants Out | Class_145 | 2100 and 2200 | (i) Grants to End Beneficiaries (EB) which are expensed upon payment. Per current guidance threshold is $30,000 (ii) Matching IMIS object codes could be 2100 and 2200
8 | UN-PSC | Class_150 | 9400 | Programme Support Costs.
9 | Travel | Class_160 | 1600 and travel component of 1200/5500/3300/3200/3100 | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel

## Budget and Workplan Instruction (hidden)
For the EA Preparation Team
1 | For each project component, refer to the section of the EA proposal with the checkboxes indicating staff and contracts to be used. Some suggestions have been provided for you.
2 | Complete the budget lines for that component in the "Budget_Template" worksheet in this file. Please only fill in the white cells -- the gray and green cells will automatically be completed.
3 | The budget items will be numbered sequentially across the components (e.g. 1201 and 1202 in component 1 and then 1203 and 1204 in component 2.
4 | If the national technical coordinator will cover project management and project activities, the same number for this person will be used throughout the document.
5 | The component totals for project activities are indicative, which means that your totals may vary depending on national priorities, needs identified, and reporting activities supported by other donor-funded projects. For the project management component, the funding is CAPPED and may not exceed $112,090.
6 | You may not need each budget class for each component. If there are no charges, you may delete the budget class.
7 | You may add or edit budget items. However, please check to make sure that the formulas in the worksheet cover the changes.
8 | If you are hiring an international consultant, his/her salary is covered under 010, while travel to/from country is covered under 160.
9 | In most cases, travel and DSA paid to workshop participants is included under 160, while the workshops themselves are itemized under 120.
10 | GEF does not allow for the lease or purchase of vehicles for EA projects.
11 | After completing the budget, please check the Terms of Reference in your EA proposal. There should be ToRs for all positions listed in the budget.
12 | Please be specific when listing equipment under 135, such as "1 laptop for the National Project Coordinator," "LEAP software license for mitigation scenarios," etc.
13 | Travel to the COP is supported for one person for participation in the facilitative multicountry sharing of progress (FMSP), following the submission of each report. Therefore, there should be a maximum of two trips to the COp supported by the budget.
14 | For the workplan, please make sure that the start and completation activities match the dates given in the EA proposal.

## Budget_Final
Annex 1: Budget in UNEP Format
Project title: Turkmenistan's BTR2 + BTR3/NC5
Project executing partner: UNDP Turkmenistan
Project implementation period: 56 Months
From: | 2026-03-31
To: | 2030-10-31
|  |  |  | Year 1 (2026) | Year 2 (2027) | Year 3 (2028) | Year 4 (2029) | Year 5(2030) | Total
Budget Codes | Umoja Classes | Description of Eligible Expense | Indicative Budget
Output 1
National inventory report (NIR) |  |  | 510000 | 132414.5 | 125385 | 126815 | 125385 | 0 | 509999.5
010 | Staff & Personnel | (i) Includes all costs and entitlements of staff and consultants- supporting GHG and NIR |  | 111799.5 | 106800 | 111800 | 106800 | 0 | 437199.5
0101 | National Technical Advisor | Support for activities under Component 1 as per Terms of Reference. | 104070 | 26017.5 | 26018 | 26018 | 26016 |  | 104069.5
0102 | International Consultant | IC / GHG inventory expert | 10000 | 5000 |  | 5000 |  |  | 10000
0103 | National Experts | Inventory experts | 323130 | 80782 | 80782 | 80782 | 80784 |  | 323130
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 12215 | 12215 | 12215 | 12215 | 0 | 48860
1201 | Contract Services--research and analysis | Contracts, agreements, Memorandum of Understanding with institutions for data collection, sectoral inventory | 32000 | 8000 | 8000 | 8000 | 8000 |  | 32000
1202 | Contract Services--venues and catering | 1. Training on IPCC methodologies; 2.Training on the GHG inventory; 3. NIR review and validation; 4. Develop written guidelines on data collection and GHG calculations. | 16860 | 4215 | 4215 | 4215 | 4215 |  | 16860
135 | Equipment, Vehicles & Furniture |  |  | 5900 | 300 | 300 | 300 | 0 | 6800
1351 | Equipment | laptop 3-$3600, monitors 3-$1500 incl accessories,printer 1-$500, consumables $300 per year | 6800 | 5900 | 300 | 300 | 300 |  | 6800
160 | Travel |  |  | 2500 | 6070 | 2500 | 6070 | 0 | 17140
1601 | International Travel and DSA | 2 experts:DSA $314 p/d, 5 days each and air ticket $2000 per person | 7140 |  | 3570 | 0 | 3570 |  | 7140
1602 | Travel and DSA for workshop participants. | Travel and DSA for workshop participants for workshops under 1202 | 10000 | 2500 | 2500 | 2500 | 2500 |  | 10000
Information necessary to track progress made in implementing and achieving nationally determined contributions under Article 4 of the Paris Agreement |  |  | 250910 | 0 | 86399 | 81500 | 83011 | 0 | 250910
010 | Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting NDC |  | 0 | 63069 | 58070 | 63071 | 0 | 184210
0101 | National Technical Advisor | Support for activities under Component 2 as per Terms of Reference. | 12605 |  | 4201 | 4202 | 4202 |  | 12605
0104 | International Consultant (if used) | IC / Mitigation Expert | 10000 |  | 5000 |  | 5000 |  | 10000
0105 | National Experts | NC / Mitigation Experts | 161605 |  | 53868 | 53868 | 53869 |  | 161605
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 0 | 16930 | 16930 | 16940 | 0 | 50800
1203 | Contract -- Mitigation Analysis | Contract,agreement, MOA for mitigation analysis | 28300 |  | 9430 | 9430 | 9440 |  | 28300
1204 | Workshops -- Venue and Catering | Workshops on topics that may include NDC scenarios, NDC targets and indicators, reporting in the Common Tabular Format, linkages between NDC update and BTR reporting, etc.). | 22500 |  | 7500 | 7500 | 7500 |  | 22500
135 | Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. |  | 0 | 3400 | 0 | 0 | 0 | 3400
1352 | Equipment/Computer and Software for projections/scenarios | 2 Laptops and 2 monitors | 3400 |  | 3400 |  |  |  | 3400
160 | Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel |  | 0 | 3000 | 6500 | 3000 | 0 | 12500
1603 | International Travel and DSA | Travel of International Consultant to in-country trainings and meetings and/or travel of national experts to regional trainings. | 3500 |  |  | 3500 |  |  | 3500
1604 | In-Country Travel and DSA | Travel and DSA for workshop participants for workshops under 1204 | 9000 |  | 3000 | 3000 | 3000 |  | 9000
Information related to climate change impacts and adaptation under Article 7 of the Paris Agreement |  |  | 200000 | 55050 | 46650 | 51650 | 46650 | 0 | 200000
010 | Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting climate change impacts & Adaptation |  | 39150 | 34150 | 39150 | 34150 | 0 | 146600
0101 | National Technical Advisor | Support for activities under Component 3 as per Terms of Reference. | 10070 | 2517 | 2517 | 2517 | 2517 |  | 10068
0106 | International Consultant (if used) | IC / adaptation expert and/or loss and damage expert. | 10000 | 5000 |  | 5000 |  |  | 10000
0107 | National Experts | NC / Adaptation and Loss and Damage Experts | 126532 | 31633 | 31633 | 31633 | 31633 |  | 126532
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 5000 | 10000 | 5000 | 10000 | 0 | 30000
1205 | Contract -- Impact assessment and Vulnerability Analysis | Contract for impact assessment and vulnerability analysis | 10000 |  | 5000 |  | 5000 |  | 10000
1206 | Workshops -- Venue and Catering | Capacity building for climate scenarios, modelling, projections, and data analysis to enhance the country's capacity to conduct vulnerability/adaptation and loss and damage assessments to strengthen climate change adaptation planning. A validation workshop with the relevant thematic working group and stakeholders to review and approve the Climate Change impacts and adaptation report. | 20000 | 5000 | 5000 | 5000 | 5000 |  | 20000
135 | Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. |  | 3400 | 0 | 0 | 0 | 0 | 3400
1353 | Equipment/PC and software license | Example -- software license or laptop (for Year 1) | 3400 | 3400 |  |  |  |  | 3400
160 | Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel |  | 7500 | 2500 | 7500 | 2500 | 0 | 20000
1605 | International Travel and DSA | Travel of International Consultant to in-country trainings and meetings and/or travel of national experts to regional trainings. | 10000 | 5000 |  | 5000 |  |  | 10000
1606 | In-Country Travel and DSA | Travel and DSA for workshop participants for workshops under 1206 | 10000 | 2500 | 2500 | 2500 | 2500 |  | 10000
Information on financial, technology development and transfer and capacity-building support needed and received under Articles 9–11 of the Paris Agreement |  |  | 40000 | 8000 | 14500 | 8000 | 9500 | 0 | 40000
010 | Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting information on financial, technology etc & Other Relevant Information |  | 8000 | 13000 | 8000 | 8000 | 0 | 37000
0101 | National Technical Advisor | Support for activities under Component 4 as per Terms of Reference. | 2000 | 500 | 500 | 500 | 500 |  | 2000
0108 | International Consultant (if used) | IC / expert on reporting on support needed and received | 5000 |  | 5000 |  |  |  | 5000
0109 | National Experts | NC / support needed and received specialists | 30000 | 7500 | 7500 | 7500 | 7500 |  | 30000
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 0 | 1500 | 0 | 1500 | 0 | 3000
1207 | Workshops -- Venue and Catering | 2 workshops/trainings on reporting on support needed and received in the Common Tabular Format, reporting on capacity support needed, reporting on technology transfer, | 3000 |  | 1500 |  | 1500 |  | 3000
Reporting on Other relevant information for the BTR1 and supplemental NC chapters for the BTR1 and BTR2/NC Report |  |  | 45000 | 562.5 | 3062.5 | 19437.5 | 21937.5 | 0 | 45000
010 | Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting reporting on Other Relevant Information |  | 562.5 | 562.5 | 19437.5 | 19437.5 | 0 | 40000
0101 | National Technical Advisor | Support for activities under Component 5 as per Terms of Reference. | 2250 | 562.5 | 562.5 | 562.5 | 562.5 |  | 2250
01011 | National Consultants -- Supplemental NC Chapters | NC / specialists ffor Other Relevant Information and supplemental chapters (systematic observation, research, public awareness, outreach, and education) | 37750 |  | 0 | 18875 | 18875 |  | 37750
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 0 | 2500 | 0 | 2500 | 0 | 5000
1208 | Workshops -- Venue and Catering | Two workshops @ USD 2500, which may include workshop on climate change and gender; and 1 workshop on supplemental NC chapters. | 5000 |  | 2500 |  | 2500 |  | 5000
Stakeholder engagement events, publication and submission of report |  |  | 55000 | 25687.5 | 9187.5 | 18937.5 | 5187.5 | 0 | 59000
010 | Staff & Personnel (Including Consultants) |  |  | 3687.5 | 687.5 | 2687.5 | 687.5 | 0 | 7750
0101 | National Technical Advisor | Support for activities under Component 6 as per Terms of Reference. | 2750 | 687.5 | 687.5 | 687.5 | 687.5 |  | 2750
01012 | Meeting consultants | Meeting facilitators, interpreters for the Inception workshop 2026, first validation workshop 2026 and second validation workshop 2028 (two workshops in 2026, one in 2028) | 5000 | 3000 |  | 2000 | 0 |  | 5000
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Commercial printing/publication contracts to be budgeted here -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 17000 | 4000 | 13500 | 0 | 0 | 34500
1209 | Workshops -- Venue and Catering | Four workshops: One Inception Workshop, one mid-term lessons learned workshop, and two Final Validation Workshops (one for each report). | 10500 | 7000 | 4000 | 3500 |  |  | 14500
12010 | Contract Services/translation costs | Translation of BTR2, BTR3/NC5 from Russian into Turkmen and English | 10000 | 5000 |  | 5000 |  |  | 10000
12011 | Publication Costs | Publication cost of the two final reports (BTR2 and BTR3/NC5) | 10000 | 5000 |  | 5000 |  |  | 10000
160 | Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel |  | 5000 | 4500 | 2750 | 4500 | 0 | 16750
16010 | Travel and DSA | Travel for one person for participation in the FMSP at the COP following the submission of each report. (2 trips -- one per report for max. $5000 / trip) | 9000 |  | 4500 |  | 4500 |  | 9000
16011 | Travel and DSA for workshop participants. | Travel and DSA for workshop participants for workshops under 1209 | 7750 | 5000 |  | 2750 |  |  | 7750
Self-Assessment and Stocktaking Exercise for Subsequent EA Activities |  |  | 20000 | 0 | 0 | 0 | 16000 | 0 | 16000
010 | Staff & Personnel (Including Consultants) | Meeting facilitators, interpreters, |  | 0 | 0 | 0 | 12000 | 0 | 12000
01013 | 010-Staff & Personnel (Including Consultants) | Consultant for stocktaking exercise for preparation of project proposal for subsequent reports (or "Support by Project Technical Coordinator for stocktaking exercise for preparation of project proposal for subsequent report(s)) -- use 0101 if using the PTC. | 12000 |  |  |  | 12000 |  | 12000
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Commercial printing/publication contracts to be budgeted here -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 0 | 0 | 0 | 4000 | 0 | 4000
12012 | Workshops -- Venue and Catering | One final workshop and/or stakeholder consultation for subsequent reporting (optional -- consultations could be included under the budget for the consultant for the stocktaking) | 4000 |  |  |  | 4000 |  | 4000
Project Management Cost (PMC) |  |  | 112090 | 24227.5987 | 28110.4637 | 29829.3837 | 29922.5537 | 0 | 112090 | 0
010 | Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff e.g. Project coordinator, Admin/Finance Assistant. |  | 6606.5 | 6606.5 | 6606.5 | 6606.5 | 0 | 26426
01014 | Project Manager | Project Manager | 6200 | 1550 | 1550 | 1550 | 1550 |  | 6200
01015 | Project Assistant | Project Assistant | 6200 | 1550 | 1550 | 1550 | 1550 |  | 6200
01016 | Administrative and Financial Assistant | Services to project, Facilities & administration & other operating costs:- UNDP support costs, determined in accordance with its cost recovery policy (Clause C of the UN2UN agreeement between UNDP and UNEP). | 40090 | 3506.5 | 3506.5 | 3506.5 | 3506.5 |  | 14026
125 | Operating & Other Costs | Includes: Rental of premises/equipment; utilities; bank charges |  | 1250 | 1250 | 1250 | 1250 | 0 | 5000
12501 | Bank charges | Bank charges | 5000 | 1250 | 1250 | 1250 | 1250 |  | 5000
| UNDP GMS | UNDP GMS fee (7% of total net costs) | 86309.965 | 16371.0987 | 20253.9637 | 21972.8837 | 22066.0537 | 0 | 80664
010 | Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff e.g. Project coordinator, Admin/Finance Assistant. |  | 11886.5487 | 15741.4137 | 17202.7337 | 17552.8037 | 0 | 62383.5
01014 | Project Manager | Project Manager |  | 5349.9854 | 7277.4179 | 8008.0779 | 8183.1129 |  | 28818.5942
01015 | Project Assistant | Project Assistant |  | 5349.9854 | 7277.4179 | 8008.0779 | 8183.1129 |  | 28818.5942
01016 | Administrative and Financial Assistant | Services to project, Facilities & administration & other operating costs:- UNDP support costs, determined in accordance with its cost recovery policy (Clause C of the UN2UN agreeement between UNDP and UNEP). |  | 1186.5779 | 1186.5779 | 1186.5779 | 1186.5779 |  | 4746.3117
125 | Operating & Other Costs | Includes: Rental of premises/equipment; utilities; bank charges |  | 1285.025 | 1737.575 | 1755.075 | 1737.925 | 0 | 6515.6
12502 | Communications and internet access costs | Communications and internet access costs |  | 1285.025 | 1737.575 | 1755.075 | 1737.925 |  | 6515.6
130 | Supplies Commodities and Materials | Includes Consumable supplies e.g. office stationary/supplies etc. |  | 1197.525 | 1650.075 | 1667.575 | 1650.425 | 0 | 6165.6
1301 | Office stationary/supplies costs | Office stationary/supplies costs |  | 1197.525 | 1650.075 | 1667.575 | 1650.425 |  | 6165.6
135 | Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. |  | 952 | 0 | 0 | 0 | 0 | 952
1353 | One PC for the project management team | One PC for the project management team |  | 952 | 0 | 0 | 0 |  | 952
160 | Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel |  | 1050 | 1124.9 | 1347.5 | 1124.9 | 0 | 4647.3
1607 | Travel expenses | Travel expenses for the project management team |  | 1050 | 1124.9 | 1347.5 | 1124.9 |  | 4647.3
| TOTAL |  | 1233000 | 245942.0988 | 313294.4637 | 336169.3837 | 337593.5538 | 0 | 1232999.5

## Budget_Template (hidden)
Annex 1: Budget in UNEP Format
Project title: Turkmenistan's BTR2 + BTR3/NC5
Project executing partner: UNDP
Project implementation period: 48 Months
From: | 2026-03-31
To: | 2030-03-01
|  |  |  | Year 1 (2026) | Year 2 (2027) | Year 3 (2028) | Year 4 (2029) | Year 5(2030) | Total
Budget Codes | Umoja Classes | Description of Eligible Expense | Indicative Budget
Output 1
National inventory report (NIR) |  |  | 510000 | 132414.5 | 125385 | 126815 | 125385 | 0 | 509999.5
010 | Staff & Personnel | (i) Includes all costs and entitlements of staff and consultants- supporting GHG and NIR |  | 111799.5 | 106800 | 111800 | 106800 | 0 | 437199.5
0101 | Project Team Leader | Support for activities under Component 1 as per Terms of Reference. | 104070 | 26017.5 | 26018 | 26018 | 26016 |  | 104069.5
0102 | International Consultant | IC / GHG inventory expert | 10000 | 5000 |  | 5000 |  |  | 10000
0103 | National Experts | Inventory experts | 323130 | 80782 | 80782 | 80782 | 80784 |  | 323130
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 12215 | 12215 | 12215 | 12215 | 0 | 48860
1201 | Contract Services--research and analysis | Contracts, agreements, Memorandum of Understanding with institutions for data collection, sectoral inventory | 32000 | 8000 | 8000 | 8000 | 8000 |  | 32000
1202 | Contract Services--venues and catering | 1. Training on IPCC methodologies; 2.Training on the GHG inventory; 3. NIR review and validation; 4. Develop written guidelines on data collection and GHG calculations. | 16860 | 4215 | 4215 | 4215 | 4215 |  | 16860
135 | Equipment, Vehicles & Furniture |  |  | 5900 | 300 | 300 | 300 | 0 | 6800
1351 | Equipment | laptop 3-$3600, monitors 3-$1500 incl accessories,printer 1-$500, consumables $300 per year | 6800 | 5900 | 300 | 300 | 300 |  | 6800
160 | Travel |  |  | 2500 | 6070 | 2500 | 6070 | 0 | 17140
1601 | International Travel and DSA | 2 experts:DSA $314 p/d, 5 days each and air ticket $2000 per person | 7140 |  | 3570 | 0 | 3570 |  | 7140
1602 | Travel and DSA for workshop participants. | [Example] Travel and DSA for workshop participants for workshops under 1202 | 10000 | 2500 | 2500 | 2500 | 2500 |  | 10000
Information necessary to track progress made in implementing and achieving nationally determined contributions under Article 4 of the Paris Agreement |  |  | 250910 | 0 | 86399 | 81500 | 83011 | 0 | 250910
010 | Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting NDC |  | 0 | 63069 | 58070 | 63071 | 0 | 184210
0101 | Project Team Leader | Support for activities under Component 2 as per Terms of Reference. | 12605 |  | 4201 | 4202 | 4202 |  | 12605
0104 | International Consultant (if used) | IC / Mitigation Expert | 10000 |  | 5000 |  | 5000 |  | 10000
0105 | National Experts | NC / Mitigation Experts | 161605 |  | 53868 | 53868 | 53869 |  | 161605
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 0 | 16930 | 16930 | 16940 | 0 | 50800
1203 | Contract -- Mitigation Analysis | Contract,agreement, MOA for mitigation analysis | 28300 |  | 9430 | 9430 | 9440 |  | 28300
1204 | Workshops -- Venue and Catering | Workshops on topics that may include NDC scenarios, NDC targets and indicators, reporting in the Common Tabular Format, linkages between NDC update and BTR reporting, etc.). | 22500 |  | 7500 | 7500 | 7500 |  | 22500
135 | Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. |  | 0 | 3400 | 0 | 0 | 0 | 3400
1352 | Equipment/Computer and Software for projections/scenarios | 2 Laptops and 2 monitors | 3400 |  | 3400 |  |  |  | 3400
160 | Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel |  | 0 | 3000 | 6500 | 3000 | 0 | 12500
1603 | International Travel and DSA | Travel of International Consultant to in-country trainings and meetings and/or travel of national experts to regional trainings. | 3500 |  |  | 3500 |  |  | 3500
1604 | In-Country Travel and DSA | Travel and DSA for workshop participants for workshops under 1204 | 9000 |  | 3000 | 3000 | 3000 |  | 9000
Information related to climate change impacts and adaptation under Article 7 of the Paris Agreement |  |  | 200000 | 55050 | 46650 | 51650 | 46650 | 0 | 200000
010 | Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting climate change impacts & Adaptation |  | 39150 | 34150 | 39150 | 34150 | 0 | 146600
0101 | Project Team Leader | Support for activities under Component 3 as per Terms of Reference. | 10070 | 2517 | 2517 | 2517 | 2517 |  | 10068
0106 | International Consultant (if used) | IC / adaptation expert and/or loss and damage expert. | 10000 | 5000 |  | 5000 |  |  | 10000
0107 | National Experts | NC / Adaptation and Loss and Damage Experts | 126532 | 31633 | 31633 | 31633 | 31633 |  | 126532
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 5000 | 10000 | 5000 | 10000 | 0 | 30000
1205 | Contract -- Impact assessment and Vulnerability Analysis | Contract for impact assessment and vulnerability analysis | 10000 |  | 5000 |  | 5000 |  | 10000
1206 | Workshops -- Venue and Catering | Capacity building for climate scenarios, modelling, projections, and data analysis to enhance the country's capacity to conduct vulnerability/adaptation and loss and damage assessments to strengthen climate change adaptation planning. A validation workshop with the relevant thematic working group and stakeholders to review and approve the Climate Change impacts and adaptation report. | 20000 | 5000 | 5000 | 5000 | 5000 |  | 20000
135 | Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. |  | 3400 | 0 | 0 | 0 | 0 | 3400
1353 | Equipment/PC and software license | Example -- software license or laptop (for Year 1) | 3400 | 3400 |  |  |  |  | 3400
160 | Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel |  | 7500 | 2500 | 7500 | 2500 | 0 | 20000
1605 | International Travel and DSA | Travel of International Consultant to in-country trainings and meetings and/or travel of national experts to regional trainings. | 10000 | 5000 |  | 5000 |  |  | 10000
1606 | In-Country Travel and DSA | Travel and DSA for workshop participants for workshops under 1206 | 10000 | 2500 | 2500 | 2500 | 2500 |  | 10000
Information on financial, technology development and transfer and capacity-building support needed and received under Articles 9–11 of the Paris Agreement |  |  | 40000 | 8000 | 14500 | 8000 | 9500 | 0 | 40000
010 | Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting information on financial, technology etc & Other Relevant Information |  | 8000 | 13000 | 8000 | 8000 | 0 | 37000
0101 | Project Team Leader | Support for activities under Component 4 as per Terms of Reference. | 2000 | 500 | 500 | 500 | 500 |  | 2000
0108 | International Consultant (if used) | IC / expert on reporting on support needed and received | 5000 |  | 5000 |  |  |  | 5000
0109 | National Experts | NC / support needed and received specialists | 30000 | 7500 | 7500 | 7500 | 7500 |  | 30000
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 0 | 1500 | 0 | 1500 | 0 | 3000
1207 | Workshops -- Venue and Catering | 2 workshops/trainings on reporting on support needed and received in the Common Tabular Format, reporting on capacity support needed, reporting on technology transfer, | 3000 |  | 1500 |  | 1500 |  | 3000
Reporting on Other relevant information for the BTR1 and supplemental NC chapters for the BTR1 and BTR2/NC Report |  |  | 45000 | 562.5 | 3062.5 | 19437.5 | 21937.5 | 0 | 45000
010 | Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting reporting on Other Relevant Information |  | 562.5 | 562.5 | 19437.5 | 19437.5 | 0 | 40000
0101 | Project Team Leader | Support for activities under Component 5 as per Terms of Reference. | 2250 | 562.5 | 562.5 | 562.5 | 562.5 |  | 2250
01011 | National Consultants -- Supplemental NC Chapters | NC / specialists ffor Other Relevant Information and supplemental chapters (systematic observation, research, public awareness, outreach, and education) | 37750 |  | 0 | 18875 | 18875 |  | 37750
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 0 | 2500 | 0 | 2500 | 0 | 5000
1208 | Workshops -- Venue and Catering | Two workshops @ USD 2500, which may include workshop on climate change and gender; and 1 workshop on supplemental NC chapters. | 5000 |  | 2500 |  | 2500 |  | 5000
Stakeholder engagement events, publication and submission of report |  |  | 55000 | 25687.5 | 9187.5 | 18937.5 | 5187.5 | 0 | 59000
010 | Staff & Personnel (Including Consultants) |  |  | 3687.5 | 687.5 | 2687.5 | 687.5 | 0 | 7750
0101 | Project Team Leader | Support for activities under Component 6 as per Terms of Reference. | 2750 | 687.5 | 687.5 | 687.5 | 687.5 |  | 2750
01012 | Meeting consultants | Meeting facilitators, interpreters for the Inception workshop 2026, first validation workshop 2026 and second validation workshop 2028 (two workshops in 2026, one in 2028) | 5000 | 3000 |  | 2000 | 0 |  | 5000
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Commercial printing/publication contracts to be budgeted here -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 17000 | 4000 | 13500 | 0 | 0 | 34500
1209 | Workshops -- Venue and Catering | Four workshops: One Inception Workshop, one mid-term lessons learned workshop, and two Final Validation Workshops (one for each report). | 10500 | 7000 | 4000 | 3500 |  |  | 14500
12010 | Contract Services/translation costs | Translation of BTR2, BTR3/NC5 from Russian into Turkmen and English | 10000 | 5000 |  | 5000 |  |  | 10000
12011 | Publication Costs | Publication cost of the two final reports (BTR2 and BTR3/NC5) | 10000 | 5000 |  | 5000 |  |  | 10000
160 | Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel |  | 5000 | 4500 | 2750 | 4500 | 0 | 16750
16010 | Travel and DSA | Travel for one person for participation in the FMSP at the COP following the submission of each report. (2 trips -- one per report for max. $5000 / trip) | 9000 |  | 4500 |  | 4500 |  | 9000
16011 | Travel and DSA for workshop participants. | Travel and DSA for workshop participants for workshops under 1209 | 7750 | 5000 |  | 2750 |  |  | 7750
Self-Assessment and Stocktaking Exercise for Subsequent EA Activities |  |  | 20000 | 0 | 0 | 0 | 16000 | 0 | 16000
010 | Staff & Personnel (Including Consultants) | Meeting facilitators, interpreters, |  | 0 | 0 | 0 | 12000 | 0 | 12000
01013 | 010-Staff & Personnel (Including Consultants) | Consultant for stocktaking exercise for preparation of project proposal for subsequent reports (or "Support by Project Technical Coordinator for stocktaking exercise for preparation of project proposal for subsequent report(s)) -- use 0101 if using the PTC. | 12000 |  |  |  | 12000 |  | 12000
120 | Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Commercial printing/publication contracts to be budgeted here -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs |  | 0 | 0 | 0 | 4000 | 0 | 4000
12012 | Workshops -- Venue and Catering | One final workshop and/or stakeholder consultation for subsequent reporting (optional -- consultations could be included under the budget for the consultant for the stocktaking) | 4000 |  |  |  | 4000 |  | 4000
Project Management Cost (PMC) |  |  | 112090 | 28022.5 | 28022.5 | 28022.5 | 28022.5 | 0 | 112090
010 | Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff e.g. Project coordinator, Admin/Finance Assistant. |  | 3100 | 3100 | 3100 | 3100 | 0 | 12400
01014 | Project Manager | Project Manager | 6200 | 1550 | 1550 | 1550 | 1550 |  | 6200
01015 | Project Assistant | Project Assistant | 6200 | 1550 | 1550 | 1550 | 1550 |  | 6200
125 | Operating & Other Costs | Includes: Rental of premises/equipment; utilities; bank charges |  | 1250 | 1250 | 1250 | 1250 | 0 | 5000
12501 | Bank charges | Bank charges | 5000 | 1250 | 1250 | 1250 | 1250 |  | 5000
130 | Administrative Support |  |  | 23672.5 | 23672.5 | 23672.5 | 23672.5 | 0 | 94690
1301 | Administrative and Financial Assistant | UNDP support costs, determined in accordance with its cost recovery policy (Clause C of the UN2UN agreeement between UNDP and UNEP). | 40090 | 10022.5 | 10022.5 | 10022.5 | 10022.5 |  | 40090
1302 | UNDP GMS | UNDP GMS fee (7% of total net costs) | 54600 | 13650 | 13650 | 13650 | 13650 |  | 54600
| TOTAL |  | 1233000 | 249737 | 313206.5 | 334362.5 | 335693.5 | 0 | 1232999.5

## Budget_Team (hidden)
[11 empty] | 80% | 5% | 5% | 10% |  | Deliverables
[11 empty] | Staff n personnel | Equipment | travel | Workshops | total | Year 1 | Year 2 | year 3
[10 empty] | Chapter 1 |  |  |  |  | 160000 | 1.1 | 1.2, 1.3, 1.4 | 1.5
[10 empty] | Chapter 2 |  |  |  |  | 120000 | 2.1, 2.2 | 2.3, 2.4
[10 empty] | Chapter 3 |  |  |  |  | 50000
Chapter 4
Chapter 5
PMC
330000
Output 1: PROPOSED BTR OUTLINE & DELIVERABLES | Indicative Budget | Staff and Other Personnel Costs(Consultants and staffs) | Contractual Services (meeting venue/publication, Audit | Grants Out | Travel(DSA/Tickets/Terminals) | Operating and Other Direct Costs (office supplies, consumables and equipment) | Supplies Commodities and Materials | Equipment Vehicles and Furniture | Total
I. National inventory report (NIR) | 160000 | 115000 | 20000 |  | 10000 | 5000 |  |  | 150000
1. A national circumstances and institutional arrangements section related to GHG inventory
2. A section on methodologies and metrics (methodologies, parameters and data, KCA, time series consistency and recalculations, Uncertainty assessment, assessment of completeness, QA/QC)
3. The national inventory report (consisting of a national inventory document, the common reporting tables and an improvement plan)
II. Information necessary to track progress made in implementing and achieving nationally determined contributions under Article 4 of the Paris Agreement | 120000 | 90000 | 20000 |  | 5000 | 5000 |  |  | 120000
4. A national circumstances and institutional arrangements section related to NDC tracking
5. A section providing country’s NDC’s overview, actions, policies and measures
6. Projections of GHG emissions and removals (time coverage, structure, NDC indicators, methodologies)
7. NDC tracking report
III. Information related to climate change impacts and adaptation under Article 7 of the Paris Agreement | 100000 | 80000 | 10000 |  | 5000 | 5000 |  |  | 100000
8. A section national circumstances, institutional arrangements and legal frameworks related to adaptation
9. A section on impacts, risks and vulnerabilities; adaptation priorities and barriers, adaptation strategies, policies, plans, goals and actions to integrate adaptation into national policies and strategies
10. A section on progress on implementation of adaptation actions; M&E of adaptation actions and processes; information related to averting, minimizing and addressing loss and damage associated with climate change impacts ; cooperation, good practice, experience and lessons learned
11. Climate Change impacts and adaptation report
IV. Information on financial, technology development and transfer and capacity-building support provided and mobilized under Articles 9–11 of the Paris Agreement | 20000 | 15000 | 2000 |  | 1500 | 1500 |  |  | 20000
12. A section on national circumstances, institutional arrangements relevant to reporting on the provision and mobilization of support
13. A description of underlying assumptions, definitions and methodologies
14. Section on financial support, technology development and transfer, and capacity- building support needed and received.
15. Report with relevant information, including on gender and climate change | 10000 | 5000 | 3000 |  | 1000 | 1000 |  |  | 10000
V. Stakeholder engagement events, publication and submission of report | 30000 | 10000 | 15000 |  | 4000 | 1000 |  |  | 30000
16. Consultations and workshops (Inception, review and validation)
17. Trainings and in-depth reviews of reports
18. Compilation, translation and executive summary
19. Publication and Dissemination
OUTPUT 2: STOCKTAKING ASSESSMENT
20. Self-assessment and stocktaking report for the preparation of subsequent BTRs |  | 10000 | [6 empty] | 10000
PMC | 44000 | 34000 | 6000 |  | 1000 | 3000 |  |  | 44000
TOTAL | 484000 | 359000 | 76000 | 0 | 27500 | 21500 | 0 | 0 | 484000
|  | 74.1736 | 15.7025 | #DIV/0! | 5.6818 | 4.4421 |  |  | 100

## Expense Report_Template (hidden)
Start Date
End Date
Reporting Period
Umoja Classes | Description of Eligible Expense | Outputs | Approved Budget | Current Year Budget | Cumulative Previous Year Expense | Current Year Cumulative | Current Quarter | Total Current Year | Cumulative Expense to Date | Cumulative Unspent Balance to-date | Description of Expenses for Current Quarter
|  |  | A | B | C | D | E | F=(D+E) | G=(C+F) | H=(A-G) | I
National inventory report (NIR) |  | OP1
010 - Staff & Personnel (Including Consultants | (i) Includes all costs and entitlements of staff and consultants- supporting GHG and NIR | OP1 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP1 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP1 | [5 empty] | 0 | 0 | 0
140 - Transfers & Grants to Implementing Partners / 145 - Grants Out? | Transfer of grant to contracted entities e.g NGOs, Government Entities? | OP1 | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | OP1 | [5 empty] | 0 | 0 | 0
Information necessary to track progress made in implementing and achieving nationally determined contributions under Article 4 of the Paris Agreement |  | OP1 | [5 empty] | 0 | 0 | 0
010 - Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting NDC | OP1 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP1 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP1 | [5 empty] | 0 | 0 | 0
140 - Transfers & Grants to Implementing Partners / 145 - Grants Out? | Transfer of grant to contracted entities e.g NGOs, Government Entities? | OP1 | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | OP1 | [5 empty] | 0 | 0 | 0
Information related to climate change impacts and adaptation under Article 7 of the Paris Agreement |  | OP1 | [5 empty] | 0 | 0 | 0
010 - Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting Adaptation | OP1 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP1 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP1 | [5 empty] | 0 | 0 | 0
140 - Transfers & Grants to Implementing Partners / 145 - Grants Out? | Transfer of grant to contracted entities e.g NGOs, Government Entities? | OP1 | [5 empty] | 0 | 0 | 0
160 - Travel |  | OP1 | [5 empty] | 0 | 0 | 0
Information on financial, technology development and transfer and capacity-building support provided and mobilized under Articles 9–11 of the Paris Agreement |  | OP1 | [5 empty] | 0 | 0 | 0
010 - Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting Other Relevant Information | OP1 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP1 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP1 | [5 empty] | 0 | 0 | 0
140 - Transfers & Grants to Implementing Partners / 145 - Grants Out? | Transfer of grant to contracted entities e.g NGOs, Government Entities? | OP1 | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | OP1 | [5 empty] | 0 | 0 | 0
Stakeholder engagement events, publication and submission of report |  | OP1 | [5 empty] | 0 | 0 | 0
010 - Staff & Personnel (Including Consultants) | Meeting facilitators, interpreters, Evaluation consultants all to be budgeted under this Class. | OP1 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Commercial printing/publication contracts to be budgeted here -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP1 | [5 empty] | 0 | 0 | 0
125 - Operating & Other Costs | Includes: communication costs and bank charges | OP1 | [5 empty] | 0 | 0 | 0
130 - Supplies, Commodities & Materials | Includes: (i) Consumable supplies e.g. office stationary/supplies,drugs, tools, etc.; (ii) Costs associated with the delivery, storage and distribution of consumable supplies procured such as transportation, freight, customs, insurance, warehousing and other logistical requirements; | OP1 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP1 | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | OP1 | [5 empty] | 0 | 0 | 0
Stocktaking Assessment
010 - Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting Stocktaking and Proposal write-up | OP2 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP2 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP2 | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | OP2 | [5 empty] | 0 | 0 | 0
PMC |  | PMC
010 - Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff e.g. Project coordinator, Admin/Finance Assistant | PMC | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Audit Fees -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | PMC | [5 empty] | 0 | 0 | 0
125 - Operating & Other Costs | Includes: Rental of premises/equipment; utilities | PMC | [5 empty] | 0 | 0 | 0
130 - Supplies, Commodities & Materials | Includes: (i) Consumable supplies e.g. office stationary/supplies,drugs, tools, etc.; (ii) Costs associated with the delivery, storage and distribution of consumable supplies procured such as transportation, freight, customs, insurance, warehousing and other logistical requirements; | PMC | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | PMC | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | PMC | [5 empty] | 0 | 0 | 0
TOTAL | [7 empty] | 0 | 0 | 0
[10 empty] | Total Duration | 0
[10 empty] | Duration to date | 0
[10 empty] | % Duration | #DIV/0!
Sub Total by Class | [6 empty] | Row Labels | Sum of Approved Budget | Sum of Current Year Budget | Sum of Cumulative Expense to Date | Sum of Current Year Cumulative | Total Actual/Total budget | Current Yr. actual/Current Yr. budget
|  |  | Current Quarter | Cumulative Expense |  |  | OP1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Staff and Other Personnel Costs |  |  | 0 | 0 |  |  | OP2 | #N/A |  | 0
Travel | [6 empty] | PMC | #N/A |  | 0
Contractual Services | [6 empty] | (blank) | #N/A | 0 | 0 | 0
Operating and Other Direct Costs | [6 empty] | Grand Total | #N/A | #N/A | #N/A | #N/A
Equipment Vehicles and Furniture
Supplies Commodities and Materials
Grants Out/ IP Direct
Total |  |  | 0 | 0

## Workplan
Project Title: Turkmenistan's BTR2 + BTR3/NC5
Name of Country: Turkmenistan
Executing Agency: UNDP
Project Duration: |  | 56 Months |  | To: | 03.2026 - 10.2030
| OUTPUTS/DELIVERABLES (d) |  | PROJECT YEAR 1 - 2026 |  |  |  | PROJECT YEAR2- 2027 |  |  |  | PROJECT YEAR3 - 2028 | [5 empty] | PROJECT YEAR4- 2029 |  |  |  | Y5 - 2030 |  | SUMMARY OF KEY ACHIEVEMENTS DURING THE REPORTING PERIOD
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | SUMMARY OF KEY ACHIEVEMENTS DURING THE REPORTING PERIOD |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
|  | 1.1 Biennial Transparency Reports and NC Preparation | [12 empty] | Percentage (%) progress at chapter level | Deliverable status explanation
CH 1 |  | National inventory report (NIR) | [12 empty] | <25% completed | [7 empty] | Select percentage (%) progress at chapter level from the dropdown | Summary of what's been achieved under each deliverable
| 1.1: | A national circumstances and institutional arrangements section related to GHG inventory for the BTR2 | [13 empty] | summary of what's been achieved under each deliverable | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q2 to PROJECT YEAR3 - 2028 Q4
| 1.2: | A section on methodologies and metrics (methodologies, parameters and data, key category analysis (KCA), time series consistency and recalculations, Uncertainty assessment, assessment of completeness, QA/QC) for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q2 to PROJECT YEAR3 - 2028 Q4
| 1.3: | The national inventory report (consisting of a national inventory document, the common reporting tables and an improvement plan) for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q2 to PROJECT YEAR3 - 2028 Q4
| 1.4 | Updated national circumstances and institutional arrangements section related to GHG inventory for the BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q2 to PROJECT YEAR3 - 2028 Q4
| 1.5 | Updated section on methodologies and metrics (methodologies, parameters and data, key category analysis (KCA), time series consistency and recalculations, Uncertainty assessment, assessment of completeness, QA/QC) for the BTR3/NC5 completed. | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q2 to PROJECT YEAR3 - 2028 Q4
| 1.6 | National inventory report (consisting of a national inventory document, the common reporting tables and an improvement plan) prepared for BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q2 to PROJECT YEAR3 - 2028 Q4
CH 2 |  | Information necessary to track progress made in implementing and achieving NDCs under the Paris Agreement
| 2.1: | A national circumstances and institutional arrangements section related to NDC tracking for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q1 to PROJECT YEAR3 - 2028 Q4
| 2.2: | Description of the country’s NDC’s for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q1 to PROJECT YEAR3 - 2028 Q4
| 2.3: | GHG emissions and removals (time coverage, structure, NDC indicators, methodologies) for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q1 to PROJECT YEAR3 - 2028 Q4
| 2.4: | NDC tracking report for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q1 to PROJECT YEAR3 - 2028 Q4
| 2.5 | Updated national circumstances and institutional arrangements section related to NDC tracking for the BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q1 to PROJECT YEAR3 - 2028 Q4
| 2.6 | Updated section for description of the NDC (if applicabe) for the BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q1 to PROJECT YEAR3 - 2028 Q4
| 2.7 | Updated projections of GHG emissions and removals (time coverage, structure, NDC indicators, methodologies) provided under BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q1 to PROJECT YEAR3 - 2028 Q4
| 2.8 | NDC tracking report for the BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q1 to PROJECT YEAR3 - 2028 Q4
CH 3 |  | Information related to climate change impacts and adaptation under Article 7 of the Paris Agreement corresponding to an Adaptation Communication as specified in Article 7 of the Paris Agreement and Decision 9/CMA.1
| 3.1: | A section on national circumstances, institutional arrangements and legal frameworks related to adaptation for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 3.2: | A section on impacts, risks and vulnerabilities; adaptation priorities and barriers, adaptation strategies, policies, plans, goals and actions to integrate adaptation into national policies and strategies for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 3.3: | Progress on implementation of adaptation actions; M&E of adaptation actions and processes; information related to averting, minimizing and addressing loss and damage associated with climate change impacts; cooperation, good practice, experience and lessons learned for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 3.4: | Climate Change impacts and adaptation chapter conforming to requirements of an Adaptation Communication prepared for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 3.5 | Updated section on national circumstances, institutional arrangements and legal frameworks related to adaptation for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 3.6 | Updated section on impacts, risks and vulnerabilities; adaptation priorities and barriers, adaptation strategies, policies, plans, goals and actions to integrate adaptation into national policies and strategies prepared for BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 3.7 | Updated section on progress on implementation of adaptation actions; M&E of adaptation actions and processes; information related to averting, minimizing and addressing loss and damage associated with climate change impacts; cooperation, good practice, experience and lessons learned for BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 3.8 | Climate Change impacts and adaptation chapter conforming to requirements of an Adaptation Communication prepared for BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
CH 4 |  | Information on financial, technology development and transfer and capacity-building support needed and received under the Paris Agreement & other relevant information.
| 4.1: | A section on national circumstances, institutional arrangements and country-driven strategies for BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 4.2: | A description of underlying assumptions, definitions and methodologies for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 4.3: | Section on financial support, technology development and transfer, and capacity- building support needed and received, including for transparency-related activities; support eventually provided and mobilized for BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 4.4: | Updated section on national circumstances, institutional arrangements and country-driven strategies for BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 4.5 | Updated description of underlying assumptions, definitions and methodologies provided for BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 4.6 | Section on financial support, technology development and transfer, and capacity- building support needed and received, including for transparency-related activities; support eventually provided and mobilized for BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
5 |  | Other relevant information and supplemental NC chapters
| 5.1 | Report with Other relevant information, including on gender and climate, for the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 5.2 | Chapter on Other Relevant Information, including information on gender and climate change, for inclusion in the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 5.3 | Report with other relevant information, including on gender and climate change for the BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 5.4 | Supplemental NC chapters (research and systematic observation; and education, training and public awareness) for the BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 5.5 | Chapter on Other Relevant Information, including information on gender and climate change and supplemental NC chapters, for inclusion in the BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
6 |  | Stakeholder engagement events, publication and submission of report
| 6.1 | Consultations and inception workshop | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 6.2 | In-depth reviews and stakeholder validation of the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 6.3 | Compilation, translation and executive summary of the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q2 to PROJECT YEAR2- 2027 Q3; PROJECT YEAR3 - 2028 Q1 to PROJECT YEAR3 - 2028 Q4
| 6.4 | Publication and Dissemination of the BTR2 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q1 to PROJECT YEAR2- 2027 Q2
| 6.5 | In-depth reviews and stakeholder validation of the BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
| 6.6 | Compilation, translation and executive summary of the BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q1 to PROJECT YEAR2- 2027 Q2
| 6.7 | Publication and Dissemination of the BTR3/NC5 | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR2- 2027 Q1 to PROJECT YEAR2- 2027 Q2
7 |  | Self-assessment and stocktaking exercise for preparation of the project proposal for subsequent reports under the UNFCCC and Paris Agreement completed
| 7.1 | A self-assessment exercise for preparation of the project proposal for subsequent BTR and/or BTR/NC completed. | [16 empty] | X | X | X
PMC |  | Project Management Cost
|  | 010 - Staff & Personnel | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
|  | 120 - Contract Services (Audit) | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
|  | 125 - Operating & Other Costs | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
|  | 130 - Supplies, Commodities & Materials | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
|  | 135 - Equipment, Vehicles & Furniture | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
|  | 160 - Travel | [14 empty] | X | X | X | X | X | bar: PROJECT YEAR 1 - 2026 Q3 to PROJECT YEAR3 - 2028 Q4
Name of Project Manager: |  |  | PROJECT YEAR 1 - 2026 Q1: Date | Date: |  | Siganture
Name of Project Manager Supervisor: |  |  | PROJECT YEAR 1 - 2026 Q1: Date | Date: |  | Siganture

## Progress % Drop down (hidden)
Progress % drop down list | Explainations
Not initiated | No activities initiated
<25% completed | Project launched,sectoral experts constituted,agreements signed
25-50% completed | Data collection commenced
50-75% completed | Analysis of different sectoral reports and drafting commenced
>75% completed | Draft chapter prepared and circulated for review and comments
Completed | Final chapter included in the BTR or NC/BTR report

## Progress % Drop down list (hidden)
Progress % drop down list | Explainations
Not initiated | No activities initiated
<25% completed | Project launched,sectoral experts constituted,agreements signed
25-50% completed | Data collection commenced
50-75% completed | Analysis of different sectoral reports and drafting commenced
>75% completed | Draft chapter prepared and circulated for review and comments
Completed | Final chapter included in the BTR or NC/BTR report

## Sheet1 (hidden)
Umoja Classes | Description of Eligible Expense | Outputs | Approved Budget | Current Year Budget | Cumulative Previous Year Expense | Current Year Cumulative | Current Quarter | Total Current Year | Cumulative Expense to Date | Cumulative Unspent Balance to-date
National inventory report (NIR) |  | OP1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
010 - Staff & Personnel (Including Consultants | (i) Includes all costs and entitlements of staff and consultants- supporting GHG and NIR | OP1 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP1 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP1 | [5 empty] | 0 | 0 | 0
140 - Transfers & Grants to Implementing Partners / 145 - Grants Out? | Transfer of grant to contracted entities e.g NGOs, Government Entities? | OP1 | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | OP1 | [5 empty] | 0 | 0 | 0
Information necessary to track progress made in implementing and achieving nationally determined contributions under Article 4 of the Paris Agreement |  | OP1 | [5 empty] | 0 | 0 | 0
010 - Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting NDC | OP1 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP1 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP1 | [5 empty] | 0 | 0 | 0
140 - Transfers & Grants to Implementing Partners / 145 - Grants Out? | Transfer of grant to contracted entities e.g NGOs, Government Entities? | OP1 | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | OP1 | [5 empty] | 0 | 0 | 0
Information related to climate change impacts and adaptation under Article 7 of the Paris Agreement |  | OP1 | [5 empty] | 0 | 0 | 0
010 - Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting Adaptation | OP1 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP1 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP1 | [5 empty] | 0 | 0 | 0
140 - Transfers & Grants to Implementing Partners / 145 - Grants Out? | Transfer of grant to contracted entities e.g NGOs, Government Entities? | OP1 | [5 empty] | 0 | 0 | 0
160 - Travel |  | OP1 | [5 empty] | 0 | 0 | 0
Information on financial, technology development and transfer and capacity-building support provided and mobilized under Articles 9–11 of the Paris Agreement |  | OP1 | [5 empty] | 0 | 0 | 0
010 - Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting Other Relevant Information | OP1 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP1 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP1 | [5 empty] | 0 | 0 | 0
140 - Transfers & Grants to Implementing Partners / 145 - Grants Out? | Transfer of grant to contracted entities e.g NGOs, Government Entities? | OP1 | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | OP1 | [5 empty] | 0 | 0 | 0
Stakeholder engagement events, publication and submission of report |  | OP1 | [5 empty] | 0 | 0 | 0
010 - Staff & Personnel (Including Consultants) | Meeting facilitators, interpreters, Evaluation consultants all to be budgeted under this Class. | OP1 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Commercial printing/publication contracts to be budgeted here -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP1 | [5 empty] | 0 | 0 | 0
125 - Operating & Other Costs | Includes: communication costs and bank charges | OP1 | [5 empty] | 0 | 0 | 0
130 - Supplies, Commodities & Materials | Includes: (i) Consumable supplies e.g. office stationary/supplies,drugs, tools, etc.; (ii) Costs associated with the delivery, storage and distribution of consumable supplies procured such as transportation, freight, customs, insurance, warehousing and other logistical requirements; | OP1 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP1 | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | OP1 | [5 empty] | 0 | 0 | 0
Stocktaking Assessment |  | OP2 | #N/A |  |  |  |  | 0 | 0 | #N/A
010 - Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff and consultants- supporting Stocktaking and Proposal write-up | OP2 | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Where meetings/workshops require venue to be hired e.g Hotel, then relevant costs to be budgeted under this Class. -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | OP2 | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | OP2 | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | OP2 | [5 empty] | 0 | 0 | 0
PMC |  | PMC | #N/A |  |  |  |  | 0 | 0 | #N/A
010 - Staff & Personnel (Including Consultants) | (i) Includes all costs and entitlements of staff e.g. Project coordinator, Admin/Finance Assistant | PMC | [5 empty] | 0 | 0 | 0
120 - Contract Services | Works and services of a commercial nature contracted following procurement procedures. -Audit Fees -Transfer of grant to contracted entities e.g. reaserch institutions, Universities, NGOs | PMC | [5 empty] | 0 | 0 | 0
125 - Operating & Other Costs | Includes: Rental of premises/equipment; utilities | PMC | [5 empty] | 0 | 0 | 0
130 - Supplies, Commodities & Materials | Includes: (i) Consumable supplies e.g. office stationary/supplies,drugs, tools, etc.; (ii) Costs associated with the delivery, storage and distribution of consumable supplies procured such as transportation, freight, customs, insurance, warehousing and other logistical requirements; | PMC | [5 empty] | 0 | 0 | 0
135 - Equipment, Vehicles & Furniture | Includes: Procurement of non-consumables e.g. IT equipment. This would relate to all costs to put asset into service and the cost of disposal of the asset upon reaching its useful life. | PMC | [5 empty] | 0 | 0 | 0
160 - Travel | i) Includes staff/consultant/meeting participant travel [DSA/Tickets/Terminals as applicable] (ii) Road / train /Fuel and vehicle/boat rental costs for staff, consultants and other project personnel | PMC | [5 empty] | 0 | 0 | 0
|  |  | A | B | C | D | E | F=(D+E) | G=(C+F) | H=(A-G)
TOTAL |  |  | #N/A |  |  |  |  | 0 | 0 | #N/A

## Workplan-Progress Report (hidden)
| OUTPUTS/DELIVERABLES (d) |  | PROJECT YEAR 1 - 2022 |  |  |  | PROJECT YEAR 2 - 2023 |  |  |  | PROJECT YEAR 3 - 2024 |  |  |  | PROJECT YEAR 4 - 2025
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | OUTPUTS/DELIVERABLES PROGRESS STATUS
|  | 1.1 Biennial Transparency Report Preparation | [16 empty] | Percentage (%) progress at chapter level | Deliverable status explanation
CH 1 |  | National inventory report (NIR) | [16 empty] | Completed
| 1.1.1: | A national circumstances and institutional arrangements section related to GHG inventory
| 1.1.2: | A section on methodologies and metrics (methodologies, parameters and data, KCA, time series consistency and recalculations, Uncertainty assessment, assessment of completeness, QA/QC)
| 1.1.3: | The national inventory report (consisting of a national inventory document, the common reporting tables and an improvement plan)
CH 2 |  | Information necessary to track progress made in implementing and achieving NDCs under the Paris Agreement | [16 empty] | Not initiated
| 1.2.1: | A national circumstances and institutional arrangements section related to NDC tracking
| 1.2.2: | A section providing country’s NDC’s overview, actions, policies and measures
| 1.2.3: | Projections of GHG emissions and removals (time coverage, structure, NDC indicators, methodologies)
| 1.2.4: | NDC tracking report
CH 3 |  | Information related to climate change impacts and adaptation under Article 7 of the Paris Agreement
| 1.3.1: | A section national circumstances, institutional arrangements and legal frameworks related to adaptation
| 1.3.2: | A section on impacts, risks and vulnerabilities; adaptation priorities and barriers, adaptation strategies, policies, plans, goals and actions to integrate adaptation into national policies and strategies
| 1.3.3: | A section on progress on implementation of adaptation actions; M&E of adaptation actions and processes; information related to averting, minimizing and addressing loss and damage associated with climate change impacts ; cooperation, good practice, experience and lessons learned
| 1.3.4: | Climate Change impacts and adaptation report
CH 4 |  | Information on financial, technology development and transfer and capacity-building support provided and mobilized under the Paris Agreement
| 1.4.1: | A section on national circumstances, institutional arrangements relevant to reporting on the provision and mobilization of support
| 1.4.2: | A description of underlying assumptions, definitions and methodologies
| 1.4.3: | Section on financial support, technology development and transfer, and capacity- building support needed and received.
| 1.4.4: | Report with relevant information, including on gender and climate change
CH 5 |  | Stakeholder engagement events, publication and submission of report
| 1.5.1: | Consultations and workshops (Inception, review and validation)
| 1.5.2: | Trainings and in-depth reviews of reports
| 1.5.3: | Compilation, translation and executive summary
| 1.5.4: | Publication and Dissemination
CH1 |  | Stocktaking Assessment & Proposal Dev
| 2.1.1 | Self-assessment and stocktaking report for the preparation of subsequent BTRs
| 2.1 | Project Management Cost
010 - Staff & Personnel
120 - Contract Services (Audit)
125 - Operating & Other Costs
130 - Supplies, Commodities & Materials
135 - Equipment, Vehicles & Furniture
160 - Travel

## Progress % Drop down list (hidden)
Progress % drop down list
Not initiated
<25% completed
25-50% completed
50-75% completed
>75% completed
Completed

## Sheet4 (hidden)
SB-001119.01.01
SB-001119.01.02
SB-001119.01.03
SB-001119.01.04
SB-001119.01.05
SB-001119.01.06
SB-001119.01.07
SB-001119.01.n
SB-001119.01.39