GP

Quarterly Progress Report cum PO’s Report

Quarter: (Tick) 1/ 2/ 3/ 4

Project: Sustainable Livelihoods and Biodiversity Conservation Project Through Multiuse Management of Anchunad and Adjoining Landscape

Date: 13-04-2020

- Project Progress

| Expected Project Outputs and Indicators including Annual Targets | Planned Activities (List all activities including M&E during the year) | Activity Progress in Quarter – Comments by PO | Quarter X (Highlight the completed quarter) |  |  |  | Comments by PO on the activity progress | Targeted Expenditure for the year | Actual Expenditure in Quarter 1 | Reasons for Under Expenditure in Quarter X, if any |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  |  |  |  |
| Outcome 1 : Strengthened capacities for community based sustainable use and management of natural resources |  |  |  |  |  |  |  |  |  |  |
| Outcome 1: Outputs 1.1 Capacities of Local Self Governments and community organizations developed to plan for sustainable resource use | 1.1.1 Workshops/meetings and consultations/discussions with relevant stakeholders including government line department and agencies, local level institutions and communities, elected representatives and civil society organizations to orient them on the objective of the project, components and implementation strategy 1.1.2 Building rapport with the local communities in 11 Gram Panchayats for mobilizing them towards action for conservation, sustainable use and development 1.1.3 Mapping key priorities and mandate of 11 GPs and linkages of the same with project objective, outputs and indicators (including Green Appraisal`, BD concerns at block level) |  |  |  |  |  | Meeting held with State Agriculture Minister, Agricultural production commissioner and senior officials of agriculture department and HKM officials on February 6, 2020 to discuss about the project and agriculture component of the project. Linkages mapped with the relevant government departments and line agencies. State Level Steering Committee held on 25 February, 2020 to provide overview of project objectives, discuss on fund flow mechanism and Annual Work Plan for 2020-21 and 2021-22. Inputs and suggestions were received from various government departments and line agencies which were incorporated into the Annual Workplan. Consultation meeting held on 6th March, 2020 with Addl. Chief Secretary, Forests on Annual Work Plan for 2020-21 and 2021-22. Consultation meeting held with Environment Director/ MD, Suchitwa Mission on Waste Management activities and components for Annual Work Plan for 2020-21 and 2021-22. Working Committee meeting held on 12th March 2020 with key stakeholders to present revised Annual Work Plan for 2020-21 and 2021-22. Multiple consultation meetings held with Haritha Keralam Mission, Forest Department, Grama Panchayath representatives in the landscape and UNDP CO team in January and February 2020. The comments and suggestions received from all stakeholders on the activities in the workplan were incorporated, synergies and complementarities of the interventions planned under the project were with the relevant government schemes/programmes and plans were mapped along with sources of co-finance. As a part of Green Appraisal of the plans of Gram Panchayats, field visits and consultations with 10 Grama Panchayats have been held. Expert meetings have also been conducted to prepare the checklist for screening the plans. |  |  |  |
|  | 1.1.4 Develop knowledge products and IEC products on project objectives, components, importance of high range ecosystems, economic value of biodiversity and ecosystem services, contribution towards mitigation of climate change and disasters; |  |  |  |  |  | Knowledge products like posters, brochures, banners etc. have been developed and disseminated amongst various stakeholders including government department and line agencies, civil society organizations and local communities for orienting them towards project objectives and intended outcomes. |  |  |  |
|  | 1.1.6 Exposure visit of select stakeholders to other landscape approach-based conservation models and training on Results-based management |  |  |  |  |  | Exposure visit to Keystone Foundation by VSS members to understand NTFP value addition and marketing of NTFP. |  |  |  |
|  | 1.1.7 Review of existing programmes, policies and schemes of relevant government departments and line agencies to map linkages and build synergies/convergence with the objectives/components of the project |  |  |  |  |  |  |  |  |  |
|  | 1.1.8 Capacity need assessment of relevant stakeholders to assess dimensions of existing capacities and future requirements (to be done through UNDP Capacity Scorecard) |  |  |  |  |  | Inception report submitted by KILA . What is the finding or methodology of KILA’s report? Pls mention |  |  |  |
|  | 1.1.9 Identification of areas for developing specific/customised training modules for capacity building exercise |  |  |  |  |  | Areas for capacity building of relevant stakeholders being identified through consultations and assessments |  |  |  |
|  | 1.1.10 Training relevant stakeholders for mainstreaming BD considerations |  |  |  |  |  | Technical expertise extended to Kerala Institute of Local Administration in development of modules related to Climate Change for training Local Self Government Institutions on developing Local level Disaster Management Plan (This was a state-wide initiative) Was part of the KILA resource group for training on Climate Change as part of development of Disaster Management plans for GPs in Devikulam Block |  |  |  |
|  | 1.1.11 Technical studies to establish baseline, assess impacts of current resource use practices, develop service-level benchmarks, develop package of practices(commissioned under earlier project; recommissioned after third NPSC) - Documenting socio-economic status and contemporary issues with focus on Biodiversity Conservation and Natural Resource Management, Comprehending the current livelihood practices and possible livelihood interventions related to Biodiversity Conservation KILA - Detailed water balance study, review of good water management practices adopted in high range of the humid tropics, preparation of integrated water resources management plan and also to provide technical support to LSG/ depts for identification & renovation of selected water resources and to develop capacities of LSGs and land scape level management units to plan for sustainable water use – CWRDM KFRI - Documentation and compilation of existing information on various taxa (flora and fauna) and identification of critical gaps in knowledge. Review of Ecological and development history of various sectors and changes in selected ecological units -KSBB - Study on Pattern of usage of pesticides and their impact on the Ecosystem of plantations and adjacent areas. - Study on Diversity and current status of fish and fisheries. - Study on the Impact of Invasive plant species on Ecology KFRI - Ecosystem requirements of hornbills and assess the status and distribution of selected mammals – SACON |  |  |  |  |  | KILA A Consultative workshop on Creation of Socio-Economic Data Base for Concurrent Evaluation for the project landscape was conducted at KILA, Thrissur on 30 -31 January 2020. A total of 56 people participated including Elected representatives, Forest department, Grama panchayat Secretary, Agriculture, officials from tribal department, Kudumbashree etc from eleven grama panchayaths participated in the workshop. Analyse changes and contemporary issues in the Munnar Landscape Project Area in all the 11 Gram Panchayats in the region. The workshop discussed various aspects like - Population trend in the recent times, types of tribes/communities, societal functions, norms, functions traditional knowledge with respect to biodiversity conservation, natural resource usage and management - Current livelihood practices based on use of natural resources, such as non-timber Forest Products, different food habits and edible items, medicinal plants, local fish varieties, food practices, plantations etc. through sample survey/ interaction with the community members etc - Peoples’ aspirations with respect to sustainable development and access to the natural resources through focus group discussions and local level meetings - Best practices in Livelihood & Conservation and recommendation of incentives Consultative workshop on Social Changes Among Tribes - Trajectory of Development - Focus on Edamalakkudi A Consultative work on Social Changes Among Tribes - Trajectory of Development - Focus on Edamalakkudi was conducted at Edamalaukudy on February 18, 2020. Various stakeholders including Elected representatives, Grama panchayat officials, tribal department officials, Kudumbashree etc participated in the workshop. Workshop discussed the outlines on the social statistics, land use practices, people’s aspirations, livelihood practices, accessibility to market, various institutions functioning, operational efficiency and in addition their livelihood practices to sustainable development. |  |  |  |
| Output 1.2: Sustainable resource use practices demonstrated for improved quality of life | Spatial crop-planning 1.2.1 Assessment of existing land-use pattern in 3 selected Gram Panchayats to delineate and analyse anomalous cropping practices |  |  |  |  |  | Identification of pilot sites for spatial crop planning completed based on the rapid assessment of current cropping pattern in 5 Grama Panchayts. Inception report submitted by NBSS, Bengaluru |  |  |  |
|  | 1.2.2 Expert consultations with technical agencies/experts and farmer groups/associations to look at sustainable cropping patterns (parameters for sustainable copping patterns to be developed and validated) considering the characteristics of landscape |  |  |  |  |  | Consultation meetings were conducted with various farmer groups, Grama Panchayats officials, Agriculture Officers, Farmers producer companies etc in these 5 Grama Panchayats |  |  |  |
|  | Comprehensive sanitation and waste management 1.2.7 Review of existing practices and models of waste management and sanitation (national and global), training, exposure visits, campaigns, pilots etc and also preparation of panchayat sanitation survey and waste-management plan |  |  |  |  |  | An awareness session on AI based garbage dumping detection system was carried out at Adimali Grama Panchayat during this quarter for different stakeholders. Further AI based garbage dumping detection system installation has been completed. A rapid assessment by Paperman Foundation Chennai on the existing waste management mechanisms of the Grama Panchayat was carried out and further strategic intervention in the coming quarters will based on the recommendations |  |  |  |
|  | 1.2.8 Detailed Project Report for “Green Munnar” and Athirappilly Panchayat for creating decentralised solid waste management (this would include interventions for waste minimisation, treatment for bio-degradable wastes like chicken and slaughter waste, bio-methanation, energy generation from biogas, treatment of plastics etc.) and demonstrations, capacity building, training, exposure visits, campaigns, pilots across clusters etc |  |  |  |  |  | Green Munnar - Mobilization of MGNREGS women for the removal of invasive species along the roadsides in Munnar - s part of convergence with departments, 2000 fruit and flower plant varieties were raised through KFDC - Conducted trainng on alternatives to plastics to 18 women and 1000 cloth bags were stitched Athirapilly - Conducted awareness campaign as part of Green Campaign in Athirappilly where 50 women had participated. - Consultation meeting with GP and IRTC – on framing DPR for developing effective solid waste management mechanism - Consultation and field visits on initiating model eco-corridor in Athirappilly; 5 nodes across a 20 km stretch has been identified where waste littering is highest in Athirappilly. Walkthrough video developed on possible interventions in each of the nodes |  |  |  |
|  | 1.2.9 Explore convergence with schemes and plans of Gram Panchayat for implementation of select interventions in Munnar, Athirappilly, other GPs and piloting of appropriate technological interventions |  |  |  |  |  | Mankulam - IRTC conducted a first level meeting with GP representatives and officials - IRTC recruited a project fellow for Mankulam waste management related activities - Discussed modalities with the GP to organize a clean drive in Anakkulam tourist area and a training for the strengthening of Haritha Karma Sena Chinnakanal - IRTC visit as part of developing DPR for effective solid waste management mechanism - Appointed a project fellow for waste management related activities - Survey initiated for estimating waste quantity Kanthalloor - Niravu visit and conducted training for Haritha Karma Sena who are a women entrepreneur network who primarily focus on collection and segregation of waste collected from Households. 20 women participated - Material Recovery Facility developed by Panchayath based on recommendations and guidelines provided by UNDP partner agency – Niravu - Door to door awareness held for shops and institutions on waste segregation - Meeting held with traders on imposition of fines for waste dumping Marayoor - Niravu visit and conducted training for Haritha Karma Sena and Kudumbashree. 55 women were participated - Door to door awareness held for shops and institutions on waste segregation - Meeting held with traders on imposition of fines for waste dumping Adimali - Conducted training on alternatives to plastics and 54 women had participated - Keltron team visit and identified one location for fixing AI based garbage dumping detection system - Assessment by Paperman Foundation on the existing waste management mechanisms in the Grama Panchayat Kuttampuzha - Meeting with relevant stakeholders held - Survey completed for preparation of DPR - Panchayath has started Material Collection Facility based on recommendation by UNDP partner agency - Household collection initiated by Haritha Karma Sena |  |  |  |
|  | Water Resource Management 1.2.11 Pilot intervention based on the integrated watershed management plans prepared for 11 Gram Panchayats in consultation with all relevant stakeholders - Renovation of selected water resource structures as part of environment building activity |  |  |  |  |  | CWRDM submitted the inception report to PMU for suggestions. Necessary inputs were shared to for incorporating in the final version CWRDM conducted field visits in 4 GPs for identifying water harvesting structures that can be utilised for better water conservations along with functionaries of GP and the project team. An average of 4 sites were identified in the four GPs for the same. |  |  |  |
|  | 1.2.18 Conservation and propagation plan for traditional practices, seed varieties; feasibility study and development of a detailed proposal for Live Museum in the Munnar landscape |  |  |  |  |  | Under propagation of traditional agriculture practices and seed conservation activities, stakeholder consultations were carried out at Adimali with agriculture department officials, Panchayat representatives and elected representatives from five Padashekhara Samithies having over 50 ha of cultivable land. Site assessment of five Padashekhara areas was carried out for by technical consultant and implementation strategy is being worked out and the implementation would be initiated in next quarter. Under traditional agriculture practices and seed conservation activities among the tribal community members, community farming of traditional Ragi cultivation was initiated in a 5-acre model plot in Edamalakkudy. Around 80 community members are part of the initiative which aims at conservation and revival of Ethnic agro-biodiversity for nutritional and income security of tribal communities. Under traditional agriculture practices and seed conservation activities, an intervention is planned at ‘Chinnapparakkudy’ (Adimali) among the tribal community members. Convergence with govt department - Janamithri Excise, agriculture dept and Grama panchayat is planned |  |  |  |
| Output 1.3: Enhanced products/services value chains developed for providing ecologically sustainable livelihoods options | 1.3.1 Detailed study on the key local commodities/ products and their respective value chains which helps in preparation of business plan |  |  |  |  |  | Following studies are in progress - Building roadmap and assessment of bamboo/ reed in Project landscape - Study on Market Mapping & Value Chain analysis of Vegetables Study on Market Mapping & Value Chain analysis of Vegetables - Building strategy and roadmap for NTFP Value addition |  |  |  |
|  | 1.3.2 Analysis of the key value chain activities and their environment impact and ecological sustainability (priority to be given to key commodities and products that have emerged from the stakeholder consultations during project preparation phase) in the context of business plan |  |  |  |  |  | Consultation in areas of NTFPs, Veg value chain, passion fruit value chain, lemon grass value chain conducted. Partner meet on Organic Mankulam was conducted on March 13,2020 with KADS. Stakeholder consultations, farmer level trainings and market linkages are planned in the coming quarter. |  |  |  |
|  | 1.3.3 Stakeholder consultations on the analysis and possible interventions strategies to address the gaps |  |  |  |  |  | A pre-launch brainstorming workshop for Green Innovation Fund was conducted on March 2,2020 with representative from 11 institutions like ICRISAT, NIT Calicut, KAU etc who are working the Startup/ Incubation space in Kerala and outside Kerala. The brainstorming workshop focused on the validation of the concept of Green Innovation, problem statements generation, Identifying startups & entrepreneurs and methodology for it, operational guidelines including Selection process and due diligence, outreach activities, suggested timelines, role of Incubation partners, risks and challenges, mitigation strategy, exit and scale out. Partner meet on Organic Mankulam was conducted on March 13,2020 with KADS. Stakeholder consultations, farmer level trainings and market linkages are planned in the coming quarter. A stakeholder consultation workshop was organised for passion fruit value chain was organised. A total of 65 people participated out of 50 were women SHG members. In addition to SHG group members representatives from Grama Panchayat, block Panchayat, agriculture, SC dept, health department and members from local volunteer organisation participated in the workshop. Workshop discussed about the potential of passion fruit value chain and value-added products that could be manufactured through the collective. A one-day awareness workshop was conducted by CIMAP on March 3,2020 for tribal farmers, forest development agency, Panchayat officials, agriculture officers, industry partners, tribal department officials and Panchayat officials. Sixty people participated in the workshop where value chain intervention in medicinal and aromatic plants were discussed. CIMAP team comprising of five scientists from Bengaluru and Lucknow centres conducted a field visit to cultivation sites and distillation units of lemon grass in Marayoor Panchayat. As a part of strengthening NTFP Value Chain, a field immersion programme for tribal community members (VSS members) and forest dept officials were conducted on Feb 21&22, 2020 to Keystone foundation, Kothagiri, Tamilnadu. The objective of the field immersion programme was to gain better understanding on the collection process, grading & cleaning process, processing, packaging and labelling and sales counter of the NTFPs products. A session on sustainable harvesting practices of wild honey was also conducted as a part of the field immersion trip. Sixteen members participated in the field immersion programme. |  |  |  |
|  | 1.3.4 Identification, development and piloting of business plans for select value chains to be piloted (this would involve exploring institutional arrangements for value chain enhancement, viable market strategies, branding and certification) |  |  |  |  |  | A partnership with Kerala Startup Mission (KSUM) through the establishment of a Green Innovation Fund (GIF) is initiated. GIF is strategically positioned as a Start-up risk capital for entrepreneurs and will focus on solutions for key emerging Social Entrepreneurships addressing the problems identified from the selected UNDP project landscape. Consultation meeting held with KSUM and HKM to develop a road map for the GIF completed. Draft guidelines have been prepared and pre-launch brain storming workshop is completed. We are converging with agriculture department for Athirappilly Tribal Valley Agricultural Project (Rs 100 mn project over three years) which envisages to improve the livelihood of tribal farmers through the adoption of better farming practices, better output from unit farm area, Organic and rainforest certified products, value addition of farm products and exploring the tribal farm tourism potential of the location. An inception workshop was conducted in February 16,2020 inaugurated by State Agriculture Minister in the presence of MLA, senior officials from agriculture department, forest department, Panchayat officials etc. Around 750 people, majority from tribal community participated in the workshop. During this quarter, tribal collective kick started their operations for procurement of agriculture and NTFP produce. Intervention in passion fruit value chain addition with the technical assistance of Kerala Agriculture University A 10-member core committee from the community has been formed for spear heading the intervention. A field level survey process has been initiated for collecting basic demographic profile, land availability and experience in the passion fruit cultivation. An exposure visit was organised for the community members to Kerala agriculture University, Pineapple Research Station, Vazhakkulam to learn about the seedlings raising, value added products and various other aspects of value chain of passion fruit. Over 8000+ saplings of local varieties of passion fruit have been raised in the research centre with the support from local farmers. A model farm tourism hub in the Horticorp campus at Munnar was launched on February 24,2020 by State Agriculture Minister in the presence of MLA, District Collector, Sub collector Devikulam, Horticorp Chairman, Managing Director, Agriculture department director and other senior state officials. It is expected that this hub will help fruit cultivation and farm tourism will help to improve the economic conditions of poor households in the region. Under the project for developing medicinal plants for livelihood generation & biodiversity conservation among women self -help groups and marginal farmers, the commercial cultivation of selected medicinal plants which has demand in Ayurveda would be carried out and would facilitate marketing of cultivated medicinal plants by linking with industry. Baseline study in the selected villages of Marayoor panchayat is completed. Consultation and discussion with various Ayurveda factories and industry experts and assessed the demands of medicinal plants was carried out and based on their demands and advices selection of following five medicinal plants in the project area was done - Plumbago indica, Vetiveria zizanioides, Kaempferia galangal, Sida rhombifolia-Curcuma zedoria. Stakeholder consultations were carried out at Marayoor Panchayat elected representatives and officials. The equipping of the mother nursery and Collection of selected species of establishing mother stocks of five selected is completed during this quarter. Commercial bee keeping activities in two tribal settlements-Vellaramkuth and Pinavoorkudi in Kuttampuzha Grama Panchayat for 40 tribal women initiated. Follow up training carried out and women has generating revenue by marketing of honey. Branding exercise and collective marketing planned. |  |  |  |
| Output 1.4: Community-based models developed for sustainable access and use of forest resources by local communities | 1.4.1 Detailed socio-economic and cultural intervention based on study analysing all aspects of life and livelihood in Edamlakudi including analysis of suggestions from consultations |  |  |  |  |  | A Consultative work on Social Changes Among Tribes - Trajectory of Development - Focus on Edamalakkudi was conducted at Edamalaukudy on February 18, 2020. Various stakeholders including Elected representatives, Grama panchayat officials, tribal department officials, Kudumbashree etc participated in the workshop. Workshop discussed the outlines on the social statistics, land use practices, people’s aspirations, livelihood practices, accessibility to market, various institutions functioning, operational efficiency and in addition their livelihood practices to sustainable development. |  |  |  |
| Outcome 2: Multiple use landscape management is applied to secure the ecological integrity of the High Range landscape |  |  |  |  |  |  |  |  |  |  |
| Output 2.1: Capacities of conservation and production sector personnel developed for applying landscape approaches in to sectoral planning and operations | 2.1.1Mapping of spatial distribution of different sectors (tea, forest plantations, tourism, agriculture, cardamom, livestock, horticulture, tribal welfare) in GIS platform. This will be feed from outcome 3 |  |  |  |  |  |  |  |  | Delayed to non-avilability of satellite data from NRSC; lock down |
|  | 2.1.2 Develop & validate state of sector documents. State of sector documents will include the beneficiaries and stakeholders of each sector, assessment of impacts on natural resources of the landscape, and potential strategies for mainstreaming biodiversity conservation. |  |  |  |  |  |  |  |  | No field visits due to lock down |
| Output 2.2: Mainstreaming of bio-diversity concerns in key production sectors demonstrated | 2.2.1 Demonstration of developed potential strategies in identified sectors like tea, forest plantations, tourism, agriculture, cardamom, livestock, horticulture, tribal welfare etc |  |  |  |  |  | IIPM had consulted few experts with regard to development of ecological perspectives for the State of Sector document First and second progress report submitted on State of Sector – Tourism document KABANI submitted inception report for sustainable tourism model conducted orientation workshop at Mankulam and Resource mapping and consultative meeting with relevant stake holders at Mankulam and Kuttampuzha EMC conducted field visits and undertook investment grade energy audit fot two factories of KDHP. The data is been analysed for compilation of report. EMC submitted the inception report to PMU for suggestions Green Islands: TIES conducted a first level discussion with GP. Identified six locations with the support of GP and Haritha Keralam Mission Stakeholder consultations for Green Islands completed at Athirappilly and Kuttanpuzha GPs. Site identification completed in both GPs. Saplings to be arranged from Central Nursery by Forest Department, Chettikulam, Thrissur, MGNREGS nursery in Athirappilly, Angamali Social Forestry Nursery and Odakkali Medicinal plants. Green island activity is included in the MGNREGS work action plan in GP. |  |  |  |
| Outcome 3: Commonly accepted governance framework for multiple-use high range landscape management evolved |  |  |  |  |  |  |  |  |  |  |
| Output 3.1: Landscape level management plans and sustainable resource management systems in place | 3.1.2 Geospatial mapping of exotic species and its habitat; Mapping of local movements of species, digitization of shola outside protected areas of the current landscape elements including all the vegetations and land use with the protection status. |  |  |  |  |  | The mapping of exotic and invasive species in Pampadumshola NP, Anamudishola NP and Mankulam Forest Division has been done using GPS. Mapping of Local movements of wildlife under Munnar Forest Division is under progress. Initiated taxonomic inventory of shola species |  |  |  |
|  | 3.1.3Review of Management Plan guidelines; drafting of management plans of 6 PAs based on the review Review of State Forest Policy; preparation of new working plans in context of landscape-based approach Drafting specie-specific policy for management and control of exotic and invasive species Drafting protocol for wildlife health monitoring of species in the project area |  |  |  |  |  | Review of Management Plans of 2 PAs – Anaimudi Shola National Park and Pampadum Shola National Park has been done, identified critical gaps, issues and challenges through consultative process. Draft Management Plan for the same is prepared and submitted to experts for vetting the same. |  |  |  |
|  | 3.1.4 Review and validation of METT and MEE scores of PAs within the project landscape to identify gaps |  |  |  |  |  | Identified the person for doing the METT, first level meeting with respective Wildlife Warden’s of the 6 PAs |  |  |  |
|  | 3.1.5 Identify issues/ threats/ concerns and challenges in the landscape with relevant stakeholders in a participatory manner. |  |  |  |  |  | Major issues and threats to biodiversity conservation in the forested areas has been identified. |  |  |  |
|  | 3.2.1 Design intervention and mitigation measures to address identified threats/concerns for biodiversity conservation (in a participatory manner) |  |  |  |  |  | Draft course material on ornithology has been prepared. The ornithology course will be done as an initiative of Thattekad Bird Sanctuary for community members, which will support in community-based bird conservation initiatives. |  |  |  |
| Output 3.2. Institutional platforms of multiple stakeholders evolved and strengthened at appropriate levels for planning and reviewing sustainable resource use | 3.2.2 Design and implement specific interventions in consultation with the State Forest Department to address the existing gaps for improving the management of PAs |  |  |  |  |  | Initiated to take advanced measures to prevent forest fire in the landscape. Technologies were applied to mitigate the road kill incidents of wildlife species – under progress. |  |  |  |
| Output 3.3: Management effectiveness of designated biodiversity rich ecosystems are strengthened to address existing and emerging challenges to ecosystem conservation and services | 3.3.2 Facilitating preparation of management prescription for removal of exotics plantations like eucalypts, wattle and invasive alien species from the PAs, other forest areas and high-altitude montane grasslands ecosystems |  |  |  |  |  | Strategies has been developed to remove the exotic plantations inside the PAs and other forest areas through consultative process, expert suggestions. The strategy has been presented before the higher forest officials of the state of Kerala. |  |  |  |
|  | 3.3.3 Facilitating preparation of management plan for eco-restoration of reed breaks and areas where the exotics and invasive alien species were removed; generating livelihood options through the removal of exotic and invasive alien species; exploring possibilities of value addition |  |  |  |  |  | Exposure visits to grassland restoration areas in the Nilgiris, part of Western Ghats were done for the forest officials to learn the procedures of restoration process, issues and challenges faced during restoration process as well as to address the same. |  |  |  |
|  | 3.3.4 Facilitating the preparation of comprehensive plan for protecting the Anayirangal elephant ecosystems in Chinnakkanal |  |  |  |  |  | First public consultative meeting were conducted at Chinnakanal GP to discuss the conservation strategy developed. Suggestions, comments by the publics were collected during the meeting towards social responsibility. Redrafting of the strategy based on the comments of the publics received during the consultation process-ongoing. |  |  |  |
|  | 3.3.5 Removal of plantations (Wattle and Eucalyptus), Eradication of alien weeds, from PAs and restoration of original vegetation, Removal of alien species from the high-altitude montane grassland (inside and outside the PAs), Eco restoration of reed outbreak (Implementation) |  |  |  |  |  | Mapping of invasive species inside forested areas has been initiated. Tendering process also initiated to remove the exotics plantations based on the strategy developed for removal of exotic tree species |  |  |  |
|  | 3.3.6 Restoration of identified vulnerable and degraded forest areas (including shola/ grasslands segments within PAs and other degraded areas) (Implementation) |  |  |  |  |  | Initiated eco restoration activities around 20 ha of degraded forests ecosystems inside the Pampadumshola National Park. |  |  |  |
|  | 3.3.7Geospatial mapping of human – wildlife conflict areas |  |  |  |  |  | Mapping of the conflict areas using GPS in Marayoor and Munnar Forest Division has been initiated. |  |  |  |
|  | 3.3.12Training on Local Action Plan on Climate Change (LAPCC) and localisation of SDGs for EDCs and VSS Training workshops and support for livelihood-based skill development (supporting local youth in skill development through IWST courses) and eco-tourism |  |  |  |  |  | KILA developed methodology for LAPCC and consulted the same with resource persons; identified key stakeholders for training workshops |  |  |  |
|  | 3.4.1 Analysis of regeneration status and barriers of RET species |  |  |  |  |  |  |  |  |  |
| Output 3.4: Rare Endangered and Threatened (RET) ecosystems and endemic species are secured through improved conservation measures | 3.4.2 Establishment of nurseries in appropriate areas, with tie-up with micro-propagation facility and hardening |  |  |  |  |  | A shola nursery (temporary) has been established at Pampadumshola NP |  |  |  |
| Project Management Cost |  |  |  |  |  |  |  |  |  |  |
|  | Sub Total: |  |  |  |  |  |  |  |  |  |
|  | Project Management Expenses: |  |  |  |  |  |  |  |  |  |
|  | Grand Total: USD 70,000 |  |  |  |  |  |  |  |  |  |