Annual Project Report [Annual: September- December 2017]

United Nations Development Programme

Cambodia

UNited For Youth Employment in Cambodia

[1 September 2017- 31 August 2019]

28th December 2017

Project ID & Title: 00107509 – UNited For Youth Employment in Cambodia (UNJP) Duration: 1 September 2017 – 31 August 2019 Total Budget Phase I (1 Sep 2017-31 Aug 2019): USD 956,000 Implementing Partners/Responsible parties: UNDP Cambodia UNDAF OUTCOME 3: By 2018, national and subnational institutions are more transparent and accountable for key public-sector reforms and rule of law; are more responsive to the inequalities in enjoyment Output 3.1: The National Strategic Development Plan (NSDP) incorporates and localizes the post-2015 agenda and Sustainable Development Goals priorities ## Table of Contents

Table of   Contents	2

I.  Executive Summary	3

Progress towards project key deliverables/sub-output	5

Progress towards project/country programme (CPAP) output	12

Progress towards country programme (CPAP) outcome	14

Capacity Development	15

Gender Marker (GEN2)	16

Lessons Learned	16

III. Project Implementation Challenges (adding new issues/risks as relevant)	20

a.	Updated project risks and actions	20

b.	Updated project issues and actions	22

IV. Financial status and utilization	23

# Executive Summary

This report covers the period of the last four months of 2017, from September 1 to December 31, 2017. Although the project document was signed off by heads of participating UN agencies on 31 August 2017, the project was up in running in late October due to many holidays in September. The first meeting of UNJP project team to discuss on workplan, terms of reference of steering committee and consultative group was conducted on 26 Sep at ILO office. The first steering committee meeting to approve on the UNJP workplan and ToRs was held at the Ministry of Labor and Vocational Training on 17 Oct 2017.

In this joint program, UNDP will fund the research on the macroeconomic effect of investments for formal jobs and on investments in education and training packages for rural entrepreneurship; and it will use social network and multimedia platforms to help vulnerable youth pursue better employment opportunities.

UNDP has three major outputs to deliver before Aug 2018, mainly research on effect of investment in education and skill development and providing capacity and enabling factors for youth, employer and government to dialogue, cooperate, and participate in the promotion of decent youth employment and increase job opportunity for youth.

The first three months (Oct-Dec 2017) were strategic. As this is a joint program, it is important that synergy and value-added outputs are the core of our work of planning. Hence UNDP project team carefully conducted some exercises such as mapping, stakeholder analysis, building strategic partnership, consultation, and reviewing key national policies. In overall, the project team has done six main tasks: 1) finalizing terms of references for the two pieces of research, 2) finalizing grant proposals with YEAC and CDPO, 3) identifying capacity needs of NEA, YEAC and UNYAP, 4) updating youth works platform with Microsoft, 5) building partnership between YEAC, NEA and BBC MA to expand multimedia communication to reach out to youth to larger scale, and 6) drafting of UNJP-UNDP annual workplan.

The process of consultations with key stakeholders and partners has resulted in the finalization of the terms of reference of the two pieces of research and the grant proposals. The recruitment was announced publicly and shared with key networks and platforms. Two out of three grant proposals were submitted by Young Entrepreneur Association of Cambodia (YEAC), Cambodian People with Disability Organization (CDPO). YEAC is granted to provide services to youth on entrepreneurial skills, info related to SMEs and start up, and platforms for youth to meet employers for employability skills and policy issues related. While the grant with CDPO is to provide support to disabled people to increase their access to decent employments through evident based policy advocacy and multi stakeholders’ networks.

Before providing the capacity development to youth leaders in analyzing and debating policy issues in relation to youth employment and development - through various capacity building format and cross-country dialogues and networking, UNDP needs to conduct capacity need assessment. Through UN Youth Task Force, capacity needs of youth leaders (UNYAP) were identified. With these needs, UNDP will provide facilitation to ensure training workshops, policy dialogues and youth networks are co-designed and participated by key players (private, youth and government) and delivered.

A brief assessment on multimedia training needs was conducted with NEA. Trainings will be provided to NEA as soon as a trainer is defined and available.  NEA has an initiative to utilize their learnings from BBC trainings on multimedia approach to communicate audience. But they have limited capacity to write its initiative into a concept note.  UNDP project manager will work closely with NEA focal point to build this capacity.

The work with Microsoft to improve linkage of demand and supply sides on employment through online platform access has gradually progressed. The platform design (initial) is offered by Microsoft. The content elements and governance structure (roles and responsibility, names of agencies, potential partners) were drafted. Next step in Jan, Microsoft will provide a tour on the platform, a show and tell presentation. UNDP will coordinate with UNJP for this meeting.

On the multimedia approach to reach out youth on decent employment and entrepreneur, the project is working closely with BBC MA, YEAC and NEA for their partnership. In meantime, through Multimedia Initiative for Youth phase II (MIY) youth (urban and rural) were actively reached out through digital and non-digital activities including TV, bespoke digital content on Facebook and Klahan9 roadshows that have targeted some of the most marginalized groups. In 2017, a brand new TV format, Dream Station, a factual reality series show, was designed based on audience (youth) feedback from the first Klahan9 TV series.  Dream Station, is a 12-episode 60 minutes reality TV show in an observational-documentary style which is a completely new format for Cambodia. Each episode follows one person’s journey (the Dreamer) and we use experts and role models to highlight how soft skills – in particular, adaptability, communication, confidence, problem-solving, negotiation and planning - can support people to achieve their own dreams. To make the episodes relatable to a wide audience the ‘Dreamers’ in Dream Station come from a wide range of geographical, socio-economic, ethnic and educational backgrounds, and a variety of job sectors.

Finally, a detailed annual workplan and budget was drafted based on above results.

II. Progress Updates

## Progress towards project key deliverables/sub-output

| KEY DELIVERABLES/SUB-OUTPUT: Output 1.1: Conduct and disseminate macroeconomic effect of investment in education and skills development |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output Indicator | Baseline (2016) | Target by 2018 | Status |  |
| - Research report/s published - No of key stakeholders/institutions participating in event where research report and recommendations are presented | N/A | -Policy makers, private sector and development partners: 200 - individuals Young women and men, through dedicated dissemination effort: 1,200 | Recruitment Announcement was posted on UNDP website on 15 Dec. Deadline for application is 1 Jan. The consultancy period is 22 Jan-30 June 2018. |  |
| (Please include narrative of project progress against activities level): After desk review and consultations with key stakeholders including MoLVT, MoEYS, and YEAC, CAMFEBA, ILO, UNJP, the ToR is finally finalized. The recruitment was announced at UNDP website and shared with networks (TAC, UNJP, LinkedIn). It is hoped to get the person on board in late Jan 2018, finish the research in May, and present it in Jun 2018. |  |  |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

| KEY DELIVERABLES/SUB-OUTPUT: Output 2.1: Conduct and disseminate macroeconomic effect of investment in education and training packages for rural entrepreneurship |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output Indicators | Baseline (2016) | Target by 2018 | Status |  |
| - Research report/s published - No of key stakeholders/institutions participating in event where research report and recommendations are presented | N/A | Policy makers, private sector and development partners: 200 individuals and1,200 Youth | ToT was finalized in Dec 2017 and will be posted on UNDP website and shared with networks. The consultancy period is 5 Feb-30 June 2018. |  |
| (Please include narrative of project progress against activities level): After desk review and consultations with key stakeholders incl MoLVT, MoEYS, and YEAC, CAMFEBA, ILO, UNJP, the ToR is finally finalized. The recruitment will be announced at UNDP website and shared with networks (TAC, UNJP, LinkedIn). It is hoped to get the person on board in early Feb 2018 and finish the research in May, present it in Jun 2018. |  |  |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

| KEY DELIVERABLES/SUB-OUTPUT: Output 3.3: Unemployed and vulnerably employed youth are better informed about their rights and employment prospects Output 3.3.1: Capacity to NEA on the use of multi-media approach to address youth employment issue and reach out to diversity young people. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output Indicators | Baseline (2016) | Target by 2018 | Status |  |
| - No of vulnerable youth including young migrants' and domestic workers' associations trained or reached by awareness campaigns. - Increased knowledge of rights at work among participants in training - # of audience reached by multimedia platform (metrics platform) | Project records on beneficiaries reached Comparison start of training survey/ End-of-training survey/evaluation | -Working with Youth Centres, 600 youth for year 1, and 600 youth for year 2 through 25 Youth Centers. A further 500 youth/year through Trade Unions TV episodes: audience reached around 1.5 million youth | In the process to define trainers |  |
| (Please include narrative of project progress against activities level): A brief assessment on multimedia training needs was conducted with NEA. Trainings will be provided to NEA as soon as a trainer is defined and available. |  |  |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

| KEY DELIVERABLES/SUB-OUTPUT: Output 3.3: Unemployed and vulnerably employed youth are better informed about their rights and employment prospects Output 3.3.2: Support NEA to pilot an initiative using acquired skills from multi-media training |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output Indicators | Baseline (2016) | Target by 2018 | Status |  |
| - No of vulnerable youth including young migrants' and domestic workers' associations trained or reached by awareness campaigns. - Increased knowledge of rights at work among participants in training - # of audience reached by multimedia platform (metrics platform) | Project records on beneficiaries reached Comparison start of training survey/ End-of-training survey/evaluation | -Working with Youth Centres, 600 youth for year 1, and 600 youth for year 2 through 25 Youth Centers. A further 500 youth/year through Trade Unions TV episodes: audience reached around 1.5 million youth | NEA is developing a concept note. |  |
| (Please include narrative of project progress against activities level): NEA has an initiative to utilize their learnings from BBC trainings on multimedia approach to communicate audience. But they have limited capacity to write its initiative into a concept note. UNDP project manager will work closely with NEA focal point to build this capacity. |  |  |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

| KEY DELIVERABLES/SUB-OUTPUT: Output 3.3: Unemployed and vulnerably employed youth are better informed about their rights and employment prospects Output 3.3.3: Expand multi-media platforms which driven by youth to enable broader engagement of young people to promote access to information on decent jobs. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output Indicators | Baseline (2016) | Target by 2018 | Status |  |
| - No of vulnerable youth including young migrants' and domestic workers' associations trained or reached by awareness campaigns. - Increased knowledge of rights at work among participants in training - # of audience reached by multimedia platform (metrics platform) | Project records on beneficiaries reached Comparison start of training survey/ End-of-training survey/evaluation | -Working with Youth Centres, 600 youth for year 1, and 600 youth for year 2 through 25 Youth Centers. A further 500 youth/year through Trade Unions TV episodes: audience reached around 1.5 million youth | Working closely with BBC MA, YEAC and NEA for their partnership to scale up. |  |
| (Please include narrative of project progress against activities level): In meantime, through Multimedia Initiative for Youth phase II (MIY) youth (urban and rural) were actively reached out through digital and non-digital activities including TV, bespoke digital content on Facebook and Klahan9 roadshows that have targeted some of the most marginalized groups. In 2017, a brand new TV format, Dream Station, a factual reality series show, was designed based on audience (youth) feedback from the first Klahan9 TV series. Dream Station, is a 12-episode 60 minutes reality TV show in an observational-documentary style which is a completely new format for Cambodia. Each episode follows one person’s journey (the Dreamer) and we use experts and role models to highlight how soft skills – in particular, adaptability, communication, confidence, problem-solving, negotiation and planning - can support people to achieve their own dreams. To make the episodes relatable to a wide audience the ‘Dreamers’ in Dream Station come from a wide range of geographical, socio-economic, ethnic and educational backgrounds, and a variety of job sectors. |  |  |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

| KEY DELIVERABLES/SUB-OUTPUT: Output 3.3: Unemployed and vulnerably employed youth are better informed about their rights and employment prospects Output 3.3.4: Strengthen the capacity of youth leaders in analyzing and debating policy issues in relation to youth employment and development - through various capacity building format and cross-country dialogues and networking. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output Indicators | Baseline (2016) | Target by 2018 | Status |  |
| - No of vulnerable youth including young migrants' and domestic workers' associations trained or reached by awareness campaigns. - Increased knowledge of rights at work among participants in training - # of audience reached by multimedia platform (metrics platform) | Project records on beneficiaries reached Comparison start of training survey/ End-of-training survey/evaluation | -Working with Youth Centres, 600 youth for year 1, and 600 youth for year 2 through 25 Youth Centers. A further 500 youth/year through Trade Unions TV episodes: audience reached around 1.5 million youth | Identified youth and needs for trainings |  |
| (Please include narrative of project progress against activities level): Before providing the capacity development to youth leaders in analyzing and debating policy issues in relation to youth employment and development - through various capacity building format and cross-country dialogues and networking, UNDP needs to conduct capacity need assessment. Through UN Youth Task Force, capacity needs of youth leaders (UNYAP) were identified. With these needs, UNDP will provide facilitation to ensure training workshops, policy dialogues and youth networks are co-designed and participated by key players (private, youth and government) and delivered. |  |  |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

| KEY DELIVERABLES/SUB-OUTPUT: Output 3.3: Unemployed and vulnerably employed youth are better informed about their rights and employment prospects Output 3.3.5: Conduct evidence-based youth advocacy in various campaign formats on key policy issues which are strategic to youth employment. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output Indicators | Baseline (2016) | Target by 2018 | Status |  |
| - No of vulnerable youth including young migrants' and domestic workers' associations trained or reached by awareness campaigns. - Increased knowledge of rights at work among participants in training - # of audience reached by multimedia platform (metrics platform) | Project records on beneficiaries reached Comparison start of training survey/ End-of-training survey/evaluation | -Working with Youth Centres, 600 youth for year 1, and 600 youth for year 2 through 25 Youth Centers. A further 500 youth/year through Trade Unions TV episodes: audience reached around 1.5 million youth | Not yet started, will do further study in Q2-Q3 2018. |  |
| (Please include narrative of project progress against activities level): |  |  |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

| KEY DELIVERABLES/SUB-OUTPUT: Output 3.3: Unemployed and vulnerably employed youth are better informed about their rights and employment prospects Output 3.3.6: Improve linkage of demand side and supply side on employment through online platform access. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output Indicators | Baseline (2016) | Target by 2018 | Status |  |
| - No of vulnerable youth including young migrants' and domestic workers' associations trained or reached by awareness campaigns. - Increased knowledge of rights at work among participants in training - # of audience reached by multimedia platform (metrics platform) | Project records on beneficiaries reached Comparison start of training survey/ End-of-training survey/evaluation | -Working with Youth Centres, 600 youth for year 1, and 600 youth for year 2 through 25 Youth Centers. A further 500 youth/year through Trade Unions TV episodes: audience reached around 1.5 million youth | In progress. |  |
| (Please include narrative of project progress against activities level): The work with Microsoft to improve linkage of demand and supply sides on employment through online platform access has gradually progressed. The platform design (initial) is offered by Microsoft. The content elements and governance structure (roles and responsibility, names of agencies, potential partners) were drafted. Next step in Jan, Microsoft will provide a tour on the platform, a show and tell presentation. UNDP will coordinate with UNJP for this meeting. |  |  |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

| KEY DELIVERABLES/SUB-OUTPUT: Output 3.3: Unemployed and vulnerably employed youth are better informed about their rights and employment prospects Output 3.3.7: Support access to employment of disabled people (employment hub, research, and database). |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output Indicators | Baseline (2016) | Target by 2018 | Status |  |
| - No of vulnerable youth including young migrants' and domestic workers' associations trained or reached by awareness campaigns. - Increased knowledge of rights at work among participants in training - # of audience reached by multimedia platform (metrics platform) | Project records on beneficiaries reached Comparison start of training survey/ End-of-training survey/evaluation | -Working with Youth Centres, 600 youth for year 1, and 600 youth for year 2 through 25 Youth Centers. A further 500 youth/year through Trade Unions TV episodes: audience reached around 1.5 million youth | In progress. CDPO is finalizing concept note. |  |
| (Please include narrative of project progress against activities level): |  |  |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

## Progress towards project/country programme (CPAP) output

| Outcome 1: Young women and men access quality formal and non-formal education including volunteerism to develop relevant technical and vocational skills |  |  |  |
| --- | --- | --- | --- |
| Output Indicators | Baseline (2016) | Target (2018) | Current status |
| - No of government initiatives to strengthen education and skills training - % / # of education providers certified according to national competency, ASEAN and industry standards and providing youth-targeted training - # of young women and men enrolled in labour market or volunteering programmes targeting employability - #/% of out-of-schools adolescents enrolled in Basic Education Equivalency programme | MoE records / survey UNV records |  | Started but exact figure and qualitative evidences will be provided and updated in June and Dec 2018. |
| Will have more to report in June 2018 as the research will have been conducted and report will have been produced by then. |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

| Outcome 2: Young women and men, both in-school and out-of-school, are equipped with adequate entrepreneurial and business skills to create and develop sustainable enterprises |  |  |  |
| --- | --- | --- | --- |
| Output Indicators 2.1.1 | Baseline (2016) | Target (2018) | Current status |
| - No of government initiatives to develop sustainable enterprises - # of certified business training providers providing youth-specific training programme - #/% of young women and men who received tested/assessed/certified entrepreneurial and business skills - % of those trained initiating/starting business enterprises. | Business Registry Perception study with association of young entrepreneurs Survey |  | Started but exact figure and qualitative evidences will be provided and updated in June and Dec 2018. |
| Will have more to report in June 2018 as the research will have been conducted and report will have been produced by then. |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

| Outcome 3: Young women and men benefit from a better condition and fair treatment at work |  |  |  |
| --- | --- | --- | --- |
| Output Indicators 2.1.1 | Baseline (2016) | Target (2018) | Current status |
| - No of government initiatives to strengthen awareness and protection of rights at work | Survey Labour inspectorate data Programme data |  | Started but exact figure and qualitative evidences will be provided and updated in June and Dec 2018. |
| Will have more to report in June 2018 and Dec 2018 as the grant agreements would have been signed off in Feb, project activity annual workplan would have been reviewed and approved in Feb and majority of the project outputs would have been delivered by then. |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

## Progress towards country programme (CPAP) outcome

| UNDAF OUTCOME 3: By 2018, national and subnational institutions are more transparent and accountable for key public-sector reforms and rule of law; are more responsive to the inequalities in enjoyment Output 3.1: The National Strategic Development Plan (NSDP) incorporates and localizes the post-2015 agenda and Sustainable Development Goals priorities |  |  |  |
| --- | --- | --- | --- |
| Indicators | Baseline (year 2015) | Target (year) | Current status (Dec/2017) |
| Measures taken by government to increase foreign direct investment, skill upgrading and value chain: the extent to which policy and institutional mechanisms in place are effective to increase - foreign direct investment in sectors with potential for value addition, - skills upgrading, and - decent employment measured as a 3 point scale (1= not effective to 3 = effective) | Baseline (2015): Not effective (1) | Target (2018): Effective (3) | Started but exact figure and qualitative evidences will be provided and updated in June and Dec 2018. |
| Will have more to report in June 2018 and Dec 2018 as the grant agreements would have been signed off in Feb, project activity annual workplan would have been reviewed and approved in Feb and majority of the project outputs would have been delivered by then. |  |  |  |
| delivery exceeds plan | delivery in line with plan |  | delivery below plan |

# Capacity Development

After meetings during the process of giving a grant, NEA expressed their issue of writing a concept note as this is their first time. So a few meetings were set up to provide some samples, guidance and explanations on process (desk review, issue analysis, logical framework, workplan, budgeting) of writing a concept.  Capacity development to NEA in writing a concept note.

# Gender Marker (GEN2)

In this planning period, it was communicated clearly to the implementing partners on the requirements in gender disaggregation and inclusion when planning (audience targeting) and reporting.

# Lessons Learned

It consumed a lot of time meetings, consultations, and reviews and analysis before approaching a research, partner, and developing a plan as this project is a five UN agencies joint program, assuring synergy among agencies is essential but most importantly, exploring for creative policy solutions that are impactful is something that UNDP as a leading UN agency in policy advisory to the government strives for.

# III. Project Implementation Challenges (adding new issues/risks as relevant)

## Updated project risks and actions

1. Influence of Coming National Election: restriction of any gatherings above 10 people, participation rate can be less than expected

Status: medium risk

The possible tension before and after the election can delay the project activities. The project can be prevented from organising any youth gathering of more than 10 people. There is opportunity that government participation in the project can be increased or decreased due to political interest. Number of participants can be less than expected if the tension becomes tighter.

Action Taken:

The project has taken notes on the critical period (three months before and three months after the election day). So in the planning it was ensured that there would not have any heavily participated activities or large gathering during this period. Core works of the outputs such as data gathering, consultations, dialogues, policy discussions, and training assessments are done three months before election. Delivery of trainings, research reports, conference and networking will be in late 2018 if situation allows.

2. Acceptance of research findings and policy recommendation by MoLVT and MoEYS

Status: low risk

The two pieces of national research on education and TVET are being conducted by UNDP. MoLVT and MoEYS may possibly not accept findings or make use of findings for their policy reform and advocacy if they are not consulted throughout the process of research.

Action Taken:

Having well noted of this crucial point, the project has consulted with these ministries. In addition, as this research is not only beneficial to the government but also to private sector and youth, the project has discussed it with representatives such as YEAC, UNJP, and Technical Advisory Committee of Youth employment which is attended by youth organisations and developing partners.

3. Capacity constraint of Implementing Partners: YEAC and NEA

Status: low risk

This is the first time that both YEAC and NEA receive a grant from UN. After going through forms internally (risk, capacity, due diligence clearance) and having several meetings with NEA and YEAC, it was found that they obtained most of required policy and resources, except for three main issues: staff mobilisation, a few policies and strategic planning.

Action taken:

Taking note of this risk, the project has worked closely with the partners NEA and YEAC to address staffing needs and internal policies by providing some policy samples to create ones of their own, and connect YEAC and NEA to volunteer organisations (UNV, VolCam).  In terms of strategic planning, UNDP project team will have a few more meetings with them to review the workplans and ensure that a new integrated workplan that is responsive (to organisational capacity and project objectives) and realistic (budget and timewise) for delivery is developed.   In addition, as soon as the grant and LoA are signed, UNDP project team will coordinate for an orientation to NEA and YEAC on rules and requirements of UNDP that they are expected to be compliant with.

Updated project issues and actions

IV. Financial Status and Utilization

Table 1: Contribution Overview [01 September 2017 to 31 August 2018]

| DONOR NAME | YEAR | CONTRIBUTIONS |  | BALANCE |
| --- | --- | --- | --- | --- |
|  |  | COMMITTED | RECEIVED |  |
| ILO (Fund:30000- Donor:00003) | Sept 2017 - Aug 2018 | $ 160,075.00 | $ 160,075.00 |  |
| TOTAL |  | $ 160,075.00 | $ 160,075.00 | $ - |

Table 1.1: Funding Balance [01 September – 31 December 2017]

| DONOR NAME | ACTUAL FUND RECEIVED | Expensed | BALANCE | (%) |
| --- | --- | --- | --- | --- |
|  |  | 2017 (Sept-Dec) |  |  |
| ILO (Fund:30000- Donor:00003) | 160,075.00 | 219.35 | 159,855.65 | 100% |
| Total | 160,075.00 | 219.35 | 159,855.65 | 100% |

| Table 2: 2017 Expenditure by Activities [01 September – 31 December 2017] |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACTIVITY | SDC |  |  |  | UNDP- Parallel |  |  |  |
|  | APPROVED BUDGET | Expenditure 2017 (Sept-Dec) | BALANCE December 2017 | DELIVERY (%) | APPROVED BUDGET | Expenditure 2017 (Sept-Dec) | BALANCE December 2017 | DELIVERY (%) |
| Outcome 1: Young women and men access quality formal and non-formal education including volunteerism to develop relevant technical and vocational skill |  |  |  |  |  |  |  |  |
| 1.1 Research on the macroeconomic effect of investment in education and skills development produced and disseminated | $ 14,953.00 | $ 219.35 | $ 14,733.65 | 1% | $ 36,000.00 |  | $ 36,000.00 | 0% |
|  Develop Consultancy ToR and research concept note |  |  |  |  |  |  |  |  |
|  Recruit research/education institution |  |  |  |  |  |  |  |  |
|  Contract a research/education institution |  |  |  |  |  |  |  |  |
|  Work closely with research/education institution to conduct the research incl. work planning and template of report |  |  |  |  |  |  |  |  |
| Consult the draft report (policy paper) with stakeholders |  |  |  |  |  |  |  |  |
|  Work closely with research/education institution to finalise the report (policy paper) |  |  |  |  |  |  |  |  |
| Work closely with research/education institution to run a dissemination workshop for 90 participants (youth and stakeholders) with lunch provided |  |  |  |  |  |  |  |  |
| Outcome 2: Young women and men, both in-school and out-of-school, are equipped with adequate entrepreneurial and business skills to create and develop sustainable enterprises |  |  |  |  |  |  |  |  |
| 2.1 Research produced and disseminated on the macroeconomic effect of investment in education and training packages for rural entrepreneurship | $ 28,972.00 |  | $ 28,972.00 | 0% | $ 14,000.00 |  | $ 14,000.00 | 0% |
|  Develop Consultancy ToR and research concept note |  |  |  |  |  |  |  |  |
|  Recruit research/education institution |  |  |  |  |  |  |  |  |
|  Contract a research/education institution |  |  |  |  |  |  |  |  |
|  Work closely with research/education institution to conduct the research incl. work planning and template of report |  |  |  |  |  |  |  |  |
|  Consult the draft report (policy paper) with stakeholders |  |  |  |  |  |  |  |  |
|  Work closely with research/education institution to finalise the report (policy paper) |  |  |  |  |  |  |  |  |
|  Work closely with research/education institution to run a dissemination workshop for 90 participants (youth and stakeholders) with lunch provided |  |  |  |  |  |  |  |  |
| 3.3 Unemployed and vulnerably employed youth are better informed about their rights and employment prospects | $ 116,150.00 |  | $ 116,150.00 | 0% | $ 307,500.00 | $ 47,320.49 | $ 260,179.51 | 15.39% |
|  Capacity development to National Employment Agency (NEA) on the use of multi-media approach to address youth employment issue and reach out to diversity young people. |  |  |  |  |  |  |  |  |
|  Grant to National Employment Agency (NEA) to pilot an initiative using acquired skills from multi-media training. |  |  |  |  |  |  |  |  |
|  Expand multi-media platforms which driven by youth to enable broader engagement of young people to promote access to information on decent jobs. |  |  |  |  |  |  |  |  |
|  Strengthen the capacity of youth leaders in analyzing and debating policy issues in relation to youth employment and development - through various capacity building format and cross-country dialogues and networking |  |  |  |  |  |  |  |  |
|  Conduct evidence-based youth advocacy in various campaign formats on key policy issues which are strategic to youth employment |  |  |  |  |  |  |  |  |
|  Improve linkage of demand side and supply side on employment through online platform access |  |  |  |  |  |  |  |  |
|  Support access to employment of disabled people |  |  |  |  |  |  |  |  |
| TOTAL | $ 160,075.00 | $ 219.35 | $ 159,855.65 | 0% | $ 357,500.00 | $ 47,320.49 | $ 310,179.51 | 13.23% |