Project Title: Being LGBTI in the Caribbean: Reducing Inequality & Exclusion Experienced by LGBTI People

Project Number: 00106385

Implementing Partner: UNDP Country Office in Barbados, Dominican Republic, Haiti and Jamaica

Start Date: Oct 2017	       End Date: Sept 2019	           PAC Meeting date: 11 December 2017

Brief Description

The Project is a partnership between UNDP and USAID which builds on the lessons-learned from the UNDP and USAID initiative Being LGBT in Asia. The project aims to enhance knowledge, partnerships, and capacities of LGBTI communities, civil society and States to reduce human rights violations and negative attitudes towards LGBTI people in the Caribbean, with country level focus in Barbados, Dominican Republic, Haiti and Jamaica, as well as regional activities The project will seek to increase access to justice for LGBTI persons, through the implementation of LGBTI inclusive public policies; increased representation of LGBTI in national and regional fora; and by addressing stigma and discrimination..

Contributing Outcome (RPD):

Outcome 2: Citizens expectations for voice, effective development, the rule of law and accountability are met by stronger systems of democratic governance; (GEN 3)

Output 2.3: National institutions, systems, laws and policies strengthened for equitable, accountable and effective delivery of HIV and related services; (GEN 3)

SP Output 3.3: Strengthened (country, regional and global) capacity for equitable, accountable and effective delivery of HIV and related services; (GEN 3)

| Total resources required: | 999,879.00 |  |
| --- | --- | --- |
| Total resources allocated: |  |  |
|  | UNDP TRAC: |  |
|  | Donor: | 999,879.00 |
|  | Government: |  |
|  | In-Kind: |  |
| Unfunded: |  |  |

Agreed by (signatures):

| UNDP Regional Bureau for Latin America and the Caribbean (RBLAC) | UNDP Regional Hub for Latin America and the Caribbean |
| --- | --- |
| Jessica Faieta UN Assistant Secretary-General & Director, Regional Bureau for Latin America and the Caribbean | Richard Barathe Regional Hub Director Bureau for Latin America and the Caribbean |
| Date: |  |

# I 	Development Challenge

The Global Context

Over the past two decades, the global movement of lesbian, gay, bisexual, transgender and intersex (LGBTI) people has achieved impressive results in contesting discrimination and violence on the basis of sexual orientation and gender identity.  As of May 2017, 124 States, have no legal penalties for consenting same-sex adult sexual activity. There are currently 22 States in the world that recognise and provide for same-sex marriage and 28 States that protects partnership relationships, joint adoption by same sex couples is permitted in 26 States.    Progress has been significantly slower, however, with regards to legal recognition of gender identity for transgender persons and protection from violence and discrimination on the basis of gender identity and expression.   In the case of intersex people only two countries, Malta and Chile, ban surgeries and treatment of intersex people without their consent.

In spite of these and related positive developments, there remains much work to be done to guarantee equality of LGBTI people under the law and ensure protection from violence and discrimination as well as equal access to services.  Currently there are 72 States where same-sex sexual relations are outlawed and in 45 of these States (24 in Africa, 13, in Asia, six in the Americas and two in Oceania) the law is applied to women as well as men.  In nine countries and territories same sex acts could lead to the death penalty. LGBT persons often face persecution because of vaguely worded laws on "crimes against the order of nature", "morality", "debauchery", "indecent acts" or "grave scandal". Even in countries that have basic legal protections in place, LGBTI people continue to face discrimination and violence.

The punitive laws and practices have a critical impact on the enjoyment of human rights, health as well as on social and economic development more broadly. Punitive laws contribute to pervasive stigma and discrimination, as well as hate crime, police abuse, torture and ill-treatment, and family and community violence. Limited protection from the law also results in widespread violence against LGBT people both from the authorities and the community at large. Even in cases where some action on violence against LGBTI is taken by authorities, this is often inadequate, resulting in under-reporting and under-investigation.

The UN human rights system has expressed its concern at the extent and gravity of human rights violations perpetrated against individuals based on their sexual orientation and gender identity. This has resulted in the passing of two important resolutions pertaining to the rights of LGBTI persons. In June 2011, the UN Human Rights Council passed the first resolution adopted by any UN body addressing human rights violations based on sexual orientation and gender identity. The resolution requested the High Commissioner for Human Rights to prepare a study on discrimination and violence against individuals based on their sexual orientation and gender identity. The High Commissioner’s study, the first official UN report to address these issues, was issued in December 2011 and presented to the Council in March 2012.   It was followed in September 2014 by a second UN resolution to combat violence and discrimination based on sexual orientation and gender identity, which also requested an update report.  The September 2014 resolution saw an increased base of support since the June 2011 resolution, from all regions.  Both reports by the High Commissioner found evidence of a pattern of violence and discriminatory laws and practices affecting LGBTI people in all regions and included detailed recommendations to Member States.

After the successful adoption of resolution 32/2 of the Human Rights Council in June of 2016, in September of the same year, Professor Vitit Muntarbhorn was appointed as the first Independent Expert on protection against violence and discrimination based on sexual orientation and gender identity. While this appointment was repeatedly challenged by some states in the various organs of the General Assembly including the Third Committee, the Fifth Committee and the plenary of the General Assembly the victory in the final vote on December 23rd, 2016, confirmed a dedicated mechanism of the United Nations devoted to documenting and responding to the human rights violations committed against persons on grounds of sexual orientation and gender identity in every country around the world.

These resolutions and statements are reinforced by political statements from top leadership of the UN – including former Secretary-General Ban Ki-moon who highlighted the connection between the Sustainable Development Goals (SDGs) and efforts to achieve greater equality for members of the LGBTI community, noting that “ending marginalization and exclusion of LGBTI people is a human rights priority and a development imperative”. The 2030 Agenda for Sustainable development agenda also includes important provisions to advance the rights of LGBT persons. Equality and inclusion for LGBTI persons are integral to the achievement of healthy lives and well-being for all at all ages (SDG 3), as well as promoting peaceful and inclusive societies, justice for all and effective, accountable and inclusive institutions at all levels (SDG 16).  In September 2015, 12 UN entities issued a joint statement calling on States to act urgently to end violence and discrimination against lesbian, gay, bisexual, transgender and intersex (LGBTI)1 adults, adolescents and children.

The Caribbean Context

Even with some progress in recent years respect for the human rights of LGBTI persons remain largely absent in the Caribbean region.   Many Caribbean countries still criminalize same sex relations resulting in pervasive stigma, discrimination and violence. Violations of civil and political, as well as economic, social and cultural rights continue.

Ten Caribbean countries have discriminatory laws against same-sex sexual acts. In Jamaica, the 1864 Offences against the Person Act, calls for a penalty of up to 10 years of imprisonment for those convicted of the “abominable crime of buggery.  Although these laws tend not to be enforced, their existence is used to harass and threaten LGBT people, and they contribute to an environment that condones discrimination, stigma and violence.

Accounts of human rights offenses against members of the LGBTI community in the Caribbean include violence and abuse from private citizens and government officials. For example, in 2016 young gay men visiting public parks were arrested and jailed, without charges, because of their sexual orientation in two prominent cities in the Dominican Republic (DR).  In September 2016, organizers were forced to cancel the first LGBTI cultural and film festival in Port-au-Prince, Haiti following criticisms by Haitian government officials and threats of violence. In 2013 a Jamaican transgender teenager was beaten, stabbed, shot and her body run over with a car for attending a party in feminine attire.  Worryingly, similar accounts exist throughout the Caribbean.

The legal, social and economic barriers the LGBTI community faces in the Caribbean serves to marginalize the community and prevent them from equally benefiting from development. In addition to laws on the books criminalizing LGBTI people in some way, homophobia and transphobia are manifested in a range of ways in the region, including violations of basic rights to identity, health, education, work, safety and housing. Moreover, LGBTI people too often are excluded from legal protections, rejected by families and communities and lack equal treatment in schools, workplaces, health care settings and the streets.

While the political environment in many parts of the Caribbean remains challenging with regards to the protection of the rights of LGBTI people, there are also positive development such as when the Anti-Sodomy law was judicially struck down in 2016 in the Caleb Orozco v. Attorney General of Belize. In 2016 the Aruban parliament passed an amendment to the Civil Code including the option of registered partnerships for both same-sex and opposite-sex couples granting similar rights and responsibilities as marriage contracts.

Of the four countries that will form part of this project, the Dominican Republic is the only country that does not prohibit consensual sex between same sex adults.  While the Criminal Code does not address discrimination based on sexual orientation or gender identity a few articles of Dominican law explicitly protect LGBTI person under specific conditions. These include Article 2 of the General Youth Law of 2000 that prohibits discrimination based on sexual orientation and Article 11 of the Code of Criminal Procedure of 2007, that established that all people are equal before the law regardless of their sexual orientation. Since 2011, the Law on HIV/AIDS prohibits discrimination on the basis of sexual orientation and gender identity.  Discrimination based on sexual orientation or gender identity is however not illegal in areas such as employment, education, housing, and health and as a result, many LGBTI continue to report that discrimination remains widespread.

While Haiti’s Constitution does include specific protection against discrimination of LGBTI persons the country does not have any laws that criminalize consensual same-sex conduct between adults. Nonetheless, there are reports of discrimination in various aspects of daily life including, denial to housing, health care, education, or employment as well as violence based on sexual orientation or gender identity. Same-sex marriage is not legal in Haiti, and advocates who lobby for that right are consistently met with public resistance and political backlash.

In Barbados, Section 9 of the country’s Sexual Offences Act of 2002, while rarely enforced, mandates one of the harshest sentences, life imprisonment for anal intercourse. In addition, Section 12 of the same Act also includes a law against “serious indecency,” which seems to criminalize all forms of same-gender intimacy including lesbian intimacy. In 2014 Barbados and St Lucia rejected attempts to create protections for LGBT individuals refusing to join the consensus on approval of an OAS resolution on sexual orientation.  The resolution condemns “all forms of discrimination against persons by reason of their sexual orientation and gender identity or expression” and call on member states “to eliminate, where they exist, barriers faced by lesbian, gay, bisexual, trans, and intersex (LGBTI) persons in equal access to political participation and in other areas of public life, and to avoid interferences in their private life.”

At the national level, the Jamaica Offences Against the Person Act, more commonly referred to as the “buggery law” has been widely discussed as have been the many acts of violence and intimidation faced by LGBTI persons. Discrimination in areas such as employment, housing and educations are not as well documented. A study by the Jamaica Forum for Lesbians, All-Sexuals and Gays (J-FLAG), reported that between 2009 and 2012, a total number 231 reports of discrimination and violence based on gender identity and sexual orientation had been filed.

The slow pace of legal reform in most Caribbean countries, is also mirrored in level of acceptance regarding the rights of LGBTI persons. Action is needed on legal reform but also in working with different sectors, a whole of government response, to ensure that LGBTI individuals can participate freely at all levels of their communities.

# Strategy

Theory of Change

The project is grounded in a theory of change that supports a multi-faceted approach to evidenced based data gathering on the human rights of LGBTI persons, to ensure strategic follow-up actions can be taken by key stakeholders. Leveraging of UNDP’s position as a convener to facilitate the engagement of a range of partners in government, the private sector, development partners and civil society organisations are also critical success factors to the project. To address the development challenge identified for the Caribbean region, the project aims to reduce inequality and exclusion experienced by LGBTI persons allowing individuals, activists, and civil society organizations (CSOs) within the selected countries to exercise their rights as equal members of society and effectively advocate for improved social change.

The desired change that the project expects to achieve is to advance LGBTI inclusive development in selected countries in the region. Key solutions to achieve this change is to strengthen data/evidence base on the rights of LGBTI people and enhance the capacity of governments, civil society and LGBTI groups to address and reduce inequality, exclusion, violence and discrimination experienced by LGBTI persons. The project will increase awareness of homophobic and transphobic violence and discrimination and strengthen the capacity of civil society organizations to challenge negative attitudes towards LGBTI people including through engaging government officials, parliamentarians, political parties, trade unions, religious leaders, civil society, media, and the general population.

Solution Pathway Diagram

Theory of Change for Being LGBTI in the Caribbean

Proposed Approach

The project provides a process to stimulate dialogue among key national and draws on examples from similar regional initiatives in Asia and the Balkans; it deliberately seeks to include the LGBTI representation in national policy for a through proactively enhancing the political participation of this historically marginalised group in the Caribbean.

The project will rely extensively on the HHD team’s experience in human rights, health, gender and sexual minorities, as well as extensive network civil society contacts. The project will leverage partnerships with regional networks such as the Caribbean Forum for Liberation and Acceptance of Genders and Sexualities (CariFLAGS); the Caribbean Vulnerable Communities Coalition (CVC); Centro de Orientación e Investigación Integral (COIN) and the Eastern Caribbean Alliance for Diversity and Equality (ECADE) who are key partners in the fight against homophobia and transphobia and end discrimination based on sexual orientation and gender identity.

At the national level, the project will strengthen partnerships between government and CSOs to improve dialogue on human rights of LGBTI persons and to address widening inequality. The project will consider access to education, employment, health including HIV prevention and treatment services, as well as to broader social services. Project activities will include:

Project civil society partners identified (at least one per country) and assessed through rapid assessment for capacity and capacity needs. Recommendations for improvement will be discussed and implemented as appropriate, resulting in:

- Increased information and data available to all stakeholders on the rights of LGBTI persons and inclusion in the selected four countries.

- “Being LGBTI in…” reports available for all four countries,

- Partnership opportunities between various stakeholders identified during national roundtables and the sub-regional dialogue and documented.

- Collaboration and dialogue between LGBTI civil society organisations, government, parliamentarians, political parties, trade unions and religious leaders initiated for each of the four selected countries.

At the regional level, the project aims to share lessons across the four countries to identify common challenges, share good practices and procure political support from supra-national stakeholders.  Regional research such as the Intersex Baseline Assessment will contribute to the knowledge base and orient evidence-based decision-making processes.

Project activities will include:

- Common challenges and opportunities for advancing LGBTI rights and inclusion documented. Good practices for regional and cross-regional collaboration produced.

- Sub-regional collaboration initiated. Inter-Caribbean Network of LGBTI organizations and individuals established.

- Eastern Caribbean countries benefiting from the sub-regional dialogue and resources created by the project.

- Factsheets, infographics and social media macros produced audiences from the project countries and regional organizations in mind.

# Results and Partnerships

Expected Results

In response to the needs and priority areas identified, the project will provide a process to strengthen the inclusion of LGBTI priorities in development through consolidation of best practices, knowledge transfer for targeted solutions, and concrete actions in target countries. In doing so, the project will strengthen LGBTI participation and representation to foster local CSO capacity and knowledge exchanges between Caribbean countries and enhance advocacy for investing in and sustaining LGBTI inclusive public policies.

The project principal objective is to “Reduce inequality and exclusion experienced by LGBTI persons” and will contribute to UNDP Strategic Plan 2014-2017, Outcome 3 “Countries have strengthened institutions to progressively deliver universal access to basic services.”, especially to Output 3.3. “Strengthened (country, regional and global) capacity for equitable, accountable and effective delivery of HIV and related services”.

The project will be achieved through three expected project results:

- Knowledge, strategic information and evidence on the impact of inequality and exclusion of LGBTI people developed and disseminated.

Activities under this result will aim to produce new knowledge and awareness of LGBTI inequality and inclusion in the four project countries, ‘Being LGBTI in…’ reports will be produced for each country, combining information from the national assessments and the outcomes of the Roundtables.  These reports will aim to outline topics of common agreement and opportunities for joint actions between government and civil society (“low hanging fruits”), as well as topics for further dialogue and advocacy. In addition, an assessment that will map policies and guidelines that govern the treatment of intersex persons in the region will be completed.  The assessment will inform advocacy efforts calling for the suspension of unnecessary normalization treatments for intersex children and adults, including irreversible surgery, without their consent.  A Communication Strategy will be developed to effectively communicate the results of the project as well as to strengthen the advocacy components of the project.

- Support meaningful engagement of governments in the selected countries through national and regional policy dialogues.

This result will be achieved through targeted interventions to engage governments and raise their awareness of the challenges faced by LGBTI people and of the benefits of an inclusive approach to development.  Such interventions will include evidence based National Dialogues inclusive of governments, CSOs and development partners.  A Regional Dialogue will be organised to share lessons across countries and gain political support to integrate human rights and programming to address legal and policy barriers.

- Capacity of LGBTI Community groups developed through enhanced coordination, increased access to existing tools, transfer of knowledge and concrete actions to address stigma and discrimination

Under this result the project will focus on engaging LGBTI civil society organisations, to facilitate their access to opportunities and skills to exercise their political rights, participate in decision-making, exercise leadership, and contribute to public policy and political processes. Capacity building support to national LGBTI organisations as well as small grants to support LGBTI CSOs to support the implementation of identified priorities will form part of the strategic initiatives to achieve this result.

These results will be achieved through efficient coordination between the UNDP Regional Hub and Country Offices, as well with USAID Country Missions. Key stakeholders and target group per country, including, Government Ministries, and LGBTI civil society organisations will be involved in implementing priority concrete actions as per country needs.

Resources Required to Achieve the Expected Results

The Project investment is primarily in human and institutional resources that can offer tools and technical and policy support. These include:

- UNDP Staff that includes UNDP Regional Hub and COs teams, for project coordination and implementation.

- Key national and community stakeholders in each country, including national LGBTI CSOs, relevant government partners,

- The HHD Team Legal Advisor will provide technical support in the areas of human rights and legal environments.

- Financial and logistics related tasks will be handled by a Programme Assistant in the regional team

- The Regional Team Leader will supervise this team, with cross-supervision from relevant CO staff.

Partnerships

The project will be implemented in Partnership with USAID Missions in the four countries.  Each UNDP Country Office has identified potential CSO partners as follows:

Barbados

- Empowerment, Quality, Unity, Acceptance, Love, Strengths [EQUALS] works primarily with the LGBTQI community in Barbados. Equals creates safe social spaces and programmes, accessing stigma and discrimination free services, defending and advocating for the human rights of LGBTQI persons.

- Barbados Gays and Lesbians Against Discrimination [B-G.L.A.D] is dedicated to the promotion of human rights for all persons within the Barbadian society and in particular lesbian, gays and bi-sexual persons. BGLAD, through education on issues of human sexuality and individual differences, promotes the acceptance of all persons and develop a positive agenda for change within Barbados.

- Movement Against Discrimination [MOVADAC] focuses on training government employees who provide critical services (such as police officers and health care workers) to interact with the LGBTI community.

- Community Education Empowerment Development [CEED] is a registered charity whose main objective is to establish, operate and promote education, empowerment and development for marginalised groups in Barbados, specifically persons who are marginalised based on sexual orientation, physical disability, poverty or HIV status.

Dominican Republic

- Aliados a ASOLSIDA (ALAS) is a group of LGBTI people that belong to the Partnership for the Fight against AIDS (ASOLSIDA).

- Alianza GTH is an alliance of different organizations of the LGBTI collective.

- Amigos Siempre Amigos (ASA) is the first organization of the Dominican Republic of gay men that and that coordinates with REVASA the biggest events of the collective like the Pride Caravan and the International LGBTI Film Festival.

- Colectiva Mujer y Salud: is an association that works for the rights of women and the empowerment of lesbian women.

- Centro de Orientación e Investigación Integral (COIN): is an organisation with a long history that works for the human rights of vulnerable groups.

- Coordinadora Lésbica y Hombres Trans (COLETH): Works for the Rights of lesbian women and transgender men.

- Comunidad de Trans, (COTRAVETD) works with transgender sex workers.

- Diversidad Dominicana: is an organisation of support to the LGBTI collective with a strong work in LGBTI Political Leadership.

- Fundación Comunidad Esperanza y Justicia Internacional (FUNCEJI): is an organisation that works on human Rights with strong links to the LGBTI community

- Red de Voluntario de Amigos Siempre Amigos (REVASA): coordinates along with ASA of the largest events of the collective such as the Pride Caravan and the International LGBTI Film Festival.

- Trans Amigas Siempre Amigas (TRANSSA): works on transgender rights

Haiti

- FOKAL is a cultural organization that engages with local communities, the Haitian government, and international organizations to develop the skills, resources, and institutions that Haitians can use to improve their lives and overcome political violence, natural disasters, and poverty.

- FOSREF promotes and provides sexual and reproductive health information and services to the Haitian population, with a view to improving the living conditions of Haitian families through interventions in the areas of housing, the environment, vocational education, and psychosocial support to vulnerable groups.

- Foundation SEROvie is a Haitian community based organization working in the field of psychosocial support for MSM who affected by HIV and AIDS.

- Kouraj is an organization of LGBTI activists, created to politicize other homosexuals and transgender persons in Haiti regarding their human rights.

- Femme en Action Contre la Stigmatisation el la Discrimination Sexuelle (FACSDIS) was founded in July 2010 as a response to the discrimination and violence LBT women and sex workers faced in Haiti in the context of the earthquake. FACSDIS’s mission is to end stigma and gender discrimination and to support the struggle of oppressed and marginalized women such as LBT women, sex workers and people living with HIV.

- KOFAVIV is an organization that works to eliminate gender-based violence in Haiti and to provide support to Haitian activists facing violence.

- MADRE is an international women’s human rights organization that works in partnership with community-based women’s organizations worldwide to address issues of health and reproductive rights, economic development, education and other human rights.

Jamaica

- Colour Pink: The Colour Pink Group is a non-government organisation focused on helping gay men, men who have sex with men (MSM), and transgender people who are homeless.

- Equality Youths: Youth-led NGO that advocates for a more inclusive society.

- J-FLAG: Non-Profit NGO that promotes social change in furtherance of the well-being of the members of the LGBT community, through a range of internally directed and externally focused tools including: Public Education, Crisis Intervention and Empowerment; Research; Rights-based Advocacy; Legal Aid and Legal Reform.

- Quality of Citizenship Jamaica: NGO dedicated to foster the enhancement of healthcare, including mental health, for lesbian, bisexual and women who have sex with other women in Jamaica and increase LGBT youth participation in all spheres of youth activity; bringing awareness to our constituents on matters of health, HIV and human rights.

- Transwave: addresses topics important to the transgender community such as HIV transmission, health care access, gender-based violence (GBV) and other social issues that put the community at risk.

- WE-Change: WE-Change is a community-based organization committed to increasing the participation of women in social justice advocacy

Risks and Assumptions

The main programmatic risk for this project arises from the complicated and often highly politicized legal environment surrounding LGBTI issues in the Caribbean. In addition, there are many social and cultural sensitivities around LGBTI persons, same-sex relationships and transgender gender identity.

Participation of LGBTI people and organizations in the project activities will need to be carefully managed and this will be addressed by sensitizing project teams and steering committees and through regular advocacy by UNDP with government stakeholders. The project will ensure that all project activities - national and regional trainings, capacity building meetings etc. - have meaningful and visible participation of LGBT groups. To strengthen national capacity and buy-in to the process, LGBT persons will also be recruited as appropriate to carry out project consultancies, to act as expert resource people and will be asked to sit on the Technical Advisory Group. It is essential to consult the associations and the persons involved so that they themselves can analyse the risks and decide for themselves upon the measures to be taken, regarding their visibility in activities in which they are concerned. Support of human rights organizations and work with other key players, such as the media, is also important to confront these concerns.

An additional risk is that governments may feel that UNDP and USAID are pursuing a particular agenda and working outside of their remit. These risks will be mitigated by anchoring the project within the SDGs and the international, regional and national human rights commitments of each country - which will provide the overarching framework for all activities. In addition, achieving end-results on sensitive issues (such as the review or reform of laws on same-sex conduct and cross-dressing) shall be seen as long-term goals in particularly sensitive contexts, and the focus will be more on identifying, agreeing and planning for the achievement of key recommendations and agreed upon interim milestones. As an example, interim milestones could include costed services for LGBT populations in national strategic plans for HIV, constructive engagement between the authorities such as police and LGBT organizations, increased positive messages in the public domain, or a moratorium on arrests, even in contexts/countries where same sex behaviour is criminalized.

Stakeholder Engagement

The key beneficiaries of this project are LGBTI people in each of the four countries. The strategies used by the project to reach these communities will be informed by partnerships with the networks of LGBTI civil society organisations who will be the implementing partners of this project. These partnerships – which have been cultivated through intensive collaboration over a number of years – will be actively managed through joint work at the regional and country levels.

At the national level LGBTI organisations will be engaged through capacity development initiatives, National Dialogues as well as the small grants programme.  At the regional level, the project will bring together national organisations with regional networks in a regional dialogue that will allow for the sharing of experiences and good practices.

South-South and Triangular Cooperation (SSC/TrC)

South- South cooperation will be a key feature of the regional project.  Knowledge sharing across the four programme countries is integral to achieving the intended results. In addition, LGBTI organisation from Eastern Caribbean countries will be invited to participate in regional activities to enhance the sharing of lessons and experiences. This project intends to use SSC as a development tool to strengthen LGBTI inclusive development, through sharing their best practices and tools.

Knowledge

Four Country Reports will be developed under this project as well as one regional research report.  Through the knowledge products UNDP hopes to provide up to date data that would enable analysis on the level of LGBTI rights and inclusion.

Sustainability and Scaling Up

Throughout the life of the project one of the key aims is to outline areas of common agreement and opportunities for joint actions between government and civil society.  In addition, the project will enhance the capacity of governments, civil society and LGBTI groups to address and reduce inequality, exclusion, violence and discrimination experienced by LGBTI persons in Barbados, Dominican Republic, Haiti and Jamaica.

# Project Management

Cost Efficiency and Effectiveness

The project is expected to deliver maximum results with available resources. It builds on existing tools and on similar ongoing initiatives being implemented in Asia, Africa and the Balkans region. It leverages best practices and lessons learned from these projects.

Combining the expertise of the LAC Regional Hub HIV, Health and Development Team along with the Africa and Asia Pacific human rights staff engaged in the implementation of USAID funded Being LGBTI projects there is a wealth of technical knowledge and expertise.

This project will draw on existing networks, infrastructure and experiences of the region in efforts to reduce inequality and exclusion experienced by LGBTI persons. It will seek synergies with ongoing initiatives and relevant actors at regional and national level, to ensure cost-efficiency, effectiveness and sustainability of the results.

Project Management

The project will be implemented by UNDP’s HIV, Health and Development Cluster at the Regional Hub in Panama; the project coordinating team will be based out of the Panama UNDP Regional Hub.   The project will be supported by the global HHD team, drawing on expertise in south-south cooperation, gender, coordination, monitoring and evaluation, in addition to expertise housed in country office.

This Being LGBTI in the Caribbean project will be implemented in four Caribbean countries: Barbados, Dominican Republic, Haiti and Jamaica. UNDP will be responsible and accountable to USAID for all resources it receives under this Agreement and for the results that are to be accomplished.

Given the regional nature of this project it will be executed using the Direct Implementation (DIM) modality. UNDP through the Regional Hub will be the Implementing Partner of this project. The Regional Hub will be primarily accountable for the overall leadership, decision-making and management of the project including budget and financial management (achievement of results, approval of budget revisions, and allocation of financial resources and overall reporting). At the national level, UNDP Country Offices in the project countries, will have a direct implementation role. They will be responsible for services related to recruitment of the Community Coordinators, and the implementation of national activities such as research and national dialogues.

Out of the total of US$999,879.00, 8% will be allocated to cover expenses associated with General Management Services (GMS).  GMS will be recovered in accordance with the funds executed in a given year.

Any challenges will be discussed and the feedback from the Project Board will be incorporated, as appropriate and necessary, with the overall goal of increasing the programme's achievement of its stated goals and objective

# Results Framework

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | ## TARGETS |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year | Year 1 | Year 2 | Year 3 | ## FINAL | ## DATA COLLECTION METHODS & RISKS |
| Output 1 Knowledge, strategic information and evidence on the impact of inequality and exclusion of LGBTI people developed and disseminated | 1.1 Number of issue/research papers on LGBTI and related issues produced and disseminated | NA | 0 | 2017 | 0 | 4 | 0 | 4 | Being LGBTI reports for all four countries; Research reports |
|  | 1.2 Communication Strategy and Action Plan implemented to ensure visibility of project results | NA | 0 | 2017 | 0 | 8 | 8 | 16 | Advocacy Campaigns, |
| Output 2 Support meaningful engagement of governments in the selected countries through national and regional policy dialogues | 2.1 Number of public forums in which national governments and LGBTI civil society members interact | NA | 0 | 2017 | 0 | 4 | 0 | 4 | Signed participant lists; Roundtable Agendas |
|  | 2.2 Number of regional dialogues/ consultations/sensitization workshops co-convened with governments | UBRAF report | 1 | 2013 | 0 | 0 | 1 | 1 | Signed participant lists; Regional Roundtable Agenda |
| Output 3 Capacity of LGBTI Community groups developed through enhanced coordination, increased access to existing tools, transfer of knowledge and concrete actions to address stigma and discrimination | 3.1 Number of LGBTI organizations trained and supported | NA | 0 | 2017 | 0 | 0 | 10 | 10 | Workshop report |
|  | 3.2 Number of LGBTI organizations trying to affect government policy or conducting government oversight. | NA | 0 | 2017 | 0 | 8 | 8 | 16 | Meeting reports |
|  | 3.3 Number of countries benefitting from South- South sharing of lessons and tools | NA | 0 | 2017 | 0 | 4 | 6 | 10 | Regional Dialogue |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans: [Note: monitoring and evaluation plans should be adapted to project context, as needed]

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. | In addition to national governments and civil society organisations, UNDP will partner with USAID to support the implementation of the project. | Monitoring Costs has been built into project |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Every six months | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. |  |  |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. |  |  |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. |  |  |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. |  |  |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) |  |  |  |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | At least annually | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. |  |  |

# Multi-Year Work Plan

All anticipated programmatic and operational costs to support the project, including development effectiveness and implementation support arrangements, need to be identified, estimated and fully costed in the project budget under the relevant output(s). This includes activities that directly support the project, such as communication, human resources, procurement, finance, audit, policy advisory, quality assurance, reporting, management, etc. All services which are directly related to the project need to be disclosed transparently in the project document.

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year |  |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Y1 | Y2 | Y3 |  |  |  | Funding Source | Budget Description | Amount |
| Output 1 Knowledge, strategic information and evidence on the impact of inequality and exclusion of LGBTI people developed and disseminated (GEN 3) | - Intersex Baseline Assessment - Communications Strategy - Four National LGBTI Reports | 0 | 16,500.00 | 0 |  | UNDP RH |  | USAID | 71310 LclCons | 16,500.00 |
|  |  | 0 | 18,000.00 | 13,500.00 |  | UNDP RH |  | USAID | 71310 LclCons | 31,500.00 |
|  |  | 0 | 21,000.00 | 0 |  | UNDP CO |  | USAID | 74210 PrintPubs | 21,000.00 |
|  |  | 0 | 57,665.00 | 0 |  | UNDP CO |  | USAID | 71405 ServCon | 57,665.00 |
|  |  | 0 | 8,000 | 0 |  | UNDP CO |  | USAID | 72805 CompHrdwre | 8,000 |
|  |  |  | 4,800 | 4,800 |  | UNDP CO |  | USAID | 72505 Stationery | 9,600 |
|  | Sub-Total for Output 1 |  |  |  |  |  |  |  |  | 144,265.00 |
| Output 2 Support meaningful engagement of governments in the selected countries through national and regional policy dialogues (GEN 3) | 2.1 Four National Roundtables 2.2 One Regional Roundtable | 0 | 24,000.00 | 0 |  |  | UNDP CO | USAID | 75705 LearnCost | 24,000.00 |
|  |  |  |  | 57,665.00 |  |  | UNDP CO |  | 71405 ServCon | 57,665.00 |
|  |  | 0 | 0 | 70,410.66 |  |  | UNDP RH | USAID | 75700 Training, Workshops and Conference | 70,410.66 |
|  | Sub-Total for Output 2 |  |  |  |  |  |  |  |  | 152,075.66 |
| Output 3 Capacity of LGBTI Community groups developed through enhanced coordination, increased access to existing tools, transfer of knowledge and concrete actions to address stigma and discrimination (GEN 3) | 3.1 Small grants for LGBTI community groups 3.2 Capacity building workshops | 0 | 0 | 280,000.00 |  |  | UNDP RH | USAID | 72605 Grants | 280,000.00 |
|  |  | 0 |  | 57,665.00 |  |  | UNDP CO | USAID | 71405 ServCon | 57,665.00 |
|  |  | 0 | 120,000.00 | 0 |  |  | UNDP CO | USAID | 75705 | 120,000.00 |
|  |  | 0 | 57,655.00 | 0 |  |  | UNDP CO | USAID | 71405 ServCon | 57,665.00 |
|  | Sub-Total for Output 3 |  |  |  |  |  |  |  |  | 515,320.00 |
| Monitoring |  |  | 8,000 | 8,000 |  |  | UNDP RH | USAID | 71605 TrvlTixInt | 16,000 |
| Project Oversight |  | 10,000 | 40,000 | 30,000 |  |  | UNDP RH | USAID | 71405; 71310; ServCon; LclCons | 80,000 |
| Direct Project Costs |  |  |  |  |  |  |  |  |  | 18,53.21 |
| General Management Support |  |  |  |  |  |  |  |  |  | $74,065.11 |
| TOTAL |  |  |  |  |  |  |  |  |  | 999,879.00 |

# Governance and Management Arrangements

| Management Structure |  |  |
| --- | --- | --- |
| Project Board (Governance Structure) |  |  |
| Senior Beneficiary Caribbean Forum for Liberation and Acceptance of Genders and Sexualities (CariFLAGS); REDLACTRANS (Caribbean) Pan Caribbean Partnership Against HIV.AIDS (PANCAP) | Executive Chair – Regional Hub Director | Senior Supplier United States Agency for International Development (USAID) |

Project Assurance Regional Programme Coordinator

Technical Support LAC Regional HHD Cluster; HHD Human Rights team, New York

Project Coordinating Team:

Regional HHD Team Leader Administration and Finance Assistant

Haiti Country Office

Dominican Republic Country Office

Barbados Country Office

Jamaica Country Office

The Project Board (PB) is responsible for making management decisions, in particular when guidance is required by the Programme Manager. The Project Board will have overall authority over the project and is responsible for its initiation, direction, review and eventual closure.

- The Project Board, a key mechanism for ensuring coordination and planning of activities across national and regional stakeholders, will have overall authority over the project and is responsible for its initiation, direction, review and eventual closure.  It is responsible for ensuring that the project remains on course to deliver high quality outputs, contributing to the stated project outcomes in the project document. Within the confines of this project, the project board will be the highest decision-making authority in accordance with UNDP’s project management regulations, rules, policies and procedures as outlined in the UNDP Programme and Operations Policies and Procedures (POPP).

- The Project Board will consist of a panel, including PANCAP, a Caribbean regional partnership of governments, and regional LGBTI organisations CARIFLAGS and REDLACTRANS, Country Office representatives and the Donor. Representatives of other stakeholders could be included in the Board as appropriate. This approach ensures that the perspectives and synergies of the partners are captured and that there is ownership, promotion of sustainability and coordination with regional and national strategies.

- The Project Board will convene on the 2nd quarter of Year 1 and on the 3rd quarter of year 2 of the project. The meetings can be face-to-face or virtual. After the meetings, the Project Board will send out minutes within 10 working days. The Project Board will be responsible for providing recommendations for project management decisions, including approvals of Workplans and requests for substantive revisions to the project. The final decisions will be responsibility of the Directorate of the Regional Bureau for Latin America and the Caribbean, through the Directorate of the Regional Center for Latin America and the Caribbean.

The Directorate of the Regional Bureau for Latin America and the Caribbean, or its deputy, will authorize the project implementation under the DIM. In addition, it will approve and sign the Project Document, and its eventual substantive revisions, and will approve the cost-sharing agreement with the donor. The Directorate of the Bureau will lead the Regional Project Board, through the Directorate of the Regional Center for LAC.  The Directorate of the Bureau will delegate the project implementation functions to the Directorate of the Regional Center for LAC, through the HIV, Health and Development Team and the Country Offices involved. The project approval in ATLAS and the revisions will be carried out by the Directorate of the Regional Center for LAC or by the delegated person, who will have the authority to fulfil this function.

UNDP Country Offices involved in the project will be responsible for their corresponding implementation activities, planning and executing planned activities, providing technical assistance, monitoring progress and achieving the expected targets. To achieve this, the project will provide the necessary resources for hiring staff, acquiring goods and services, as well as managing payments, according to a Workplan. Each CO budget will be decentralized through Department IDs; the Regional office will retain oversight, establish expenditure limits, and be responsible for budget revisions. The Regional office will review expenditure on a quarterly basis and reserves the right to reallocate resources that are not being utilized. COs are responsible for financial management, ensuring that all project process are in line with UNDP Programme and Operations Policies and Procedures (POPP), in accordance with the terms established in the UNDP Grant No. AID-517-IO-17-00001 (Being LGBTI in the Caribbean), signed between the USAID and UNDP. Each CO is accountable for project hiring processes, the procurement and supplier processes, the organization of workshops, the preparation of payment requests (SPD) and requisitions in ATLAS, and implementation of project activities.

The Regional Team Leader for HIV, Health and Development will be responsible for the technical supervision of the project and for the project personnel. She will substantively follow up to the Project, conducting monitoring visits to the countries where activities are implemented; she will support the execution of the Project, ensuring its technical consistency, its compliance with the Workplan, the achievement of its products and results, and the technical quality of the reports. The Regional Team Leader will work in collaboration with the Regional Programme Coordinator as project guarantor, to ensure that the results are entered in Atlas in a timely manner and delivered to the Project Board and to the donor. The Regional Programme Coordinator, will ensure quality assurance and oversight, while daily management and supervision of implementation will be responsibility of the HIV, Health and Development Team.

The Project Guarantor will be the Regional Programme Coordinator. Its function is to ensure and support the monitoring of annual Workplans, progress reports, substantive and budget revisions, and proposals for equipment transfer at the end of the Project. She will also be responsible for monitoring the ATLAS system, ensuring that the information is updated, at least every three months (when receiving the quarterly reports). She will ensure that the funds for project implementation are available, and used properly. She will also monitor the quality of the project implementation and the risk indicators every year.

Community coordinators hired especially by - or assigned to - the project by UNDP, will be responsible for conducting technical, logistical and administrative processes in order to implement the activities in each country of intervention, to monitor the implementation of the National Work Plans, and to achieve the desired outputs. The community coordinator will report to their respective unit supervisor matrixed with the Regional Team Leader.

The Project Team will be supported by the UNDP Regional HHD Legal Advisor and the HHD Unit Program Finance and Administration Associate. The project team will receive technical assistance from the Project Guarantor, the Global HHD team and Program Officers from each Country Office.

# Legal Context

This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions to the Project Document attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

The Implementing Partner shall ensure best value for money, fairness, integrity, transparency, and effective international competition in the financial governance applied to implementing the project. This project will be implemented by [name of entity] (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. In all other cases, UNDP's Financial Regulations and Rules and governance procedures shall be followed.

# Risk Management

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - Choose one of the three following options:

Option 1: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

Annex I

Risk Log

| Project Title: Challenging stigma and discrimination to improve access to and quality of HIV services in the Caribbean |  |  |  |  |  | Award ID: 00107155 |  | Date: 4 December, 2017 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response |  | Owner | Submitted, updated by | Last Update | Status (reducing, increasing or no change) |
| 1 | A worsening legal environment and lack of political will to address issues that adversely affect LGBTI persons could seriously delay realization of project objectives. | October 2017 | Political | P = 3 I = 5 | CSOs have developed a set of mutually reinforcing initiatives to organize bottom-up alternatives: documentation; advocacy; use of the courts to do what legislatures will not; leveraging international human rights commitments; and other initiatives to build alliances, tap private sector influence, and influence public opinion. |  | UNDP | Karin Santi | 4 Dec 2017 | No change |
| 2 | Governments may feel that UNDP and USAID are pursuing a particular agenda and working outside of their remit. | September 2017 |  | P = 2 I = 4 | This risk will be mitigated by anchoring the project within the SDGs and the international, regional and national human rights commitments of each country - which will provide the overarching framework for all activities. |  | UNDP | Karin Santi | 4 Dec 2017 | No Change |
| 3 | Covering four distinct countries with three languages and differing legal and political systems will present challenges. | September 2017 | Operational | P = 1 I = 2 | To cope with this diversity, a community coordinator will be recruited in each of the countries to oversee activities. |  | UNDP | Karin Santi | 4 Dec 2017 | No Change |
| 4 | Data-collection capacity and tools are in place to monitor program performance. | September 2017 |  | P = 1 I = 3 | UNDP has comprehensive monitoring and evaluation arrangements in place which include collecting and recording programmatic data with appropriate quality control measures; supporting the preparation of regular reliable programmatic reports; and making data available for the purpose of evaluations and other studies. |  | UNDP | Karin Santi | 4 Dec 2017 | No Change |

Annex II

Social and Environmental Screening Template

| Project Information |  |
| --- | --- |
| - Project Title | Being LGBTI in the Caribbean: Reducing Inequality & Exclusion Experienced by LGBTI People |
| - Project Number | 00107155 |
| - Location (Global/Region/Country) | Four Caribbean Countries (Barbados, Dominican, Haiti, and Jamaica, |

Part A. Integrating Overarching Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Overarching Principles in order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the Project mainstreams the human-rights based approach

A range of human rights violations impact LGBTI communities. Multiple reports have documented how states have failed to protect LGBTI people, from violence and human rights violations. A Universal Periodic Review and Inter-American Commission on Human Rights hearings, English-speaking Caribbean states have repeatedly rejected recommendations to repeal laws that criminalize sex between men, or to take greater leadership in anti-discrimination campaigns, and states frequently cite lack of public support as a reason for retention of discriminatory laws, policies and practices. This project aims to empower LGBTI persons across four Caribbean countries, to enhance knowledge, partnerships, and capacities of LGBTI communities, civil society and States to reduce human rights violations and negative attitudes towards LGBTI people

Briefly describe in the space below how the Project is likely to improve gender equality and women’s empowerment

The project aims to strengthen the evidence base, develop advocacy capacity and public information materials, and convene regional and national dialogues that bring together national decision makers from the executive, legislative and judiciary branches of government with LGBTI civil society organizations, their allies and other stakeholders. Gender equality has largely been limited in the region to integrating a gender focus to pursue greater equity for cisgender women, and has largely been driven by donor requirements on dis-aggregating data by sex. This approach has not focused on the multiple ways sexual orientation and gender identity interact in different sociocultural contexts to increase the vulnerability of LGBTI persons. Using a sequence of targeted training, mentor strengthening, and hands-on learning methods, UNDP will work with USAID and partner CSOs to build alliances between civil society and government partners for an improved response to human rights violations experienced by LGBTI persons.

Briefly describe in the space below how the Project mainstreams environmental sustainability

The project is not directly related to environmental sustainability.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Describe briefly potential social and environmental risks identified in Attachment 1 – Risk Screening Checklist (based on any “Yes” responses). If no risks have been identified in Attachment 1 then note “No Risks Identified” and skip to Question 4 and Select “Low Risk”. Questions 5 and 6 not required for Low Risk Projects. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6 |  |  |  | QUESTION 6: What social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for Risks with Moderate and High Significance)? |  |
| --- | --- | --- | --- | --- | --- | --- |
| Risk Description | Impact and Probability (1-5) | Significance (Low, Moderate, High) | Comments |  | Description of assessment and management measures as reflected in the Project design. If ESIA or SESA is required note that the assessment should consider all potential impacts and risks. |  |
| Risk 1: No risks identified | I = P = | 1 2 | As is common with projects dealing with sensitive issues there is a likelihood of backlash from social or religious groups as it relates to rights of LGBTI persons. |  | The project design has taken this into account and incorporates outreach and capacity building, including sensitivity training of key actors. |  |
|  | QUESTION 4: What is the overall Project risk categorization? |  |  |  |  |  |
|  | Select one (see SESP for guidance) |  |  |  |  | Comments |
|  | Low Risk |  |  | x |  |  |
|  | Moderate Risk |  |  | ☐ |  |  |
|  | High Risk |  |  | ☐ |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |  |  |  |  |  |
|  | Check all that apply |  |  |  |  | Comments |
|  | Principle 1: Human Rights |  |  | x |  |  |
|  | Principle 2: Gender Equality and Women’s Empowerment |  |  | ☐ |  |  |
|  | 1. Biodiversity Conservation and Natural Resource Management |  |  | ☐ |  |  |
|  | 2. Climate Change Mitigation and Adaptation |  |  | ☐ |  |  |
|  | 3. Community Health, Safety and Working Conditions |  |  | ☐ |  |  |
|  | 4. Cultural Heritage |  |  | ☐ |  |  |
|  | 5. Displacement and Resettlement |  |  | ☐ |  |  |
|  | 6. Indigenous Peoples |  |  | ☐ |  |  |
|  | 7. Pollution Prevention and Resource Efficiency |  |  | ☐ |  |  |

Final Sign Off

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor (Programme Manager) |  | UNDP staff member responsible for the Project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver () |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair (Richard Barathe) |  | UNDP chair of the PAC. In some cases PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| Principles 1: Human Rights | Answer (Yes/No) |
| 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | Y |
| 2. Is there a likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | N |
| 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | N |
| 4. Is there a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | N |
| 5. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | N |
| 6. Is there a risk that rights-holders do not have the capacity to claim their rights? | N |
| 7. Have local communities or individuals, given the opportunity, raised human rights concerns regarding the Project during the stakeholder engagement process? | N |
| 8. Is there a risk that the Project would exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals? | N |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| 1. Is there a likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | N |
| 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | N |
| 3. Have women’s groups/leaders raised gender equality concerns regarding the Project during the stakeholder engagement process and has this been included in the overall Project proposal and in the risk assessment? | N |
| 4. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | N |
| Principle 3: Environmental Sustainability: Screening questions regarding environmental risks are encompassed by the specific Standard-related questions below |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 Would the Project potentially cause adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | N |
| 1.2 Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | N |
| 1.3 Does the Project involve changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | N |
| 1.4 Would Project activities pose risks to endangered species? | N |
| 1.5 Would the Project pose a risk of introducing invasive alien species? | N |
| 1.6 Does the Project involve harvesting of natural forests, plantation development, or reforestation? | N |
| 1.7 Does the Project involve the production and/or harvesting of fish populations or other aquatic species? | N |
| 1.8 Does the Project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | N |
| 1.9 Does the Project involve utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | N |
| 1.10 Would the Project generate potential adverse transboundary or global environmental concerns? | N |
| 1.11 Would the Project result in secondary or consequential development activities which could lead to adverse social and environmental effects, or would it generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested lands will generate direct environmental and social impacts (e.g. felling of trees, earthworks, potential relocation of inhabitants). The new road may also facilitate encroachment on lands by illegal settlers or generate unplanned commercial development along the route, potentially in sensitive areas. These are indirect, secondary, or induced impacts that need to be considered. Also, if similar developments in the same forested area are planned, then cumulative impacts of multiple activities (even if not part of the same Project) need to be considered. | N |
| Standard 2: Climate Change Mitigation and Adaptation |  |
| 2.1 Will the proposed Project result in significant greenhouse gas emissions or may exacerbate climate change? | N |
| 2.2 Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | N |
| 2.3 Is the proposed Project likely to directly or indirectly increase social and environmental vulnerability to climate change now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | N |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 Would elements of Project construction, operation, or decommissioning pose potential safety risks to local communities? | N |
| 3.2 Would the Project pose potential risks to community health and safety due to the transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | N |
| 3.3 Does the Project involve large-scale infrastructure development (e.g. dams, roads, buildings)? | N |
| 3.4 Would failure of structural elements of the Project pose risks to communities? (e.g. collapse of buildings or infrastructure) | N |
| 3.5 Would the proposed Project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? | N |
| 3.6 Would the Project result in potential increased health risks (e.g. from water-borne or other vector-borne diseases or communicable infections such as HIV/AIDS)? | N |
| 3.7 Does the Project pose potential risks and vulnerabilities related to occupational health and safety due to physical, chemical, biological, and radiological hazards during Project construction, operation, or decommissioning? | N |
| 3.8 Does the Project involve support for employment or livelihoods that may fail to comply with national and international labor standards (i.e. principles and standards of ILO fundamental conventions)? | N |
| 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g. due to a lack of adequate training or accountability)? | N |
| Standard 4: Cultural Heritage |  |
| 4.1 Will the proposed Project result in interventions that would potentially adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: Projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | N |
| 4.2 Does the Project propose utilizing tangible and/or intangible forms of cultural heritage for commercial or other purposes? | N |
| Standard 5: Displacement and Resettlement |  |
| 5.1 Would the Project potentially involve temporary or permanent and full or partial physical displacement? | N |
| 5.2 Would the Project possibly result in economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | N |
| 5.3 Is there a risk that the Project would lead to forced evictions? | N |
| 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | N |
| Standard 6: Indigenous Peoples |  |
| 6.1 Are indigenous peoples present in the Project area (including Project area of influence)? | N |
| 6.2 Is it likely that the Project or portions of the Project will be located on lands and territories claimed by indigenous peoples? | N |
| 6.3 Would the proposed Project potentially affect the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the Project is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? If the answer to the screening question 6.3 is “yes” the potential risk impacts are considered potentially severe and/or critical and the Project would be categorized as either Moderate or High Risk. | N |
| 6.4 Has there been an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | N |
| 6.5 Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | N |
| 6.6 Is there a potential for forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? | N |
| 6.7 Would the Project adversely affect the development priorities of indigenous peoples as defined by them? | N |
| 6.8 Would the Project potentially affect the physical and cultural survival of indigenous peoples? | N |
| 6.9 Would the Project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | N |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 Would the Project potentially result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | N |
| 7.2 Would the proposed Project potentially result in the generation of waste (both hazardous and non-hazardous)? | N |
| 7.3 Will the proposed Project potentially involve the manufacture, trade, release, and/or use of hazardous chemicals and/or materials? Does the Project propose use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Conventions on Persistent Organic Pollutants or the Montreal Protocol | N |
| 7.4 Will the proposed Project involve the application of pesticides that may have a negative effect on the environment or human health? | N |
| 7.5 Does the Project include activities that require significant consumption of raw materials, energy, and/or water? | N |

ANNEX V

Terms of Reference

PROJECT BOARD

1.	BACKGROUND

Even with some progress in recent years respect for the human rights of LGBTI persons remain largely absent in the Caribbean region.   Many Caribbean countries still criminalize same sex relations resulting in pervasive stigma, discrimination and violence. Violations of civil and political, as well as economic, social and cultural rights continue.

Ten Caribbean countries have discriminatory laws against same-sex sexual acts. In Jamaica, the 1864 Offences against the Person Act, calls for a penalty of up to 10 years of imprisonment for those convicted of the “abominable crime of buggery”.  Although these laws tend not to be enforced, their existence is used to harass and threaten LGBT people, and they contribute to an environment that condones discrimination, stigma and violence.

Being LGBTI in the Caribbean: Reducing Inequality & Exclusion Experienced by LGBTI People” will examine the experiences of LGBTI people in four select Caribbean countries: Barbados, Dominican Republic, Haiti and Jamaica. This project will simultaneously address LGBTI issues in the region from a human rights and a development perspective, as well as contextualize the issues against the backdrop of civil society capacity development, community mobilization and government engagement.

The project aims to strengthen the evidence base, develop advocacy capacity and public information materials, and convene regional and national dialogues that bring together national decision makers from the executive, legislative and judiciary branches of government with LGBTI civil society organizations, their allies and other stakeholders.  The main outputs of the project are;

- To strengthen data/evidence base on the rights of LGBTI people and enhance the capacity of governments, civil society and LGBTI groups to address and reduce inequality, exclusion, violence and discrimination experienced by LGBTI persons in four countries – Barbados, Dominican Republic, Haiti and Jamaica.

- To increase awareness of homophobic and transphobic violence and discrimination and strengthen the capacity of civil society organizations to challenge negative attitudes towards LGBTI people including through engaging government officials, parliamentarians, political parties, trade unions, religious leaders, civil society, media, and the general population in four countries – Barbados, Dominican Republic, Haiti and Jamaica and regionally.

2. 	COMPOSITION

Representatives from the following organisations shall comprise the Project Board:

Executive:

Chair - UNDP Director Regional Hub

Senior Beneficiaries:

CARIFLAGS; REDLACTRANS-Caribbean; PANCAP

Senior Supplier:

USAID

Project Assurance:

Regional Programme Manager

Project Review Committee:

Team Leader HHD (Regional Hub); UNDP Deputy Country Directors in Barbados, Dominican Republic, Haiti and Jamaica

3. FUNCTIONS OF THE PROJECT BOARD

- Offer overall policy and technical guidance and direction towards the implementation of the project, ensuring it remains within any specified constraints;

- Provide input into work plans, budgets and implementation schedules to guide the achievement of project objectives;

- Approve project implementation schedule, annual work plan (AWP) and indicative project budget at the commencement of each project year within its remit;

- Provide guidance and agree on possible countermeasures/management actions to address specific project risks and challenges;

- Address project issues and/or challenges as raised by the Programme Manager or members of the Project Board;

- Review and endorse changes in project work plans, budgets and schedules as necessary;

- Monitor project implementation and provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Review and make decisions on recommendations related to project management from the Executing Agency or Implementing Agency;

- Arbitrate where necessary and decide on any alterations to the programme;

- Endorse an overall project evaluation and monitoring function for the duration of the project through a mechanism agreeable to all Project Board parties; and

- Providing necessary oversight to ensure sustainability of project.

4.	MEETINGS

The Project Board will meet virtually once each year, at a time convenient to all members.  A quorum will be constituted by 50% plus one of the representatives (listed under 2. Composition) and must be present for meetings of the Project Board to be convened. Additional meetings may also be convened as needed. Fifty-one percent (51%) of the Board needs to be present for decisions to be made. The Project Board makes decisions by votes at meetings. Project Board members attending meetings must devote every effort to achieving consensus.

5. 	CHAIRPERSON

The Project Board Chair will chair the Project Board meeting and is responsible for:

1.   The conduct of the meeting

2.   Ensuring that an accurate record of the discussions and decisions of each meeting is prepared and forwarded to all members

3. Ensuring adequate follow-up on the undertakings of the members of the Project Board.

6. 	SECRETARIAT OF THE COMMITTEE

The HHD Team Leader, or their designate, will provide secretariat services to the Project Board and will carry out the following activities in support of Project Board meetings:

- Preparation of an agenda, and provision of necessary materials (reports, work plans etc.); consolidation of information provided by Project Board members (documents, reports etc.)

- Advance submission of the draft agenda and accompanying materials for the review and approval of the Chairperson or his or her appointed delegate prior to the meeting;

- Announcement of the time and location of the meeting and distribution of approved materials to the Project Board members no less than ten days (10) before the meeting.

7. 	COMMUNICATION

Documentation being presented for review at any meeting of the Project Board will, as far as possible, be distributed ten days (10) prior to the meeting. The preparation of the records and notes of all official meetings of the Project Board will be the responsibility of the Secretary. These records must be forwarded to Project Board members no later than two (2) weeks after its conclusion. The Secretary will ensure all minutes are endorsed by attendees and filed.

8.	DURATION

The Project Board will exist for the duration of the project.

10.	MEETING LOCATION

Meetings of the Project Board will be held virtually.

ANNEX VI

| Project QA Assessment: Design and Appraisal |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Overall Project |  |  |  |  |  |  |  |
| Exemplary (5) |  | Highly Satisfactory (4) | Satisfactory (3) | Needs Improvement (2) | Inadequate (1) |  |  |
| At least four criteria are rated Exemplary, and all criteria are rated High or Exemplary. |  | All criteria are rated Satisfactory or higher, and at least four criteria are rated High or Exemplary. | At least six criteria are rated Satisfactory or higher, and only one may be rated Needs Improvement. The SES criterion must be rated Satisfactory or above. | At least three criteria are rated Satisfactory or higher, and only four criteria may be rated Needs Improvement. | One or more criteria are rated Inadequate, or five or more criteria are rated Needs Improvement. |  |  |
| DECISION |  |  |  |  |  |  |  |
| - APPROVE – the project is of sufficient quality to continue as planned. Any management actions must be addressed in a timely manner. - APPROVE WITH QUALIFICATIONS – the project has issues that must be addressed before the project document can be approved. Any management actions must be addressed in a timely manner. - DISAPPROVE – the project has significant issues that should prevent the project from being approved as drafted. |  |  |  |  |  |  |  |
| RATING CRITERIA |  |  |  |  |  |  |  |
| Strategic |  |  |  |  |  |  |  |
| - Does the project’s Theory of Change specify how it will contribute to higher level change? (Select the option from 1-3 that best reflects the project): - 3: The project has a theory of change with explicit assumptions and clear change pathway describing how the project will contribute to outcome level change as specified in the programme/CPD, backed by credible evidence of what works effectively in this context. The project document clearly describes why the project’s strategy is the best approach at this point in time. - 2: The project has a theory of change. It has an explicit change pathway that explains how the project intends to contribute to outcome-level change and why the project strategy is the best approach at this point in time, but is backed by limited evidence. - 1: The project does not have a theory of change, but the project document may describe in generic terms how the project will contribute to development results, without specifying the key assumptions. It does not make an explicit link to the programme/CPD’s theory of change. *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence Global Fund Proposal; UNGASS Reports |  |
| - Is the project aligned with the thematic focus of the UNDP Strategic Plan? (select the option from 1-3 that best reflects the project): - 3: The project responds to one of the three areas of development work as specified in the Strategic Plan; it addresses at least one of the proposed new and emerging areas; an issues-based analysis has been incorporated into the project design; and the project’s RRF includes all the relevant SP output indicators. (all must be true to select this option) - 2: The project responds to one of the three areas of development work19 as specified in the Strategic Plan. The project’s RRF includes at least one SP output indicator, if relevant. (both must be true to select this option) - 1: While the project may respond to one of the three areas of development work19 as specified in the Strategic Plan, it is based on a sectoral approach without addressing the complexity of the development issue. None of the relevant SP indicators are included in the RRF. This answer is also selected if the project does not respond to any of the three areas of development work in the Strategic Plan. |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence |  |
| Relevant |  |  |  |  |  |  |  |
| - Does the project have strategies to effectively identify, engage and ensure the meaningful participation of targeted groups/geographic areas with a priority focus on the excluded and marginalized? (select the option from 1-3 that best reflects this project): - 3: The target groups/geographic areas are appropriately specified, prioritising the excluded and/or marginalised. Beneficiaries will be identified through a rigorous process based on evidence (if applicable.) The project has an explicit strategy to identify, engage and ensure the meaningful participation of specified target groups/geographic areas throughout the project, including through monitoring and decision-making (such as representation on the project board) (all must be true to select this option) - 2: The target groups/geographic areas are appropriately specified, prioritising the excluded and/or marginalised. The project document states how beneficiaries will be identified, engaged and how meaningful participation will be ensured throughout the project. (both must be true to select this option) - 1: The target groups/geographic areas are not specified, or do not prioritize excluded and/or marginalised populations. The project does not have a written strategy to identify or engage or ensure the meaningful participation of the target groups/geographic areas throughout the project. *Note: Management Action must be taken for a score of 1 |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | The target groups are sub-recipients and sub-sub recipients of the project |  |
| - Have knowledge, good practices, and past lessons learned of UNDP and others informed the project design? (select the option from 1-3 that best reflects this project): - 3: Knowledge and lessons learned (gained e.g. through peer assist sessions) backed by credible evidence from evaluation, corporate policies/strategies, and monitoring have been explicitly used, with appropriate referencing, to develop the project’s theory of change and justify the approach used by the project over alternatives. - 2: The project design mentions knowledge and lessons learned backed by evidence/sources, which inform the project’s theory of change but have not been used/are not sufficient to justify the approach selected over alternatives. - 1: There is only scant or no mention of knowledge and lessons learned informing the project design. Any references that are made are not backed by evidence. *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence PRODOC |  |
| - Does the project use gender analysis in the project design and does the project respond to this gender analysis with concrete measures to address gender inequities and empower women? (select the option from 1-3 that best reflects this project): - 3: A participatory gender analysis on the project has been conducted. This analysis reflects on the different needs, roles and access to/control over resources of women and men, and it is fully integrated into the project document. The project establishes concrete priorities to address gender inequalities in its strategy. The results framework includes outputs and activities that specifically respond to this gender analysis, with indicators that measure and monitor results contributing to gender equality. (all must be true to select this option) - 2: A gender analysis on the project has been conducted. This analysis reflects on the different needs, roles and access to/control over resources of women and men. Gender concerns are integrated in the development challenge and strategy sections of the project document. The results framework includes outputs and activities that specifically respond to this gender analysis, with indicators that measure and monitor results contributing to gender equality. (all must be true to select this option) - 1: The project design may or may not mention information and/or data on the differential impact of the project’s development situation on gender relations, women and men, but the constraints have not been clearly identified and interventions have not been considered. *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence The project fully takes into account gender as well as vulnerability as it relates to gender identity, sexual orientation |  |
| - Does UNDP have a clear advantage to engage in the role envisioned by the project vis-à-vis national partners, other development partners, and other actors? (select from options 1-3 that best reflects this project): - 3: An analysis has been conducted on the role of other partners in the area where the project intends to work, and credible evidence supports the proposed engagement of UNDP and partners through the project. It is clear how results achieved by relevant partners will contribute to outcome level change complementing the project’s intended results. If relevant, options for south-south and triangular cooperation have been considered, as appropriate. (all must be true to select this option) - 2: Some analysis has been conducted on the role of other partners where the project intends to work, and relatively limited evidence supports the proposed engagement of and division of labour between UNDP and partners through the project. Options for south-south and triangular cooperation may not have not been fully developed during project design, even if relevant opportunities have been identified. - 1: No clear analysis has been conducted on the role of other partners in the area that the project intends to work, and relatively limited evidence supports the proposed engagement of UNDP and partners through the project. There is risk that the project overlaps and/or does not coordinate with partners’ interventions in this area. Options for south-south and triangular cooperation have not been considered, despite its potential relevance. *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence UNDP’s HHD team has successfully implemented similar projects in three other regions. |  |
| Social & Environmental Standards |  |  |  |  |  |  |  |
| - Does the project seek to further the realization of human rights using a human rights based approach? (select from options 1-3 that best reflects this project): - 3: Credible evidence that the project aims to further the realization of human rights, upholding the relevant international and national laws and standards in the area of the project. Any potential adverse impacts on enjoyment of human rights were rigorously identified and assessed as relevant, with appropriate mitigation and management measures incorporated into project design and budget. (all must be true to select this option) - 2: Some evidence that the project aims to further the realization of human rights. Potential adverse impacts on enjoyment of human rights were identified and assessed as relevant, and appropriate mitigation and management measures incorporated into the project design and budget. - 1: No evidence that the project aims to further the realization of human rights. Limited or no evidence that potential adverse impacts on enjoyment of human rights were considered. *Note: Management action or strong management justification must be given for a score of 1 |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence PRODOC – project explicitly focus on human rights of LGBTI persons |  |
| 8. Did the project consider potential environmental opportunities and adverse impacts, applying a precautionary approach? (select from options 1-3 that best reflects this project): - 3: Credible evidence that opportunities to enhance environmental sustainability and integrate poverty-environment linkages were fully considered as relevant, and integrated in project strategy and design. Credible evidence that potential adverse environmental impacts have been identified and rigorously assessed with appropriate management and mitigation measures incorporated into project design and budget. (all must be true to select this option). - 2: No evidence that opportunities to strengthen environmental sustainability and poverty-environment linkages were considered. Credible evidence that potential adverse environmental impacts have been identified and assessed, if relevant, and appropriate management and mitigation measures incorporated into project design and budget. - 1: No evidence that opportunities to strengthen environmental sustainability and poverty-environment linkages were considered. Limited or no evidence that potential adverse environmental impacts were adequately considered. *Note: Management action or strong management justification must be given for a score of 1 |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence NA |  |
| 9. Has the Social and Environmental Screening Procedure (SESP) been conducted to identify potential social and environmental impacts and risks? The SESP is not required for projects in which UNDP is Administrative Agent only and/or projects comprised solely of reports, coordination of events, trainings, workshops, meetings, conferences and/or communication materials and information dissemination. [if yes, upload the completed checklist. If SESP is not required, provide the reason for the exemption in the evidence section.] |  |  |  |  |  | Yes | No |
|  |  |  |  |  |  | SESP Not Required |  |
| Management & Monitoring |  |  |  |  |  |  |  |
| - Does the project have a strong results framework? (select from options 1-3 that best reflects this project): - 3: The project’s selection of outputs and activities are at an appropriate level and relate in a clear way to the project’s theory of change. Outputs are accompanied by SMART, results-oriented indicators that measure all of the key expected changes identified in the theory of change, each with credible data sources, and populated baselines and targets, including gender sensitive, sex-disaggregated indicators where appropriate. (all must be true to select this option) - 2: The project’s selection of outputs and activities are at an appropriate level, but may not cover all aspects of the project’s theory of change. Outputs are accompanied by SMART, results-oriented indicators, but baselines, targets and data sources may not yet be fully specified. Some use of gender sensitive, sex-disaggregated indicators, as appropriate. (all must be true to select this option) - 1: The results framework does not meet all of the conditions specified in selection “2” above. This includes: the project’s selection of outputs and activities are not at an appropriate level and do not relate in a clear way to the project’s theory of change; outputs are not accompanied by SMART, results-oriented indicators that measure the expected change, and have not been populated with baselines and targets; data sources are not specified, and/or no gender sensitive, sex-disaggregation of indicators. *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence PRODOC |  |
| 11. Is there a comprehensive and costed M&E plan in place with specified data collection sources and methods to support evidence-based management, monitoring and evaluation of the project? |  |  |  |  |  | Yes | No |
| 12. Is the project’s governance mechanism clearly defined in the project document, including planned composition of the project board? (select from options 1-3 that best reflects this project): - 3: The project’s governance mechanism is fully defined in the project composition. Individuals have been specified for each position in the governance mechanism (especially all members of the project board.) Project Board members have agreed on their roles and responsibilities as specified in the terms of reference. The ToR of the project board has been attached to the project document. (all must be true to select this option). - 2: The project’s governance mechanism is defined in the project document; specific institutions are noted as holding key governance roles, but individuals may not have been specified yet. The prodoc lists the most important responsibilities of the project board, project director/manager and quality assurance roles. (all must be true to select this option) - 1: The project’s governance mechanism is loosely defined in the project document, only mentioning key roles that will need to be filled at a later date. No information on the responsibilities of key positions in the governance mechanism is provided. *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence PRODOC |  |
| 13. Have the project risks been identified with clear plans stated to manage and mitigate each risks? (select from options 1-3 that best reflects this project): - 3: Project risks related to the achievement of results are fully described in the project risk log, based on comprehensive analysis drawing on the theory of change, Social and Environmental Standards and screening, situation analysis, capacity assessments and other analysis. Clear and complete plan in place to manage and mitigate each risk. (both must be true to select this option) - 2: Project risks related to the achievement of results identified in the initial project risk log with mitigation measures identified for each risk. - 1: Some risks may be identified in the initial project risk log, but no evidence of analysis and no clear risk mitigation measures identified. This option is also selected if risks are not clearly identified and no initial risk log is included with the project document. *Note: Management Action must be taken for a score of 1 |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence Risk Log |  |
| Efficient |  |  |  |  |  |  |  |
| 14. Have specific measures for ensuring cost-efficient use of resources been explicitly mentioned as part of the project design? This can include: i) using the theory of change analysis to explore different options of achieving the maximum results with the resources available; ii) using a portfolio management approach to improve cost effectiveness through synergies with other interventions; iii) through joint operations (e.g., monitoring or procurement) with other partners. |  |  |  |  |  | Yes (3) | No (1) |
| 15. Are explicit plans in place to ensure the project links up with other relevant on-going projects and initiatives, whether led by UNDP, national or other partners, to achieve more efficient results (including, for example, through sharing resources or coordinating delivery?) |  |  |  |  |  | Yes (3) | No (1) |
| 16. Is the budget justified and supported with valid estimates? - 3: The project’s budget is at the activity level with funding sources, and is specified for the duration of the project period in a multi-year budget. Costs are supported with valid estimates using benchmarks from similar projects or activities. Cost implications from inflation and foreign exchange exposure have been estimated and incorporated in the budget. - 2: The project’s budget is at the activity level with funding sources, when possible, and is specified for the duration of the project in a multi-year budget. Costs are supported with valid estimates based on prevailing rates. - 1: The project’s budget is not specified at the activity level, and/or may not be captured in a multi-year budget. |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence PRODOC multi-year workplan |  |
| - Is the Country Office fully recovering the costs involved with project implementation? - 3: The budget fully covers all project costs that are attributable to the project, including programme management and development effectiveness services related to strategic country programme planning, quality assurance, pipeline development, policy advocacy services, finance, procurement, human resources, administration, issuance of contracts, security, travel, assets, general services, information and communications based on full costing in accordance with prevailing UNDP policies (i.e., UPL, LPL.) - 2: The budget covers significant project costs that are attributable to the project based on prevailing UNDP policies (i.e., UPL, LPL) as relevant. - 1: The budget does not adequately cover project costs that are attributable to the project, and UNDP is cross-subsidizing the project. *Note: Management Action must be given for a score of 1. The budget must be revised to fully reflect the costs of implementation before the project commences. |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence GMS |  |
| Effective |  |  |  |  |  |  |  |
| 18. Is the chosen implementation modality most appropriate? (select from options 1-3 that best reflects this project): - 3: The required implementing partner assessments (capacity assessment, HACT micro assessment) have been conducted, and there is evidence that options for implementation modalities have been thoroughly considered. There is a strong justification for choosing the selected modality, based on the development context. (both must be true to select this option) - 2: The required implementing partner assessments (capacity assessment, HACT micro assessment) have been conducted and the implementation modality chosen is consistent with the results of the assessments. - 1: The required assessments have not been conducted, but there may be evidence that options for implementation modalities have been considered. *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence Assessments of CSOs |  |
| 19. Have targeted groups, prioritizing marginalized and excluded populations that will be affected by the project, been engaged in the design of the project in a way that addresses any underlying causes of exclusion and discrimination? - 3: Credible evidence that all targeted groups, prioritising marginalized and excluded populations that will be involved in or affected by the project, have been actively engaged in the design of the project. Their views, rights and any constraints have been analysed and incorporated into the root cause analysis of the theory of change which seeks to address any underlying causes of exclusion and discrimination and the selection of project interventions. - 2: Some evidence that key targeted groups, prioritising marginalized and excluded populations that will be involved in the project, have been engaged in the design of the project. Some evidence that their views, rights and any constraints have been analysed and incorporated into the root cause analysis of the theory of change and the selection of project interventions. - 1: No evidence of engagement with marginalized and excluded populations that will be involved in the project during project design. No evidence that the views, rights and constraints of populations have been incorporated into the project. |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence Consultations were held with groups at the national level |  |
| 20. Does the project conduct regular monitoring activities, have explicit plans for evaluation, and include other lesson learning (e.g. through After Action Reviews or Lessons Learned Workshops), timed to inform course corrections if needed during project implementation? |  |  |  |  |  | Yes (3) | No (1) |
| 21. The gender marker for all project outputs are scored at GEN2 or GEN3, indicating that gender has been fully mainstreamed into all project outputs at a minimum. *Note: Management Action or strong management justification must be given for a score of “no” |  |  |  |  |  | Yes (3) | No (1) |
|  |  |  |  |  |  | Evidence |  |
| 22. Is there a realistic multi-year work plan and budget to ensure outputs are delivered on time and within allotted resources? (select from options 1-3 that best reflects this project): - 3: The project has a realistic work plan & budget covering the duration of the project at the activity level to ensure outputs are delivered on time and within the allotted resources. - 2: The project has a work plan & budget covering the duration of the project at the output level. - 1: The project does not yet have a work plan & budget covering the duration of the project. |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence |  |
| Sustainability & National Ownership |  |  |  |  |  |  |  |
| 23. Have national partners led, or proactively engaged in, the design of the project? (select from options 1-3 that best reflects this project): - 3: National partners have full ownership of the project and led the process of the development of the project jointly with UNDP. - 2: The project has been developed by UNDP in close consultation with national partners. - 1: The project has been developed by UNDP with limited or no engagement with national partners. |  |  |  |  |  | 3 | 2 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence CCM consultations |  |
| 24. Are key institutions and systems identified, and is there a strategy for strengthening specific/ comprehensive capacities based on capacity assessments conducted? (select from options 0-4 that best reflects this project): - 3: The project has a comprehensive strategy for strengthening specific capacities of national institutions based on a systematic and detailed capacity assessment that has been completed. This strategy includes an approach to regularly monitor national capacities using clear indicators and rigorous methods of data collection, and adjust the strategy to strengthen national capacities accordingly. - 2.5: A capacity assessment has been completed. The project document has identified activities that will be undertaken to strengthen capacity of national institutions, but these activities are not part of a comprehensive strategy to monitor and strengthen national capacities. - 2: A capacity assessment is planned after the start of the project. There are plans to develop a strategy to strengthen specific capacities of national institutions based on the results of the capacity assessment. - 1.5: There is mention in the project document of capacities of national institutions to be strengthened through the project, but no capacity assessments or specific strategy development are planned. - 1: Capacity assessments have not been carried out and are not foreseen. There is no strategy for strengthening specific capacities of national institutions. |  |  |  |  |  | 3 | 2.5 |
|  |  |  |  |  |  | 2 | 1.5 |
|  |  |  |  |  |  | 1 |  |
|  |  |  |  |  |  | Evidence NA |  |
| 25. Is there is a clear strategy embedded in the project specifying how the project will use national systems (i.e., procurement, monitoring, evaluations, etc.,) to the extent possible? |  |  |  |  |  | Yes (3) | No (1) |
| 26. Is there a clear transition arrangement/ phase-out plan developed with key stakeholders in order to sustain or scale up results (including resource mobilisation strategy)? |  |  |  |  |  | Yes (3) | No (1) |

2 The Gender Marker measures how much a project invests in gender equality and women’s empowerment. Select one for each output: GEN3 (Gender equality as a principle objective); GEN2 (Gender equality as a significant objective); GEN1 (Limited contribution to gender equality); GEN0 (No contribution to gender quality)

Aengus Carroll and Lucas Ramón Mendos, 2017, State-Sponsored Homophobia: A World Survey of Sexual Orientation Laws: Criminalisation, Protection and Recognition, http://ilga.org/downloads/2017/ILGA_State_Sponsored_Homophobia_2017_WEB.pdf

Ibid

Ending Violence and Discrimination against Lesbian, Gay, Bisexual, Transgender and Intersex People; 2015; ILO, OHCHR, UNAIDS, UNDP, UNESCO, UNFPA, UNICEF, UNHCR, UNODC, UNWOMEN, WFP and WHO, http://www.undp.org/content/undp/en/home/librarypage/hiv-aids/LGBTIjointstatement.html

Human Rights First; 2012; Fact Sheet; LGBT Issues in Jamaica; https://www.humanrightsfirst.org/sites/default/files/Jamaica-LGBT-Fact-Sheet.pdf

Reuters; Haiti's first LGBT film festival postponed after threats, police ban, Reuters; September 2016; http://www.reuters.com/article/us-haiti-lgbt-idUSKCN11Y2H8

McFadden, David, 11 August 2013, "In Jamaica, transgender teen killed by mob". Associated Press, https://web.archive.org/web/20140103213141/http://bigstory.ap.org/article/jamaica-transgender-teen-murdered-mob

Boris Dittrich, 28 September 2016, At Long Last, Change Is Coming for Caribbean Gays; The Advocate, https://www.hrw.org/news/2016/09/28/long-last-change-coming-caribbean-gays

Human Rights First; 2015; Hope Will Prevail: Advancing the Human Rights of LGBT People in the Dominican Republic

2014, Allyn Gaestel, 2014, Haiti's Fight for Gay Rights: As LGBT community becomes more visible, anti-gay violence rises, too, Al Jazeera America, http://projects.aljazeera.com/2014/haiti-lgbt/

Human Rights First; 2012; Fact Sheet; LGBT Issues in Jamaica; https://www.humanrightsfirst.org/sites/default/files/Jamaica-LGBT-Fact-Sheet.pdf

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a project budget affecting the scope (outputs), completion date, or total estimated project costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner

Prohibited grounds of discrimination include race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender people and transsexuals.

In regards to CO2, ‘significant emissions’ corresponds generally to more than 25,000 tons per year (from both direct and indirect sources). [The Guidance Note on Climate Change Mitigation and Adaptation provides additional information on GHG emissions.]

Forced evictions include acts and/or omissions involving the coerced or involuntary displacement of individuals, groups, or communities from homes and/or lands and common property resources that were occupied or depended upon, thus eliminating the ability of an individual, group, or community to reside or work in a particular dwelling, residence, or location without the provision of, and access to, appropriate forms of legal or other protections.

1. Sustainable development pathways; 2. Inclusive and effective democratic governance; 3. Resilience building

sustainable production technologies, access to modern energy services and energy efficiency, natural resources management, extractive industries, urbanization, citizen security, social protection, and risk management for resilience