United Nations Development Programme

Electoral Support Project (ESP), Nepal

## Concept Paper for ESP Extension

(January – May 2018)

The UNDP Electoral Support Project (ESP) Phase II was designed to provide the Election Commission of Nepal (ECN) with long-term capacity-building as well as technical assistance and support for the organization of credible elections throughout the electoral cycle. The current duration of ESP is until 11 January 2018, which is likely to be shortly after the announcement of the final results of the direct House of Representatives and Provincial Assembly elections, and before the indirect elections for the National Assembly and President and Vice-President are completed.

The concept of electoral cycle support has been developed on the basis of the experience that the months following an election are the most critical period for strengthening the capacity of electoral authorities to improve processes for future elections. It is at a time when the strengths and weaknesses of an elections implementations have become evident and the memory of the process is fresh, but when no immediate political nor operational pressures are faced, that the changes that are required can be clearly identified and their implementation planned and started.

Accompanying and supporting the ECN through this process is the prime reason behind the proposed extension until the end of May 2018. Not only is the immediate post-electoral period the most appropriate for working towards the project’s primary objective – strengthening ECN capacity – but the eventual closure of the project will mean the departure of the project staff who has been supporting ECN over the years, with inevitable loss of institutional memory and first-hand experience of supporting the electoral processes. In addition the primary objective of to the primary objective of

- enhancing ECN capacity-building through supporting a post-electoral analytical review, the extension would also allow

- the completion of some activities scheduled for 2017 but which could not be implemented during the electoral operational phase, notably the urgent deployment of the new voter registration software,

- support for new strategic work that also needs to be implemented in the first half of 2018, such as supporting ECN in the realignment of its structure and processes to the new federal structure, and

- ensuring that administrative and operational requirements of the project, notably the final report and evaluation, are in themselves substantive contributions to the electoral process in Nepal.

# KEY AREAS OF ASSISTANCE

With the completion of the election operation itself, most of the proposed support areas are for the output of long-term capacity development. Much of the work listed below was agreed with ECN for implementation in 2017, but could not be carried out while the elections were being held.

Document lessons learned and best practices

As agreed with ECN, following the elections, ESP proposes to facilitate and operationally support a bottom-up review of the overall process of the three tiers of elections, involving the various key electoral stakeholders. This would allow lessons to be documented and would facilitate the ECN production of the final report. Issues to be addressed in future elections can thereby be integrated into the next ECN strategic plan. Also already agreed but postponed to 2018 is a review of the professional development courses implemented using the BRIDGE methodology. ESP is also ready to support a broader ECN institutional capacity self-assessment for which the UNDP methodology could be deployed.

Electoral Dispute Resolution

ESP will support ECN in gathering, consolidation and analysis of information on court cases regarding the electoral process, in order to support ECN efforts in avoiding and/or responding to similar cases in future.

ESP will also support ECN in the development of processes, mechanisms and software to record, transmit and provide responses to cases of complaints lodged with ECN. Over time, this will help ECN to provide consistent responses, analyse patterns and identify issues.

Deployment of the software for continuous voter registration

As previously agreed, ESP will provide technical support for the deployment, field testing and handover of the new voter list application developed for ECN that will provide a significant upgrade in functionality and security for the voter registration process.

Support on strengthening the local offices of ECN in the federal context

ESP will provide technical assistance to ECN in its efforts to realign its functions in the federal context as per the spirit of the Constitution of Nepal and the newly adopted Civil Service Adjustment Act. In order to further strengthen the effectiveness and efficiency of its assistance to the citizens, and taking into consideration learning from the series of elections held in 2017, ECN could relook into its business module and how to decentralize some of its functions at sub-national levels.

Final evaluation

In line with the project document, UNDP will commission the final evaluation of the project. Similarly and as per the EU framework agreement, the EU will also undertake an independent evaluation of ESP before the final closure of the project. This is anticipated to be carried out in the second quarter of 2018. ESP will complete all archiving and reporting requirements as well as the operational closure of the project as per UNDP policy.