## Sheet1
DEMOCRATIZATION AND HUMAN RIGHTS PROGRAMME IN UKRAINE
Year: 2017
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | Source of Funding | PLANNED BUDGET
Baseline associated indicators and annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Description | Approved budget | Revision | Revised budget | Comments
OUTPUT 1: 00089246 Civil society organizations strengthened to promote democracy and foster participatory and result-driven Government-CSO dialogue in Ukraine | Activity 1.3. Networking events (seminars and training) for CSOs inside the country and with the CSOs in Belarus and Moldova |  |  |  |  | DMFA | 71300 Consultants | 0 | 1470 | 1470 | CSD Expert $1470*2 = 2,940. Cost-shared 50% with 2.1
| Co-organise the IX international Conference “Social Innovations: New Ways to Solve Old Problems” in Kyiv on February 16th, 2017 | [5 empty] | 74200 Printing, Translations | 1500 | 0 | 1500 | Dissemination materials for th4e conference
| Ensure presentation of UNDP experiences of civil society engagement in social innovation at the conference. Prepare dissemination materials on the subject for wider coverage | [5 empty] | 75700 Trainings and Conferences | 2000 | 2000 | 4000 | Co-funding for the conference
[7 empty] | 71600 Travel | 0 | 5000 | 5000 | Travel of international experts to the conference
[7 empty] | 75100 Facilities & Administration (8%) | 245 | 712.6 | 957.6
| Total | [6 empty] | 3745 | 9182.6 | 12927.6
| Activity 1.4. Advocate for wider and results-driven Government-CSO dialogue - Korean Budget For replication of Clean Construction System in Ukraine. |  |  |  |  | Korean budget | 71400 Contractual services - Individ | 2756 | 1398.675 | 4154.675 | Team lead per month Feb-Mar: $2580 $17 pension $85.08 Cigna Medical insurance $8.88 Cigna Death & Disability Total: 2,691 * 2= 5382.00 + $250.67 - Separation costs in Mar 2017. Total: $5632,67 Cost-sharing: 1.4 = $5,131.00 1.5 = $501.67
[7 empty] | 74200 Printing, Translations | 0 | 976.32 | 976.32
[7 empty] | 72600 Grants | 10000 | 0 | 10000 | DHRP-GA-CSD-2016-05 TI Ukraine 2nd (216,000 UAH ) 3rd (54 000 UAH)
| Total | [6 empty] | 12756 | 2374.995 | 15130.995
| Activity 1.5. Effective project management | [5 empty] | 71200 International Consultants | 18000 | -8000 | 10000
| Office premises rent | [5 empty] | 71400 Contractual services - Individ | 10601.4 | -9329.908 | 1271.492 | Team lead salary + Pr.Asc in Jan incl charges and separation cost 2691 + 2470.03 + $ $501.67 (нехватка в корейских деньгах) = 5994
| Project Manager (Jan 2017) | [5 empty] | 73400 Vehicle Maintenance Service | 500 | -500 | 0
| Project Associate (Jan 2017) | [5 empty] | 73100 Rent & Utilities | 5943 | 921.5 | 6864.5 | Actually depends on a number of staff in project - need to discuss and reserve the cost with Olena Karelina
| Miscellaneous Expenses | [5 empty] | 74500 Miscellaneous Expenses | 600 | 0 | 600
| DPC (4%) | [5 empty] | 64300 Staff Mngmt Costs | 3528 | -1978 | 1550
[7 empty] | 75100 Facilities & Administration (8%) | 2495.11 | -872.2306 | 1622.8794
| Total | [6 empty] | 41667.51 | -19758.6386 | 21908.8714
TOTAL OUTPUT 00089246 | [7 empty] | 58168.51 | -8201.0436 | 49967.4664
OUTPUT 2: 00089247 Capacities of human rights actors strengthened to promote and defend human rights in Ukraine | Activity 2.1. Institutional support to the selected mid-size regional CSOs through individually tailored capacity development programme |  |  |  |  | DMFA | 71300 Consultants local | 3000 | -1470 | 1530 | CSD Expert $1470*2 = 2,940. Cost-shared 50% with 1.3
| Adapt the HRBA training package for Ukraine (November-December 2016) | [5 empty] | 71600 Travel | 2500 | -477 | 2023
| Deliver 8 HRBA trainings for at least 160 local CSOs representatives in 8 regions by hubs. Chernihiv hubs is responsible for leading the process (January - February 2017) | [5 empty] | 72600 Grants | 0 | 2000 | 2000 | Grant Center for Civic Liberties DHRP-GA-HR-2016-02 3rd tr final 73,014.00 UAH (2000 USD)
| The practical guide how to integrate HRBA into CSOs work based on experience of hubs prepared and published. Chernihiv hub is responsible (February-March 2017) | [5 empty] | 75700 Trainings and Conferences | 26000 | 6000 | 32000 | HRBA trainings 8w/s * 3000 + 3000 for JFPC
| Strategic planning session for the JfPC in Kyiv, February | [5 empty] | 74200 Audio Visual & Printing Production Costs | 4000 | -1000 | 3000 | Printing of HRBA manual
[7 empty] | 74500 Miscellaneous Expenses | 500 | 0 | 500
[7 empty] | 64300 Staff Mngmt Costs | 0 | 2100 | 2100
[7 empty] | 75100 Facilities & Administration (8%) | 2520 | 932.24 | 3452.24
| Total | [6 empty] | 38520 | 8085.24 | 46605.24
| Activity 2.4. Support the preparation of shadow reports within the framework of Ukraine’s international human rights commitments |  |  |  |  | DMFA | 71600 Travel | 4000 | -3000 | 1000
| Support the development and advocacy of the shadow report on Ukraine's compliance with CEDAW (Gender Startegic Platform) in coordination with OO project and UN Women | [5 empty] | 75700 Trainings and Conferences | 0 | 4200 | 4200 | CEDAW meeting in Kyiv (cofee-break)
[7 empty] | 74200 Audio Visual & Printing Production Costs | 0 | 2000 | 2000 | CEDAW meeting in Kyiv (Printing)
[7 empty] | 72600 Grants | 0 | 1800 | 1800
[7 empty] | 75100 Facilities & Administration (8%) | 280 | 440 | 720
| Total | [6 empty] | 4280 | 5440 | 9720
TOTAL OUTPUT 00089247 | [7 empty] | 42800 | 13525.24 | 56325.24
OUTPUT 3: 00098503 Strengthened HRBA and gender capacities of the DMFA Implementing Partners and their partners in UA, MD and BL | Activity 3.2. Conduct the regional study "HRBA in the region – strategies that work" |  |  |  |  | DMFA | 72100 Contractual services | 0 | 1390 | 1390 | PO 0000031351 Fresno last tranche 1390 USD.
| Make the HRBA study available in Russian. Prepare the layout of the publication. | [5 empty] | 74200 Audio Visual & Printing Production Costs | 0 | 1500 | 1500 | Design and printing, translation
| Organise the launch of the study at the Rights Activism conference | [5 empty] | 71600 Travel | 0 | 3000 | 3000
[7 empty] | 75100 Facilities & Administration (8%) | 0 | 471.2 | 471.2
| Total | [6 empty] | 0 | 6361.2 | 6361.2
| Activity 3.3. Organise the 3-country conference "Rights Activism including improved innovative communication tools and strategies" |  |  |  |  | DMFA | 75700 Trainings and Conferences | 40000 | -18000 | 22000
| Organise the 3-country conference "Rights Activism including improved innovative communication tools and strategies" to build capacity of the regional Programme partners on the rights activism and provide platform for innovative experience sharing | [5 empty] | 71600 Travel | 9000 | 2059.12 | 11059.12
[7 empty] | 74200 Audio Visual & Printing Production Costs | 2488.65 | 1000 | 3488.65
| Project Manager (50%) | [5 empty] | 71400 Contractual services - Individ | 8034 | 1342.121 | 9376.121 | Pr.Associate Jan-60%; Feb-March-100%
| Project Associate (60%) | [9 empty] | Pr.Lead Jan-50%; Feb-March-30%
| DPC (4%) | [5 empty] | 64300 Staff Mngmt Costs (DPC 4%) | 2678.53 | 2221.47 | 4900
[7 empty] | 75100 Facilities & Administration (8%) | 4761.812 | -695.9007 | 4065.9113
| Total | [6 empty] | 66962.992 | -12073.1897 | 54889.8023
| Activity 3.4. Hold the Theory of Change workshop |  |  |  |  | DMFA | 71300 Consultants local | 0 | 4000 | 4000
| Organise the workshop on Social Impact Measurement as part of the Social Innovation Conference in Kyiv with participation of the CSOs from three countries | [5 empty] | 71200 Consultants international | 0 | 9700 | 9700
| Event coordinator (IC) | [5 empty] | 71600 Travel | 0 | 9100 | 9100
| DPC (4%) | [5 empty] | 75700 Trainings and Conferences | 0 | 9100 | 9100
[7 empty] | 64300 Staff Mngmt Costs | 0 | 0 | 0
[7 empty] | 75100 Facilities & Administration (8%) | 0 | 2552 | 2552
| Total | [6 empty] | 0 | 34452 | 34452
| Activity 3.5. Conduct the 2-country study on "Measuring the Civic Literacy" |  |  |  |  | DMFA | 71600 Travel | 0 | 9000 | 9000
| Launch the results of the regional study at the Forum of Young Leaders in Minsk on 4-5 Match 2017 | [5 empty] | 74200 Audio Visual & Printing Production Costs | 0 | 5000 | 5000
[7 empty] | 75700 Trainings and Conferences | 0 | 9000 | 9000
[7 empty] | 74500 Miscellaneous Expenses | 0 | 2000 | 2000
[7 empty] | 75100 Facilities & Administration (8%) | 0 | 2000 | 2000
| Total | [6 empty] | 0 | 27000 | 27000
TOTAL Facilities & Administration (8%) | [7 empty] | 10301.922 | 5539.9086 | 15841.8306
TOTAL OUTPUT 00098503 | [7 empty] | 66962.992 | 55740.0103 | 122703.0023
TOTAL AWP 2017 | [7 empty] | 167931.502 | 61064.2066 | 228995.7086
Prepared by DHRP Team Lead: Ms. Olena Ursu _________________________________
Cleared by Finance Analyst: Ms. Olga Iurlova __________________________________
Approved by DCD: Ms. Blerta Cela __________________________________
[10 empty] | DMFA funds | 213864.7136 | 213865 | 8554.6
[10 empty] | Korean funds | 15130.995 | 15131
228996
[11 empty] | 213866 | Средства DMFA 2017 года (3 месяца)
[9 empty] | DPC regional | 4908.12 | 122703 | Кеш регионального компонента 00085903
[9 empty] | DPC other | 3646.48 | -0.00228 | Сумма к распределению по региональному компоненту
[11 empty] | 1.2886 | Сумма для распределения по статьям аутпутов 46 и 47