Project ID: Project Title

00087334: Institutional Support to Climate Change Adaptation and Mitigation

Annual Progress Report

Photo credits and caption

January – December 2014

Project Snapshot

| Date: |  |  | 2nd December 2014 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Award ID: |  |  | 00075411 |  |  |  |
| Project ID: |  |  | 00087334 |  |  |  |
| Project Title: |  |  | Institutional Support to Climate Change Adaptation and Mitigation |  |  |  |
| Project Start Date: |  |  | August 1,2013 |  |  |  |
| Project End Date: |  |  | December 31,2017 |  |  |  |
| Implementing Partner: |  |  | UNDP |  |  |  |
| Responsible Parties: |  |  |  |  |  |  |
| Project Budget (all years): |  |  |  |  |  |  |
| Core Resources: Non-Core Resources: Government contribution: Donor 1 Donor 2 |  |  | 2004 TRAC UNDP: $470,000.00 |  |  |  |
| Project Brief Description and Outputs: The National Climate Change Policy for Pakistan was officially launched on February 26, 2013. The policy includes framework of implementation of National Climate Change Policy and was developed through UNDP support. This project aims at undertaking a series of activities to help mobilize substantially enhanced funding for climate change adaptation and mitigation related initiatives, within the over-arching framework defined by the climate change policy. This project is, therefore, aimed at providing institutional support for the large scale operationalization of the National Climate Change Policy in the long term within the context of climate change adaptation and mitigation. It is focused on developing and implementing climate change adaptation and mitigation strategies and action plans. |  |  |  |  |  |  |
| Overall Project Quality Rating (mark on the scale of 1 to 5 as per the following criteria):3 |  |  |  |  |  |  |
| Exemplary (5) ***** | High (4) **** |  |  | Satisfactory (3) *** | Poor (2) ** | Inadequate (1) * |
| All outputs are rated High or Exemplary | All outputs are rated Satisfactory or higher, and at least two criteria are rated High or Exemplary |  |  | One output may be rated Poor, and all other criteria are rated Satisfactory or higher | Two outputs are rated Poor, and all other criteria are rated Satisfactory or higher | One output is rated Inadequate, or more than two criteria are rated Poor |
| Budget 2014 |  | 470,0000 |  |  |  |  |
| Expenditure 2014 |  |  |  |  |  |  |
| Delivery % |  |  |  |  |  |  |

Contents

- Introduction

- Situation Analysis

- Project Performance and Results

  - Contribution toward Country Programme Outcome

  - Achievement of Project Results/Outputs

- Lessons Learnt

- The Way Ahead/Key Priorities for 2015

Annex 1: 	AWP Based reporting matrix

Annex 2: 	Annual Project Quality Assurance Assessment

Acronyms

Climate Change (CC)

Climate Change Division (CCD),

Climate Public Expenditure and Institutional Review (CPEIR):

Controller General of Accounts (CGA)

Every Drop Matters (EDM)

Khyber Pakhtunkhwa (KP)

Pakistan Tehreek-e-Insaaf (PTI)

Sustainable Development Policy Institute (SDPI)

Sustainable Energy for All (SE4ALL)

- Introduction

2014 was the first year of implementation for this project. A series of activities were planned to support climate change programme development and resource mobilization for pilot implementation at local level. The overall outcome would be in terms of the benefit that vulnerable populations would receive from improved sustainable environmental management practices, focusing on climate change mitigation and adaptation.

- SITUATION ANALYSIS

Briefly describe any changes in the project’s external context that have positively or negative impacted the achievement of project results

The DIM project was introduced in context of the National Climate Change Policy for Pakistan, launched in 2013. The policy provided an overarching framework for implementation, based on which this project was developed to support government departments/ministries and other organizations to design strategies and implement projects aimed at CC adaptation and mitigation. This created a favorable environment for the project to leverage support from the government for projects aligned with the National Climate Change Policy.

However, the project suffered negatively due to some unforeseen changes in the political environment of the country. The ongoing political unrest due to the protests from opposition party PTI (Pakistan Tehreek-e-Insaaf) created challenges in gathering data/interviews from both federal and KPK government. For more than a month government officials had refused to provide data and become available for consultations as all state apparatus was involved in dealing with the political upheaval.

The project was also delayed due to some internal power struggle within Controller General of Accounts (CGA) concerning judicial court involvement. This created difficulties in communicating with relevant officials in CGA to provide us with budgetary data needed for analysis.

- Project Performance and results

  - Contribution towards Country Programme Outcome

| CPAP Outcome: 3.2 Vulnerable populations benefit from improved sustainable environmental management practices, including climate change adaptation and mitigation. Output 3.2.1 Climate Change adaptation and mitigation strategies and action plans developed and piloted at local level federal and provincial governments, private sector, academia and civil society, including women’s groups. |  |  |  |
| --- | --- | --- | --- |
| Indicator(s): Per cent reduction in CO2 emissions; Number of key environmental institutions implementing adaptation and mitigation plans; Number of private sector companies, academic institutions and media bodies engaged in joint public awareness/advocacy initiatives on climate change Number of gender sensitive provincial climate change adaptation and mitigation action plans developed and implementation supported. | Baseline: National Climate Change Policy developed; Limited capacities at federal and provincial levels for policy implementation; | Target(s): Modern techniques introduced in order to adapt to climate change in two regions; GHG emission reduced by improvement in one local manufacture industries; Local community based initiatives for adaptation to climate change promoted in two locations | Achievement(s): Climate Public Expenditure and Institutional Review (CPEIR): -A draft report for CPEIR in Pakistan is being finalized and will be launched by end of this year. -$0.5 million USD has been mobilized through DFID to upscale the project and support integration of climate change into the national budgetary system. Sustainable Energy for All (SE4ALL): -The report has been finalized and will be launched by December. -Through the initiative, Pakistan has now been included in the list of 8 prioritized countries for funding from ADB under SE4ALL. Every Drop Matters (EDM) -Three NGOs (funded through the project) have implemented clean water supply, sanitation and Climate Change (CC) adaptation projects in different parts of the country. Support CC related activities -Different initiatives have been supported at national/ regional level to create linkages and partnerships which help create awareness of CC related issues and encourage targeted action plans to be designed. -UNDP is also strengthening GEF Cell’s expansion into the Climate Finance Unit at Climate Change Division (CCD), which will help leverage greater international CC funds. |
| Description of output level high/outcome level results achieved in 2014: - The CPEIR report will help strengthen climate public finance in Pakistan, by supporting climate responsive budgeting and effective spending, which encourages foreign donors to invest in CC in Pakistan. The aim is to benefit vulnerable populations from greater/improved spending on CC. The action plans and strategies outlined through the document need to be implemented now for resource mobilization, to ultimately support CC mitigation and Adaptation. The CPEIR will also support and strengthen the budgetary process for Ministry of Finance. - The SEALL report provides an assessment and gap analysis of sustainable energy in Pakistan, which will become the basis for targeted investment in the sector, and for mobilizing international funds for SE4ALL initiatives in the country. The investment plan for sustainable energy now needs to be piloted to generate resources. The report will support and enhance the energy portfolio for Ministry of Water and Power. -Vulnerable populations in different parts of Sindh (Thatta and Malir), and Nushki District, Balochistan have benefitted from access to clean water supply and sanitation facilities provided by different projects funded through the EDM initiative. These projects have provided environmentally sustainable solutions of water management for the communities, and helped build capacities for three different NGOS/CSOs. -Different CC initiatives at national and regional level are being supported through the project, which provide platforms for increasing awareness of CC related issues and leveraging greater and national/international funding for projects aimed at CC adaptation and mitigation. Through the project the key institutions engaged with/strengthened include: GEF Cell at CCD, Ministry of Science and Technology and UNESCO, and SDPI. Summary -2 programmes/studies developed -9 institutions (ministries, CSOs, NGOs) engaged with and strengthened. -3 Local community based initiatives, employing modern techniques which contribute towards climate change mitigation and adaptation, have been implemented -o.5 million dollars mobilized through the project for upscaling the CPEIR initiative |  |  |  |
| Means of Verification -Specific publications, evaluations, field observations, interviews, and consultation workshops. |  |  |  |

  - Progress towards Project Results/Outputs

| Project Output I: Climate change adaptation and mitigation strategies and action plans developed and implemented. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Indicator(s): - # of new programmes/action plans developed - # of projects and action plans implemented - % of resources mobilized required to implement newly designed programmes/projects |  | Baseline: - Zero programmes/action plans developed - Zero projects and action plans implemented - 0% of resources mobilized for implementation of various programmes/ projects under development |  | Target(s): -09 programmes/ studies will be developed -03 projects shall be implemented -50% resources shall be mobilized to support various programmes/ projects |  | Achievement(s): CPEIR: Climate Public Expenditure and Institutional Review (CPEIR): -A draft report for CPEIR in Pakistan is being finalized and will be launched by end of this year. -$0.5 million USD has been mobilized through DFID to upscale the project and support integration of climate change into the national budgetary system. Sustainable Energy for All (SE4ALL): -The report has been finalized and will be launched by December. -Through the initiative, Pakistan has now been included in the list of 8 prioritized countries for funding from ADB under SE4ALL. Every Drop Matters (EDM) -Three NGOs (funded through the project) have implemented clean water supply, sanitation and Climate Change (CC) adaptation projects in different parts of the country. Support CC related activities -Different initiatives have been supported at national/ regional level to create linkages and partnerships which help create awareness of CC related issues and encourage targeted action plans to be designed. -UNDP is also strengthening GEF Cell’s expansion into the Climate Finance Unit at Climate Change Division (CCD), which will help leverage greater international CC funds. |  |
| Description of output level results achieved in 2014: - The CPEIR report will help strengthen climate public finance in Pakistan, by supporting climate responsive budgeting and effective spending, which encourages foreign donors to invest in CC in Pakistan. The aim is to benefit vulnerable populations from greater/improved spending on CC. The action plans and strategies outlined through the document need to be implemented now for resource mobilization, to ultimately support CC mitigation and Adaptation. The CPEIR will also support and strengthen the budgetary process for Ministry of Finance. - The SEALL report provides an assessment and gap analysis of sustainable energy in Pakistan, which will become the basis for targeted investment in the sector, and for mobilizing international funds for SE4ALL initiatives in the country. The investment plan for sustainable energy now needs to be piloted to generate resources. The report will support and enhance the energy portfolio for Ministry of Water and Power. -Vulnerable populations in different parts of Sindh (Thatta and Malir), and Nushki District, Balochistan have benefitted from access to clean water supply and sanitation facilities provided by different projects funded through the EDM initiative. These projects have provided environmentally sustainable solutions of water management for the communities, and helped build capacities for three different NGOS/CSOs. -Different CC initiatives at national and regional level are being supported through the project, which provide platforms for increasing awareness of CC related issues and leveraging greater and national/international funding for projects aimed at CC adaptation and mitigation. Through the project the key institutions engaged with/strengthened include: GEF Cell at CCD, Ministry of Science and Technology and UNESCO, and SDPI. Summary -2 programmes/studies developed -9 institutions (ministries, CSOs, NGOs) engaged with and strengthened. -3 Local community based initiatives, employing modern techniques which contribute towards climate change mitigation and adaptation, have been implemented -o.5 million dollars mobilized through the project for upscaling the CPEIR initiative |  |  |  |  |  |  |  |
| Overall Output Status (mark the output on the scale of 1 to 5 as per the following criteria): 4 |  |  |  |  |  |  |  |
| Exemplary (5) ***** | High (4) **** |  | Satisfactory (3) *** |  | Poor (2) ** |  | Inadequate (1) * |
| The project is expected to over-achieve targeted outputs and/or expected levels of quality, and there is evidence that outputs are contributing to targeted outcomes | The project is expected to over-achieve targeted outputs and/or expected levels of quality |  | The project is expected to achieve targeted outputs with expected levels of quality |  | The project is expected to partially achieve targeted outputs, with less than expected levels of quality |  | Project outputs will likely not be achieved and/or are not likely to be effective in supporting the achievement of targeted outcomes |
| Means of Verification Office meetings, field visits, email correspondence, conference calls and progress reports. |  |  |  |  |  |  |  |

- Lessons Learnt

Please indicate if the lesson you are describing was derived from either a project success (e.g. the results were achieved or even exceeded) or from a project challenge (e.g. the results were not achieved within intended time/budget/quality parameters). Please cite evidence or any other sources that support your assertions to the success/challenge of the project. Report on any review/evaluations undertaken relating to the project and how they were used during implementation. What are the key findings?

Political economy of the state and power/policy relations between the federal and the provincial governments need to be taken into account while planning and preparing national level action plans and programmes. This is derived from the delay in data collection for CPEIR, which can largely be accredited to organizational hierarchies and power struggles at CGA, and political tensions at the center.

Feedback from federal government needs to be streamlined in accordance with the scope of the project, and channeled through planned formal and informal mediums. This should be planned in advance, keeping in mind the bureaucratic processes involved and the time it would realistically take. This is derived from the delay in finalization of the SE4ALL report due to delayed and inconsistent inputs from various ministries.

It is useful to do a more thorough background study of the type and level of work that will be expected from each team member in the project, to avoid backlog caused by unplanned additional work. Additional team members needed to be hired in the middle of the CPEIR exercise.

It is useful to effectively engage relevant officials from both provincial and federal government throughout a policy study (CPEIR), in order to improve chances of endorsement and implementation by the state.

It is necessary to maintain regular communication and conduct regular monitoring visits to projects where tangible activities can be verified. Projects which have short term funding (EDM) need to be monitored very stringently to make sure activities are completed on time.

- The way forward/ key Priorities FOR 2015

State priority actions/recommendations planned for the coming period to overcome constraints, build on achievements and partnerships, and use the lessons learned during the period. Indicate any major adjustments in strategies, targets or key results planned for the coming period; taking into consideration project alignment with the national developments/trends etc.

Annex: AWP based Reporting Matrix

| EXPECTED OUTPUTS And baseline, associated indicators and annual targets | PLANNED ACTIVITIES (as per AWP) | Activity Status Completed, Ongoing, Delayed, Cancelled | AWP Budget ($) | Expenditure ($) | % Delivery |
| --- | --- | --- | --- | --- | --- |
| Project Output 1 Climate Change adaptation and mitigation strategies and action plans developed and implemented Indicators: -# of new programmes/action plans Developed -# of projects and actions plans implemented -% of resources mobilized required to implement newly designed programmes/projects Baseline: -zero programmes/action plans developed - zero projects and actions plans implemented - zero resources mobilized for implementation of various programmes/projects under development Targets: -09 programmes/studies will be developed -03 projects shall be implemented - 50% resources shall be mobilized to support various programmes/projects that will be developed | 1.1 Activity : UNDP Pakistan’s Climate Change Programme designed and operationalized | Ongoing | 35,000 |  |  |
|  | 1.2 Activity: Undertake Climate Public Expenditure and Institutional Review (CPEIR) through APRC support | Will be completed by Dec 2014 | 70,000 |  |  |
|  | 1.3 Activity: Develop UNDP Pakistan’s SE4ALL (Sustainable Energy for All) Programme | Completed- Launch remains | 5,000 |  |  |
|  | 1.4 Scoping the potential for mainstreaming environment and climate change into the development agenda of Khyber-Pakhtunkhwa (KP) | Delayed | 5,000 |  |  |
|  | 1.5 UNFCC Negotiations support/participation of relevant Federal/provincial government officials in COP 20 | Will be completed by Dec 2014 | 20,000 |  |  |
|  | 1.6 Scoping the potential for Low Carbon, Low Emission Urban Development in Pakistan | Delayed | 0 |  |  |
|  | 1.7 Manage “New World: Inclusive Sustainable Human Development Initiatives” Project (UNDP’s Global programme funded by Coca-Cola) | Ongoing | 0 |  |  |
|  | 1.8 Support Climate Change related initiatives at national/regional level to create linkages and promote partnerships | Will be completed by Dec 2014 | 28,000 |  |  |
|  | 1.9 strengthening GEF Cell in the GOP’s Climate Change Division | Ongoing | 110,000 |  |  |
|  | 1.10 Management and administration |  | 197,000 |  |  |
| TOTAL |  |  | 470,000 |  |  |

Outcomes describe the intended changes in development conditions that result from the  interventions  of  governments  and  other  stakeholders,  including  international development  agencies  such  as  UNDP. They  are  medium-term  development  results created through the delivery of outputs and the contributions of various partners and non-partners.  Outcomes  provide  a  clear  vision  of  what  has  changed  or  will  change globally or in a particular region, country or community within a period of time. They normally relate to changes in institutional performance or behavior among individuals or groups. Outcomes cannot normally be achieved by only one agency and are not under the direct control of a project manager.

Outputs are short-term development results produced by project and non-project activities. They must be achieved with the resources provided and within the time-frame specified (usually less than five years).