Narrative Report

FGM Abandonment & Family Empowerment Program

1 July -31 December 2014

FGM Abandonment and Family Empowerment Joint Program

Progress Report

1 July – 31 December 2014

Summary Program Action Overview in Second half of 2014:

This program mainly aims to reduce FGM prevalence rates through promoting human rights and family empowerment concepts both at policy and local levels.  FGM abandonment remains a key area of the program, thus ensuring that public hype remains, legislation implemented and that FGM abandonment concepts are mainstreamed effectively within national programs targeting young families with girls at risk.  The program provides a family rights package that addresses other issues such as early marriage and domestic violence.    Human rights and gender perspectives are cross cutting approaches that are continually adopted by the program.

The second half of 2014 witnessed a number of key achievements on the road to achieving the ultimate goal of FGM Abandonment nationwide.  Primarily the Joint Program succeeded in mobilizing families to speak out against their personal experience with FGM under the slogan of “Many people stopped FGM, You too can stop” and the overall campaign’s slogan is “Enough FGM”.  Bringing back organized media campaigns against FGM sends a message to the public confirming that the government will continue working to stop this detrimental practice.  At village level the media campaign strengthens the status of NGOs and CDA’s refuting FGM as most families on the ground consider TV a primary source for receiving information on social, political and other issues related to their daily lives.

Maintaining community activities on the ground and awareness campaigns on FGM detriments within the discourse of school activities, the impact of activities addressing girls and boys in school was captured excessively in the UNDP FGM Abandonment Documentary thus showing girls courageously refuting FGM and are not embarrassed to say that they were spared circumcision as their parents considered FGM a humiliating practice.

The First Degree Ruling of the Legal case of Soheir, who passed away during FGM by a physician, came as a disappointment since the guilty doctor was acquitted by Aga District Misdemeanor Court, thus public opinion response nationally and internationally expressed disappointment in ruling.  The Public Prosecutor of Dakahlia Governorate presented an appeal to the Dakahlia Appeal Court that showed the controversies in the ruling.  In December 2014 session of the appeal court the case was postponed to January 2015 for perusing thoroughly the first FGM case transferred to Egyptian Court.

In December 2014 the Project at NPC in collaboration with UNFPA launched training of district attorneys of Cairo and Giza governorates.  The training program enhanced building mechanism with General Prosecutor for mainstreaming and unifying approach of district attorneys when interrogating FGM cases similar to Soheir’s First Case.  The project agreed to implement 2 training courses with the Center for Judiciary Studies and the General Prosecutor for implementing a national Training Program in all governorates.

Summary Highlights of Program (July – December 2014)

- Finalize Media Campaign “Enough FGM” and preparing airing media plan.

- Public Prosecutor of Dakahlia Governorate submits an appeal to Dakahlia Appeal Court for Refuting first Degree Ruling or Sentence that acquitted guilty doctor.

- Voices of Young girls and boys empowered to speak out on the ground denouncing FGM as a detrimental and harmful practice.

### Project Activities and Results per Output:

### Output 1: National Population Council

### NPC has the capacity to mobilize and support line ministries, the medical community, regional universities, NGOs and other civil society entities media and civil servants to plan and implement strategies aimed at abandoning FGM.

The first output is mainly concerned with enhancing the capacity of NPC personnel, NGOs, project management unit to enable the sustainability and mainstreaming of FGM Abandonment Strategies and incorporate program goals and objectives within the existing NPC structure.  This component targets NPC Central Technical Secretariat and the branches in the governorates, Local Plans at governorate level, and the gender sensitization of education curriculums in collaboration with the Ministry of Education.   Below mentioned are the activities implemented according to project contract.

### Activities implemented According to Project Contract

Activity in Project Contract:  Training of Government and NGO Staff in selected governorates and districts according to the Capacity Assessment Exercise (page 25 of contract)

Capacity Building on Reproductive Health, FGM Abandonment and Family Empowerment module implemented for the NPC Branches in all governorates completed (Training Summary Report in English – Annex 1)

- Program unified training material on Reproductive Health (RH part developed by MOHP, UNICEF & UNFPA), Family Empowerment, and Gender for the NPC Branches, furthermore, the training module unified and coordinated with the MOHP (Population and Primary Health Care Sectors)to mainstream RH, FGM Abandonment and Family Empowerment messages through existing health service channels on the ground.  First phase of training implemented for NPC Branches of 27 governorates and the Central Technical Secretariat through 6 training courses each for five days including 30 trainees per training (Total 180 trainees).  The cost of logistics for trainings were supported by UNICEF, yet fully coordinated technically by the FGM Abandonment and Family Empowerment Program Unit at NPC. The program is currently preparing for supporting NPC Branches on incorporating above mentioned issues within the regional plans of the NPC in addition to the National Action Plan of the NPC with Family Empowerment reproductive health, concepts mainstreamed.

- Support NPC to develop operational steps and mechanisms for implementing national strategy for Eliminating Early Marriage.

Capacity enhanced and strengthened for NPC Media Department to Mainstream Family Empowerment Package on all the NPC Social Media Pages

- Upon completion of Mass & Social Media Training for NPC Personnel in the first half of the year of 2014, focusing on Social Development Issues including FGM, Early Marriage, Girls’ Education etc., the NPC staff started implementing skills strengthened by the capacity building on job training courses through developing a number of Social Media Pages on Facebook, twitter highlighting social issues related to family rights including violence issues, FGM, early marriage. Based on Capacity Development exercise implemented in the first half of 2014, the project selected members with outstanding skills from Media Department to participate in the Media platform for Family Empowerment.

Impact of Activities in Enhancing Output 1

### Increased Sensitization of NPC personnel centrally and regionally toward FGM abandonment and Family Empowerment issues.

- NPC Personnel incorporating training module of reproductive rights, family empowerment approach as an entry point to population strategy in their quarterly reports, media strategy of NPC, and on the NPC awareness/advocacy agenda plans in the governorates.

- FGM Abandonment included in all plans and strategy exercise of NPC, (Population and Reproductive Health Strategy).

- Addition of Gender Sensitive messages on FGM Abandonment, Early Marriage, gender discrimination consequences in Primary and Preparatory Education Curricula in Arabic and Social Studies’ Subjects.

Challenges and risks encountered in Output 1

- Coordination mechanisms between NPC Branches and ministries at governorate level needs to be strengthened and more focused.

- Budgets allocated at governorate levels for FGM abandonment and Family Empowerment issues are limited.

### Output 2:  Line Ministries mainstream the anti-FGM discourse in their programs and curricula and help empower families by providing comprehensive health social and education services packages

This Output focuses on strengthening networks with line ministries, religious organizations, universities, syndicates or special civil society groups concerned with policy matters pertaining to FGM Abandonment and Family Empowerment Issues.  The section below shows the cluster of activities in output 2 according to the Project Contract that were tackled in the second half of 2014 including training of District Attorney’s and the launch of the Communication Platform for Family Rights with media personnel concerned with family empowerment and other social issues.

### Activities implemented According to Project Contract

Activity in Project Contract:  Sessions with judiciary, women judges, district attorneys.  (page 28 of project contract)

5 Training courses on FGM Abandonment from Comprehensive Approach Completed Targeting 100 Senior and Middle Level District Attorneys from Greater Cairo Areas including Giza Governorate (First phase Training implementation completed December 2014 -  attached photos of training Annex 2).

- The program launched training program for district attorneys (senior and middle level) on FGM Detriments:  A comprehensive Perspective starting December 2014 in collaboration between the project and UNFPA.  The project held 5 courses with an average of 20-25 district attorney’s/course and the training duration was full day from 9a.m. -5.00p.m.  The course presented FGM from the Medical and Religious perspective and furthermore one of the public prosecutors from Greater Cairo or Dakahlia presented the legal process for FGM cases.  The case of Soheir from Dakahlia governorate who died during an act of FGM was referred to and the district attorneys discussed all the loopholes created in the case by the Forensic medicine in addition to their recommendations on how to proceed in the second level of the case with the Appeal Court. The first phase of the training targeted a total of 110 district attorneys from Cairo areas (popular slum areas where FGM is practiced more).

FGM Abandonment Training Module Mainstreamed in the Basic Preliminary courses targeting district attorneys with the Centre for Judiciary Studies of the Ministry of Justice

- The program in collaboration with the General Prosecutor’s Office mainstreamed 1 day training on FGM Detriments from the different perspectives within the capacity building program implemented for all newly appointed district attorney’s from different parts of the country.  Furthermore, the FGM program held in November 2014 a 2 trainings day for 220 newly appointed district attorneys on FGM detriments.  The feedback on the training from the Judiciary Centre Director was very positive thus they requested maintaining the training for the remaining groups joining in 2015.  This kind of mainstreaming is very sustainable as all costs and expenses for the trainees are carried by the Centre and the project only provided the external experts to cover the medical and religious perspectives of the training.

Activity in Project Contract:  Training for teachers, girls' education facilitators and religious leaders (page 28 of project contract)

- Curriculums approved by Minister of Education with the amendments made by Project Task force suggestions and recommendations in Arabic and Social Studies curriculums for Primary and Preparatory Education.  The Project Task Force included messages on FGM Abandonment, Early Marriage, reproductive health, gender discrimination problems.  Training guidelines for teachers on curriculum amendments developed in collaboration with the Ministry of Education.

Activity in Project Contract:  Establish a Family Rights Platform consisting of specialized civil society entities, representatives from upcoming political parties, experts and renowned media personalities.  (page 28 of project contract)

FGM Abandonment and Family Empowerment Dialogue Platforms Launched (Attached Annex 3– sample photos of first Platform Launch for Family Empowerment)

- In August 2014 the project (PMU at NPC) in collaboration with UNICEF and other partners of the JP launched the Family Rights Platform among 50-55 Journalists and media personnel including artists, social media experts, TV personnel and social development experts.  The first expert group meeting of the platform highlighted issues related to family violence issues were brought to the media agenda including FGM abandonment, child marriage, domestic violence etc.  The launch was documented on all the official social media pages of the NPC with full coverage on the platform including the overall goal, objective and it role in strengthening family empowerment messages among media personnel. (Second platform meeting with Rosaelyoussef Journal Organization covered under activity 5 according to financial expenditures).

Impact of second half 2014 Activities Implemented on Enhancing Output 2

- General Prosecutor’s Technical Team advocating for FGM Criminalization Law among Legal Community.

- Anti-FGM Culture spread among District Attorneys at different levels (newly appointed, middle level and senior level) as reflected in the participation level of the training and the recommendations that resulted from the training courses.

Key Recommendations for District Attorney Trainings on FGM Abandonment and Effectuating FGM Criminalization law:

- Coordinating the Implementation of FGM criminalization law between General Prosecutor, National Population Council, and Ministry of Health.

- Increasing punishment for perpetrators FGM Criminalization low 242 in penal code.

- Include clear Definition of FGM with health detriments to the forensic Medicine Standards Schedule.

- Training forensic Medicine Doctors on FGM Detriments.

- Anti-FGM culture widespread among the media organizations as reflected in the competition among different institutions like El Ahram or Al-Akhbar to host and support the family empowerment media platform issues including FGM Abandonment, Early Marriage, Education etc…Eight articles,covering the platform, were published in key national papers and websites including El Gomhouria, Rosaelyoussef, el Watan, Shabab el Nil, El Assema Program, El Akhbar, etc.)

Challenges and Risks Encountered in Output 2

- Effectuating FGM Criminalization Law will entail many legal partners that project needs to network with:  Forensic Medicine under the Ministry of Justice, Department of  Supervision on Private Health vicinities of the Ministry of Health, Doctor's Syndicate, thus the legal component requires intensified project efforts.

Output 3:  Strengthening and expanding the operational and regulatory environment to promote the abandonment of FGM and other forms of family violence, while implementing a holistic approach that empowers families by improving health and education services at the local level.

This output focuses on enhancing the socio-cultural environment at governorate level toward FGM Abandonment and Family Empowerment issues, through promoting comprehensive family rights service package (mainly health and education services) accompanied by local Rights Based Campaigns focusing on FGM addressing families to enable them to abandon the practice.  Other intervention areas of this output focuses on enhancing lobby groups on the ground to become watch dogs of the criminalization law by encouraging them to report perpetrators of the FGM Law.  Output 3 is also concerned with building capacity of legal persons, MOHP personnel and other local entities to implement the law thus transforming FGM from cultural norm to crime.  Proceeding effectively with FGM cases reported to the District Attorney’s influences the attitudes of families positively against the practice.

Activity Implemented According to Project Contract

Activity in Project Contract:  Organize awareness raising sessions, workshops and coordinated community campaigns on FGM.  (page 29 of Project Contract)

FGM Abandonment Program Coordinated Awareness Campaigns implemented in 10 Governorates (Beni Suef, Minya, Assiut, Sohag, Qena, Aswan, Fayoum, Qalubia, Gharbia, and Port Said)(Annex 4 – Sample Photos of community awareness campaigns and initiative from different governorates)

- The FGM abandonment Coordinated campaigns at village and governorate level are implemented by 20 National Focal NGOs in 10 governorates.  The Focal NGOs are also responsible for creating civil society synergies at the lower levels with the community development associations that enable larger organizations to implement their programs at village level.  The project strategy on the ground focuses on targeting young generations in schools or newly married families with girls at risk of undergoing FGM, thus many community campaigns focus on education and youth services provided at village level.  The community campaigns are run in primary and preparatory schools and furthermore,  health units with high flow of women and children as health and education services bring most of the village community together.    Below mentioned are further details of the community services and the number targeted at village and governorate level:

Brief on Coordinated FGM Abandonment and Family Empowerment Campaigns:

Detailed Topics for Awareness Sessions

- FGM

- Early Marriage

- Reproductive Health (Maternal Health, Family Planning, Child Nutrition etc.)

- Domestic Violence

The awareness focused on medical, social and religious perspectives of above mentioned topics.

- Total Refresher Trainings for the field workers in 10 governorates (123 trainings (average 2 days/workshop) on an average 20-25 persons/training (Community leaders, field workers, religious leaders, teachers, social workers, doctors and civil society activists).  (Total number of trainees 2623).

- Awareness Sessions on FGM Abandonment & Early Marriage Parallel to the Medical Caravans to invest women and children gatherings for service (32 sessions targeting 900 women) in Sohag, Qena and Aswan Governorates.

- Total awareness sessions in the 10 governorates (sessions held in big schools) targeting children (boys and girls in schools) primary and preparatory schools (79 awareness activities targeting total 2615 students).

- Door to door Home Visits implemented by female raedat (field workers) executed addressing girls at risk (Total home visits with total targeted women and men of 1157 persons).

Simultaneous to the awareness programs on the ground the focal NGOs are implementing different community service initiatives targeting health, education and other local initiatives requested by the respective communities in the project villages.  The community initiatives are tailored according to the village community priorities and needs as indicated in the village profile reports developed by the Focal NGOs in 10 governorates.

- 53 Medical Caravans in 53 villages (based on community need) targeting 1278 persons.

- School support scholarships (Books, school bags, notebooks etc.) targeting 945 child from 19 villages.

- Furbishing 4 nurseries (Tables, chairs, shelves, educational materials) targeting 150 child.  (Nursery services are required at village level as it is a main children outlet for families.

- Economic empowerment trainings for women to enhance their small informal home projects in 54 women clubs of 54 villages targeting 1628 women.

Activity in Project Contract:  Produce a manual on FGM that targets youth and peer to peer education. (page 29 of project contract)

Project provides technical support for UNICEF to implement Focus Group Meetings with Youth, Revise and Edit Peer to Peer Manual on FGM Abandonment

- Focus Group Discussions completed by Project NGO Coordinator with Youth who developed Y Peer Manual on FGM through 3 day workshop supported by UNICEF.  Furthermore, a second round of meetings scheduled early 2015 prior to completing and finalizing Y Peer Manual.

Activity in Project Contract:  Enhancing and building the capacity of district attorneys and judges on the philosophy behind criminalizing FGM and the detriments of the practice in order to encourage strict sentences on practitioners. (page 29 of project contract)

First Degree Court Ruling (Doctor Acquitted) for FGM Case of Soheir from Dakahlia Governorate

- The Dakahlia Misdemeanour Court held Three Court Hearings for the Period from July – November 2014.  Project/NPC lawyers provided court with detailed reports and memos on detriments and philosophy behind FGM Criminalization.   In November 2014 the First Degree Misdemeanour Court Acquitted Doctor who performed FGM for Victim Soheir el Batei.  The General Prosecutor on the same day of the ruling submitted an Appeal to the court for Revisiting Sentence in the Dakahlia Appeal Court.

Impact of Output 3 Activities

- Increased anti-FGM Momentum at village level in comparison to years 2012 and 2013.

- Youth Involvement on FGM Abandonment Efforts increased through Y Peer Manual Developed in collaboration with young target groups.

- Despite Disappointing Court Ruling in FGM Case, General Prosecutor Team responded positively through official appeal request.

Challenges and risks encountered in Output 3

- First Degree Court ruling acquitting FGM Doctor disappointing, yet project created public hype on the detriments of FGM Practice and its consequences.

Output 4:

Effective national and sub-national monitoring and evaluation systems are in place that can measure change and successes with respect to the abolishment of FGM.  This includes monitoring and follow up mechanisms in existing branches at the governorate level and further strengthening networking schemes between civil society and NGOs at the local Level.

Output 4 is one that is concerned with two dimensions of monitoring and evaluation.  The first one is concerned with measuring and evaluating the progress of FGM abandonment interventions both at policy and local levels, and secondly output 4 aims to strengthen existing monitoring mechanisms in the concerned organizations (NPC, line ministries, civil society etc.) to enhance follow up effectively of FGM Abandonment interventions.

Implemented Activities in Project Contract under Output 4

Activity in Project Contract:  Train NPC Branches personnel on M&E systems for assessing the impact of family rights and anti-FGM national programs. (page 30 of project contract)

- Trained NPC Monitoring and Evaluation Central Department and Governorate Branches on Reporting, Strengthening Logical Framework with impact indicators related to family empowerment (education, health, early marriage, FGM abandonment etc.)during training on Reproductive Health and FGM Abandonment mentioned above in Output 1 as 1.5 days of the Training Course was designated to Mainstreaming above mentioned issues and indicators in the regular monitoring plans of the NPC M&E Department. (Total Training Days for all Branches targeting NPC Personnel is 9 days targeting 180 persons).

Activity in Project Contract: Carry out an impact evaluation for up-scaling the FGM joint programme. (page 30 in project contract)

- Revision of First Draft Project Evaluation Report by project team to verify decline in FGM trends on the ground in the Project Focused Areas at governorate level.  Furthermore, the report documents all community service initiatives and its relation and impact on the targeted families with girls at risk. The Evaluation report provides both a quantitative and qualitative analysis on FGM Abandonment and other family rights services in the villages.  The report also captures some key findings on FGM and differences between Upper and Lower Egypt governorates as mentioned below:

  - Capacity of Upper Egypt NGOs is bigger than Lower Egypt NGOs as there is a longer Experience in Upper Egypt NGOs with projects implementation.

  - Prevalence rates in Lower Egypt is higher than Upper Egypt as a whole, yet openness among women and men in Upper Egypt reflects that project succeeded to completely break community silence on practice.

  - Control Villages show that media has brought information on FGM abandonment yet behavior change among families with girls at risk is very evident in project focused areas.

  - Key recommendations of report ensure vitality of focusing on young age groups in school as they are the real agents for change, thus working in schools and social services related to girls and boys in preparatory education years is essential.

Additional M&E Project mechanisms for Joint Program

UNDP and NPC PMU Coordination with UN Partners

The coordination of the PMU/UNDP with all UN agencies represented in the National FGM Abandonment Steering Committee is a core mechanism for follow up and coordination to ensure that any parallel activities implemented under the Joint Program do not overlap with the EU supported project.  The coordination mechanism includes a National Steering Committee headed by NPC and the UN Resident Coordinator and a Project Management Committee which meets at the level of project officers to enhance vision of Joint Program Implementation with Unified messages, approaches etc.  This Coordination mechanism falls under the Output 4 (Related to Monitoring and Evaluation).

In November 2014 1 Project Management Committee Meeting was held at UNDP in presence of the NPC EU supported Project team and representatives from UNFPA, UNICEF and UNWomen. Furthermore, the meeting discussed coordination among partners on the following items:

- Distribution of Airing Cost for “Enough FGM” Media Campaign.

- Workplan for 2015

- Coordination of District Attorney’s Training for strengthening implementation of FGM Law.

- Coordinating activities related to awareness programs in primary and preparatory schools to maximize geographic scope of Joint Program.

FGM Abandonment Efforts in Egypt’s CRC Report (Annex 5 – Summary Brief on FGM Abandonment Efforts submitted in Egypt’s CRC Report 2014)

Project Submitted Anti-FGM Actions Implemented in Egypt’s Report for Child Rights to the Ministry of Foreign Affairs through the Minister of Health and Population’s Office.  (Attached Summary Brief on Findings of FGM Abandonment Efforts in Egypt’s CRC Report)

Impact of Activities implemented under Output 4

- Mainstreaming FGM Abandonment in monitoring and quarterly reports of the government institution (NPC).

- Maximize resources for implementing key effective components like media campaigns, training of district attorneys, and awareness campaigns on the ground.

Challenges and Risks encountered in Output 4

- Management Change at NPC in November 2014 could have disturbed project implementation, yet selected Rapporteur was familiar with project file previously thus momentum did not slow down.

Output 5:

Advocacy and Communication Strategy is strengthened to support national and local campaigns for the abandonment of FGM as well as focusing on democratic family values against all forms of domestic violence.

This output is concerned with activities pertaining to advocacy and media components.  Output 5 focuses on media campaigns including TV, Radio and Press, capacity development on family rights issues for media personnel, renowned effective writers, TV presenters etc.

Implemented Activities in Project Contract under Output 5

Activities and Results implemented Related to Project Contract Under Output 5

Activity in Project Contract:  Develop and implement a communication strategy and plan of action on FGM and other forms of domestic/family violence and abuse.

- Communication Plan of Action initiated through the establishment and launch of the first Media Platform for Family Rights in August 2014.  The platform consisted of media experts and social development experts concerned with family empowerment issues including (FGM Abandonment, Early Marriage, Domestic and Community Violence, gender issues etc.) The platform aims to highlight social family empowerment issues in different media channels, thus the platform enhances providing media personnel with documented information on family empowerment portfolio, list of experts (speakers and guest in respective programs), and finally the platform enhances young media persons to adopt family right issues for keeping media momentum on the social files.

- The communication strategy aims toward enhancing the role of media organizations for adopting Family Empowerment and FGM Abandonment, the media platform was hosted by National Paper (Rosa el Youssef Media Institute) in collaboration with the NPC/PMU and UNICEF (JP Partner) to promote ownership among media organizations for adopting a family rights agenda.  The project created a network with leading media organizations to continue hosting the media platform and adopting social issues and values related to family rights.  In 2015 the project intends to hold media platform for family rights in Al-Akhbar and Al-Ahram organizations.  (Annex 6 – Sample photos of Rosaelyoussef Meeting with Media Personnel & Development Experts November 2014)

- The media platform established a data base with all media persons concerned with family rights issues from national and private media organizations.  Through the platform the project launched a social media page to create a consensus on family rights issues among young groups.  The PMU Communication and Training Coordinator organized the social media program agenda for the NPC Media Staff to feed and follow up on the feedback on the media platform social media pages.  (This activity is supported by EU and UNICEF).

- Paper coverage on the media platform included the following paper headings:

  - Launching a Media Platform for Enhancing role of media persons in addressing development issues.

  - NPC organizes second workshop for Media Platform on Development.

  - NPC organizes a workshop for addressing human development and social issues media wise.

Activity in Project Contract:  Production of advocacy materials on FGM for Dissemination.  (page 32 of project contract)

- TV Production (Audio Visual Material)

- Finalize production of two TV spots on FGM abandonment addressing the mother and father separately in collaboration with a technical committee consisting of technical team of NPC PMU and UNFPA technical team.  The spots include two versions, firstly testimonials of normal Egyptians who abandoned FGM men and women thus targeting both mothers and fathers.  The second set of spots is in drama version of a hesitant family that finally refused FGM for their daughter under campaign slogan “Enough FGM”.  The project team at NPC supported shooting the spot with testimonials from the villages or project site of the FGM Abandonment and Family Empowerment Project. (DVD with spots for campaign attached)

- Secondly the procedure for selecting and bidding for the media airing companies was completed.  TV spots on FGM Abandonment will be launched on all prime time channels.

- Support UNDP Media Crew to shoot short documentary on FGM Abandonment efforts on the ground in  Qena Governorate, the film includes or throws light on the below mentioned captured trends of the film:

UNDP New York Communication Department shot documentary film on Families abandoning FGM in Beir Anbar Village, Qena Governorate in November 2014.  The film captured briefly the following areas related to the project:

- An interview with Project Director on the approaches adopted by project, partnerships and impact.

- Families telling their stories on how they decided to abandon FGM with the increasing information they received both locally or through media.

- Young girls refuting the practice and denouncing practitioners of FGM.

- Footage showing the messages and rhymes denouncing FGM developed by the local field workers and school girls of the village.

- Change implied by the project and its impact on hesitant families and furthermore, the young generations that is culturally exposed to the detriments and criminality of FGM.

(Annex 7 - List of Audio-visual materials Links on You tube and sample of Articles related to FGM in Egypt)

Printed Materials Produced

- Re-printing 1000 copies of Communication Strategy for Family Empowerment.

- Printing 3 books on Women Rights in Islam verifying family rights issues focusing on women from a religious perspective (books printing supported by UNWomen).

Activity in Project Contract:  Youth trained to design popular media campaigns on FGM.  (page 32 of project contract).

- Launching “Enough FGM” Social Media Campaign in August 2014, the page documents all material developed on FGM Abandonment and furthermore provides an outlet for young people to ask further questions on the detriments of the practice thus enhancing youth to refuse FGM and challenge fanatic groups promoting continuity of the practice.  The page also is an outlet for civil society organizations concerned with FGM abandonment efforts to share their work and initiatives implemented to support program objective.  The slogan for the TV Campaign came from the support and consensus made by young people on the slogan “Enough FGM”.  The page is coordinated by the PMU and supported by field groups of the project in 10 governorates. (Facebook Link:  www.facebook.com/fgmenough)

Impact of Activities implemented under Output 5

- Increased coverage in Egyptian Press and Media on FGM Abandonment and Family Empowerment Issues.

- Identifying concerned media persons and creating ongoing mechanism with media to maintain family empowerment issues in Egyptian media channels.

- Increased public hype on FGM Abandonment Efforts in international media mostly focused on Egypt.

- Unified FGM Abandonment Discourse with consistent messages in the Egyptian media channels, press, social media etc.

Challenges and risks encountered under Output 5

- Negative Media impact regarding FGM Legal Case of Soheir from Dakahlia was a great challenge faced by the project, yet communicating rapidly with media corrective action and concern of the project enhanced moving forward with the project.