United Nations Development Programme

Programme of Assistance to the Palestinian People

### برنامج الأمم المتحدة الإنمائي/ برنامج مساعدة الشعب الفلسطيني

PROJECT DOCUMENT

Project Title: Improvement of Health Care Waste Management system in the Southern Governorates of the Gaza Strip

Project Number: Atlas Proposal Number 109210, Output Number 108575

Implementing Partner: DEX Modality in coordination with Ministry of Health, Ministry of Local Government, Environment Quality Authority, and the Solid Waste Joint Service Council in in the Southern Governorates of the Gaza Strip

Start Date: 1 April 2019	End Date: 31 March 2020	LPAC date: 12 February 2019

Brief Description

This project aims to protect the public health and improve the wellbeing of the Palestinian population in the Gaza Strip through controlling the pollution resulting from improper management of health care waste. Throughout its implementation the project will enhance the capacity of the Joint Service Council in the Southern Governorates of the Gaza Strip on health care waste by supplying, commissioning and operating a medical waste treatment device (microwave) that will be used in the treatment of the medical waste. The capacities of Ministry of Health in health care management will be improved through training of MOH personnel. This project will build and complement the ongoing pilot project implemented by JICA and focused on the improvement of health care waste management within the hospitals and clinics. It will also improve the efficiency and operation of the medical waste treatment facility in the southern area of the Gaza Strip.

| Total resources required: | USD 516,000 |  |
| --- | --- | --- |
| Total resources allocated: |  |  |
|  | UNDP TRAC: | 0 |
|  | Donor (GoJ): | USD 516,000 |
|  | Donor: |  |
|  | In-Kind: |  |
| Unfunded: | 0 |  |

Contributing Outcome (UNDAF/CPD, RPD or GPD):

UNDAF Strategic priority 4: Leaving No One Behind: social development and protection: By 2022, all Palestinians, especially the most vulnerable who are often left behind, have access to quality services, including health and education and social protection systems.

UNDP Strategic Plan 2018-2021 Outcome 3:

Strengthen resilience to shocks and crisis

UNDP/PAPP Output of the Palestinian Programmatic Framework (PPF)

4.1.3: Support and build the capacity of PWA, Ministry of Local Government, and related municipalities in wastewater and solid waste management (i.e. wastewater tariff, cost recovery, promote community participation, and raise awareness) and Improve access to wastewater and solid waste services including collection, treatment and reuse/recycling

Gender marker: GEN1 (contributes to gender equality in a limited way)

Agreed by (signatures):

UNDP / PAPP

Print Name: Roberto Valent, Special Representative of the Administrator

Date:

- Development Challenge

Medical waste is generally defined as “any solid waste that is generated in the diagnosis, treatment, or immunization of human beings or animals, in research pertaining thereto, or in the production of testing of biologicals, including but not limited to soiled or blood soaked bandages, culture dishes and other glassware, discarded surgical gloves-after surgery, discarded surgical instruments-scalpels, needles – used to give shots and draw blood; cultures, stocks, swabs used to inoculate cultures, removed body organs- tonsils, appendices, limbs, placentas, etc.  Medical waste also covers pharmaceutical waste, chemical waste with high metal contents such as mercury and cadmium, and radioactive waste.  Infectious waste (regulated waste) and pathological waste usually constitute 15% of the health care facilities’ total waste.

In 2012, The United Nations Development Program (UNDP) conduced a feasibility study of Solid Waste Management in Gaza Strip; the study presented an initial analysis of the medical waste sector in Gaza and some initial recommendations. The study supported the following actions that have to be undertaken:

- Strengthening institutional capacities regarding regulatory issues within Gaza;

- Strengthening capabilities within the major municipalities in Gaza, and the major hospitals;

- Supply of Autoclave equipment and related medical waste containers;

- Awareness raising among medical staff in the public.

According to an in depth Assessment Study for the Health Care Waste Sector in the Gaza Strip which was conducted by the Japan International Cooperation Agency (JICA) in 2016, the health care facilities, i.e. hospital and primary health clinics and other medical centers, generate 7,161 kg/day of medical waste; of which 1,068 Kg is infectious waste.  The Ministry of Health (MoH) hospitals are considered the main generators of waste, estimated at 4,701 kg/day of which 715 kg/day is infectious.

According to discussions with the Ministry of Health, Environmental Quality Authority, Municipalities, Joint Service Councils and many studies and reports that were recently conducted and referred to in earlier paragraphs, it is evident that health care waste management in the Gaza Strip is crippled, underdeveloped and poses a great public health risk on the Palestinian population in general and the personnel of health care facilities and medical waste handlers in particular.  Moreover, poor management and treatment of medical waste leads to environmental pollution and degradation of natural resources.

The main challenges posed by medical waste in the Gaza Strip are:

- The infectious waste is dumped in municipal landfills along with regular solid waste, thus posing high public health and environmental risks. This is because there is no proper waste sorting inside the hospitals. Most health care facilities conduct sorting processes only for sharp boxes and dispose all other infectious waste with the regular solid waste.

- There is no treatment facility and no special collection system for infectious waste, which reduces the incentive for health care facilities and service providers to sort waste. Infectious waste is collected by the same municipal staff, disposed in the same containers as the regular solid waste and transported in the same vehicles.

- The main treatment procedure for health care waste in the Gaza Strip is incineration There are two incinerators with a capacity less than 250kg/day and are utilized to incinerate safety boxes from all medical centres in Gaza. However, there are no health, safety or environmental monitoring procedures in place for the operation of these incinerators or their emissions. Inefficiency and incomplete combustion can cause air pollution and lead to the emission harmful gases such as methane and carbon dioxide, among others.

- Other hazardous waste such as heavy metals, chemotherapy waste and photographic chemicals used in radiology is disposed of is not separated from the municipal waste stream and is also disposed of and collected with the general municipal waste and ends up in the landfill.

These malpractices, within the solid waste sector, threaten the public health of a large number of people putting entire communities at risk, cause major negative impacts to the environment and result in natural resources degradations.  These risks are summarized as follows:

- In the current situation, people living in the targeted area are at risk of blood born pathogens that lead to AIDS, Hepatitis B & C which are fatal diseases.

- As there is no proper collection system of medical waste, the population at large is at risk of blood born pathogens that may result from needle stick and injuries from other medical contaminated sharps waste that they can come in contact with.

- The inefficient incinerators at Shifa, Nasser and the mental health hospitals in the area in addition to the open burning of waste in the dumpsites all around the Gaza Strip, that usually contains medical waste (including pathogens, heavy metals, poly vinyl chloride) will release noxious gases and volatile heavy metals such as mercury, cadmium, arsenic. It will also release DIOXIN, which is known to be the most toxic substance known to science, as it has multiple of adverse effect on the human health even at very low exposures.  Dioxin is also a well-known carcinogen that can cause Cancer. Moreover, Dioxins causes reproductive and developmental effects and damages the immune system leading to increased susceptibility and vulnerability to infectious diseases.

- If mercury is not separated from the general waste stream in the hospitals and is collected and disposed of with the general waste, but instead ends up in the incinerators of the hospitals or at the landfill and dumpsites and is burned, then it becomes an air-born mercury that will potentially enter the environmental cycle and pollute, water, soil and all human and wildlife. Mercury is very poisonous because it attacks the body’s nervous system, it can also harm the brain, kidneys and lungs and results in slurred speech, impaired hearing and muscle weakness memory loss and mental disturbance.

- Runoff and leachate of the accumulated solid waste and dumps infiltrate into the ground and pollute the aquifers, ground and surface water resources. It also contaminates the soil and renders it unsuitable for cultivation, especially if medical waste and heavy metals are dumped indiscriminately.

- Odours can be a real nuisance, particularly for the most vulnerable members of the community such as, the infirm (especially those who suffer from respiratory track and chest infections), the elderly, children and women.

- Illegal solid waste dumping damages aesthetic environment, degrades the natural sceneries.  Moreover, it discourages development in the areas of waste dumping.

Considering the above-mentioned challenges and risks, there is an urgent need to intervene to protect public health and control pollution of the natural resources as the problems are many and diverse in nature and need to be addressed at different levels. During the last two years, UNDP/PAPP and JICA have been discussing these alarming issues and problems with the Ministry of Health, Environment Quality Authority, Ministry of Local Government and other related partners, including NGOs, to address the health care waste problems and replicate the successful pilots in the West Bank.  Two earlier concepts were prepared (in 2016 and 2017) to address and improve the health care waste management in the Gaza Strip.  Fortunately, in 2017, JICA managed to mobilize resources and initiate a pilot in the Middle and Southern Governorates of the Gaza Strip, namely in the Middle area, Khan Younis and Rafah with a total population of around 1 million.

The current JICA programme aims at developing a model of onsite and offsite management of health care waste to functionalize the system in the Gaza Strip through the provision of efficient and environmentally/socially-sound treatment and disposal. The ongoing program consists of the following activities: 1) Support JSC south capacity to be the responsible entity for the off-site collection, transportation, treatment and final disposal, 2) Development of medical waste management manual and materials, 3) Procurement of consumable materials for MOH and JSC south (targeting primary health clinics), 4) Construction of an Autoclave house in JSC south, 5) Relocate the Autoclave to the JSC south and training to MoH and JSC staff. In addition, the World Bank will develop Management Information System (MIS) for Solid waste management including the Medical Waste and Qatar Charity will install Solar Energy Panel for the medical waste facility.

The existing treatment is mainly using the Autoclave technique. During the service, JSC faced many operational problems due to the machine technical limitations. The existing machine operates with a small-scale capacity. The operational manual of the machine states that the sterilization chamber accommodates 50kg/cycle/1.5hr.; however, the actual operation of the machine shows that the maximum quantity that the sterilization chamber can accommodate is 28kg/cycle/2.5hr. This technical limitation results in high operational and maintenance costs reflected in an increased tariff from 2.5NIS/kg to 10NIS/kg. In addition to that, the service expands to cover the governmental clinics in South and Middle Area with two department of Al Shifa with an average generation 1000kg/week. With the existing low capacity of the machine, the service may stop. Stopping the work of the device will lead to the collapse of the safe collection and disposal system and return to improper medical waste management with no possibility of future expansion.

Thus, the option of the Autoclave is not feasible on the long-term horizon for the future expansion of Gaza health centres. Looking for other treatment technologies with higher capacity and lower maintenance and energy costs is necessary for two main objectives beside the ultimate one of protecting the environment from serious pollution resulting from unsafe handling of medical waste and combat infection within health institutions:

- To expand the medical waste treatment services for hospitals, NGOs clinics and private health centres to be integrated in the project.

- To strengthen the culture of medical waste onsite and offsite management.

# Strategy

UNDP/PAPP project will build and complement the ongoing pilot (currently implementing by JICA) in the targeted area and focus on the improvement of health care waste management within the hospitals along with the strengthening of the Joint Service Council capacity in solid waste management, in the Southern Governorates of Gaza. It will also improve the efficiency and operation of the treatment facility. For a successful completion of this pilot in the south, UNDP/PAPP will continue its partnership with JICA, the Ministry of Health, the Ministry of Local Government, the Environment Quality Authority and the Joint Service Council for Solid Waste Management in Gaza and the Northern Governorates, to identify lessons learned and gaps and replicate the pilot in the northern area and Gaza city. This project will have a great impact on the protection of public health and would reduce pollution resulting from improper management of health care waste.

The proposed project is in line with the United Nations Sustainable Development Goals (SDG’s 2030), ensuring healthy lives and promoting well-being for all at all ages, making cities and human settlements inclusive, safe, resilient and sustainable (SDG 3,6,9,11 and 15). This project is also in line with the national policy agenda of 2017-2022 where national priority nine called for “Quality Health Care for All” and related national policies “Better Health Care Services” and “Improving Citizens’ Health and Well-Being”. In addition to national priority ten “Resilient Communities” and related national policy “Ensuring a sustainable environment and adapting to climate change”.

# Results and Partnerships

Outcomes:

The public health protected, the environment saved, and pollution controlled through improvement of health care waste management in the Gaza Strip.

Outputs and Activities:

Output 1:  The Capacity of the Joint Service Council in the Southern Governorates of the Gaza Strip regarding health care waste is enhanced

Activity 1.1: Procurement, installation, and operation of microwave (treatment equipment)

These activities will complement the previous and ongoing activities that are being conducted by JICA regarding building the capacities of the JSC in health care waste management, with regards to handling, transportation, storage and treatment of infectious waste. JICA is currently planning to conduct a training programme for the JSC. This project will support the JSC in procurement microwave to treat the medical waste and to start implementation of the health care waste management systems inside the hospitals in the South of Gaza and in the kidney and laboratory units in Al-Shifa Hospital in Gaza city which will leads to reduce the operational cost, to sustain the operation and the services.  According to a signed MOU between the JICA, MOH, EQA and the JSC, JICA agreed to support the operational cost for the health care waste until the system is well established and in place and until the governmental partners can pay for the services themselves. The government of Japan agreed to this issue to support the health system and kick off this project. Therefore, UNDP/PAPP will sign an MOU with the JSC and the MOH to support the operational of the health care waste facility by providing a new microwave and training the MOH staff.

Microwave technology is the eco-friendliest method available in treating the medical waste. This technique allows microbial inactivation of biomedical waste in 30 to 35 minutes. Unlike autoclaves, this process does not require pressurization, and this minimizes any risk of explosion due to poor maintenance and training of operators. All types of biomedical waste (solids, liquids, glass, sharps, blades, etc.) can be treated with the system, and the entire process is traceable. Microwave also converts biomedical waste into dry, inert material and reduces its weight by more than 25% and its volume by 80%. This resulting material is similar to municipal waste and can be used as secondary fuel with a high-energy output.

Output 2:  Capacities of Ministry of Health for health care management are improved

Activity 2.1: Training of MOH personnel in health care management

Activity 2.2: Design and printing of awareness and educational materials

To be able to operate and sustain the health care waste management systems that JICA and the Joint Service Council started and initiated in the south during 2017, UNDP/PAPP will partner with them and train the Ministry of Health personnel (i.e. doctors, nurses, lab technicians. Etc) in the targeted hospitals and clinics to have them aware of the established system and the guidelines for the health care waste separation and management within the health care facilities. The training will target around 2,000 healthcare personnel from hospitals in all Gaza Strip.

The concept and structure of the training will show the various aspects of medical waste management. This belongs to four main training areas:

- Information on overall aspects of medical waste management.

- Information on the management aspects that shows the policies of medical waste management.

- Information on the administrative aspects that shows roles and responsibilities of each staff involved in medical waste management.

- Information on the technical aspects that shows guidance relevant to the target group in applying medical waste management practices.

To address the training needs of the different groups of actors, the training shall cover the following actors:

Group (A): Service providers and head of departments

- Medical waste laws and compliance;

- Roles and Tasks entitled for staff involved in medical waste management;

- Medical waste classification, principles of medical waste management;

- Sources of medical waste;

- Medical waste separation and sorting;

- Risks types and Occupational Health & Safety;

- Medical waste temporary storage.

Group (B): Infection control and medical waste management department

- Medical waste laws and compliance;

- Roles and Tasks entitled for staff involved in medical waste management;

- Medical waste classification, principles of medical waste management;

- Sources of medical waste;

- Medical waste separation and sorting;

- Medical waste collection, transport and storage;

- Medical waste treatment;

- Risks types and Occupational Health & Safety;

- Reporting, Documentation (registration, manifest form);

- Control of medical waste management;

- Management of operations and monitoring performance.

Group (C): Cleaners

- Medical waste laws and compliance;

- Roles and Tasks entitled for staff involved in medical waste management;

- Medical waste classification, principles of medical waste management;

- Sources of medical waste;

- Medical waste separation and sorting;

- Medical waste collection, transport and storage;

- Record of delivery and receipt of medical waste;

- Risk types and Occupational Health & Safety;

- Work ethics.

Resources Required to Achieve the Expected Results

A total budget of USD 516,000 is required to fully implement the proposed Project activities and achieve the desired results. UNDP will utilize its expertise and resources for the optimal implementation of the Project activities. A detailed budget breakdown is shown in Annex I.

Partnerships

UNDP/PAPP will work with a multiple of partners who are the major partners and stakeholders of the project.

JICA

The project comes as a main finding of JICA study on Medical Waste Management in the Gaza Strip, that was conducted in May/June 2016 and because of JICA and UNDP joint efforts and meetings with Gaza Stakeholders to start implementation of HCW in the Gaza Strip hospitals.

JICA has already started the implementation of pilot project targeting primary health clinics and UNRWA clinic in the middle area as well as Khan Younis and Rafah Governorates in addition the pilot project that targets the laboratory and kidney department at Al-Shifa Hospital in Gaza City.

UNDP project will build on JICA pilot project and target the 6 hospitals in the middle and southern Governorates of the Gaza Strip and ensure the full cycle of health care waste management is implemented. UNDP and JICA will also partner to replicate this pilot in the Gaza city and the Northern Governorates in 2020.

UNDP and JICA worked together and organized the meetings with the stakeholders to discuss the project implementation and the needs.

It is worth to note that this project builds on the UNDP/ ROJ first pilot project in addressing the medical waste management in the Ramallah Governorate that was very successful and replicated in Hebron Governorate.  All the bylaws, regulations, operational manuals as well as specifications for equipment and tools that were developed through the project were adopted at the national levels and used by many partners and stakeholders, and many built on this successful experience.  Now is the opportunity to expand the strategic partnership among ROJ, JICA and UNDP to replicate, build upon and replicate this experience in Gaza and have a great impact to protect the public health and natural resources in the Gaza Strip.

UNRWA

UNRWA has a parallel programme with JICA and we will be coordinating with them only.

Joint Service Council for Solid Waste Management in the Local Governorate Units in Governorate of Khan Younis, Rafah and the Middle Area (JSC-KRM)

The JSC was established in 1995 with the support of German Technical Cooperation Ag3ency (GTZ) with 13-member municipalities located in the Middle Area and Khan Younis Governorate, under the name of “Joint Service Council for Solid Waste Management in the Governorates Khan Younis and Deir Al Balah”. The council was expanded in 2012 to include the local government units in the Governorate of Rafah increasing the total number of LGUs served by the council to 17 under the name of JSC-KRM. Council services comprises approximately 64% of Gaza Strip’s total geographical area inhabited by 46% of the total Gaza Strip’s population. The Palestinian National Strategy of Solid Waste Management 2010-2014 reflects the foundation of Council’s work, which aims at setting the bases capable of improving the quality of service within the framework of preparing a healthy environment.

JSC-KRM is the main beneficiary and partner of the project. UNDP will sign a MoU with JSC-KRM to support the operational of the health care waste facility.

MoH

The Ministry of Health of the Palestinian Authority is one of the independent institutions state of Palestine committed to the principle of joint work with all partners to develop performance in the health sector, and develop it in order to ensure a professional management of the health sector and create a leadership capable of policy development and organization of work and ensure the provision of quality services in all health sector; public and private. UNDP/PAPP will sign an MOU with the MOH to support the operational of the health care waste

The Environment Quality Authority (EQA):

EQA is the responsible national body for safeguarding the Environment and protecting the natural resources in Palestine.  It is responsible to formulate the national policies and strategies for all environmental issues. It is also responsible to implement the international environmental agreement with regards to biodiversity and protection of natural resources. EQA will work and cooperate with UNDP and will be part of the technical steering committee.

Risks and Assumptions

The basic assumptions necessary for Programme implementation are as follows:

- All partners work attentively to implement the different components of the medical waste facility using their available funds. As example Qatar charity to install and operate the solar panel system and RoJ to fund the upgrading of the existing autoclave;

- MoH extend the MoU with JSC-KRM beyond January 2020.

Risk Register

The volatile political situation in the Gaza Strip is the major potential risk for the implementation of the programme. There are other factors with less significance to be considered in this regard.

The entry of materials is currently from Israeli crossing only and needs access coordination through the current established UNDP mechanism which normally takes huge efforts and long time for entry of relevant equipment. Below is the risk log:

| Risk | Probability | Impact | Risk Response |
| --- | --- | --- | --- |
| Environmental/Political: |  |  |  |
| Resumption of hostilities or Internal fight / disputes | Moderate | High | Careful monitoring of the political situation to avoid incurring any losses to the Project. If major hostilities or internal fighting occur, UNDP will: - Suspend the activities until the risk is removed. - Precautionary secure the work sites and materials. - Inform all parties with the GPS coordinates of the sites. - inform the local authorities about the active Projects and assets seek assistance to safeguard the assets and operations. - Make revision of the budget and work plan. |
| Operational Risk |  |  |  |
| Delay in access of materials | Moderate | High | - The materials’ entry is coordinated through the UNDP access coordination mechanism. - All technical information is properly shared with the borders Authorities. - Early and continuous follow up on obtaining relevant approval. - Approval of materials are carried as early as possible. - Support from ROJ may needed to allow the microwave to enter Gaza |
| Support in equipment installation and operation | Low | Moderate | - UNDP will make sure to facilitate the movement and access of any international staff to support the installation and proper operation for the equipment. - UNDP will make sure to supply the needed spare parts to cover any regular maintenance. |
| Financial Risks |  |  |  |
| Increase in cost pertaining to procured materials. | Low | Moderate | The tender will be advertised at the early stage of the project. If the price of the microwave exceeds the cost estimate, a revised budget will be submitted to RoJ including reallocation between budget lines. |
| Depreciation in the value of US$. | Low | Moderate | Effective and efficient management and use of financial resources are well maintained through monitoring and evaluation scheme established in UNDP at the local and global level. In procurement, contractors are asked to provide their prices in either USD or local currency (ILS) where all currencies of the received bids are converted to USD based on the UNDP prevailing rate of exchange at date of bid opening. Resulted contract with winning contractor will reflect the currency originally quoted by the contractor. New policy in procurement is requesting fixation of the contract value in local versus USD through the banks. |

Stakeholder Engagement

One of the UNDP’s approaches is to strengthen social networks, community ties, and build social awareness to increase communities’ access to safe environmentally friendly essential services, with the objective of increasing the community’s sense of ownership for public Projects.

Steering committee meetings will be hosted by UNDP in order to energize their engagement with the project activities and obtain their support to resolve any raised issues. Their technical inputs will be an added value for the project as sectors regulators and will assure the sustainability and successful performance of the intervention.

Knowledge

In close cooperation with JICA, a model of onsite and offsite management of medical waste will be developed to functionalize the system in the Gaza strip through the provision of efficient and environmentally/socially-sound treated disposal. The project will be replicated to cover all Gaza Strip.

Sustainability and Scaling Up

It is worth to note that this project builds on the UNDP/ ROJ first pilot project in addressing the medical waste management in the Ramallah Governorate that was very successful and replicated in Hebron Governorate.  All the bylaws, regulations, operational manuals as well as specifications for equipment and tools that were developed through the project were adopted at the national levels and used by many partners and stakeholders, and many built on this successful experience.

To address the medical waste risks in Gaza, a consensus was reached in 2016 among Ministry of Local Government (MoLG), Ministry of Health (MoH), the Environment Quality Authority (EQA), UNRWA to expand the mandatory of Joint Service Councils (JSC) to be the responsible entity for the off-site management of medical wastes. Where Japan International Cooperation Agency (JICA) financed the program to develop a model of onsite and offsite management of medical waste to functionalize the system in the Gaza strip through the provision of efficient and environmentally/socially-sound treated disposal.

JICA launched medical waste project in Gaza Strip to be implemented into three Stages, Preparation Stage 2017, Second Collecting and Separation Stage 2018 and Expansion Stage 2019. The program is targeting 32 Governmental Primary Health Care Clinics (PHCC) and 13 UNRWA’s clinics in jurisdiction area of JSC KRM; namely Khan Younis, Rafah and Middle Area. The program will also include two departments of Al Shifa hospital specifically, laboratory and haemodialysis departments. UNDP/PAPP proposed project will build on and complement the ongoing pilot in the targeted area. Build upon this experience, the project will be scaled up to cover all the hospitals and clinic in jurisdiction area of Joint Service Council for Gaza and North.

The JSC-KRM will be responsible for the sustainability of the project. The council’s mandate included the provision of secondary waste collection and waste disposal. Service agreement was signed between the service provider JSC-KRM and MoH on 14 January 2019 to target MoH clinics in Middle and South Gaza in addition to the two departments of Al Shifa hospital (lab and haemodialysis).

# Results Framework

| Intended Outcome as stated in the UNDAF/Country [or Global/Regional] Programme Results and Resource Framework: UNDAF Strategic priority 4: Leaving No One Behind: social development and protection: Outcome 1: More Palestinians, especially the most vulnerable, benefit from safe, inclusive, equitable and quality services UNDP Strategic Plan 2018-2021 Outcome 3: Strengthen resilience to shocks and crisis |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome indicators as stated in the PPF Results and Resources Framework, including baseline and targets: Outcome 4.1 Indicator: % of families served by medical solid waste services. Baseline: N/A Target: 50% of the Middle and South Governorates |  |  |  |  |  |  |  |
| Applicable Output(s) from the UNDP Strategic Plan: SP Outputs Output 1.2.1 Capacities at national and sub-national levels strengthened to promote inclusive local economic development and deliver basic services4 including HIV and related services Indicators Number and proportion of people accessing basic services Baseline: 0 Target: 390,000 PPF Outputs: Output 4.1.3: Support and build the capacity of PWA, Ministry of Local Government, and related municipalities in wastewater and solid waste management (i.e. wastewater tariff, cost recovery, promote community participation, and raise awareness) and Improve access to wastewater and solid waste services including collection, treatment and reuse/recycling Indicators: Number of families with improved access to medical solid waste services. Baseline: 0 Target: 78,000 |  |  |  |  |  |  |  |
| Project title and Atlas Project Number: Improvement of Health Care Waste Management system in the Southern Governorates of the Gaza Strip Atlas Proposal Number: 109210 Atlas Output Number: 108575 |  |  |  |  |  |  |  |
| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | ## TARGETS |  | ## DATA COLLECTION METHODS & RISKS |
|  |  |  | Value | Year | Value | ## Year |  |
| OUTPUT 1: The Capacity of the Joint Service Council in the South of the Gaza Strip regarding health care waste is enhanced. | - A medical waste treatment facility is in place and operates in effective manner | UNDP and Partners reports | Autoclave with small capacity 28kg/cycle/2.5 h. | 2018 | Additional microwave for treatment of 75 kg/h of medical waste. | 2019-2020 | Meetings, Site Visits, BoQ, and Reports. |
| OUTPUT 2: Capacity of Ministry of Health for health care management are improved. | 2.1 Number of Palestinian medical staff benefitting from improved medical waste services | UNDP and Partners reports | 700 | 2018 | Additional 2,000 person will be trained. | 2019-2020 | Meetings, Site Visits, BoQ, and Reports and Beneficiary Survey |
|  | 2.2 Number of Palestinian people benefitting from improved medical waste services | UNDP and Partners reports | 0 | 2018 | At least 390,000 persons | 2019-2020 | Reports and Beneficiary Survey |

# Monitoring And Evaluation

The formal performance measurement of the Project will involve the application of the Programme Measurement Framework (PMF), and the collection of data specific to each of the applicable PMF indicators, at regular intervals and in line with Project reporting.

The indicators will be assessed annually and output indicators at regular intervals. While the monitoring of outcomes is carried out as a formal process in line with the PMF, the ongoing monitoring and evaluation at the level of outputs and activities are also essential for effective implementation and management decision-making.

The Project’s PMF is presented on the pages which follow, providing an overview of the outcomes, their respective indicators, as well as information pertaining to the process and schedule for monitoring them.

In accordance with UNDP’s programming policies and procedures, the Project will be monitored through the following:

Within the annual cycle

- Track Progress. Following the frequency cited in the monitoring plan, progress data against the results indicators will be collected and analysed to assess the progress of the Project in achieving the agreed outputs. National data sources should be used whenever possible. Slower than expected, progress will be addressed by the Project management. Beneficiary feedback will be part of regular data collection and performance assessment.

- Monitor and Manage Risk. Based on the initial risk analysis submitted (see annex 2), a risk log shall be actively maintained, including by reviewing the external environment that may affect the Project implementation. Risk management actions will be identified and monitored using a risk log. This includes monitoring social and environmental management measures and plans that may have been required as per UNDP’s Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk.

- Evaluate and Learn. Evaluations shall be conducted in accordance with the evaluation plan. Knowledge, good practices and lessons should be captured and shared, as well as actively sourced from other Projects and partners, and integrated back into the Project. If a Project evaluation is required (e.g., when mandated by partnership principles, or due to the complexity or innovative aspects of the Project), it should be conducted in accordance with the Project’s evaluation plan.

- Review and Make Course Corrections. The Project management will review the data and evidence collected (through all of the above) on a regular basis within the annual cycle, and make course corrections as needed. The frequency of review depends on the needs of the Project, but an internal review of the available progress data against the results indicators is required at least quarterly. Any significant course corrections that require a decision by the Project Board should be raised at the next Project Board meeting.

Annually

- Annual Project Quality Rating. On an annual basis and at the end of the Project, the quality of the Project will be rated by the QA Assessor against the quality criteria identified in UNDP’s Project Quality Assurance System. Any quality concerns flagged by the process must be addressed by Project management.

- Annual Project Review and Report. The Project Board shall hold a Project review at least once per year to assess the performance of the Project and appraise the Annual Work Plan for the following year. An annual report will be presented to the Project Board for the review, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual Project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. Any concerns on the quality or progress of the project should be discussed by the Project Board where any necessary management actions should be taken to address such issues. This review is driven by the Project Board and may involve other stakeholders as required.

Closure

- In the Project’s final year, the Project Board shall hold an end-of Project review to capture lessons learned and discuss opportunities for scaling up.

# Annual Work Plan

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Activities Timeframe |  |  |  | RESPONSIBLE PARTY |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Q2 2019 | Q3 2019 | Q4 2019 | Q1 2020 |  |
| Output 1: 1. The Capacity of the Joint Service Council in the South of the Gaza Strip regarding health care waste is enhanced. Gender marker: GEN1 | 1.1. Procurement and operating of Microwave with capacity 75kg/h | x | X | X | X | UNDP/PAPP |
| Output 2: 2. Capacity of Ministry of Health for health care management are improved. Gender marker: GEN1 | 2.1 Training of MOH personnel in health care management |  | X | X | X | UNDP/PAPP |
|  | 2.2 Activity: design and printing of awareness and educational materials |  | X | X | X |  |
| Project Management | Monitoring & Evaluation | X | X | X | X | UNDP/PAPP |
|  | Advocacy and Visibility | X | X | X | X | UNDP/PAPP |

# Governance and Management Arrangements

UNDP will assign a Project Manager from its staff to follow up on all managerial, including administrative and financial issues related to the Project. In addition, UNDP will assign an Programme Analyst, who will take on the role of a Technical Quality Assurance, to manage and assess the daily technical monitoring of the Project. The day to day Management (Project Manager) will be handled by the Project Manager, whereas the UNDP Programme Analyst will be responsible for the overall Project assurance.

A Project board will be established to follow up the works implemented by UNDP. The members of the board will include the Government of Japan as the donor, a representative of the Ministry of Health & JSC-KRM as the end beneficiary and owner and that coordinates the Project with other PA counterparts, and UNDP/PAPP as the implementing partner. This board will meet every 3 months or exceptionally upon request by Board members, to review priorities and progress towards expected results.

Project Assurance

Programme Analyst (15%)

Senior Beneficiary

JSC-KRM and MoH

Senior Supplier

Government of Japan

Executive

UNDP

Project Board (Governance Mechanism)

Project Organization Structure

Project Manager

Project Manager (50%)

Project Support

Procurement Assistant (25%)

Project Assistant (20%)

Contractors

The UNDP will utilize its standard Management, Procurement, Contracting, and Financial procedures in the implementation of the Project. The Project will be tendered locally and internationally and through the UNDP procurement web site portal. A public tender opening will occur in which all relevant parties may be present. UNDP’s procurement unit will evaluate the tender and only upon approval from UNDP Contracts, Assets, and Procurement Committee will a contract be awarded to the winning contractor.

Based upon the Japan International Cooperation Agency’s (JICA) technical assessment of priorities and needs of health facilities, UNDP and MoH will coordinate the technical specifications and works to ensure that the results are in line with the PA Palestine National Policy Agenda for 2017 – 2022 Plan.  UNDP will monitor and supervise all construction works on a daily basis and will be responsible for verifying all works and the issuance of payments to contractors based upon actual works performed.  Through this mechanism UNDP will directly execute all Project activities. The Project budget would cover the costs of the Project Implementation Unit, all Project-based expenses, and UNDP’s General Management Services.

# Visibility Plan

UNDP is considering the importance of the communication and visibility, and therefore, includes a line for this purpose. The Project Team in close coordination with UNDP/PAPP Communication Unit will develop a communication plan that includes the following:

  - Full participation of the initial inauguration and handover of the Project

  - Production of press releases to cover Project news and events

  - Production of Project fact sheets which will be published in UNDP/PAPP official website.

  - Highlighting the funding source for the Project in all announced activities

  - Signing and Closing Ceremonies

  - Maintaining the proper logos and all related materials during the Project lifecycle that includes tendering, construction plaques, inauguration plaques, etc.

  - Standard UNDP communication branding for donors' visibility

# Effective communication with all stakeholders (Palestinian institutions, UN agencies, donors, media and beneficiaries), is fundamental to the Project’s success. Information and communication needs of the stakeholders' relative to the progress of the Project will be determined and highlighted as a communications plan/matrix. It will play an essential role in mitigating expected risks in ensuring advocacy.

# Legal Context

The Project document shall be the instrument envisaged and defined in the Supplemental Provisions to the Project Document, attached hereto and forming an integral part hereof, as “the Project Document”.

This Project will be implemented by UNDP/PAPP in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [Project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct Project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the Project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other Project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or Project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to Project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the Project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, subcontractors and sub-recipients in implementing the Project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and Projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where it becomes aware that a UNDP Project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the Project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

# ANNEXES

Budget:

| Expected outputs | Output Indicators | Activities | Proposed budget USD |
| --- | --- | --- | --- |
| OUTPUT 1: |  |  |  |
| 1. The Capacity of the Joint Service Council in the South of the Gaza Strip regarding health care waste is enhanced | 1.1. One microwave procured and operated. | 1.1. Procurement of Microwave with capacity 75kg/h | 350,000 |
| OUTPUT 2: |  |  |  |
| 2. Capacity of Ministry of Health for health care management are improved | 2.1 number of staff trained (2,000 staff members are targeted) | 2.1 Activity: training of MOH personnel in health care management | 21,500 |
|  | 2.2 No. of printed materials | 2.2 Activity: design and printing of awareness and educational materials | 10,000 |
| Direct Project Cost |  | UNDP Direct Implementation, field Administration and Operation Cost | 96,278 |
|  |  | sub total | 477,778 |
| GMS (8%) |  |  | 38,222 |
| TOTAL |  |  | 516,000 |

UNDP Project Direct Implementation Cost

| Item | No./Unit | Year/Month | Unit Rate $ | Total $ |
| --- | --- | --- | --- | --- |
| Programme Analyst (NOB) | 0.15 | 12 | 9,475 | 17,054 |
| Project Manager (SB4/3) PM | 0.5 | 12 | 4,955 | 29,729 |
| Project Assistant-SB3/3 | 0.2 | 12 | 4,044 | 9,705 |
| Implementation Support Services -Procurement Assistant UNV | 1 | 4 | 2,200 | 8,800 |
|  |  |  | Subtotal 1 | 65,288 |
| GOE(Office) (years) | 1.1 | 1 | 14,220 | 15,642 |
| Transportation | 1 | 9 | 450 | 4,050 |
| Services (stationary, tools and Miscellaneous) | L.S |  | 1,298 | 1,298 |
| Management and Financial Audit | L.S |  | 5,000 | 5,000 |
| Communication | L.S |  | 5,000 | 5,000 |
|  |  |  | Subtotal2 | 30,990 |
|  |  |  | Total | 96,278 |

www.epa.gov/epaoswer/other/medical/

Desk Study on the Environment in the Occupied Palestinian Territories, UNEP, 2003;  Pollution Handbook,NSCA,1993; Dr. Imad Al-Khatib, Training on Medical Waste Management in The West Bank and Gaza’s Hospitals, Community and Public Health Institute- Beir Zeit University,2002.

Science, Technology& Health Hazards Of Incineration, How to shut Down Incinerator, Health Care without Harm, www.noharm.org; Medical Waste Treatment Technology: Evaluating Non-Incineration Alternatives, Health Care without Harm: The Campaign For Environmentally Responsible Health Care, May 2000; www.sustainablehospitals.org/HTMLSrc/Glossary.html

Dr. Imad Al-Khatib, Training on Medical Waste Management in The West Bank and Gaza’s Hospitals, Community and Public Health Institute- Beir Zeit University,2002.

Science, Technology& Health Hazards Of Incineration, How to shut Down Incinerator, Health Care without Harm, www.noharm.org; Medical Waste Treatment Technology: Evaluating Non-Incineration Alternatives, Health Care without Harm: The Campaign For Environmentally Responsible Health Care, May 2000.

Medical Waste Treatment Technology: Evaluating Non-Incineration Alternatives, Health Care without Harm: The Campaign For Environmentally Responsible Health Care, May 2000.

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner