Quarterly Progress Report

January - March 2021

Name of Project: Human Rights Programme (Atlas Project ID: 00097336)

List of Acronyms

| CPD | Country Programme Document |
| --- | --- |
| CSO | Civil Society Organization |
| EOP | End of Project |
| GBV | Gender-based Violence |
| HRP | Human Rights Programme |
| LNOB | Leave No One Behind |
| LVGs | Low Value Grants |
| NHRC | National Human Rights Commission |
| NIC | National Inquiry Committee |
| NLASO | National Legal Aid Services Organization |
| PWD | Person with Disability |
| SDC | Swiss Agency for Development and Cooperation |
| SDG | Sustainable Development Goal |
| SIDA | Swedish International Development Agency |
| SP | Strategic Plan |
| UPR | Universal Periodic Report |
| VAW | Violence against Women |
| WSSP | Women Safety in Public Places |

| Project Information |  |  |  |
| --- | --- | --- | --- |
| Funded by: | SDC and SIDA |  |  |
| Implementing Partners: | National Human Rights Commission, Bangladesh Police, Civil Society, Academician, National Legal Aid and Services Organization, Judiciary |  |  |
| Project Locations/Coverage: | All over Bangladesh (only plain land) Pilot districts - 1. Dhaka 2. Manikganj 3. Rajshahi 4. Dinajpur 5. Khulna 6. Jessore 7. Barishal 8. Cox’s Bazar 9. Mymensingh 10. Moulvi Bazar 11. Madaripur 12. Gaibandha 13. Habiganj 14. Satkhira 15. Sirajganj 16. Rangpur |  |  |
| CPD Output: | CPD Outcome 2: Develop and implement improved social policies and programmes that focus on good governance, reduction of structural inequalities and advancement of vulnerable individuals and groups CPD Output 2.1: Civil society, interest groups, relevant government agencies and political parties haves tools and knowledge to set agendas and to develop platforms for building consensus on national issues CPD Output 2.2: The Government has the capacity to carry out formal or quasi-formal, demand-driven and gender-sensitive reforms of the justice sector to provide more equal access to justice to women and men, especially those from marginalized groups |  |  |
| SP Output: | SP Outcome 2: Accelerate structural transformations for sustainable development SP Output 2.2.3 (Governance): Capacities, functions and financing of rule of law and national human rights institutions and systems strengthened to expand access to justice and combat discrimination, with a focus on women and other marginalised groups. SP Output 2.6.1 (Gender): Capacities strengthened to raise awareness on and undertake legal, policy and institutional reforms to fight structural barriers to women’s empowerment |  |  |
| SDG Target: | SDG Goal 5: Achieve gender equality and empower all women and girls SDG Target 5.1: End all forms of discrimination against all women and girls everywhere SDG Goal 16: Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions at all levels SDG Target 16.a: Strengthen relevant national institutions, including through international cooperation, for building capacity at all levels, in particular in developing countries, to prevent violence and combat terrorism and crime SDG Target 16.2: End abuse, exploitation, trafficking and all forms of violence against and torture of children |  |  |
| Project Starting Date (DD/MM/YYYY): | 01.01.2016 |  |  |
| Original Completion Date (DD/MM/YYYY): | 31.12.2020 | Expected Completion Date (DD/MM/YYYY): | 31.12.2021 |
| Project Budget (USD): | 10,597,570.00 | Fund Received (USD): | 9,450,157.00 |

Narratives

| Key Results achieved |  |  |  |  |
| --- | --- | --- | --- | --- |
| The significant results achieved during the reported period are as follows: - Development of Integrated Office Management Systems is under process which will enable NHRC to better handle human rights violations complaints more efficiently and effectively resulting in improved client satisfaction; and to improve monitoring human rights in combination with SDG monitoring tools. - Human Rights Focal Desks in all ministries have been reactivated, oriented on the UPR mechanism and their respective roles in the national reporting. - HRP has been able to engage itself in the initiative of NHRC – national inquiry on VAW with a focus on rape. - Increased awareness of 340,983 of the most vulnerable and marginalized people (Male=203,249, Female=136,055 and TG=1679) has created a foundation for advancing common voices of the people at grassroot level. - More than 300 indigenous youth leaders connected to promote youth-led indigenous culture and diversity. - Collaboration with Bangladesh Police has been strengthened and 135 number of women officials have increased level of understanding on their role to address gender-based violence. - Increased awareness on gender equality (245K people received gender equality and women rights focused awareness messages). - Skills of 27 youth (ethnic and excluded minorities) developed on mobile photography which was presented in a virtual exhibition. - 29 youths have been better capacitated on GBV issues to promote women and girls’ rights by addressing gender-based violence in 10 areas of Bangladesh. - Development of judicial portal, online cause list, SMS based case tracking system under process as part of accelerating digital justice system. - Legal aid services via national legal aid helpline center and district legal aid offices were provided. From January till March 2021 the total number of calls were received from the helpline center was 10963. Among those 8536 were men, 2190 were women, 290 calls were related to the children in conflict with law and, 07 calls were addressed to the people from third gender community. From January till March 2021 the total number 720 people received services from workers legal aid cells from Dhaka and Chattogram. Among those 121 cases were solved through mediation, 435 people have received legal aid and consultation, 164 labor court related cases received assistance from the cells. A total of BDT 2768381.00 was realized as the compensation money to the labor community sought legal aid from the concerned cells. |  |  |  |  |
| Gender/ Leaving No One Behind (if any) |  |  |  |  |
| Gender Gender equality and empowerment have been central to the project and gender issues have been effectively mainstreamed across all programmatic approaches. During the reporting period the project has observed the International Women’s Day and conducted series of activities to enhance awareness and sensitization on gender equality issues including responding GBV. Appox. 245K peoples were reached out through number of online and on ground interventions. In regard to strengthening capacity 155 women received skills and knowledge enhancement training and workshop. Persons with Disabilities (PWD) The project has taken initiatives to integrate disability issues as a top priority in its interventions in order to make the Programme more inclusive and respond to the needs of the marginalized populations. In 2021, 1 LVG support provided to CSO (Turning Point Foundation) on rights of the persons with disabilities to connect more than 1000 PWDs beneficiaries in Dhaka, Moulvibazar and Khulna districts. |  |  |  |  |
| COVID-19 Responses (if any) |  |  |  |  |
| - Reported under HRP’s separate COVID project |  |  |  |  |
| Innovation (if any) |  |  |  |  |
| - Integrated Office Management Systems of NHRC will enable NHRC to better address and handle human rights violations complaints more efficiently and effectively resulting in improved client satisfaction; and to improve monitoring human rights in combination with SDG monitoring tools. - National Inquiry Committee on VAW - Engagement of indigenous youth leaders to restore and preserve the cultural rights and diversity of the indigenous groups/community in plain land areas of Bangladesh, where they have had the opportunity to interact and raise their common issues and concerns for the future actions. - Sports-based interactive events and special rewards for young girls are found effective to reduce the social barriers and shaping of life for the young girls at grassroots level. |  |  |  |  |
| Monitoring |  |  |  |  |
| Due to pandemic, HRP is mostly practicing remote monitoring system instead of direct monitoring visits. The remote monitoring includes coordination meeting, frequent follow up and reporting, etc. |  |  |  |  |
| Project Risks & Mitigation Measures |  |  |  |  |
| Sr | Project Risk | Likelihood (High/ Moderate/Low) |  | Mitigation Measure |
| 1 | Strategic and Political: Increasingly restrictive political and civil rights environment stifles human rights dialogue | High |  | Human rights monitoring as part of the United Nations’ Rights up Front policy will inform all Programme-based decisions and be subject to regular review |
| 2 | Operational: Priorities of NHRC change following transition | Moderate |  | HRP is working closely with new members to mitigate the risk |
| Project Issues & Remedial Actions |  |  |  |  |
| Sr | Project Issue |  | Remedial Action |  |
| 1 | Rights of the ethnic, excluded minorities and other LNOB category people are at risk in getting health services and survival foods during COVID 19 situation |  | HRP provided support through its partner CSOs, HRDs, youth leaders and distributed the essential foods and PPEs including masks. |  |
| 2 | Increasing livelihood struggle of the ethnic, Dalits and other vulnerable communities due to COVID |  | HRP is taking initiative to introduce and create alternative livelihood skills, support and opportunities in collaboration with CSOs for the selected HHs of these communities in upcoming months |  |
| 3 | Violence against women and girls’ is in increasing trend during COVID 19 situation. It may continue in post COVID 19 situation |  | The Project has been monitoring and taking awareness raising initiatives through partner CSOs at grassroots level on domestic violence. |  |
| 4 | Limitation in conducting field coordination amid increasing trend of COVID 19. |  | Initiatives taken to introduce and create alternative mode of communication and continue coordination with the national and local level justice stakeholders. |  |
| 5 | With the second wave of the pandemic the planned activities of the newly formed National Inquiry Committee have been interrupted, particularly the field survey. This may result in delay in the outcome of the initiative. |  | The continuity of the initiative is going on with a slower pace. In the meanwhile, HRP is supporting in the stakeholders discussions that is expected to enrich the understanding of the concept. |  |
| Lessons Learned |  |  |  |  |
| - The Coalition based working approach of the rights based CSOs is effective to act together in addressing local human rights problems and issues. |  |  |  |  |
| - Extended moral, technical and materialistic support to indigenous girls is necessary to restore and preserve the declining cultural and traditions of the indigenous communities in plain land areas. |  |  |  |  |
| - Youth-led interactive discussion and awareness raising sessions at community and school/college level is necessary for better realisation of their rights and extended space for indigenous youth in education and other local opportunities. |  |  |  |  |
| - Engaging duty bearers was very crucial while designing the legal aid programme within the extended period of LoA between NLASO and UNDP. The schedule of actions was reflected from the direct recommendations from the district legal aid officers. |  |  |  |  |
| - Implementation of complex digitalization projects like Accelerating Digital Justice system is Bangladesh, where multi sectoral stakeholders’ coordination shows good progress through synergies between projects of UNDP, as HRP and A2I is working so closely. |  |  |  |  |

Indicator Progress

| Indicators | Baseline | EOP Target | Annual Target (2020) | Progress (Q4-2020) |
| --- | --- | --- | --- | --- |
| Output 1 | The National Human Rights Commission (NHRC) can more effectively deliver on its mandate. (HRP – Output1) |  |  |  |
| Outcome indicators |  |  |  |  |
| 1.1) The extent to which the NHRC’s legal framework and operation are aligned to the Paris Principles (ICC) | NHRC was accredited by the Sub-Committee of Accreditation of Global Alliance of the National Human Rights Institutions with a ‘B’ status in May 2013 and again in March 2015. This indicates that it is largely, but not fully, in compliance with the Paris Principles | 3 (composite based on scaling) | 3 (composite based on scaling) | NHRC had a discussion with the Ministry of Law, Justice and Parliamentary Affairs for the review of NHRC Act 2009 in 2020. The government has expressed their willingness to amend the law. |
| 1.2) Percentage of NHRC clients expressing satisfaction in the complaint’s mechanism of the NHRC. | Baseline: 10% Respondents complained among them 39% were very satisfied) Follow-up Perception Survey-2015 | 0% (2017) 20% (2018) 20% (2019) 10% (2020) 10% (2021) 60% (2021 Cumulative) At least 60 % clients indicating the services to be moderate – good (2021) | 10% | Client Satisfaction Survey is officially introduced from Dec 2018 at the front Desk of NHRC to digitalize. However, HRJ is in the process of installing the Integrated Office Management Systems for the NHRC. This system is expected to enhance the client satisfaction of the services including complaints relating to human rights violations – in the digital system itself. |
| Output indicators |  |  |  |  |
| 1.3 A) Number of submissions made by NHRC- B to international human rights instruments /mechanisms (Human rights council, UPR, treaty bodies and special procedures | 4 | 6 | 1 | As of December 2020, Cumulative -5 |
| 1.3.B) Number of dialogues/ consultations held by NHRC with government authorities and CSOs for preparation of reports to international Human Rights mechanisms. | 0 | 15 | 6 | As of December 2020, Cumulative -11 |
| 1.3 C) Number of recommendations made by rights forums that have resulted in implementation or policy advice or procedural changes. | 4 | 50% of total decisions (2021 Cumulative) | 50% | As of December 2020 – 6 |
| 1.3.D. Number of recommendations made by national stakeholders (including private sector) for legislative, policy procedures, services, and practices in post-COVID 19 situation | 0 | 6 (2021 Cumulative) | 3 | As of December 2020 - 0 |
| 1.4) Number of Human Rights focal points across the Government re-established and that actively participates in the decision-making process of the NHRC Human Rights forums. | 15 | 30 (2021 Cumulative) | 10 | The present reactivated and oriented the newly appointed 24 Human Rights Focal Desks in January 2021. |
| 1.5) Extent to which NHRC has demonstrated a proactive approach in 1. Finalizing SOPs 2. Establish NHRC – Fund 3. Recruit needed staff 4. Build staff capacity 5. Outreach of services following and applying a i) HRBA and ii) mainstreaming gender issues. | Dr i) Drafted-6, Adopted-1, Consolidated SOPs ii) Fund-allocation from Ministry of Law, Justice and Parliamentary Affairs iii. NHRC Staff/Official iv)Build staff capacity v) Outreach- 0 afted-6, f | i) 100% (2021 Cumulative) ii) 100% (2021 Cumulative) | i) 40% (2020) ii) 40% (2020) | - 15% (Dec 2020) - Fund - Staff - Staff capacity building ii) Outreach As of December 2020: Work in progress |
| 1.6) % of trained human rights defenders who have reported a human rights situation or violation to NHRC. | 0 | 70% (2021Cumulative) | 20% | 50 trained (Male 38, Female 12) (As of Dec 2017) 37 trained (Male25-, Female-12 as of Dec 2018) 87 HRDs (As of December 2018 Cumulative) Male-63 Female-24 129 HRDs (male:94 & female:35) as of Dec 2019. 10% of HRDs in Dec 2019) 39 HRDs (M=19 and F=20) from 10 districts (as of March 2020) |
| 1.7) Number of Human rights (annual) situational analysis reports produced from data collection system including CMS data and CSO/CBO/HRD data | 6 | 6 | 1 | 1(July 2017) 2 (Drafted 2018) |
| Output 2 | CSO/CBOs raise human rights awareness and promote a human rights culture. (HRP output 2) |  |  |  |

| Indicator | Baseline | EOP Target | Annual Target (2020) | Progress (Q4-2020) |
| --- | --- | --- | --- | --- |
| Outcome indicators |  |  |  |  |
| 2.1) Number of human rights legislative or policy consultations between Government and CSO/CBOs resulting implementation or policy advice or procedural changes (linked with 1.3 C) | 04 (2015) | 5 (2021 Cumulative) | 4 (Cumulative) | 6 cumulative (As of 2020) |
| 2.2) % trained CSOs reporting on international obligations of Bangladesh under selected treaties and UN special procedure. | 0 | 70% (2021 Cumulative) | 50% CSOs (cumulative) | 21% CSOs Cumulative (as of 2020) |
| 2.3) % beneficiary of HRP belong to LNOB category | TBD | 50% (2021) | 10% (2020) | 47% cumulative (as of 2020) |
| Output indicators |  |  |  |  |
| 2.4) Number of HR victims benefiting from legal aid and /or referral services including psycho-social services | 0 | 100 (2021 Cumulative) | 60 (2020 cumulative) | 69 cumulative (as of 2020) |
| 2.5 A) Number of CSO coalitions formed under the support of HRP (including challenge fund) to improve Human Rights situation at grass roots level. | 0 | 60 (2021 Cumulative) | 47 CSOs coalition (cumulative) | 57 CSOs coalition cumulative (as of 2020) Cumulative plan for 2021- 69 CSOs coalition Cumulative achievement for 2021- 69 CSOs coalition |
| 2.5.B) Numbers of CSOs/CSO Coalitions produced and submitted HRV report and /or HR situation reports to NHRC and other platforms (New) | TBD | 20 ((2021 Cumulative) | 10 (2020) | 5 CSOs/CSOs coalition (as of 2020) |
| 2.5 C) Number of LNOB category people of HRP get access to local support services and opportunities in post COVID-19 situations. | TBD | 5000 (2021 Cumulative) | 2000 (2020) | *Progress not yet calculated |
| 2.6) Number of Human Rights Defenders’ active in online/offline networking and joint platform | 0 | 250 (2021 Cumulative) | 200 (cumulative) | 183 HRDs (as of 2020) |
| 2.6 A) i) % of small grants that have met respective target and goals and ii) % of small grants consulted with women or minority groups in their design | 0 | i) 85% (2020 Cumulative) ii) 50% (2020) | i) 85% (2020 Cumulative) ii) 50% (2020) | i) 100% (as Feb. of 2021) ii) 80% (Dec 2020) |
| 2.7) Number of rights forums jointly undertaken by NHRC thematic committees and CSOs to discuss contemporary human right issues. | 07 (2014) | 25 (2021 Cumulative) | 35 (cumulative) | 39 (as of 2020) |
| 2.8) Number of students with increased awareness of human rights as a result of school campaigns with CSO/CBOs. and youth leaders. | 4.9% (November 2017) | 80% (2021 Cumulative) | 50% (cumulative) | 57.4% (16,182 student as of Dec 2020) |
| Output 3 | Improved well-being in poor urban slums particularly for women and girls |  |  |  |
| Indicator | Baseline | EOP Target | Annual Target (2021) | Progress (Q1-2021) |
| Outcome indicators |  |  |  |  |
| 3.1) Number of cases reported against law enforcement agencies and police to NHRC. |  |  |  |  |
| 3.2) Number of targeted CSOs and HRDs expressing their satisfaction on the role of coordination by the law enforcement officers |  |  |  |  |
| Output indicators |  |  |  |  |
| 3.2 A) % of human focal points actively engaged in human rights initiatives and actions in the post-covid-19 situation. | 15% (2017) | 100% (2021) | 25% (2021) | In the reporting period at least 3 focal points i.e one from Police Staff College, another from Bangladesh Police Women Network and Chottogram Metropolitan Police were active engaged in human rights initiative and actions. |
| 3.2.B) % of trained LEA Officials actively engaged in human rights actions and effectively dealt with human rights concerns/issue in the post-covid-19 situation. |  |  | 30% (2021) | Some of the trained police officials have been actively engaged in human rights actions particularly in the COVID-19 situation. Exact data need to be collected. |
| 3.3) % of police officials that have better understanding (change attitude and its application) of Human Rights issues as a result of human rights training and rights advocacy. |  |  | 30% (2021) | 135 number of women police officials have increased level of understanding on their role to address gender-based violence. |
| 3.4) Number of times the police Officials take part in human rights dialogues with the NHRC judiciary, CSOs, NLASO on different emerging issues in post-COVID 19 situations. |  |  |  | No progress |
| 3.6) % of established Human Rights Desks at district level Police HQ that have effectively dealt with human rights concerns/issues of the service recipients (people) as well as the police. |  |  |  | No progress |
| 3.7) Numbers of police officials from the ethnic, excluded, and other minorities actively engaged in Human Rights actions. |  |  | 100 (2021) | 2 women police officials from the ethnic and other minorities have actively engaged in the consultation organized in collaboration with BPWN to mark the IWD |
| 3.8) Gender parity policy introduced in the policy framework of the Police institution |  |  |  | Under progress |
| Output: 4 | NHRC and national stakeholders better protect and promote women’s right |  |  |  |
| Indicator | Baseline | EOP Target | Annual Target (2021) | Progress (Q1-2021) |
| Outcome indicators |  |  |  |  |
| 4.1) Number of cases that the NHRC and legal aid offices provided legal assistance/advise to women and girls victims of violence. |  |  |  |  |
| 4.2) % of women population who understands and are aware of their rights as a human being and as women. |  |  |  |  |
| Output indicators |  |  |  |  |
| 4.3) % of students, adolescents and youth that have a better understanding on women and girl’s rights as a result of campaigns. | 2.8 % (February 2018) |  | 30%(2021) | 56 numbers of youth have better understanding on women and girls rights as a result of engaging with Women Safety in Public Places (WSPP) campaign and participating in the activities to mark the International Women’s Day in 2021 |
| 4.4) Number of policy recommendations made as a result of research findings and rights dialogues on women rights and GBV. with stakeholders: Bangladesh Women Police Network, VSU, Women Judges Network and CSO/CBOs. | 0 |  | 7 (2021) | A set of policy recommendations have made as a result of rights dialogue on Gender and GBV Responsive Policing organized in collaboration with the Bangladesh Police Women Network (BPWN) |
| 4.5) Number of complaints of women’s rights violations submitted to the NHRC by the Committee on Violence Against Women and Children (NNPC) and CSOs/CBOs. | 20% cases (2016) |  | 20% (2021) | During the reporting period no complaint submitted to the NHRC by CSOs/CBOs |
| 4.6) Number of children engaged in child labour enrolled in education. |  |  | 200 (2021) | No progress |
| 4.7) Number of women able to participate in family income and decisions. (new) |  |  | 300 (2021) | No progress |
| Output 5: | NHRC and national stakeholders better protect and promote the rights of ethnic minorities. (HRP Output-5) |  |  |  |
| Indicator | Baseline | EOP Target | Annual Target (2020) | Progress (Q4-2020) |
| Outcome indicators |  |  |  |  |
| 5.1) % of ethnic and excluded minority populations aware of their human rights and as per international human rights instruments. | 5% (August 2018) | 30 % increase from bassline (2021 Cumulative) | 35% (cumulative) | 35% (cumulative) |
| 5.2) Number of international instruments/national laws/acts/policies on the rights of ethnic minority and other vulnerable groups adopted and implemented by government. | o | 4 (2021 Cumulative) | 04 Cumulative (Dec. 2020) | 04 Cumulative (Dec. 2020) |
| Output indicators |  |  |  |  |
| 5.3) % collaborations between the NHRC, parliamentary caucus and CSOs/CBOs that have resulted in at least one policy initiative or campaign on ethnic and excluded minority rights. | 0 | 50% increase (2020 Cumulative) * No target in 2021 | 8 collaborative actions (Dec. 2020) | 8 collaborative actions (as of Dec. 2020) |
| 5.4) Number of collaborative actions (fact-findings, rapid response, spot visit, published media reports etc.) taken by the NHRC, Parliamentarians and CSOs in post CIVID-19 situation. | 0 | 15 (2021 Cumulative) | 9 fact-finding mission with rapid response) cumulative | 9 fact-finding mission with rapid response) cumulative (as of 2020) |
| 5.5 A) Number of community radio stations broadcasting minority language programming and rights education programmes. | o | 5 (2020 Cumulative) | 4 (Cumulative Dec 2020) | 4 (Cumulative Dec 2020) Target 2021= 17 Achievement= 17 |
| 5.6) % of youth leaders trained have become active in transforming their leadership role to promote the rights of ethnic, excluded and other LNOB category people. | 0 (November 2017) | 70% (2020 Cumulative) | 70% cumulative | 73.5% cumulative (as of 2020) Cumulative Target 2021= 75% Achievement= 75% |
| 5.7) Number of ethnic, excluded and LNOB category peoples’ representatives included and active in the local decisions making structure/platform (including LGIs standing committees). | 0 (November 2017) | 150 (2021) Cumulative) | 100 (cumulative) | 92 cumulative (as of 2020) |
| 5.8) No. of interfaith leaders trained and transforming their role in promoting peace, tolerance, and harmony in the society in the post COVID-19 situation. | TBD | 250 (2021 Cumulative) | 150 (cumulative) | 75 cumulative (as 0f 2020) |
| Output 7 |  |  |  |  |
| Indicator | Baseline | EOP Target | Annual Target (2020) | Progress (Q4-2020) |
| 6.1) % of pending cases disposed of the Nari Shishu Nirjaton DamanTribunal. | TBD | 15% (2021) 20% (2021) cumulative | 5% (2020) | No Progress calculated yet |
| 6.2) % of LNOB category people have increased access to quality legal aid services. | 06 (2020) | 20% (2021) | 10% (2020) Cumulative | 10% increase of providing legal aid services to the people from third gender via National Helpline Center. |
| 6.3) Number judges and public prosecutors have adequate knowledge to deal with a digitalized case management system | TBD | 300 (2021) 600 (2021 Cumulative) | 300(2020) | No Progress calculated yet |
| 6.4) % of pending cases reduced in the lower court cases (Nari o Shishu Nirajotn Daman Tribunal | 0 | 10% (2021) 15% (2021 Cumulative) | 5% (2020) | No Progress calculated yet |
| 6.5) Number of policy recommendations made on reduction of VAW cases and followed up by NJCC, DJCC | TBD | 2 (2021) 3 (2021 Cumulative) | 1 (2020) | No Progress calculated yet |
| 6.6) Number of women judges played leadership role in the judicial reform and innovation process. | TBD | 100 (2021) | 100 (2020) | 20% as by end of March 20 women judges from Bangladesh Women Judges Association have been playing the role of researcher in identifying the challenges to ensure speedy justice for GBV victims. |
| 6.7) Number High Court benches record system digitalized on commercial nature. | TBD | 02 (2021) 04 (2021 Cumulative) | 02 (2020) | No Progress calculated yet |

Activity Progress

| Output wise Progress against Activities |  |  |  |  |
| --- | --- | --- | --- | --- |
| Output 1 |  |  |  |  |
| Planned Activities (Three Months) | Progress Achieved | Challenges | Planned Activities (Next Three Months) | Financial Expenditure (USD) |
| Activity-1.1.1: Support to NHRC thematic committees to undertake rights dialogues in their spheres Action: strengthen capacity of Commission and its staff (training etc.) | HRP supported NHRC (in collaboration with UPR INFO, an International NGO) organizing a UPR Workshop from 17-20 January 2021. The objective of the Workshop was to orient the re-activated Human Rights Focal Desks of ministries with the concept of UPR, the overview of implementation of UPR, mid-term reporting, good practices for all stakeholders including CSOs and how to effectively engage with the mechanism. | With the second wave of the pandemic the planned activities have been interrupted. The continuity of the tasks including the further discussion and engagement physically with the HRFDs on the human rights reporting | Continue to support NHRC in its capacity development to effectively engage with the Human Rights Focal Desks for their effective and better engagement with the human rights reporting and implementation |  |
| Activity-1.1.1: Support to NHRC thematic committees to undertake rights dialogues in their spheres Action: Integrated digital system of operationalization of NHRC | Draft module on how to handle complaints on human rights violations developed and demonstrated on 23 March 2021. | Demonstration and confirmation have been a challenge due to remote office management | It is expected that in the next quarter at the 2 modules of the integrated office management systems will be up and running. |  |
| Activity 1.5.1: Regional centres are established and have the capacity to deliver on their mandate Action: Establish district offices of NHRC/support National inquiry committee | HRP has been able to engage itself in the initiative of NHRC – national inquiry on VAW with a focus on rape. So far, HRP assisted NHRC with the development of a NI Concept Note, which has been adopted by the NIC. Among other issues, the Note specifies the focus area of the inquiry, the scope and its methodology. HRP has also provided some material assistance and funding for a high-level consultant. | With the blow of second wave of the COVID-19 pandemic, the continuity of the tasks relating to the national inquiry, particularly the field survey has been interrupted together with the hiring of the data collectors. This may result in delay in the outcome of the initiative. | Continue supporting NHRC in the initiative of the National Inquiry including facilitating dialogues with experts/forums/UN agencies. - meeting with the UN agencies on 4 April 2021 - meeting with APF on 13 April 2021 - meeting on 26 April 2021 with the Office of the Ombudsman/NHRI of Samoa who has conducted a public national inquiry in the past with the aim to learn about the experience and lessons learned |  |
| Output 2 |  |  |  |  |
| Planned Activities (Three Months) | Progress Achieved | Challenges | Planned Activities (Next Three Months) | Financial Expenditure (USD) |
| Activity 2.1.1: Coordination and learning exchange of CSOs | On 31 March 2021, HRP organised an online coordination and learning exchange workshop with CSOs working under the LVG and Challenge fund support. Total 14 lead CSOs, 18 coalition members and Bangladesh Betar attended the online workshop. | - The newly emerged COVID-19 pandemic restricted the CSOs to interact (in person) for sharing of their learning and achievements - Online mechanisms are not always applicable for connecting voices of the grassroots people that truly requires in person programme. | - Final payment |  |
| Activity 2.4.1: Provide small scale grants to CSOs/CSO coalitions | HRP successfully completed all the proceedings of LVG support to CSOs and CSOs coalition during Q-1, 2021. The GSSC approved total 12 CSOs for LVG support in 2021. The LVG support is required total 12,572,512 BDT ($148,413) that allocated in the AWP-2021. | The applications of competitive process in selection of potential CSOs as per UNDP’s LVG proceedings in COVID-19 pandemic situation took addition time to complete the whole process of signing agreement with CSOs | - Support to GSSC meeting (7th April 2021) and signing of agreement between the approved CSOs and UNDP - Orientation of newly selected CSOs and coalition members - Monthly action planning of CSOs (new) |  |
| Output 3 |  |  |  |  |
| Activity 3.2: Map of human rights interventions taking place within the police force. Action: Commissioning of three research | HRP is continuing support to the Police Staff College (PSC) to conduct research on 3 emerging human rights issues where police have significant role to improve the situation. During the reporting period number of research tools i.e FGD, KII, Survey questionaries have been developed, reviewed, and finalized. On 28th February a meeting held between research team, PSC key officials and HRP to finalize the tools and field visit plan. | Due to the 2nd wave of C-19 pandemic resulting difficulties to the data collection process. | Continue support to the Police Staff College (PSC) to conduct 3 research on human rights related topics. |  |
| Activity 3.3.1: Undertake joint campaigns with law enforcement | HRP supported the Bangladesh Police Women Network (BPWN) to organize a workshop titled "Gender Responsive Policing: An Approach of Bangladesh Police and Role of Bangladesh Police Women Network (BPWN)" held on 22 March 2021. The event convened as part of celebrating the International Women's Day. Dr. Benazir Ahmed BPM (Bar), Inspector General of Bangladesh Police was present as chief guest while Shaila Farjana, Secretary of BCS Women Network and Van Nguyen, Deputy Resident Representative of UNDP were present as special guests. Total 135 women officials of Bangladesh Police actively joined the day long workshop whereas the inaugural session was attended by 200 participants including representatives from media. |  | Support to organize seminar/ consultation on emerging human rights issues. |  |
| Action: Online HRs training for police | To develop an online course on Human Rights for Police a contracting firm has been hired in collaboration with a2i. To implement the planned tasks with having clear acuity an inception meeting held on 30th March where representative from hired firm, relevant colleagues from a2i and HRP team joined and discussed about the roadmap of this project. | COVID-19 situation may hinder to implement the plan within stipulated timeframe. | Continuing support to develop the e- learning course on human rights course for Police |  |
| Output 4 |  |  |  |  |
| 4.1.1 Greater advocacy and awareness of women’s and girl’s rights. Action: Workshop on ‘Virtual Exhibition through Mobile Photography by the Youth on the Life of Marginalized Women’. | On 22-23rd February HRP organized a workshop on Mobile Photography for the marginalized youth on the life and plight of ethnic and marginalized women. The objectives of the workshop were to traine them on the technical aspect of photography and capture the life of marginalized women through the youth lens with the aim to present those snaps in a virtual exhibition during IWD 2021. Total 27 youths (Male-17, Female- 10) from different ethnic minority communities and geographical locations took part in the workshop. The sessions covered theoretical aspects, technical skills including community focused practical session in a Dalit colony in Dhaka. The best 30 photos were selected for virtual exhibition launched on IWD. | To accomplish the plan within the timeframe where marginalized youth had to learned a new skills and apply to capture the life of their respective communities women by meeting the expectations | To publish the showcased photos as Photo Book to document the innovative work and empower the ethnic and underprivileged youth. |  |
| Action: Day Observance: International Women’s Day on 8th March 2021 | To mark the International Women’s Day 2021 HRP undertook series of activities – - E-book publication titled “How Kusumpur Changed” - TV Talk Show on ‘Synergy between observing IWD and 50 Years Journey of Women Empowerment in Bangladesh’ held on 8th March broadcasted by DBC Channel. Key discussants of the talk show were Nasima Begum, Chairperson, NHRC; Meher Afroz Chumki, MP, Chairperson of Parliamentary Standing Committee on Ministry of Women and Child Affairs; Maleka Banu, General Secretary, Bangladesh Mahila Parishad and Tania Huq, Professor, Gender Studies Department, DU. Approx. 80,000 viewers watched the talk show. | COVID-19 crisis situation resulted challenge to organize a planned consultation physically | Document the work through publication. |  |
| Action: Awareness raising campaign on GBV particular focus on Women Safety in Public Spaces (WSPP) | To implement the Women Safety in Public Places (WSPP) Campaign at field level, an orientation workshop was held on 1-3 February 2021 jointly with Young Bangla- the youth platform of the Centre for Research and Information (CRI) and HRP in collaboration with the NHRC. Before WSPP campaign can commence at the field level in full swing, this orientation workshop provided an opportunity for the campaign bearers to gather and learn about the preparatory theories of managing the WSPP campaign from experts of various backgrounds. WSPP is intended to be an action-focused awareness raising campaign to bring positive transformation on perceptions, attitudes and behaviours of the youth, community members and relevant stakeholders with regards to creating safe public spaces for women. A total of 29 (Male-19, Female-10) youths from 10 district participated the two days long virtual workshop. After the orientation workshop 6 youth organizations have completed the FGD to analyse local context. They have also formed the local volunteer’s groups in the field level campaign locations i.e in Chittagong, Khulna, Rajshahi, Natore, Narayangonj, and Dhaka. | Ongoing COVID-19 pandemic created obstacles to organize the orientation workshop physically which could have been more effective as well as to roll out the planned activities at field level. | Continue support to implement the Women Safety in Public Places (WSPP) campaign |  |
| Activity 4.1.2: NHRC is continuing to advocate for women’s rights as a priority the national level Action: Strengthen the functions of TC, NHRC to better promote women rights and child rights | During the reporting period the Child Rights committee of NHRC has organized a meeting on the occasion of the National Children Day and Centenary of 100 Years of Bangabandhu held on 17th March 2021. |  | Continue support to NHRC to organize thematic committee meeting on Child Rights and Women’s Rights |  |
| Output 5 |  |  |  |  |
| No activity implemented in Q-1 | N/A | Country-wise impact of the second wave of COVID-19 pandemic situation restricts timely implementation of planned activities (AWP-2021) | - Support to Cultural rights and diversity initiatives of the CSOs (Baha Porbo at Dinajpur on 02 April 2021) - Online youth consultation on COVID-19 Human Rights and preventive measures - Support to youth-led awareness sessions/campaign (Own Community level) | - |
| Output 7 |  |  |  |  |
| Activity 7.1.7Support to reinforce the functions of NLASO for quality legal aid services to LNOB people through LoA | Hold a programme planning workshop with NLASO and 21 District Legal Aid Officers to design results-oriented actions towards increased legal aid at the selected pilot areas. National Helpline Centre for legal aid was kept functional throughout this quarter. Workers Legal Aid cell were also functional and ensured continued services for the labor community from LNOB and women with legal aid. | - The newly emerged COVID-19 pandemic restricted the movement and coordination in the field and pilot areas. In person interventions is crucial at the newly identified pilot areas stakeholders like judges, court staffs, digital centers etc. - Online mechanisms are not always applicable for connecting the union parishad level stakeholders like UPLAC members. | - Support to extend the workers legal aid cells in Khulna and Sylhet. (Establishment of newly identified (two workers legal aid cells are planned and agreed in the LoA extension) - Orientation of newly selected DLAC and UPLAC on the increased use of ADR and digitalized legal aid services. - Launching the internship programme for legal aid. | - |
| Activity 7.2.1: joint initiatives with Bangladesh Women Judges Association (BWJA) in addressing GBV cases amid COVID-19 and beyond | Partnership with BWJA under process through singing of a MoU. The draft MoU and action plan, and ToR to hire national consultant to conduct the study has been prepared and shared with BWJA. | Country-wise impact of the second wave of COVID-19 pandemic situation restricts timely implementation of planned activities | - National Consultant hiring process to be completed. - Survey on case data, legal and procedural barriers in the selected Nari-o-Shishu Nirjatan Daman tribunals. - Initiate the divisional consultation with the justice stakeholders. |  |

Financial Progress

| Output | Total Budget (2021) | Allocated Budget (Q1: 2021) | Expenditure (Q1: 2021) | Cumulative Expenditure (Q1+Q2+Q3: 2021) | Balance (Cumulative) | Delivery Rate (Cumulative) |
| --- | --- | --- | --- | --- | --- | --- |
| Activity: 1 | US$ 547,070.00 | US$ 136,767.50 | US$ 149,869.65 | US$ 149,869.65 | US$ 397,200.35 | 27.39% |
| Activity: 2 | US$ 286,020.00 | US$ 71,505.00 | US$ 79,421.27 | US$ 79,421.27 | US$ 206,598.73 | 27.77% |
| Activity: 3 | US$ 269,562.50 | US$ 67,390.62 | US$ 41,719.71 | US$ 41,719.71 | US$ 227,842.79 | 15.48% |
| Activity: 4 | US$ 156,630.00 | US$ 39,157.50 | US$ 76,701.95 | US$ 76,701.95 | US$ 79,928.05 | 48.97% |
| Activity: 5 | US$ 157,311.00 | US$ 39,327.75 | US$ 16,602.30 | US$ 16,602.30 | US$ 140,708.7 | 10.55% |
| Activity: 6 | US$ 131,546.50 | US$ 32,886.63 | US$ 36,724.16 | US$ 36,724.16 | US$ 94,822.34 | 27.92% |
| Activity: 7 | US$ 184,994.00 | US$ 46,248.50 | US$ 10,743.80 | US$ 10,743.80 | US$ 174,250.2 | 5.81% |
| Grand Total | US$ 1,733,134.00 | US$ 433,283.50 | US$ 411,782.84 | US$ 411,782.84 | US$ 1,321,351.16 | 23.77% |