# FINAL REPORT OF MEXICO BIENNIAL UPDATE REPORT’S PROJECT

Monitoring and Evaluation plans of climate change enabling activities for the preparation of National Communications on Climate Change and/or Biennial Update Reports do not require the production and publication of Terminal Evaluation Reports. Therefore, a number of intended purposes of such terminal exercises are not captured in full, including:

- The promotion of accountability and transparency, and the assessment and disclosure of the extent of the project accomplishments;

- A synthesis of lessons that can help to improve the selection, design and implementation of future GEF financed UNDP activities;

- The provision of feedback on issues that are recurrent across the portfolio, attention needed, and on improvements regarding previously identified issues; and

- The contribution to the GEF Evaluation Office databases for aggregation, analysis and reporting on effectiveness of GEF operations in achieving global environmental benefits and on the quality of monitoring and evaluation across the GEF system.

The intent of this Final Report is not to propose an abridged alternative to the Terminal Evaluation Report. Instead, its purpose is to gather some insightful details about the process of preparing the mandatory report under the UNFCCC that can be of use to both the UNDP support teams, and the current and future national project teams. Its focus is therefore on providing:

- A synthesis of lessons that can help to improve the selection, design and implementation of future GEF financed UNDP activities; and

- Feedback on issues that are recurrent across the portfolio, attention needed, and on improvements regarding previously identified issues.

National project teams in charge of the future enabling activity for the preparation of the National Communication or Biennial Update Report can therefore rely on a valuable source of information from inception to closure of the project, and UNDP support teams can further disseminate lessons across borders, fully up-taking its guiding role as implementing agency and partner within the Global Support Programme (GSP, previously known as National Communications Support Programme).

The template has been designed with the purpose of collecting relevant information, without representing a time-intensive and human resource-intensive burden to the current national project team. It is therefore divided into three core sections – project identification phase, project implementation phase and project follow-up –with for each section a limited number of open questions.

The intention is to have the team leader, project manager or equivalent figure completing the template, in close collaboration with other team members within the last two months of project implementation. It is furthermore the intention of the completion of this Final Report to trigger the discussions of the upcoming National Communication and/or Biennial Update Report, taking advantage of the momentum created by the ongoing project, the presence of the core of the current national project team, and the renewed interest of national counterparts with the perspectives of an eminent or recent submission to the UNFCCC.

The completion of this template has been made mandatory and has been budgeted for in all projects that received approval post 2013 (3 working days equivalent of project manager’s time). You are kindly invited to send the completed template to Damiano Borgogno, damiano.borgogno@undp.org and to Eva Huttova, eva.huttova@undp.org.

## Details of the project

| Project’s title | Biennial Update Report 2014 to the UNFCCC |
| --- | --- |
| PIMS number | 5237 |
| Overall budget including GEF grant including co-financing | USD $646,461 USD $321,461 USD $325,000 |
| Duration of implementation | 2013-2018 |
| Planned duration of project | 2013-2014 |
| Implementing partner | National Institute for Ecology and Climate Change (INECC) |
| Team Leader’s name and contact details | INECC: Dra. María Amparo Martínez Arroyo, marroyo@inecc.gob.mx UNDP: Gerardo Arroyo O´Grady, gerardo.arroyo@undp.org |
| Link to final report | INECC: http://inecc.gob.mx UNFCCC: https://unfccc.int/documents?f%5B0%5D=country%3A309 |

## Project identification phase

Duration of preparatory phase (expressed in months)

This project did not require a preparatory phase. Check with Gerardo Arroyo.

Was the project document developed by a national/international consultant? (Please, provide name if yes and expand on the satisfaction of this collaboration.)

No Check with Gerardo Arroyo.

Please, shortly describe the milestones of this initial preparatory phase (e.g. consultation workshops held, telephone interviews with key stakeholders, among others)

At the beginning of the process of integration of the BUR, an inception workshop was held in Mexico City on October 10th to inform representatives of the sectors to be included in the National Inventory (mobile sources, electricity generation, residential and commercial, oil and gas, industry, agriculture, waste and USCUSS) about this national commitment to the UNFCCC. Since it was the first time that Mexico had to make a BUR, it was important to involve all stakeholders in order to have the best information. In that workshop, information was given on the differences of this report and the National Communication, and participants were notified about the needs of information and the timing of the process, and about the need to establish communication and collaboration mechanisms for the generation and integration of the necessary information to be included in the first BUR of Mexico.

The workshop was very useful to start a relationship with all sectors involved and to call attention on the importance of the systematization of information on greenhouse gas emissions in order to be able to generate public policies for its mitigation.

Where consultations made with one or more of the following stakeholder groups?

|  | Ministry of Finance (or equivalent) Yes |  | Women’s associations No |
| --- | --- | --- | --- |
|  | Other Ministries (not being the Ministry in charge of climate change) Yes |  | Youth movements No |
|  | Local Governments No |  | Indigenous peoples’ representatives No |
|  | National universities Yes |  | Environment or climate related NGOs No |
|  | Domestic Research Centers Yes |  | Other NGOs/CSOs No |
|  | Media No |  | Others (specify) |

What were the main objectives for the project identified as a result of this preparatory phase?

The main objective of the Project was to assist Mexico in the preparation of its First Biennial Update Report (BUR) for the fulfilment of its obligations under the United Nations Framework Convention on Climate Change (UNFCCC).

The project had two stages. The first one was executed from 2013 to 2015 and the second one from 2016 to 2018.

The First BUR was developed during the first stage and was submitted to UNFCCC on October 2015. The second stage of the project was aimed to fully comply with the guidelines agreed at the UNFCCC meeting held in Bonn, Germany, in May 2016, according to which the second BUR should be accompanied by a report on the methodology used to carry out the National Inventory Report (NIR).

Therefore, the extension of the duration of the First BUR Enabling Activity Project was requested in September 2017, aiming to use the remaining funds to strengthen capacities and strategies for the development of BUR2 and NIR2, such as: reflect the application of the IPCC 2006 Guidelines in the estimations in all sectors; include the recommmendations of the International Technical Expert Group (TTE) of the International Consultation and Analysis (ICA) process into the different sectors of the Inventory; continue the improvements to methodological approach and activity data that were implemented in the 2013 Inventory and that had to be reflected in the 2016 Inventory Update; reconstruct the historical series 1990-2015 on a year-on-year basis with the 2006 IPCC methodologies (in the First BUR it was not possible to construct the historical series consistently).

This second stage was developed in coordination with the team and the budget of Project 85488 (6th National Communication and BUR2), since all the identified activities that were necessary to achieve the above objectives exceeded the scope and budget of the GEF grant for the Sixth Communication.

What were the major challenges faced during this phase?

When the development of the BUR started, the National Institute for Ecology (INE) was in a process of adjustment required to be in line with the by then recent publication of the General Law on Climate Change. This Law created the actual National Institute for Ecology and Climate Change (INECC) and the administrative structure of the previous INE had to be modified. Therefore, the Project Document (Prodoc) had to be adjusted and this process required negotiations with UNDP and GEF that generated delays in the management and signature of it. Nevertheless, this situation had some positive effects, since it facilitated the appropriation of the Project by the new team in INECC.

Looking back, what issues that were identified and/or overlooked during this preparatory phase had an impact on the successive implementation phase?

The production of the First BUR would have been easier if the team had asked the UNFCCC for support. Not knowing the guidelines for the preparation of these reports and the details and precise information expected by the Convention, such as the structure of the document, made it more difficult. To know in advance the aspects that experts review when a BUR is delivered, and the implications of each stage of the process of the international review (ICA) would have been very useful.

The team did not gauge the implications of migration to IPCC 2006 methodologies and therefore capacities were not fully developed at that time.

## Project implementation phase

Technical components

- GHG inventory

Base year of the GHG inventory: 2010

Base years used in previous GHG inventories: 1990, 1994, 1997, 2002, 2006, 2010

| Expected outcome | National GHG Inventory has been updated |
| --- | --- |
| Expected output 1 | National GHG Inventory updated to 2012 (period 2010-2012) for the categories: Energy, Waste, Industrial processes and Agriculture (1990-2012) |
| Expected output 2 | Analysis of information and methodologies required for the category: land use, land use change and forestry using IPCC 2006 |
| Expected output 3 | Inventory Report produced |

| Final outcome | National GHG Inventory was updated to 2013 |
| --- | --- |
| Final output 1 | National GHG Inventory was updated to 2012 (period 2010-2012) for the categories: Energy, Waste, Industrial processes (2010-2012). Agriculture was calculated for the period 1990-2012. Additionally, 2013 Inventory was calculated with a bottom up methodology in all categories (for GHG and Black Carbon emmissions). |
| Final output 2 | Categories were analysed with IPCC 2000 and 2003 methodologies, because capacities to migrate to IPCC 2006 were not developed at that time. |
| Final output 3 | Inventory Report was produced and submitted to the UNFCCC in August 2015 |

Please, shortly discuss the expected outcomes and outputs of the GHG inventory component, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the causes (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

Significant methodological improvements were made in almost all emission categories for the year 2013 and this laid the foundation for the analysis that supported the preparation of Mexico’s Intended Nationally Determined Contribution delivered to the UNFCCC in the first quarter of 2015.

These methodological improvements, however, could not be applied in all sectors for the calculation of the 1990-2012 historical series and, therefore, a discontinuity can be seen in the estimation of the 1990-2012 Inventory and the emissions reported for the year 2013.

Since the objective was to present clear and methodologically transparent information, the estimations for 2013 emissions were presented in a differentiated way than those of the historical series.

The calculation of uncertainties of the main categories could not be done at that time and neither the quality assurement of the inventory.

In the second stage of the Project, IPCC 2006 methodologies were used for the estimation of  emissions in all sectors and in the reconstruction of historical series 1990-2015. Recommendations of TTE were also applied for the construction of the Inventory update, to be included in the Sixth National Communication.

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

Institutional arrangements with key stakeholders of each sector were implemented to ensure the flow of information. These were heterogeneous, since they had to respond to the needs and communication mechanisms established with each institution, but facilitated the development of better activity data and emission factors.

Nevertheless, these arrangements were not formalized and this is something that needs to be done, because there are continuous changes in the personnel in public offices.

Results of agriculture and USCUSS categories were subject of quality assurance, but the rest of the categories of the inventory should also be assured.

What pieces of advice do you have for future project teams?

It is important to ensure the consistency of historical data series by using the same methodology in all categories and in all years, and also the uncertainty calculation of main categories.

Follow IPCC guidelines to report under their categories.

Maintain institutional communication arrangements and implement mechanisms to ensure continuity of developed capacities in public officials.

Develop a national database that updates regularly the information needed for the Inventory (fully operational GHG Inventory management system) and generate institutional mechanisms to guarantee the continuance of the already developed capacities in public officials, regardless personnel rotation.

- Mitigation actions

| Expected outcome(s) | Implemented GHG mitigation policies and actions have been updated and reported for the period 2012-2014 |
| --- | --- |
| Expected output 1 | Information on the institutional arrangements to enable the implementation of NAMAs including the establishment of the national registry |
| Expected output 2 | Baseline and mitigation scenarios until 2030 for abatement of GHG emissions developed (energy, agriculture, transport and waste sectors) |
| Expected output 3 | Support given to the mitigation related activities proposed in the Fifth Communication: the establishment of the national NAMA registry, NAMAs designed and implemented up to 2014, including MRV methodologies and GHG mitigation potential, and the training and awareness raising activities for NAMAs for sectors with mitigation potential. |
| Expected output 4 | Progress of policies and actions to mitigate GHG implemented and planned from 2012 to 2014, at national, state and local levels. |
| Expected output 5 | Information provided on participation in international market carbon mechanisms. |

| Final outcome(s) | Implemented GHG mitigation policies and actions were updated and reported for the period 2012-2014 in the BUR |
| --- | --- |
| Final output 1 | Information on the institutional arrangements to enable the implementation of mitigation actions (not only NAMAs), including the national registry, were included in the BUR |
| Final output 2 | Baseline and mitigation scenarios until 2030 for abatement of GHG emissions were developed for energy, agriculture, transport, industry, USCUSS and waste sectors and included in the BUR |
| Final output 3 | When the Prodoc was designed, NAMA´s were the main instrument for the implementation of mitigation actions. The international discussion evolved towards the National Determined Contributions (NDC) and therefore the First BUR of Mexico included the analysis of the actions presented in the INDCs and NAMAs registered at that time. |
| Final output 4 | Policies and actions to mitigate GHG implemented and planned from 2012 to 2014, at national, state and local levels, were reported. |
| Final output 5 | Information on participation in international market carbon mechanisms was provided. |

Please, shortly discuss the expected outcomes and outputs of the vulnerability and adaptation measures and mitigation measures components, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the causes (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

In terms of the mitigation measures, difficulties to have the requested information were faced with all sectors, since methodologies, consistency and quality of data were heterogeneous. The presentation of concrete and tangible results was also difficult, and this did not allow to reflect all the efforts made at the national level.

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

A public consultation meeting was held to request the collaboration of government, industrial sector and other actors to identify possible mitigation measures to comply with the INDC commitment. Technical conversations were held with key actors of specific sectors, to establish tangible mitigation actions (energy, forestry, industry).

What pieces of advice do you have for future project teams?

Generate institutional and precise mechanisms to receive, analyze and agree on information of emission reductions with each sector.

Communicate with stakeholders at the beginning of the process of integration of the BUR.

Organize workshops in three stages: one for planning activities and prior to requesting information in order to agree methodologies, formats, characteristics of actions to be reported; one for follow-up activities and progress assessment; and final presentation and validation of results workshop

Develop methodologies to identify and measure mitigation actions.

Negotiate support from both governmental and private sectors to support continuity for the mitigation measures identified.

- Vulnerability & Adaptation for NC or MRV for BUR

| Expected outcome(s) | Measurement, Reporting and Verification arrangements are supported |
| --- | --- |
| Expected output 1 | Identification and analysis of different methodologies for MRV up to 2014 of the mitigation actions in different sectors |
| Expected output 2 | Support given to the process of development of the national institutional arrangements and framework for MRV |
| Expected output 3 | Progress of implementation of such institutional arrangements and framework described |

| Final outcome(s) | Measurement, Reporting and Verification arrangements were supported |
| --- | --- |
| Final output 1 | Different activities and instruments for MRV in different sectors were identified and analized. |
| Final output 2 | The process of development of the national institutional arrangements and framework for MRV was started. |
| Final output 3 | Implementation of institutional arrangements and framework for the National Inventory was described in the BUR |

Please, shortly discuss the expected outcomes and outputs of the vulnerability and adaptation measures and mitigation measures components, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the main reasons (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

The process of construction of an MRV system in Mexico was reported in the BUR. Several instruments were reported, such as the National Emissions Registry (RENE), the National Registry of NAMAs; the REDD+ strategy, and some areas of opportunity were identified, such as the need to extend, strengthen and integrate MRV mechanisms to achieve a national system with sufficient information to monitor progress in the achievement of national goals.

In relation to the MRV methodologies used in various sectors, it was found that there were different calculation methods, different assumptions and time horizons and also differences at the federal and subnational level, which made it difficult to estimate progress in mitigation. However, recommendations were generated so that in the future, within the context of an MRV framework, a comparable accounting of the actions carried out could be provided.

Regarding institutional arrangements for greenhouse gas inventories, in addition to those described above for the national inventory, a coordination protocol was established between the federal Ministry for Environment and Natural Resources (Semarnat) and INECC to support the alignment of climate change programs and greenhouse gas inventories at the federal and state levels.

During the second stage of the Project hardware and software was purchased, which strengthed INECC´s capacities for the construction of the MRV system .

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

Communication was maintained with different governmental agencies and private sector organizations, in order to have information on their mitigation actions and the methodological assumptions used for their calculation.

What pieces of advice do you have for future project teams?

Organize workshops in three stages: one for planning activities and prior to requesting information in order to explain the process of integration of the report, agree methodologies, formats, characteristics of mitigation actions to be reported; one for follow-up activities and progress assessment; and final presentation and validation of results workshop. This can help to maintain close communication with stakeholders along the process.

- Constraints and Gaps/Support needed

| Expected outcome | Relevant information on financial support has been compiled and updated |
| --- | --- |
| Expected output 1 | Information on financial resources and technical support received for activities related to climate change (including collaboration activities related to technology transfer and capacity building and the financial support received since the publication of the Fifth National Communication) |
| Expected output 2 | Technology, financial and capacity needs for mitigation assessed (including financial requirements for the assessment of mitigation opportunities) |
| Expected output 3 | Financial report produced |

| Final outcome | Relevant information on financial support was compiled and updated |
| --- | --- |
| Final output 1 | Information on financial resources and technical support for activities related to climate change was estimated and provided. include the analysis of the decrease in the budget of INECC |
| Final output 2 | Technology, financial and capacity needs for mitigation were assessed |
| Final output 3 | Financial report included in the BUR |

Please, shortly discuss the expected outcomes and outputs of the Constraints and gaps, and related financial, technical and capacity needs component, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the main reasons (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

UNFCCC has not yet agreed with it’s member parties a methodology for the quantification of resources for climate change actions and for their reporting. Mexico started a discussion among stakeholders in order to agree on definitions, in the first place, and on tracking mechanisms of tagged resources for climate change and for the systematization of this information. Also a study was undertaken, but there is still uncertainty in this matter and it has not been possible to have precise information on this matter.

(Helena we can improve this paragraph with the comments of the last Mexico_National Communication and Biennial Update Report Status Survey

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

Information was requested to government institutions involved in climate change actions (basically members of the Inter Ministerial Commission on Climate Change (CICC)) and to international organizations / donors. A study was undertaken, to learn more about financing from international (bilateral and multilateral cooperation) organizations to promote or strengthen actions on climate change in Mexico and also from national institutions.

In the second stage of the Project, a review of the climate change transversal annex of the federation's budget was also carried out. Nevertheless, the information collected was not rigorous enough and therefore could not be considered definitive.

What pieces of advice do you have for future project teams?

UNFCCC should generate guidelines and methodologies for the identification, quantification  and reporting of financial resources for climate change that can show in a transparent way, the resources granted and those received. A tracking system of climate change financing should be promoted.

Helena we can improve this paragraph with the comments of the last Mexico_National Communication and Biennial Update Report Status Survey

Capacities and use of capacities

Do you believe the project has built - in a durable and cost-effective way - human and institutional capacities? Please, elaborate.

The General Law on Climate Change strengthened INECC to exercise its new responsibilities and attributions for the development of the Inventory and the definition of mitigation routes to fulfill its commitments to UNFCCC. This Project fostered the involvement of other ministries and stakeholders in the estimation of their emissions and in assuming their responsibilities in the implementation of mitigation actions. It also promoted information-sharing and inter-agency synergies.

During the second stage of the Project, staff members of INECC (institution responsible of the integration of the National Inventory on GHG Emissions and the preparation of Biennial Reports and National Communications) were trained with the latest IPCC methodologies (2006), which enhanced the 2015 Inventory and the Second BUR.

Future Inventories might benefit from sub-national activities and strategies to involve state and local level governmental authorities that, according to the General Law on Climate Change, have specific obligations in this matter. Therefore, capacities should be enhanced at the local level in order to use comparable methodologies for the calculation of state-level GHG inventories.

Please, estimate the amount of work done by national consultants versus international consultants:

15% national consultants, 0% international consultants and 85% national staff of the implementing partner (INECC).

What work was entrusted to international consultants and for what reasons?

Quality assurement of data in the following sectors: energy, IPUU, AFOLU and waste. Consultants are members of UNFCC roster of experts.

What would you have done differently, or do you advise the next project team to consider in this context?

Strengthen capacities of the responsible institution of the integration of the national BUR´s (INECC) in mitigation and technology topics and extend these capacities to other institutions in order to facilitate integration and to be able to reflect in the document the efforts of all sectors, at a national and subnational level.

Strengthen the implementing partner with technical personnel, capacity building in most current methodologies and with software and software for data follow up and the implementation of a MRV system.

(See MTR of Sexta, Jon prepared some comment about this)

Additional remarks

Institutional arrangements

Please, summarize an overview of the institutional arrangements for the project implementation.

In the first stage, the Project was coordinated by the General Coordination on Climate Change and Low Carbon Development created when INE was transformed into INECC and that area had total responsibility of the integration of the BUR but had multiple additional responsibilities and therefore had a very strong workload. The project only hired an administrative coordinator, and the need to have the support of a technical coordinator was felt during the process.

In the second stage of the project, working together with the Sixth Communication Project offered the opportunity to create a unit for administrative and technical matters. This strengthened both projects, since human and economic resources could be used efficiently and economies of scale were reached.

Please, describe the composition of the project team.

In the first stage, the Project Steering Committee was constituted by the General Director of INECC, General Coordinator on Climate Change and Low Carbon Development (INECC), Sustainable Development director and the Manager of UNDP Office in Mexico, Project Administrative Coordinator.

In the second stage of the project, two members of the Sixth Communication Project worked together with the General Coordination on Mitigation of Climate Change (former General Coordination on Climate Change and Low Carbon Development) of INECC, and with the Sustainable Development director and the Manager of UNDP Office in Mexico.

Will the team remain in place, even after the project has fully closed?

Yes, staff members of INECC responsible for the update of the Inventory and mitigation actions will remain. Personell hired to help with the update of the Inventory was absorbed by INECC, which has widened the Institute´s capacities for further work in this matter.

Were gender considerations taken into account during the project design and implementation? If so, how?

Gender considerations were not included specifically in the Prodoc, but the implementation was carried out with gender perspective: women were part of the directing team, were hired as experts for the review and update of categories of the Inventory, among other activities

In fact all GEF project need the application of the social and environment safeguards, that include gender consideration. We need to verify this internally. Please also note that we identified this as challenge in …….

Which were the strengths and weaknesses of the institutional arrangements used?

Not hiring a technical coordinator for the Project created a strong workload for INECC´s coordinating staff.

What suggestions have you to make regarding the institutional arrangements for future NC/BUR work?

To constitute a technical team exclusively dedicated to the integration of the BUR since the beginning of the Project, with the support of UNDP. This team should work very close with INECC, in order to take advantage of lessons learned during the process or BUR1.

Additional remarks

Technical support from GSP, CGE, or other bodies

Has the project team, or members of the project team, participated in national, regional or global training events organized by a center of excellence or above mentioned body during the course of the project? If yes, please, specify the training event(s).

19 staff members of INECC responsible for the development of the BUR were trained by the GHG Institute in the use of 2006 IPCC methodologies and could also participate in an evaluation workshop with the International Technical Expert Group (TTE) of the ICA process. This experience strengthened their capacities for further work in this matters.

in fact It was a necessity we identified in the Survey, copy and page the recommendation.

What has been the contribution of this participation to the project results?

Capacities of staff members of INECC were strengthened. In fact, some of them have been included in the expert roster of UNFCCC

The inventory could be updated with better methodologies and data-

What identified knowledge gaps holding back the proper implementation of the NC project could not be

addressed by any of the above mentioned bodies? ( see the survey comments)

Preguntar a Fabiola ___________________________________________________________________

In addition to capacity building support, what other assistance did the project team receive

during project implementation? (E.g. review of draft report, technical backstopping of international expert)

Workshop held in Mexico City with experts of the UNFCC roster for the review of the 2013 National Inventory and enhancement of BUR2. This workshop was organized with the support of GIZ.

(check the survey)

Has UNDP provided timely and valuable support during project design and implementation? Please explain.

UNDP Office in Mexico has been strategic and contributed appropriately to both technical and administrative aspects of the Project. Some of the issues that added important value to the results of the Project are the following:

- Flexibility of administrative procedures made it possible to speed up processes that could hardly have been done by INECC, such as:

  - Hire consultancies to be developed over two years

  - Hire international consultants

  - Purchase equipment (computer, photographic) and software

  - Pay training courses in foreign institutions (GHG Institute)

  - Hold workshops and meetings with the participation of national and international experts

  - Hire specialized technical support for the assurance of quality of the inventory

- Synergies between projects strengthened the construction of the NIR

- Transparency in the execution of resources, with international standards

- Technical and administrative support to ensure the efficient exercise of resources and the achievement of expected results

## Next steps

How will findings of the project be further disseminated, if at all?

In the second stage of the project, information was disseminated during the second and third national conference on climate change held in Mexico City in 2017 and 2018. During the latter, a special workshop with media was carried out, so that participants of this sector had access to the information of the Inventory and the BUR.

The National Inventory was presented to experts and media during a special meeting, in March 2018.

In order to assure the project’s sustainability, together with the Sixth Communication Project, a communication strategy, which includes a national web site for climate change has been developed and will be available by the end of 2018.

INECC´s webpage: https://www.gob.mx/cms/uploads/attachment/file/314955/2015_bur_mexico.pdf

and UNFCCC webpage

Are balance funds available under the NC/BUR project going to be used to identify the strategy of the

next report?

Yes, the possibility of extension of the Project made in 2017 made the review of estimations of GHG in all sectors possible and the application of IPCC 2006 methodologies in all sectors of the Second BUR, which will also present the historical series 1990-2015 estimated with the same methodology. This report is going to be part of Mexico´s Sixth Nacional Communication.

At full project closure, is there a person or institute to whom one can turn in case there are follow-up

questions to the NC/BUR?

National Institute for Ecology and Climate Change (INECC) and United Nations Development Programme Office in Mexico

Has the Government expressed interest to further work with UNDP on the next coming report?

If no, please explain.

Yes. Particularly in view of the near future change in administration, work is underway to define a portfolio of projects to meet INECC´s commitments, such as BUR3, the 7th Communication and the National Adaptation Plan.

## Additional information

| Date |  |
| --- | --- |
| Name and e-mail address of person who completed this template | Berta Helena de Buen Richkarday and Gerardo Arroyo, Director of the Sustainable Program (UNEP-Mexico) |
| Others involved in completion of this template (names of individuals and their institutions) | Irma Fabiola Ramírez, Director of Inventories and Prospects of GHG Emissions (INECC) Iris Jiménez, Director for International Affairs, INECC Arianne Hidalgo, UNEP |
| In case a terminal evaluation report has been produced, please link it here. | Monitoring and Evaluation plans of climate change enabling activities for the preparation of National Communications on Climate Change and/or Biennial Update Reports do not require the production and publication of Terminal Evaluation Reports. Preguntar PNUD/ Yes. |
| Other attachments | Liga del BUR en la página del INECC y CMNUCC https://unfccc.int/resource/docs/natc/mexbur1.pdf |