Project Title: Strengthening the Capacities of the Ministry of Foreign Affairs of Montenegro

Project Number: 00108858

Implementing Partner: UNDP Office in Podgorica

Start Date: 1st June 2018 End Date: 31st December 2019 PAC Meeting date: 25 May 2018

Brief Description

Briefly describe the overall development challenge and the expected results of the project. The objective of the project is to strengthen the capacities of the Ministry of Foreign Affairs (MFA) in the areas of international development cooperation and humanitarian aid sending. Montenegro has a dual role in this area – traditionally it has been a recipient of assistance and aid, but slowly it is also becoming a donor country, which is in line with its European aspirations. The project will be focused on the MFA and enhancing its capacities to fulfil new responsibilities that it needs to assume in order to become a donor country, and thus contribute to the global sustainable development through the provision of financial and other resources to the partner countries in need. Having in mind the new role that Montenegro will assume in international development cooperation arena as a donor country and the implications this will have on the international relations of the country, the project will also contribute to further enhancing of the capacities of the MFA’s staff with a specific focus to civil servants that are required to carry out diplomatic and consular tasks.

Contributing Outcome (UNDAF/CPD, RPD or GPD):

By 2021, people-centred, accountable, transparent and effective judiciary, Parliament, public administration and independent institutions ensure security, equal access to justice and quality services to all people.

Indicative Output(s) with gender marker2: GEN1

| Total resources required: | 83,000 EUR |  |
| --- | --- | --- |
| Total resources allocated: |  |  |
|  | UNDP TRAC: |  |
|  | Donor: Government of Montenegro | 83.000 EUR |
|  | In-Kind: |  |
| Unfunded: |  |  |

Agreed by (signatures):

| Government | UNDP | Implementing Partner |
| --- | --- | --- |
| Ministry of Foreign Affairs Print Name: Srdjan Darmanovic, Minister | UNDP in Montenegro Print Name: Fiona McCluney, Resident Representative | Print Name: |
| Date: | Date: | Date: |

# Development Challenge

The concept of development cooperation has various interpretations, but given its history and development potential, a broad consensus is achieved about its three major tasks:

1. supporting the efforts of developing countries to guarantee the provision of basic social standards and enjoyment of fundamental human rights to their citizens;

2. complementing the efforts of developing countries to achieve higher levels of income and, thus, correcting extreme inequalities;

3. supporting the efforts of developing countries to participate in the provision of international public goods.

Development cooperation is targeted at supporting both national and international development priorities and it should rely on internationally accepted development goals – SDGs, and other international and regional development agreements.  In relation with this, Montenegro integrated SDGs through the adoption of National Strategy of Sustainable Development until 2030 and accepted to concentrate all its efforts toward achieving the defined targets, one of which is international development cooperation.

The Montenegrin government reconfirmed the country’s reform focus on measures required to secure Montenegro’s entry to the European Union. In Montenegro 2018 Report prepared by the European Commission, the issue of international development cooperation has been mentioned: “On development policy and humanitarian aid, a department for development cooperation and humanitarian aid has been established within the Ministry of Foreign Affairs, as well as an inter-ministerial working group which includes representatives of the state administration, civil society and businesses community. A related legislative and strategic framework is under preparation. Additional funds from the budget will be needed to implement the law. Initial steps have been taken to develop a database of donor support projects (received and provided) using the OECD Development Assistance Committee methodology. Montenegro needs to continue its preparations in this chapter in accordance with its overall Action Plan on external relations.”

Chapter 30 on external relations which includes development policy and humanitarian aid was opened on 30 March 2015. The Montenegrin Government adopted an action plan in October 2016 aimed at further alignment of legislation with the acquis communautaire and strengthening institutional and administrative capacities in this field. According to the plan, the adoption of the Law on Development Cooperation and Humanitarian Aid is set as one of the main priorities. Following a two-phase wide consultative process of preparation with all key stakeholders, the Government adopted the Draft Law on International Development Cooperation and Sending Humanitarian Aid on March 15th, 2018. The Law was approved by the Parliament of Montenegro on April 27th. Chapter 30 - External relations, was provisionally closed at the ninth meeting of the Accession Conference with Montenegro at ministerial level that was held in Luxembourg in June 2017. However, the EU underlined that it would devote particular attention to „monitoring all specific issues mentioned in its common position” and that “will, if necessary, return to this chapter at an appropriate moment.”

Montenegro has long been a recipient of Official Development Assistance (ODA). However, as a part of the Federal Republic of Yugoslavia and State Union of Serbia and Montenegro, Montenegro was isolated from the international community during the 1990s and received international humanitarian aid in this period. Also, until 1998, the European Commission provided Montenegro with humanitarian assistance, support for democratization and independent media. By 2000, donor support consisted mainly of humanitarian assistance and emergency reconstruction of infrastructure.

From 2000 onwards, donor support moved towards the provision of development assistance to build institutional capacities in support of European integration process. Through the CARDS program (Community assistance for reconstruction, development and stabilization, an instrument of technical and financial assistance that is intended to support the stabilization process and the association of Western Balkan Countries), Montenegro received 60.8 million EUR in the period from 2001 to 2004. In the period from 2013 until 2015, Montenegro was number 10 of ODA recipients in Europe and received 317 million USD, with an average distribution of 106 million USD per year.

It should be noted that apart from non-existence of legislative framework, the issue of records keeping in this field is prominent. There is no unified database and publicly available data of development cooperation and humanitarian assistance that Montenegro received by bilateral and multilateral donors.

The main donors are EU Institutions, with a contribution of about 88.34 million USD (2014-2015 average); the second Germany, with about 27.47 million USD followed by the United Arab Emirates, with contributions of 7.82 million USD, and Turkey with 4.64 million USD. Other ODA Donors are: United States (2.73 million USD), OSCE (2.31 million USD), Slovenia (1.63 million USD), Norway (1.24 million USD), United Kingdom (1.19 million USD) and UNICEF (0.97 million USD).

Regarding the distribution of ODA by sector, economic infrastructure and services receive about 34% of ODA, education receives little more than 8% of ODA, production about 0.6%, multisector about 1%, less than 2% is destined to action relating to debt and about 2% to Other and unallocated/unspecified. The main recipient sector is “Other Social Sector”, with 52% of ODA.

On the other hand, since the restoration of independence in 2006, Montenegro has implemented certain forms of international development cooperation and provided international humanitarian aid to other countries. However, no centralized records have been maintained on these activities, and in 2010 the responsibility for the implementation and monitoring of this policy was given to MFA. Bearing in mind the international orientation of Montenegro and clearly defined expectations of the European Union (EU) in the negotiation process, in this area, Montenegro has both the need and the obligation to define its own development policy, develop an adequate legislative and strategic framework, and determine the mechanisms for coordination, planning, implementation, recording, monitoring and financing of international development cooperation and providing international humanitarian aid.

In the light of the abovementioned, it is clear that Montenegro’s EU membership will require many efforts toward strengthening the capacities of the country in various areas, inclusive of international development cooperation, especially having in mind Montenegro’s shift from being only recipient to becoming also a donor-country. The overall aim of these reforms will be to contribute to global sustainable development and realization of SDGs through the provision of material and non-material resources to countries in need. This is a very complex and demanding task and the Ministry of Foreign Affairs is in charge of leading the process. This is the reason why the support to MFA and building its capacities will be at the focus of this process.

In the light of the fact that, apart from being recipient country, Montenegro will also become a donor country in the field of international development cooperation, the position of the country in the international arena will be changed to a significant extent. Given that the purpose of the provision of official development assistance and humanitarian aid sending is the contribution to the increased human rights and fundamental freedoms observance globally, as well as the contribution toward reducing inequalities and poverty among the countries in need, Montenegro will have a chance to contribute to the global peace and security in this manner. With all this in mind, this new role of the country in international relations will need to be widely promoted, which will be mainly done by the MFA staff dealing with diplomatic and consular affairs. This is the reason why it will be particularly important to include this topic in the agenda of the Diplomatic Academy in the forthcoming years and work toward educating MFA staff in this regard.

It should be noted that the need for strengthening capacities required to conduct foreign service affairs was recognized in 2003 when the Diplomatic Academy was established as a special project of the Faculty of Law and the Faculty of Political Science. Since that period, the Diplomatic Academy has changed its status and in 2010 was established as an internal organizational unit of the Ministry of Foreign Affairs of Montenegro by passing the Law on Foreign Affairs and additional responsibilities were assigned to Diplomatic Academy with the new Law on Foreign Affairs from 2017.The afore mentioned Law recognized the importance of training of employees in the foreign service, and it was defined that, in addition to professional development prescribed by the law regulating the rights and duties of civil servants, the training is also carried out through special programs in the field of foreign affairs organized by the Diplomatic Academy, whose forms, manner and duration as proposed by the Diplomatic Academy are prescribed by the Ministry of Foreign Affairs. Among the developed programs, Summer School for Young Diplomats represents the major regional event organised by the Diplomatic Academy. Having in mind the new role that Montenegro will assume in international development cooperation arena as a donor country and the implications that this will have on the overall position of the country in the field of international relations, the training in the field of foreign affairs has becoming ever more important.

# Strategy

During the EU accession process, Montenegro will embark on the path of becoming a donor country from being a recipient of Official Development Assistance (ODA). This is a very demanding task and there are some challenges that will be faced in the process, some of them stated in Montenegro 2018 Report, which shows that “Montenegro has reached a good level of preparation (… and that) progress was made on the legislative and institutional setup for international development cooperation and humanitarian aid (…), but that Montenegro should in particular: adopt a legislative and strategic framework, in line with the acquis, on development policy and humanitarian aid; and develop a database of donor support”

In Montenegro, most of the institutions are or have a potential to become actors in the area of development policy. The need for inclusive sustainable development partnerships, as outlined in the Agenda 2030, is well reflected in the newly adopted Law on International Development Cooperation and Sending Humanitarian Aid. Article 9 of the Law prescribes that international development cooperation shall be carried out by the state bodies, state administration bodies, local self-government and local government bodies, public institutions, legal entities with public authority and other entities within their respective competencies or activities. Also, other entities within the framework of the sustainable development partnership (companies and entrepreneurs, non-governmental and other domestic and international organizations, other departments and institutions, citizens and other interested parties) may also participate in the implementation of international development cooperation.

In terms of humanitarian aid policy, the key actors include: the Ministry of Foreign Affairs, Red Cross of Montenegro, the Ministry of Labour and Social Welfare (Office for Refugees) and the Ministry of Interior – Directorate for Emergency Management (Direction for Civil Protection and Humanitarian Aid). Montenegro engages in humanitarian aid on an ad-hoc basis since 2006 by the Cabinet of the Prime Minister, and later by the MFA. The newly adopted Law opens the possibilities for the same set of actors as defined under Article 9 to be involved in the humanitarian policy as well (Article 11).

Although Montenegro has a dual role in the field of development cooperation and humanitarian aid, still being a recipient, but also simultaneously providing development and humanitarian assistance, there are no centralized records about either of those flows. For example, the Montenegrin government provided humanitarian aid to the countries in the region such as Macedonia, Serbia and Albania that were affected by floods in the period from 2014 to 2017. Additionally, Montenegro was an ad-hoc humanitarian aid donor for Haiti (earthquake in 2010), but also “Syria, Pakistan, Sierra Leone and Palestine in the period from 2008 to 2013”. More recently, Montenegro provided EUR 10,000 to Mexico after the devastating earthquakes in September 2017 and in April 2018 EUR 10.000 to Yemen in support to the Yemen Humanitarian Response Plan.

It should be also noted that there are no statistics on the Montenegrin development cooperation. Within the Ministry of Foreign Affairs, a Directorate General for Economic and Cultural Cooperation (DGECC) has been established with the key task to implement development and humanitarian aid policy. The mandate of DGECC is to establish the legal framework, but also to collect data on provided aid and prepare the methodology of calculating its value. Upon consultations with the relevant stakeholders on methodology of data collection, the Ministry initiated the development of a comprehensive database on development cooperation and humanitarian aid in 2016. The database would track both the incoming donor assistance and Montenegro’s allocations for development cooperation and humanitarian assistance. The first advanced version of the database was expected to be prepared by November 2016, but this database has not yet been created, due to the lack of a software tool.

In the light of the abovementioned, it should be noted that the establishment of normative framework and database, along with strengthening administrative capacities within the MFA will contribute to the fulfilment of preconditions for Montenegro’s transition to a donor country.

Hence, the project will be primarily focused on strengthening of capacities of the MFA in the area of strategic planning, implementation and monitoring of development co-operation policies and humanitarian aid, creation of normative framework, relevant records keeping and outreach to the public. Additionally, diplomatic activities of the Ministry of Foreign Affairs should be intensified and its capacities in this domain are to be further enhanced. MFA needs to additionally build and strengthen capacity of the staff with a specific focus to civil servants that are required to carry out diplomatic and consular tasks in order to prepare and support them to respond to the professional requirements that await them in the future.

# Results and Partnerships

Expected Results

The long-term goal of the project is support the Government of Montenegro to assume its new role as a donor country and respond to new demands in the areas of international development cooperation and humanitarian aid.

The primary objective of the project is to enhance the capacities of MFA to fulfil new responsibilities that it needs to assume in order to support Montenegro to become a donor country, instead of a recipient only, and thus contribute to the global sustainable development through both the provision and receipt of financial and other resources targeted at fulfilling various development priorities

The support will be implemented in two main areas. The project will have the following expected results:

1.	Capacities of the Ministry of Foreign Affairs in the area of international development cooperation and international aid strengthened through the implementation of the following activities:

1.1. By-laws for the Law on International Development Cooperation and Sending Humanitarian Aid (the Law) prepared by the end of the second quarter of 2019;

1. 2.	Databases for the inflows and outflows of development cooperation and humanitarian aid of Montenegro created;

1.3.	Strategy on International Development Cooperation and Humanitarian Aid (the Strategy) prepared and adopted by the end of the second quarter of 2019;

1.4.	Public awareness about the role of MFA in implementing International Development Cooperation and Sending Humanitarian Aid (the Law) raised;

2. 	Capacities of the MFA staff dealing with diplomatic and consular affairs strengthened through the organization of the Summer School for Young Diplomats.

1.1. The Law on International Development Cooperation and Sending Humanitarian Aid (the Law) envisages the preparation of two sets of bylaws, which need to be adopted by the Montenegrin Government and Parliament:

1.1. Bylaws on data collection, record keeping and reporting as defined under Art. 12 (which states that the Ministry shall collect data on international development cooperation and international humanitarian aid from bodies, legal entities and other entities participating in international development cooperation and international humanitarian aid referred to in Article 9 paragraph 1 and Article 11 paragraph 1, and other entities referred to in Article 9 paragraph 2 and Article 11 paragraph 2) and Art. 13 (which stipulates that the Ministry shall submit to the Government an annual report on international development cooperation and international humanitarian aid of Montenegro.);

1.2. Bylaws on the implementation modalities of the international development cooperation (Art. 9) and providing international humanitarian aid (Art.11), which are the most challenging ones. These are dependent on the provisions of the future Strategy that will regulate this area.

1.2. Creating databases for the inflows and outflows of development cooperation and humanitarian aid of Montenegro:

1.2.1. The database of outflows is linked to the Law and, at this point, it is envisaged to use the EU DEVFIN database that is linked to the CRS++ and IATI reporting tools, instead of creating a new database unique to Montenegro. The plan is to use the version already upgraded by the new EU member states that have been using it (including Romania, which partnered with UNDP on this) rather than using the original platform created by the EC.

1.2.2. The database of inflows is the second one that needs to be created, as Montenegro is still a recipient of development assistance. An efficient and a light system is necessary to keep records of the incoming assistance, which will allow the country to achieve better donor coordination as well as better planning for the following years in terms of the selection of priorities and partners.

1.3. Preparing and adopting the Strategy on International Development Cooperation and Humanitarian Aid (the Strategy), which is an obligation defined under Art. 7 of the Law:

The Strategy will be an expert-based document, as development cooperation is one of key foreign policy tools. In this regard, two sets of consultations are planned:

1.3.1. Policy level consultations, with Minister and other high-level members of the MFA (two-day high-level workshop, held on April 18-20 this year followed by a report presentation at a Government's session) and

1.3.2. Expert level consultations, with key stakeholders in the country as well a multi-stakeholder WG functioning under the MFA since the end of 2016, with experts from the line ministries, academia, business and NGO sectors, independent experts.

The activities will contribute to defining the specific strengths and the niche that Montenegro can have as a new provider of development cooperation within the larger development community, as well as part of the creation of a multi-year ODA strategy, setting out specific targets and priorities for cycles of 4-5 years.

All of the mentioned activities need very strong, focused and clear communication campaign, which is the fourth sphere of the planned activities:

1.4. Communication and Outreach: As this is an integral part of all UNDP projects, all the joint project activities will include it integrally, however, as this is a strategic priority of the Government, additional resources will be invested in organizing public consultations (the general public, separately NGOs as one of the key groups, businesses) and communication tools (inter alia flyers, interviews, panels).

2. Summer School for Young Diplomats: Diplomatic Academy will lead the implementation of the eleventh summer school for young diplomats and in the same time honouring the fifteenth anniversary of the Diplomatic Academy.

This year’s Summer School will lay a particular emphasis on “The Role and the Importance of Diplomacy in the Time of (De) Integration - Contribution to the Global Peace and Security”. Special attention will be given to the issues related to the role and significance of diplomacy in maintaining the international peace and security, overcoming crises and developing new models of economic, political and security cooperation in international arena. It will also provide an opportunity for young diplomats to get acquainted with the history, culture, as well as foreign policy priorities of the participating countries, and establish through learning, exchange of views and socializing, mutual rapport and the basis for future cooperation.

As for years now, this year’s Summer School will bring together a considerable number of participants from the countries of the region, the European Union and, indeed, from all over the world, as well as prominent lecturers who will bring closer contemporary issues of international politics to their younger colleagues. It expected to have 50 participants from at least 30 countries of the globe.

In the same time, this will be the occasion to celebrate 15 years since is recognizes the need for having the Diplomatic Academy in Montenegro, recalling the reasons and importance of this decisions, and setting the road for the future.

Resources Required to Achieve the Expected Results

The proposed project implementation team includes a Project Manager (part time) and Project Finance and Administration Officer (part time). The Project Manager will be responsible for the overall implementation of the project including operational and financial responsibility. The Project Finance and Administration Officer will deal with day-to-day administrative activities related to procurement, project administration, payments and monitoring. Project Finance and Administration Officer will work under the supervision of the Project Manager to ensure that all aspects of project coordination are in place.

Partnerships

The proposed action was designed through the consultative process with the Ministry of Foreign Affairs (the beneficiary) and it will be implemented in close cooperation with the beneficiary and other stakeholders involved. UNDP will assume full responsibility and accountability for the overall management of the Action, including monitoring and evaluation of interventions, achieving of the objectives and specified results, and the efficient and effective use of resources. We will apply the principles of Quality Management, by streamlining all internal working procedures, organizational structures and establishing standardized feedback and improvement mechanisms.

Risks and Assumptions

One of the key risks is a low capacity of MFA to receive the support and implement new tasks in the area of international development cooperation and humanitarian aid due to the limited human resources. This is a very demanding task and workload of the MFA staff will be increased with the new obligations. Therefore, the Project will carefully plan the dynamics for the capacity building interventions.

Stakeholder Engagement

Since the essence of the project is to contribute to enhancing the capacities of the Ministry of Foreign Affairs in the area of international development cooperation, the national stakeholders’ engagement will be very important. The activities will relate to the establishment of strategic and normative framework in the area of international development cooperation and humanitarian aid, in which process the staff of MFA will have a crucial role, especially in terms of contribution to formulating the relevant documents.

South-South and Triangular Cooperation (SSC/TrC)

In the scope of one of the activities related to the creation of databases for the inflows and outflows of development cooperation and humanitarian aid of Montenegro, the exchange of experience and knowledge sharing with Romania will be essential for the successful completion of the planned task. The database of outflows is linked to the Law and, at this point, it is envisaged to use the EU DEVFIN database that is linked to the CRS++ and IATI reporting tools, instead of creating a new database unique to Montenegro. The plan is to use the version already upgraded by the new EU member states that have been using it (including Romania, which partnered with UNDP on this) rather than using the original platform created by the EC. It should be noted that SSC/TrC will be the subject of the Strategy and that the report prepared by UNOSSC will be one of the inputs to be considered in the process of the Strategy preparation.

Knowledge

- Strategy on International Development Cooperation and Humanitarian Aid will be created and it will provide strategic framework for this area, which may be further used and upgraded at a later stage;

- By-laws for the Law on International Development Cooperation and Sending Humanitarian Aid will be prepared in order to enable better implementation of the Law and, together with the law, they will compose the normative framework for this area;

- Public consultations on the topic of International Development Cooperation and Humanitarian Aid will result in a relevant report, which may be used for further reference;

- Brochures, flyers and other promotional material on the topic of International Development Cooperation and Humanitarian Aid will be produced in the scope of the project;

- Summer School Bulletin will be produced in the scope of the project and for further reference of the MFA.

Gender mainstreaming

UNDP has a strong corporate commitment towards gender mainstreaming with a record of long-lasting good practices in the CO Montenegro office, certified with global gold standards in gender mainstreaming. UNDP has been working in the country in creating strategic and legal frameworks for gender equality and gender mainstreaming since 2008 and implements program focusing on gender concerns from EU IPA financial support. Montenegro, is a signatory of all relevant UN and CoE conventions and on its path towards EU membership needs to further develop capacities for gender mainstreaming and assure its meaningful implementation.

Montenegro, as well as EU and UN have chosen two-fold approach where one is specific issue-oriented work through programs (such as LGBT rights, women in decision making, etc.) and the second one is gender mainstreaming approach into all policies and programs (such as gender responsive employment programs).

In the context of international development cooperation, the gender issues gain particular importance, especially having in mind that women in crisis are more vulnerable and less resilient, since majority of them do not own their own property and financial resources that would help them in overcoming hardship. Due to the fact that women are more affected to the negative consequences of crises than men, the integration of gender responsive measures in policies and actions related to the provision of official development assistance and sending humanitarian aid is especially important.

Apart from contributing to more effective implementation of SDG 5 – Gender equality, it is important to mention that the activities conducted through this project will also have a multiplying effect on other SDGs, such as SDG 1 – No poverty and SDG 3 – Good health and well-being, taking into account that the provision of assistance in the scope of international development cooperation will enable both women and populations of developing countries in general to have access to food, water and basic health services, which are their fundamental human rights.

In this context, the project “Strengthening Capacities of the Ministry of Foreign Affairs of Montenegro” will contribute to the capacity development of the Ministry through following general and specific interventions:

- With regard to recruitment of local and international consultants UNDP corporate requirement is to include gender mainstreaming competences (general intervention);

- Strategy on International Development Cooperation and Humanitarian Aid prepared in the course of the project should integrate gender mainstreaming aspects, such as integration of the findings of the relevant data, statistics and gender analyses in the document, as well as at least one gender responsive measure, which is particularly relevant for the countries where women are in less favourable position than men(specific intervention);

- By-laws for the Law on International Development Cooperation and Sending Humanitarian Aid developed during the project will reflect gender-specific concerns and at least one gender responsive measure, which is particularly relevant for the countries where women are in less favourable position than men (specific intervention);

- Public consultations on the topic of International Development Cooperation and Humanitarian Aid will aim to include minimum 30% of female participants, who will be equally represented in the process of policy creation and decision-making.

Sustainability and Scaling Up

The expected impact of the support will be manifold. The capacities of the Ministry of Foreign Affairs (MFA) in the areas of international development cooperation and humanitarian aid will be improved, which will have a positive impact on the degree of fulfilling the goals set by 2030 Agenda for Sustainable Development that Montenegro adopted and on the overall EU accession process. The sustainability of the project will be ensured by the creation of the relevant strategic and normative framework, by means of preparing the Strategy on International Development Cooperation and Humanitarian Aid and two sets of bylaws for the Law on International Development Cooperation and Sending Humanitarian Aid, as well as through capacity building of the MFA staff. Furthermore, public consultations in the area of International Development Cooperation and Humanitarian Aid will be held, which will create opportunities for scalability of the project results by experience and knowledge sharing with other countries investing efforts to this end.

# Project Management

Cost Efficiency and Effectiveness

The proposed project implementation team includes a Project Manager (part time) and Project Finance and Administration Officer (part time).

Additionally, all project activities will be carefully planned and monitored by the Project Board members, inclusive of the representatives of the beneficiary, UNDP and Istanbul Regional Hub (IRH). Namely, during the Project Board meetings, all aspects of engaging consultants, organizing workshops, identifying participants and eligible costs will be defined for the upcoming six months period.

Project Management

The project will be implemented through Direct Implementation modality. The project costs are subject to direct project costing of operational services as per the UNDP procedures and in accordance with UNDP CO established practices. The project will be on daily basis managed together with MFA.

# Results Framework

Intended Outcome as stated in the UNDAF/Country [or Global/Regional] Programme Results and Resource Framework: By 2021, people-centred, accountable, transparent and effective judiciary, Parliament, public administration and independent institutions ensure security, equal access to justice and quality services to all people.

Outcome indicators as stated in the Country Programme [or Global/Regional] Results and Resources Framework, including baseline and targets:

Applicable Output(s) from the UNDP Strategic Plan:

Project title and Atlas Project Number: Strengthening Capacities of the Ministry of Foreign Affairs, Project Number: 00108858

|  |  |  | Indicator data |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| LEVEL | EXPECTED RESULT | INDICATORS | BASELINE Y0 | TARGET Y1 | TARGET Y2 | FINAL TARGET YX | Data source of verification |
| IMPACT | Ministry of Foreign Affairs successfully assumes its new role as a donor in the field of international development cooperation and humanitarian aid and the related responsibilities | EC Report Montenegro 2019, Chapter 30: - legislative and strategic framework in the area of IDCHA adopted; - database of donor support in the field of IDCHA created | EC Report Montenegro 2018, Chapter 30: - no legislative and strategic framework in the area of IDCHA; - no database of donor support in the field of IDCHA | Responsibilities in the field of international development cooperation and humanitarian aid successfully fulfilled by MFA as per EC Progress Report Montenegro 2018 | Responsibilities in the field of international development cooperation and humanitarian aid successfully fulfilled by MFA as per EC Progress Report Montenegro 2019 |  | Statements on the progress of Montenegro in the area of international development cooperation, humanitarian aid in the relevant EC Progress Reports 2019 |
| ACTIVITY 1 | Capacities of MFA to respond to new requirements related to international development cooperation and humanitarian aid improved | Strategic framework created, normative framework upgraded and data collection system improved | Strategic framework does not exist, normative framework and data collection system need an upgrade | Strategic and normative framework fully developed | Tracking system for international development cooperation, humanitarian aid developed through creation of specialized databases |  | EC Montenegro Report 2019 |
| Act. 1.1 | Secondary legislation for the purpose of implementation of the Law on International Development Cooperation and Sending Humanitarian Aid (the Law), including at least one gender-responsive measure, developed and adopted by the Government and Parliament of Montenegro | - The first set of bylaws on data collection, record keeping and reporting as defined under Art 12 prepared - The second set of bylaws on the implementation modalities of the international development cooperation (Art 9) and providing international humanitarian aid (Art 11), including at least one gender-responsive measure,prepared | - Bylaws do not exist | - Based on the first set of bylaws, the Ministry enabled to collect data on international development cooperation and international humanitarian aid from bodies, legal entities and other entities participating in international development cooperation and international humanitarian aid | - Based on the second set of bylaws, the Ministry enabled to submit to the Government an annual report on international development cooperation and international humanitarian aid of Montenegro | Both set of bylaws prepared by the end of the second quarter of 2019 and their provisions fully implemented by the Ministry | MFA report on the activities implemented in the relation to international development cooperation and international humanitarian aid, EC Montenegro Report 2019 |
| Act. 1.2 | System for keeping records on incoming and outgoing development cooperation assistance and humanitarian aid of Montenegro developed | - Databases for the inflows and outflows of development cooperation and humanitarian aid of Montenegro created | - Databases do not exist | - Database for keeping records on outflows successfully developed | - Database for keeping records on inflows successfully developed | Functional capacities of MFA related to keeping records on incoming and outgoing international development assistance improved | Internal work processes |
| Act. 1.3 | Strategic framework for international development cooperation and humanitarian aid created, including at least one gender-responsive measure | Strategy on International Development Cooperation and Humanitarian Aid created and adopted, including at least one gender-responsive measure | - Strategy does not exist | - Consultancy support enabled for the preparation of the Strategy | - Strategy adopted by the Government of Montenegro by the end of the second quarter of 2019 | Strategic framework for international development cooperation and humanitarian aid fully developed | EC Montenegro Report 2019 |
| Act. 1.4 | New responsibilities of MFA in the area of international development cooperation, humanitarian aid successfully communicated to the general public | - Public consultations (with the participation of general public, NGOs, businesses) organized - Communication tools (brochures, interviews, panels) developed and organized | - Awareness of the role of MFA in the area of international development cooperation, humanitarian aid low | - At least one public consultation/round table (with the participation of general public, NGOs, businesses) organized | - At least one brochure developed and at least one interview/panel organized | Awareness of the general public about international development cooperation, humanitarian aid raised | Media reports, EC Montenegro Report 2019 |
| ACTIVITY 2 | Capacities of MFA staff dealing with diplomatic and consular affairs strengthened through continued organization of Summer School for Young Diplomats | Summer School for Young Diplomats organized | - n/a | Summer School for Young Diplomats organized in 2018 | Summer School for Young Diplomats organized in 2019 | Summer School for Young Diplomats organized | Number of participants (countries); Agenda; Conclusions/Minutes; Media reports from the Diplomatic Schools; Participants Evaluation Report |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans:

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action |
| --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. | Twice a year | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. All aspects of engaging consultants, organizing workshops, identifying participants and eligible costs will be defined by the Project Board members for the upcoming six months period. |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) |  |
| Project Review (Project Board) | The project’s governance mechanism (project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Twice a year | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. |

# Multi-Year Work Plan

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Funding Source | Budget Description | 2018 | 2019 |
|  |  |  |  |  | (EUR) |  |
| Activity 1: Official Development Assistance | 71400 Contractual Services-Individuals | UNDP | GOM | 71400 Contractual Services-Individuals | 500 | 500 |
|  | 71300 Local Consultants | UNDP | GOM | 71300 Local Consultants | 2,000 | 1,800 |
|  | 71200 International Consultant | UNDP | GOM | 71200 International Consultants | 3,000 | 1,300 |
|  | 71600 Travel | UNDP | GOM | 71600 Travel | 300 | 300 |
|  | 75100 GMS |  |  |  | 174 | 126 |
|  | TOTAL Activity 1 |  |  |  | 5,974 | 4,026 |
| Activity 2: Diplomatic Academy | 61200 National Personnel | UNDP | GOM | 61200 National Personnel | 2,000 |  |
|  | 71300 Local Consultants | UNDP | GOM | 71300 Local Consultants | 10,000 | 5,000 |
|  | 71600 Travel | UNDP | GOM | 71600 Travel | 10,000 |  |
|  | 72100 Contractual Services-Companies | UNDP | GOM | 72100 Contractual Services-Companies | 37,870 |  |
|  | 74200 Audio Visual & Print Prod Costs | UNDP | GOM | 74200 Audio Visual & Print Prod Costs | 5,000 | 1,000 |
|  | 75100 GMS |  |  |  | 1,950 | 180 |
|  | TOTAL Activity 2 |  |  |  | 66,820 | 6,180 |
| TOTAL PER YEARS |  |  |  |  | 72,794 | 10,206 |
| TOTAL ALL YEARS |  |  |  |  | 83,000 |  |

# Governance and Management Arrangements

The project will be managed and implemented by UNDP CO Montenegro within the DIM modality, in line with the UNDP Programming for Results Management User Guide. The Project Board will be responsible for making, management decisions for the Action. It will be formed immediately upon start of the Action. The Project Board’s scope of work will include project oversight, as well as regular review of work plans and reports. In addition to overseeing the Action implementation progress, the Project Board will provide strategic guidance, as well as give final approval to milestone strategic and operational matters. During the Project Board meetings, all aspects of engaging consultants, organizing workshops, identifying participants and eligible costs will be defined for the upcoming six months period. The Project Board will include the two representatives of the Ministry of Foreign Affairs (MFA) in the capacity of the Chairperson, and representatives of UNDP. It will be meeting twice a year during the project implementation. In order to ensure UNDP’s ultimate accountability, final decision-making rests with UNDP in accordance with its applicable regulations, rules, policies and procedures. Project reviews by this group are made at designated decision points during the running of a project, or as necessary when raised by the Project Manager.

The proposed project implementation team includes a Project Manager (part time) and Project Finance and Administration Officer (part time). The Project Manager will be responsible for the overall implementation of the project including operational and financial responsibility. The Project Finance and Administration Officer will deal with day-to-day administrative activities related to procurement, project administration, payments and monitoring. Project Finance and Administration Officer will work under the supervision of the Project Manager to ensure that all aspects of project coordination are in place. The project team will provide strategic advice and administrative support and is responsible for financial disbursements, controlling and reporting. The UNDP’s Team Leader for Democratic Governance Cluster will provide advisory and operational support to the programme implementation.

Senior Beneficiary will be the MFA, represented by the Deputy Minister or similar level. The Government of Montenegro will provide in-kind contribution towards project costs in the form of logistical support for organizing different events and conferences and assignment on temporary basis of regular staff to assist project team in implementation of different project activities.

Project Team

Project Board

Senior Beneficiary (MFA)

Executive (UNDP)

UNDP

Project Assurance

(DG Team Leader)

Project Support (consultants, specialists, etc.)

Project Organisation Structure

# Legal Context

# The country has signed the Standard Basic Assistance Agreement (SBAA)

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of (country) and UNDP, signed on (date).   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by [name of entity] (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

UNDP (DIM)

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - Choose one of the three following options:

Option 1: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Option 2: Each responsible party, subcontractor or sub-recipient agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

# ANNEXES

- Project Quality Assurance Report

“Montenegro 2018 Report”, link: https://ec.europa.eu/neighbourhood-enlargement/sites/near/files/20180417-montenegro-report.pdf

“Montenegro Country Paper”, October 2017, a publication which is part of the project “Western Balkan CSOs for Global Development” financed by the Austrian Development and HORIZONT3000 through its partner organizations.

Ibid

Ibid

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a project budget affecting the scope (outputs), completion date, or total estimated project costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner