## AWP 2022
Annual Work Plan 2022 (Version A)
Atlas PROJECT ID: | 00128406
Atlas OUTPUT ID: | c
ATLAS Project/Programme Title: | Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq
Atlas OUTPUT Name | Energy Efficiency Policy
UNSDCF/CPD Outcome (2020-2024): | UNSDCF OUTCOME INVOLVING UNDP: 4.1. Strengthened and resourced policies and frameworks are implemented for managing natural resources (including transboundary issues), developing renewable resources, and increasing resilience to climate change, environmental stress and natural hazards, and human-induced and natural disasters.
Applicable Key Result Area/Output (from 2018-2021 Strategic Plan): | Outcome 2: Accelerate structural transformations for sustainable development 2.4.1 Gender-responsive legal and regulatory frameworks, policies and institutions strengthened, and solutions adopted, to address conservation, sustainable use and equitable benefit sharing of natural resources, in line with international conventions and national legislation
Applicable Key Result Area/Output (from 2022-2025 Strategic Plan): | OUTPUT 4.2 Public and private investment mechanisms mobilized for biodiversity, water, oceans, and climate solutions
CPD Output (s) 2020-2024: | Output 4.1. National capacities improved for climate change adaptation and mitigation.
EXPECTED OUTPUTS | Expected Outcomes | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
And baseline, associated indicators and annual targets |  | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Fund Code | Donor Name | Donor Code | Account Code | Budget Description | Amount (USD)
Output 1:
COMPONENT 1: Enabling regulatory and institutional framework is designed to promote EE in the buildings sector, including the development of Buildings Energy Efficiency Codes (BEEC) and Minimum Energy Performance Standards (MEPS) for buildings Indicators: 1.1: Number assessment report of existing policies, programmes and national plans or Executive Regulation for EE in Buildings is drafted and submitted for government approval. 1.2: Number of documents drafted on the assessment, workplan or workplan of the NEEAP in Iraq is conducted 1.3 Not applicable for 2022 1.4 Not applicable for 2022 Baselines: 1.1: Zero 1.2: Zero 1.3: Not applicable for 2022 1.4: Not applicable for 2022 Annual Target: 1.1 One assessment report completed on existing policies, programmes and national plans 1.2 Zero 1.3 Not applicable for 2022 1.4 Not applicable for 2022 | Outcome 1 Appropriate regulatory and institutional framework is designed to catalyze existing policies and programs for promoting EE in buildings, including the operationalization of the National Energy Efficiency Action Plan (NEEAP) | 1.1. An analysis of the existing policies, programmes and national plans is conducted, and an Executive Regulation for EE in Buildings is drafted and submitted for government approval. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 25000
|  | 1.2. An analysis of the NEEAP in Iraq is conducted, and the elements required for its operationalization is provided to support rolling-out EE development with a focus on the buildings sector. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 0
| Outcome 2 Internationally recognized BEEC and MEPS for buildings are selected and localized to become suitable for Iraq, including the associating Monitoring, Verification and Enforcement (MVE) procedure | 2.1. Appropriate BEEC, including the associating labelling, certification scheme and testing procedure, is selected, localized, and submitted for government approval. This will include aspects of passive design and thermal insulation standards. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 25000
|  | 2.2. Appropriate MEPS, including the associating labelling, certification scheme and testing procedure, is selected, localized, and submitted for government approval. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 1500
[12 empty] | Sub-total GEF | 51500
[12 empty] | TOTAL ACTIVITY 1 | 51500
Output 2:
COMPONENT 2: The Energy Efficiency Center (EEC) is established with mandate for advancing EE measures in the buildings sector through providing technical advice to the public, training to practitioners, and supporting the implementation of the proposed MVE procedure Indicators: 3.1a: Number of Public Private Partnership established or site assessment completed 3.1b: Status of retrofit activities on the two buildings under Baghdad University and Ministry of Education 3.2 Not applicable for 2022 4.1 Not applicable for 2022 4.2 Not applicable for 2022 Baselines: 3.1a: Zero 3.1b: Zero 3.2 Not applicable for 2022 4.1 Not applicable for 2022 4.2 Not applicable for 2022 Annual Target: 3.1a: One Public Private Partnership for the EEC established and two site assessments completed 3.1b: Retrofitting activities initiated on the two buildings under Baghdad University and Ministry of Education 3.2 Not applicable for 2022 4.1 Not applicable for 2022 4.2 Not applicable for 2022 | Outcome 3 Energy Efficiency Center (EEC) is established and capacitated to support the development of EE programs and applications in the buildings sector | 3.1. EEC is established, legally and with physical presence, and is operational as the focal point for promoting EE in the Iraqi buildings sector. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 20000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants
[7 empty] | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 10000
|  | 3.2. Staff at the EEC are capacitated to inform decision-makers, advise investors, raise public awareness, and deliver general and technical training on EE in buildings. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services - Companies | 0
| Outcome 4 Testing facility and certification programmes are established under EEC, in accordance with the proposed BEEC and MEPS, to support the implementation of the framework’s MVE procedure | 4.1. A testing facility containing suitable equipment to measure energy consumption behavior in the buildings sector and perform regular inspection for buildings, in accordance with the proposed BEEC and MEPS, is established at the EEC and operated by EEC staff. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 72300 | Material & Goods | 0
[7 empty] | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference
|  | 4.2. Certified Energy Management and Building Auditors Programmes are adopted by EEC, where Energy Managers are capacitated to conduct building inspections and make recommendations for optimizing EE in buildings nation-wide. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 0
[12 empty] | Sub-total GEF | 30000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71200 | International Consultants | 0
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71300 | Local Consultants | 0
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71400 | Contractual services – Individuals | 0
[7 empty] | UNDP | 4000 | UNDP | 00012 | 75700 | Training, workshop, conference | 0
[12 empty] | Sub-total UNDP | 0
[12 empty] | TOTAL ACTIVITY 2 | 30000
COMPONENT 3: Individual and institutional capacity and EE technical knowledge and expertise are strengthened to enhance the ability of national parties to develop and operationalize EE policies, regulations, technical codes, and performance standards in the buildings sector Indicators: 5.1: Not applicable for 2022 5.2: Not applicable for 2022 6.1: Not applicable for 2022 6.2: Not applicable for 2022 6.3: Not applicable for 2022 Baselines: 5.1: Not applicable for 2022 5.2: Not applicable for 2022 6.1: Not applicable for 2022 6.2: Not applicable for 2022 6.3: Not applicable for 2022 Annual Target: 5.1: Not applicable for 2022 5.2: Not applicable for 2022 6.1: Not applicable for 2022 6.2: Not applicable for 2022 6.3: Not applicable for 2022 | Outcome 5 Coordination between national parties for the enforcement of existing policies and strategies, including the Iraqi building code, is strengthened | 5.1. Develop a Data Flow Diagram (DFD) consistent with the proposed Executive Regulation for EE in Buildings to advocate intra-government collaboration and obtain consensus of the parties on the DFD and the manuals to use for staff training. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants
|  | 5.2. Policy-level training on the proposed regulatory and institutional framework for EE in buildings is conducted, targeting decision makers, public officials, and national experts. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 10000
| Outcome 6 The awareness of practitioners involved in the buildings sector, as well as end-users of electricity, on EE regulation and best practices is strengthened | 6.1. Technical training on EE in buildings is conducted targeting students, technicians, contractors, civil engineers, and architects. This will constitute a Training of Trainers (ToT) workshops to enhance the sustainability of knowledge sharing. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals
[7 empty] | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services – Companies
|  | 6.2. Awareness campaigns and events are organized to promote EE applications and programs, and relevant marketing material is developed to increase consumers’ commitment to EE practices. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference
|  | 6.3. Existing financial schemes and incentive mechanisms dedicated to promoting EE buildings investments and attracting the engagement of the banking sector, are identified, promoted, and monitored. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel
[12 empty] | Sub-total GEF | 10000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71200 | International Consultants | 0
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71300 | Local Consultants | 0
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71400 | Contractual services – Individuals | 0
[12 empty] | Sub-total UNDP | 0
[12 empty] | TOTAL ACTIVITY 3 | 10000
Component 4: Knowledge and expertise on EE in the buildings sector in Iraq is managed, guided by best practices from other countries, and the impacts of the developed regulatory and institutional framework is continuously monitored and evaluated Indicators: 7.1: Not applicable for 2022 7.2: Not applicable for 2022 8.1: Not applicable for 2022 8.2: Not applicable for 2022 8.3: Not applicable for 2022 Baselines: 7.1: Not applicable for 2022 7.2: Not applicable for 2022 8.1: Not applicable for 2022 8.2: Not applicable for 2022 8.3: Not applicable for 2022 Annual Target: 7.1: Not applicable for 2022 7.2: Not applicable for 2022 8.1: Not applicable for 2022 8.2: Not applicable for 2022 8.3: Not applicable for 2022 | Outcome 7 A Knowledge Management (KM) system is developed, and best practices are catalogued through conducting exchange missions to other countries | 7.1. A KM system is developed in the form of an online portal for the dissemination of EE in building practices, programs, code, and MVE procedure, on the national level. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals
[7 empty] | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services – Companies
|  | 7.2. Exchange missions to relevant regional or international countries with advanced experience in EE buildings deployment are conducted and a best practices catalogue is developed. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference
[7 empty] | UNDP | 62000 | GEF | 10003 | 71600 | Travel
| Outcome 8 A Monitoring and Evaluation (M&E) system is developed to track and document progress and impacts of EE initiatives and support the sustainability of EE interventions in the buildings sector | 8.1. Set up an institutional mechanism to revise and update building energy performance standards regularly, including the development of guidelines for enforcing EE measures in building. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants
[7 empty] | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants
|  | 8.2. Set up an inventory mechanism and database management system for national energy balance, detailed consumption statistics and related Greenhouse Gas (GHG) emission in the buildings sector to monitor and evaluate EE programs. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 74200 | Audio Visual & Print Prod Costs
[7 empty] | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference
|  | 8.3. Capacity building to EEC staff on aspects of M&E, including database management, data collection and reporting, is conducted. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel
[12 empty] | Sub-total GEF | 0
[12 empty] | TOTAL ACTIVITY 4 | 0
Project Management Cost (PMC) | [6 empty] | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 0
[7 empty] | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 0
[7 empty] | UNDP | 62000 | GEF | 10003 | 72400 | Communic & Audio Visual Equip | 0
[7 empty] | UNDP | 62000 | GEF | 10003 | 72500 | Supplies | 0
[7 empty] | UNDP | 62000 | GEF | 10003 | 72800 | IT Equipment | 0
[7 empty] | UNDP | 62000 | GEF | 10003 | 74200 | Audio Visual & Print Prod Costs | 0
[12 empty] | Sub-total GEF | 0
[11 empty] | 72800 | IT Equipment | 0
[11 empty] | 74100 | Professional services | 0
[11 empty] | 72400 | Audio Visual & Print Prod Costs | 0
[12 empty] | Sub-total UNDP | 0
[12 empty] | TOTAL ACTIVITY 5 | 0
SUB-TOTAL GEF | [12 empty] | 91500
[11 empty] | SUB-TOTAL UNDP |  | 0
[11 empty] | PROJECT TOTAL |  | 91500
Mohammed Al-Attar |  |  | Ghimar Deeb
Project Manager Name & Signature |  |  | Resident Representative/ Deputy Resident Representative: Name & Signature
Date: |  |  | Date:

## AWP 2023
Annual Work Plan 2023 (Version A)
Atlas PROJECT ID: | 00128406
Atlas OUTPUT ID: | 00122419
ATLAS Project/Programme Title: | Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq
Atlas OUTPUT Name | Energy Efficiency Policy
UNSDCF/CPD Outcome (2020-2024): | UNSDCF OUTCOME INVOLVING UNDP: 4.1. Strengthened and resourced policies and frameworks are implemented for managing natural resources (including transboundary issues), developing renewable resources, and increasing resilience to climate change, environmental stress and natural hazards, and human-induced and natural disasters.
Applicable Key Result Area/Output (from 2018-2021 Strategic Plan): | Outcome 2: Accelerate structural transformations for sustainable development 2.4.1 Gender-responsive legal and regulatory frameworks, policies and institutions strengthened, and solutions adopted, to address conservation, sustainable use and equitable benefit sharing of natural resources, in line with international conventions and national legislation
Applicable Key Result Area/Output (from 2022-2025 Strategic Plan): | OUTPUT 4.2 Public and private investment mechanisms mobilized for biodiversity, water, oceans, and climate solutions
CPD Output (s) 2020-2024: | Output 4.1. National capacities improved for climate change adaptation and mitigation.
EXPECTED OUTPUTS | Expected Outcomes | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
And baseline, associated indicators and annual targets |  | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Fund Code | Donor Name | Donor Code | Account Code | Budget Description | Amount (USD)
Output 1:
COMPONENT 1: Enabling regulatory and institutional framework is designed to promote EE in the buildings sector, including the development of Buildings Energy Efficiency Codes (BEEC) and Minimum Energy Performance Standards (MEPS) for buildings | Outcome 1 Appropriate regulatory and institutional framework is designed to catalyze existing policies and programs for promoting EE in buildings, including the operationalization of the National Energy Efficiency Action Plan (NEEAP | 1.1. An analysis of the existing policies, programmes and national plans is conducted, and an Executive Regulation for EE in Buildings is drafted and submitted for government approval. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 55000
|  | 1.2. An analysis of the NEEAP in Iraq is conducted, and the elements required for its operationalization is provided to support rolling-out EE development with a focus on the buildings sector. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 60000
| Outcome 2 Internationally recognized BEEC and MEPS for buildings are selected and localized to become suitable for Iraq, including the associating Monitoring, Verification and Enforcement (MVE) procedure | 2.1. Appropriate BEEC, including the associating labelling, certification scheme and testing procedure, is selected, localized, and submitted for government approval. This will include aspects of passive design and thermal insulation standards. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 10000
|  | 2.2. Appropriate MEPS, including the associating labelling, certification scheme and testing procedure, is selected, localized, and submitted for government approval. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 8500
[12 empty] | Sub-total GEF | 133500
[12 empty] | TOTAL ACTIVITY 1 | 133500
Output 2:
COMPONENT 2: The Energy Efficiency Center (EEC) is established with mandate for advancing EE measures in the buildings sector through providing technical advice to the public, training to practitioners, and supporting the implementation of the proposed MVE procedure | Outcome 3 Energy Efficiency Center (EEC) is established and capacitated to support the development of EE programs and applications in the buildings sector | 3.1. EEC is established, legally and with physical presence, and is operational as the focal point for promoting EE in the Iraqi buildings sector. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 58000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 60000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 102000
|  | 3.2. Staff at the EEC are capacitated to inform decision-makers, advise investors, raise public awareness, and deliver general and technical training on EE in buildings. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services - Companies | 100000
| Outcome 4 Testing facility and certification programmes are established under EEC, in accordance with the proposed BEEC and MEPS, to support the implementation of the framework’s MVE procedure | 4.1. A testing facility containing suitable equipment to measure energy consumption behavior in the buildings sector and perform regular inspection for buildings, in accordance with the proposed BEEC and MEPS, is established at the EEC and operated by EEC staff. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 72300 | Material & Goods | 400000
[7 empty] | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | $ -
|  | 4.2. Certified Energy Management and Building Auditors Programmes are adopted by EEC, where Energy Managers are capacitated to conduct building inspections and make recommendations for optimizing EE in buildings nation-wide. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 10000
[12 empty] | Sub-total GEF | 730000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71200 | International Consultants | 10000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71300 | Local Consultants | 10000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71400 | Contractual services – Individuals | 40000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 75700 | Training, workshop, conference | 10000
[12 empty] | Sub-total UNDP | 70000
[12 empty] | TOTAL ACTIVITY 2 | 800000
COMPONENT 3: Individual and institutional capacity and EE technical knowledge and expertise are strengthened to enhance the ability of national parties to develop and operationalize EE policies, regulations, technical codes, and performance standards in the buildings sector | Outcome 5 Coordination between national parties for the enforcement of existing policies and strategies, including the Iraqi building code, is strengthened | 5.1. Develop a Data Flow Diagram (DFD) consistent with the proposed Executive Regulation for EE in Buildings to advocate intra-government collaboration and obtain consensus of the parties on the DFD and the manuals to use for staff training. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 40000
|  | 5.2. Policy-level training on the proposed regulatory and institutional framework for EE in buildings is conducted, targeting decision makers, public officials, and national experts. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 20000
| Outcome 6 The awareness of practitioners involved in the buildings sector, as well as end-users of electricity, on EE regulation and best practices is strengthened | 6.1. Technical training on EE in buildings is conducted targeting students, technicians, contractors, civil engineers, and architects. This will constitute a Training of Trainers (ToT) workshops to enhance the sustainability of knowledge sharing. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | $ -
[7 empty] | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services – Companies | 40000
|  | 6.2. Awareness campaigns and events are organized to promote EE applications and programs, and relevant marketing material is developed to increase consumers’ commitment to EE practices. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | $ -
|  | 6.3. Existing financial schemes and incentive mechanisms dedicated to promoting EE buildings investments and attracting the engagement of the banking sector, are identified, promoted, and monitored. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 5000
[12 empty] | Sub-total GEF | 105000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71200 | International Consultants | 6000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71300 | Local Consultants | 6000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71400 | Contractual services – Individuals | 30000
[12 empty] | Sub-total UNDP | 42000
[12 empty] | TOTAL ACTIVITY 3 | 147000
Component 4: Knowledge and expertise on EE in the buildings sector in Iraq is managed, guided by best practices from other countries, and the impacts of the developed regulatory and institutional framework is continuously monitored and evaluated | Outcome 7 A Knowledge Management (KM) system is developed, and best practices are catalogued through conducting exchange missions to other countries | 7.1. A KM system is developed in the form of an online portal for the dissemination of EE in building practices, programs, code, and MVE procedure, on the national level. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 20000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services – Companies | 20000
|  | 7.2. Exchange missions to relevant regional or international countries with advanced experience in EE buildings deployment are conducted and a best practices catalogue is developed. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 2000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 10000
| Outcome 8 A Monitoring and Evaluation (M&E) system is developed to track and document progress and impacts of EE initiatives and support the sustainability of EE interventions in the buildings sector | 8.1. Set up an institutional mechanism to revise and update building energy performance standards regularly, including the development of guidelines for enforcing EE measures in building. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | $ -
[7 empty] | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 8000
|  | 8.2. Set up an inventory mechanism and database management system for national energy balance, detailed consumption statistics and related Greenhouse Gas (GHG) emission in the buildings sector to monitor and evaluate EE programs. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 74200 | Audio Visual & Print Prod Costs | $ -
[7 empty] | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 7000
|  | 8.3. Capacity building to EEC staff on aspects of M&E, including database management, data collection and reporting, is conducted. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 17000
[12 empty] | Sub-total GEF | 84000
[12 empty] | TOTAL ACTIVITY 4 | 84000
Project Management Cost (PMC) | [6 empty] | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 10000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 40000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72400 | Communic & Audio Visual Equip | 2000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72500 | Supplies | 1700
[7 empty] | UNDP | 62000 | GEF | 10003 | 72800 | IT Equipment | 2500
[7 empty] | UNDP | 62000 | GEF | 10003 | 74200 | Audio Visual & Print Prod Costs | 4000
[12 empty] | Sub-total GEF | 60200
[11 empty] | 72800 | IT Equipment | 1000
[11 empty] | 74100 | Professional services | 3600
[11 empty] | 72400 | Audio Visual & Print Prod Costs | 1000
[12 empty] | Sub-total UNDP | 5600
[12 empty] | TOTAL ACTIVITY 5 | 65800
SUB-TOTAL GEF | [12 empty] | 1112700
[11 empty] | SUB-TOTAL UNDP |  | 117600
[11 empty] | PROJECT TOTAL |  | 1230300
Mohammed Al-Attar |  |  | Ghimar Deeb
Project Manager Name & Signature |  |  | Resident Representative/ Deputy Resident Representative: Name & Signature
Date: |  |  | Date:

## AWP 2024
Annual Work Plan 2024 (Version A)
Atlas PROJECT ID: | 00128406
Atlas OUTPUT ID: | 00122419
ATLAS Project/Programme Title: | Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq
Atlas OUTPUT Name | Energy Efficiency Policy
UNSDCF/CPD Outcome (2020-2024): | UNSDCF OUTCOME INVOLVING UNDP: 4.1. Strengthened and resourced policies and frameworks are implemented for managing natural resources (including transboundary issues), developing renewable resources, and increasing resilience to climate change, environmental stress and natural hazards, and human-induced and natural disasters.
Applicable Key Result Area/Output (from 2018-2021 Strategic Plan): | Outcome 2: Accelerate structural transformations for sustainable development 2.4.1 Gender-responsive legal and regulatory frameworks, policies and institutions strengthened, and solutions adopted, to address conservation, sustainable use and equitable benefit sharing of natural resources, in line with international conventions and national legislation
Applicable Key Result Area/Output (from 2022-2025 Strategic Plan): | OUTPUT 4.2 Public and private investment mechanisms mobilized for biodiversity, water, oceans, and climate solutions
CPD Output (s) 2020-2024: | Output 4.1. National capacities improved for climate change adaptation and mitigation.
EXPECTED OUTPUTS | Expected Outcomes | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
And baseline, associated indicators and annual targets |  | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Fund Code | Donor Name | Donor Code | Account Code | Budget Description | Amount (USD)
Output 1:
COMPONENT 1: Enabling regulatory and institutional framework is designed to promote EE in the buildings sector, including the development of Buildings Energy Efficiency Codes (BEEC) and Minimum Energy Performance Standards (MEPS) for buildings | Outcome 1 Appropriate regulatory and institutional framework is designed to catalyze existing policies and programs for promoting EE in buildings, including the operationalization of the National Energy Efficiency Action Plan (NEEAP | 1.1. An analysis of the existing policies, programmes and national plans is conducted, and an Executive Regulation for EE in Buildings is drafted and submitted for government approval. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 40000
|  | 1.2. An analysis of the NEEAP in Iraq is conducted, and the elements required for its operationalization is provided to support rolling-out EE development with a focus on the buildings sector. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 30000
| Outcome 2 Internationally recognized BEEC and MEPS for buildings are selected and localized to become suitable for Iraq, including the associating Monitoring, Verification and Enforcement (MVE) procedure | 2.1. Appropriate BEEC, including the associating labelling, certification scheme and testing procedure, is selected, localized, and submitted for government approval. This will include aspects of passive design and thermal insulation standards. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference
|  | 2.2. Appropriate MEPS, including the associating labelling, certification scheme and testing procedure, is selected, localized, and submitted for government approval. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 5000
[12 empty] | Sub-total GEF | 75000
[12 empty] | TOTAL ACTIVITY 1 | 75000
Output 2:
COMPONENT 2: The Energy Efficiency Center (EEC) is established with mandate for advancing EE measures in the buildings sector through providing technical advice to the public, training to practitioners, and supporting the implementation of the proposed MVE procedure | Outcome 3 Energy Efficiency Center (EEC) is established and capacitated to support the development of EE programs and applications in the buildings sector | 3.1. EEC is established, legally and with physical presence, and is operational as the focal point for promoting EE in the Iraqi buildings sector. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 25000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 30000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 10000
|  | 3.2. Staff at the EEC are capacitated to inform decision-makers, advise investors, raise public awareness, and deliver general and technical training on EE in buildings. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services - Companies | 50000
| Outcome 4 Testing facility and certification programmes are established under EEC, in accordance with the proposed BEEC and MEPS, to support the implementation of the framework’s MVE procedure | 4.1. A testing facility containing suitable equipment to measure energy consumption behavior in the buildings sector and perform regular inspection for buildings, in accordance with the proposed BEEC and MEPS, is established at the EEC and operated by EEC staff. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 72300 | Material & Goods | 200000
[7 empty] | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 40000
|  | 4.2. Certified Energy Management and Building Auditors Programmes are adopted by EEC, where Energy Managers are capacitated to conduct building inspections and make recommendations for optimizing EE in buildings nation-wide. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 5000
[12 empty] | Sub-total GEF | 360000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71200 | International Consultants | 5000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71300 | Local Consultants | 5000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71400 | Contractual services – Individuals | 20000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 75700 | Training, workshop, conference | 5000
[12 empty] | Sub-total UNDP | 35000
[12 empty] | TOTAL ACTIVITY 2 | 395000
COMPONENT 3: Individual and institutional capacity and EE technical knowledge and expertise are strengthened to enhance the ability of national parties to develop and operationalize EE policies, regulations, technical codes, and performance standards in the buildings sector | Outcome 5 Coordination between national parties for the enforcement of existing policies and strategies, including the Iraqi building code, is strengthened | 5.1. Develop a Data Flow Diagram (DFD) consistent with the proposed Executive Regulation for EE in Buildings to advocate intra-government collaboration and obtain consensus of the parties on the DFD and the manuals to use for staff training. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 40000
|  | 5.2. Policy-level training on the proposed regulatory and institutional framework for EE in buildings is conducted, targeting decision makers, public officials, and national experts. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 30000
| Outcome 6 The awareness of practitioners involved in the buildings sector, as well as end-users of electricity, on EE regulation and best practices is strengthened | 6.1. Technical training on EE in buildings is conducted targeting students, technicians, contractors, civil engineers, and architects. This will constitute a Training of Trainers (ToT) workshops to enhance the sustainability of knowledge sharing. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 40000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services – Companies | 40000
|  | 6.2. Awareness campaigns and events are organized to promote EE applications and programs, and relevant marketing material is developed to increase consumers’ commitment to EE practices. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 40000
|  | 6.3. Existing financial schemes and incentive mechanisms dedicated to promoting EE buildings investments and attracting the engagement of the banking sector, are identified, promoted, and monitored. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 5000
[12 empty] | Sub-total GEF | 195000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71200 | International Consultants | 5000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71300 | Local Consultants | 3000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71400 | Contractual services – Individuals | 15000
[12 empty] | Sub-total UNDP | 23000
[12 empty] | TOTAL ACTIVITY 3 | 218000
Component 4: Knowledge and expertise on EE in the buildings sector in Iraq is managed, guided by best practices from other countries, and the impacts of the developed regulatory and institutional framework is continuously monitored and evaluated | Outcome 7 A Knowledge Management (KM) system is developed, and best practices are catalogued through conducting exchange missions to other countries | 7.1. A KM system is developed in the form of an online portal for the dissemination of EE in building practices, programs, code, and MVE procedure, on the national level. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 20000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services – Companies | 20000
|  | 7.2. Exchange missions to relevant regional or international countries with advanced experience in EE buildings deployment are conducted and a best practices catalogue is developed. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 2000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71600 | Travel | $ -
| Outcome 8 A Monitoring and Evaluation (M&E) system is developed to track and document progress and impacts of EE initiatives and support the sustainability of EE interventions in the buildings sector | 8.1. Set up an institutional mechanism to revise and update building energy performance standards regularly, including the development of guidelines for enforcing EE measures in building. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 40000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 24000
|  | 8.2. Set up an inventory mechanism and database management system for national energy balance, detailed consumption statistics and related Greenhouse Gas (GHG) emission in the buildings sector to monitor and evaluate EE programs. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 74200 | Audio Visual & Print Prod Costs | 1000
[7 empty] | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | $ -
|  | 8.3. Capacity building to EEC staff on aspects of M&E, including database management, data collection and reporting, is conducted. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 1000
[12 empty] | Sub-total GEF | 108000
[12 empty] | TOTAL ACTIVITY 4 | 108000
Project Management Cost (PMC) | [6 empty] | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 5000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 20000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72400 | Communic & Audio Visual Equip | 1000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72500 | Supplies | 500
[7 empty] | UNDP | 62000 | GEF | 10003 | 72800 | IT Equipment | 500
[7 empty] | UNDP | 62000 | GEF | 10003 | 74200 | Audio Visual & Print Prod Costs | 2000
[12 empty] | Sub-total GEF | 29000
[11 empty] | 72800 | IT Equipment | 500
[11 empty] | 74100 | Professional services | 1800
[11 empty] | 72400 | Audio Visual & Print Prod Costs | 500
[12 empty] | Sub-total UNDP | 2800
[12 empty] | TOTAL ACTIVITY 5 | 31800
SUB-TOTAL GEF | [12 empty] | 767000
[11 empty] | SUB-TOTAL UNDP |  | 60800
[11 empty] | PROJECT TOTAL |  | 827800
Mohammed Al-Attar |  |  | Ghimar Deeb
Project Manager Name & Signature |  |  | Resident Representative/ Deputy Resident Representative: Name & Signature
Date: |  |  | Date:

## AWP 2025
Annual Work Plan 2025 (Version A)
Atlas PROJECT ID: | 00128406
Atlas OUTPUT ID: | 00122419
ATLAS Project/Programme Title: | Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq
Atlas OUTPUT Name | Energy Efficiency Policy
UNSDCF/CPD Outcome (2020-2024): | UNSDCF OUTCOME INVOLVING UNDP: 4.1. Strengthened and resourced policies and frameworks are implemented for managing natural resources (including transboundary issues), developing renewable resources, and increasing resilience to climate change, environmental stress and natural hazards, and human-induced and natural disasters.
Applicable Key Result Area/Output (from 2018-2021 Strategic Plan): | Outcome 2: Accelerate structural transformations for sustainable development 2.4.1 Gender-responsive legal and regulatory frameworks, policies and institutions strengthened, and solutions adopted, to address conservation, sustainable use and equitable benefit sharing of natural resources, in line with international conventions and national legislation
Applicable Key Result Area/Output (from 2022-2025 Strategic Plan): | OUTPUT 4.2 Public and private investment mechanisms mobilized for biodiversity, water, oceans, and climate solutions
CPD Output (s) 2020-2024: | Output 4.1. National capacities improved for climate change adaptation and mitigation.
EXPECTED OUTPUTS | Expected Outcomes | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
And baseline, associated indicators and annual targets |  | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Fund Code | Donor Name | Donor Code | Account Code | Budget Description | Amount (USD)
Output 1:
COMPONENT 1: Enabling regulatory and institutional framework is designed to promote EE in the buildings sector, including the development of Buildings Energy Efficiency Codes (BEEC) and Minimum Energy Performance Standards (MEPS) for buildings | Outcome 1 Appropriate regulatory and institutional framework is designed to catalyze existing policies and programs for promoting EE in buildings, including the operationalization of the National Energy Efficiency Action Plan (NEEAP | 1.1. An analysis of the existing policies, programmes and national plans is conducted, and an Executive Regulation for EE in Buildings is drafted and submitted for government approval. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 40000
|  | 1.2. An analysis of the NEEAP in Iraq is conducted, and the elements required for its operationalization is provided to support rolling-out EE development with a focus on the buildings sector. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 30000
| Outcome 2 Internationally recognized BEEC and MEPS for buildings are selected and localized to become suitable for Iraq, including the associating Monitoring, Verification and Enforcement (MVE) procedure | 2.1. Appropriate BEEC, including the associating labelling, certification scheme and testing procedure, is selected, localized, and submitted for government approval. This will include aspects of passive design and thermal insulation standards. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference
|  | 2.2. Appropriate MEPS, including the associating labelling, certification scheme and testing procedure, is selected, localized, and submitted for government approval. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 5000
[12 empty] | Sub-total GEF | 75000
[12 empty] | TOTAL ACTIVITY 1 | 75000
Output 2:
COMPONENT 2: The Energy Efficiency Center (EEC) is established with mandate for advancing EE measures in the buildings sector through providing technical advice to the public, training to practitioners, and supporting the implementation of the proposed MVE procedure | Outcome 3 Energy Efficiency Center (EEC) is established and capacitated to support the development of EE programs and applications in the buildings sector | 3.1. EEC is established, legally and with physical presence, and is operational as the focal point for promoting EE in the Iraqi buildings sector. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 25000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 30000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 10000
|  | 3.2. Staff at the EEC are capacitated to inform decision-makers, advise investors, raise public awareness, and deliver general and technical training on EE in buildings. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services - Companies | $ -
| Outcome 4 Testing facility and certification programmes are established under EEC, in accordance with the proposed BEEC and MEPS, to support the implementation of the framework’s MVE procedure | 4.1. A testing facility containing suitable equipment to measure energy consumption behavior in the buildings sector and perform regular inspection for buildings, in accordance with the proposed BEEC and MEPS, is established at the EEC and operated by EEC staff. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 72300 | Material & Goods | 200000
[7 empty] | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 40000
|  | 4.2. Certified Energy Management and Building Auditors Programmes are adopted by EEC, where Energy Managers are capacitated to conduct building inspections and make recommendations for optimizing EE in buildings nation-wide. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 5000
[12 empty] | Sub-total GEF | 310000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71200 | International Consultants | 5000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71300 | Local Consultants | 5000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71400 | Contractual services – Individuals | 20000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 75700 | Training, workshop, conference | 5000
[12 empty] | Sub-total UNDP | 35000
[12 empty] | TOTAL ACTIVITY 2 | 345000
COMPONENT 3: Individual and institutional capacity and EE technical knowledge and expertise are strengthened to enhance the ability of national parties to develop and operationalize EE policies, regulations, technical codes, and performance standards in the buildings sector | Outcome 5 Coordination between national parties for the enforcement of existing policies and strategies, including the Iraqi building code, is strengthened | 5.1. Develop a Data Flow Diagram (DFD) consistent with the proposed Executive Regulation for EE in Buildings to advocate intra-government collaboration and obtain consensus of the parties on the DFD and the manuals to use for staff training. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 40000
|  | 5.2. Policy-level training on the proposed regulatory and institutional framework for EE in buildings is conducted, targeting decision makers, public officials, and national experts. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 30000
| Outcome 6 The awareness of practitioners involved in the buildings sector, as well as end-users of electricity, on EE regulation and best practices is strengthened | 6.1. Technical training on EE in buildings is conducted targeting students, technicians, contractors, civil engineers, and architects. This will constitute a Training of Trainers (ToT) workshops to enhance the sustainability of knowledge sharing. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 40000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services – Companies | 40000
|  | 6.2. Awareness campaigns and events are organized to promote EE applications and programs, and relevant marketing material is developed to increase consumers’ commitment to EE practices. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 40000
|  | 6.3. Existing financial schemes and incentive mechanisms dedicated to promoting EE buildings investments and attracting the engagement of the banking sector, are identified, promoted, and monitored. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 5000
[12 empty] | Sub-total GEF | 195000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71200 | International Consultants | 5000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71300 | Local Consultants | 3000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71400 | Contractual services – Individuals | 15000
[12 empty] | Sub-total UNDP | 23000
[12 empty] | TOTAL ACTIVITY 3 | 218000
Component 4: Knowledge and expertise on EE in the buildings sector in Iraq is managed, guided by best practices from other countries, and the impacts of the developed regulatory and institutional framework is continuously monitored and evaluated | Outcome 7 A Knowledge Management (KM) system is developed, and best practices are catalogued through conducting exchange missions to other countries | 7.1. A KM system is developed in the form of an online portal for the dissemination of EE in building practices, programs, code, and MVE procedure, on the national level. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 15000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services – Companies | 20000
|  | 7.2. Exchange missions to relevant regional or international countries with advanced experience in EE buildings deployment are conducted and a best practices catalogue is developed. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 13000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 25000
| Outcome 8 A Monitoring and Evaluation (M&E) system is developed to track and document progress and impacts of EE initiatives and support the sustainability of EE interventions in the buildings sector | 8.1. Set up an institutional mechanism to revise and update building energy performance standards regularly, including the development of guidelines for enforcing EE measures in building. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | $ -
[7 empty] | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 4000
|  | 8.2. Set up an inventory mechanism and database management system for national energy balance, detailed consumption statistics and related Greenhouse Gas (GHG) emission in the buildings sector to monitor and evaluate EE programs. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 74200 | Audio Visual & Print Prod Costs | $ -
[7 empty] | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | $ -
|  | 8.3. Capacity building to EEC staff on aspects of M&E, including database management, data collection and reporting, is conducted. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 1000
[12 empty] | Sub-total GEF | 78000
[12 empty] | TOTAL ACTIVITY 4 | 78000
Project Management Cost (PMC) | [6 empty] | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 5000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 20000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72400 | Communic & Audio Visual Equip | 1000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72500 | Supplies | 500
[7 empty] | UNDP | 62000 | GEF | 10003 | 72800 | IT Equipment | 500
[7 empty] | UNDP | 62000 | GEF | 10003 | 74200 | Audio Visual & Print Prod Costs | 2000
[12 empty] | Sub-total GEF | 29000
[11 empty] | 72800 | IT Equipment | 500
[11 empty] | 74100 | Professional services | 1800
[11 empty] | 72400 | Audio Visual & Print Prod Costs | 500
[12 empty] | Sub-total UNDP | 2800
[12 empty] | TOTAL ACTIVITY 5 | 31800
SUB-TOTAL GEF | [12 empty] | 687000
[11 empty] | SUB-TOTAL UNDP |  | 60800
[11 empty] | PROJECT TOTAL |  | 747800
Mohammed Al-Attar |  |  | Ghimar Deeb
Project Manager Name & Signature |  |  | Resident Representative/ Deputy Resident Representative: Name & Signature
Date: |  |  | Date:

## AWP 2026
Annual Work Plan 2026 (Version A)
Atlas PROJECT ID: | 00128406
Atlas OUTPUT ID: | 00122419
ATLAS Project/Programme Title: | Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq
Atlas OUTPUT Name | Energy Efficiency Policy
UNSDCF/CPD Outcome (2020-2024): | UNSDCF OUTCOME INVOLVING UNDP: 4.1. Strengthened and resourced policies and frameworks are implemented for managing natural resources (including transboundary issues), developing renewable resources, and increasing resilience to climate change, environmental stress and natural hazards, and human-induced and natural disasters.
Applicable Key Result Area/Output (from 2018-2021 Strategic Plan): | Outcome 2: Accelerate structural transformations for sustainable development 2.4.1 Gender-responsive legal and regulatory frameworks, policies and institutions strengthened, and solutions adopted, to address conservation, sustainable use and equitable benefit sharing of natural resources, in line with international conventions and national legislation
Applicable Key Result Area/Output (from 2022-2025 Strategic Plan): | OUTPUT 4.2 Public and private investment mechanisms mobilized for biodiversity, water, oceans, and climate solutions
CPD Output (s) 2020-2024: | Output 4.1. National capacities improved for climate change adaptation and mitigation.
EXPECTED OUTPUTS | Expected Outcomes | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
And baseline, associated indicators and annual targets |  | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Fund Code | Donor Name | Donor Code | Account Code | Budget Description | Amount (USD)
Output 1:
COMPONENT 1: Enabling regulatory and institutional framework is designed to promote EE in the buildings sector, including the development of Buildings Energy Efficiency Codes (BEEC) and Minimum Energy Performance Standards (MEPS) for buildings | Outcome 1 Appropriate regulatory and institutional framework is designed to catalyze existing policies and programs for promoting EE in buildings, including the operationalization of the National Energy Efficiency Action Plan (NEEAP | 1.1. An analysis of the existing policies, programmes and national plans is conducted, and an Executive Regulation for EE in Buildings is drafted and submitted for government approval. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | $ -
|  | 1.2. An analysis of the NEEAP in Iraq is conducted, and the elements required for its operationalization is provided to support rolling-out EE development with a focus on the buildings sector. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 30000
| Outcome 2 Internationally recognized BEEC and MEPS for buildings are selected and localized to become suitable for Iraq, including the associating Monitoring, Verification and Enforcement (MVE) procedure | 2.1. Appropriate BEEC, including the associating labelling, certification scheme and testing procedure, is selected, localized, and submitted for government approval. This will include aspects of passive design and thermal insulation standards. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 15000
|  | 2.2. Appropriate MEPS, including the associating labelling, certification scheme and testing procedure, is selected, localized, and submitted for government approval. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | $ -
[12 empty] | Sub-total GEF | 45000
[12 empty] | TOTAL ACTIVITY 1 | 45000
Output 2:
COMPONENT 2: The Energy Efficiency Center (EEC) is established with mandate for advancing EE measures in the buildings sector through providing technical advice to the public, training to practitioners, and supporting the implementation of the proposed MVE procedure | Outcome 3 Energy Efficiency Center (EEC) is established and capacitated to support the development of EE programs and applications in the buildings sector | 3.1. EEC is established, legally and with physical presence, and is operational as the focal point for promoting EE in the Iraqi buildings sector. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | $ -
[7 empty] | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 30000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 10000
|  | 3.2. Staff at the EEC are capacitated to inform decision-makers, advise investors, raise public awareness, and deliver general and technical training on EE in buildings. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services - Companies | $ -
| Outcome 4 Testing facility and certification programmes are established under EEC, in accordance with the proposed BEEC and MEPS, to support the implementation of the framework’s MVE procedure | 4.1. A testing facility containing suitable equipment to measure energy consumption behavior in the buildings sector and perform regular inspection for buildings, in accordance with the proposed BEEC and MEPS, is established at the EEC and operated by EEC staff. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 72300 | Material & Goods | $ -
[7 empty] | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 20000
|  | 4.2. Certified Energy Management and Building Auditors Programmes are adopted by EEC, where Energy Managers are capacitated to conduct building inspections and make recommendations for optimizing EE in buildings nation-wide. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | $ -
[12 empty] | Sub-total GEF | 60000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71200 | International Consultants | 5000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71300 | Local Consultants | 5000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71400 | Contractual services – Individuals | 20000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 75700 | Training, workshop, conference | 5000
[12 empty] | Sub-total UNDP | 35000
[12 empty] | TOTAL ACTIVITY 2 | 95000
COMPONENT 3: Individual and institutional capacity and EE technical knowledge and expertise are strengthened to enhance the ability of national parties to develop and operationalize EE policies, regulations, technical codes, and performance standards in the buildings sector | Outcome 5 Coordination between national parties for the enforcement of existing policies and strategies, including the Iraqi building code, is strengthened | 5.1. Develop a Data Flow Diagram (DFD) consistent with the proposed Executive Regulation for EE in Buildings to advocate intra-government collaboration and obtain consensus of the parties on the DFD and the manuals to use for staff training. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 40000
|  | 5.2. Policy-level training on the proposed regulatory and institutional framework for EE in buildings is conducted, targeting decision makers, public officials, and national experts. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 30000
| Outcome 6 The awareness of practitioners involved in the buildings sector, as well as end-users of electricity, on EE regulation and best practices is strengthened | 6.1. Technical training on EE in buildings is conducted targeting students, technicians, contractors, civil engineers, and architects. This will constitute a Training of Trainers (ToT) workshops to enhance the sustainability of knowledge sharing. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 40000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services – Companies | 30000
|  | 6.2. Awareness campaigns and events are organized to promote EE applications and programs, and relevant marketing material is developed to increase consumers’ commitment to EE practices. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 40000
|  | 6.3. Existing financial schemes and incentive mechanisms dedicated to promoting EE buildings investments and attracting the engagement of the banking sector, are identified, promoted, and monitored. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 4771
[12 empty] | Sub-total GEF | 184771
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71200 | International Consultants | 5000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71300 | Local Consultants | 3000
[7 empty] | UNDP | 4000 | UNDP | 00012 | 71400 | Contractual services – Individuals | 15000
[12 empty] | Sub-total UNDP | 23000
[12 empty] | TOTAL ACTIVITY 3 | 207771
Component 4: Knowledge and expertise on EE in the buildings sector in Iraq is managed, guided by best practices from other countries, and the impacts of the developed regulatory and institutional framework is continuously monitored and evaluated | Outcome 7 A Knowledge Management (KM) system is developed, and best practices are catalogued through conducting exchange missions to other countries | 7.1. A KM system is developed in the form of an online portal for the dissemination of EE in building practices, programs, code, and MVE procedure, on the national level. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 15000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72100 | Contractual services – Companies | 20000
|  | 7.2. Exchange missions to relevant regional or international countries with advanced experience in EE buildings deployment are conducted and a best practices catalogue is developed. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | 13000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71600 | Travel | $ -
| Outcome 8 A Monitoring and Evaluation (M&E) system is developed to track and document progress and impacts of EE initiatives and support the sustainability of EE interventions in the buildings sector | 8.1. Set up an institutional mechanism to revise and update building energy performance standards regularly, including the development of guidelines for enforcing EE measures in building. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 40000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71300 | Local Consultants | 24000
|  | 8.2. Set up an inventory mechanism and database management system for national energy balance, detailed consumption statistics and related Greenhouse Gas (GHG) emission in the buildings sector to monitor and evaluate EE programs. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 74200 | Audio Visual & Print Prod Costs | 1000
[7 empty] | UNDP | 62000 | GEF | 10003 | 75700 | Training, workshop, conference | $ -
|  | 8.3. Capacity building to EEC staff on aspects of M&E, including database management, data collection and reporting, is conducted. |  |  |  |  | UNDP | 62000 | GEF | 10003 | 71600 | Travel | 2000
[12 empty] | Sub-total GEF | 115000
[12 empty] | TOTAL ACTIVITY 4 | 115000
Project Management Cost (PMC) | [6 empty] | UNDP | 62000 | GEF | 10003 | 71200 | International Consultants | 5000
[7 empty] | UNDP | 62000 | GEF | 10003 | 71400 | Contractual services – Individuals | 20000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72400 | Communic & Audio Visual Equip | 1000
[7 empty] | UNDP | 62000 | GEF | 10003 | 72500 | Supplies | 500
[7 empty] | UNDP | 62000 | GEF | 10003 | 72800 | IT Equipment | 500
[7 empty] | UNDP | 62000 | GEF | 10003 | 74200 | Audio Visual & Print Prod Costs | 2038
[12 empty] | Sub-total GEF | 29038
[11 empty] | 72800 | IT Equipment | 500
[11 empty] | 74100 | Professional services | 1800
[11 empty] | 72400 | Audio Visual & Print Prod Costs | 500
[12 empty] | Sub-total UNDP | 2800
[12 empty] | TOTAL ACTIVITY 5 | 31838
SUB-TOTAL GEF | [12 empty] | 433809
[11 empty] | SUB-TOTAL UNDP |  | 60800
[11 empty] | PROJECT TOTAL |  | 494609
Mohammed Al-Attar |  |  | Ghimar Deeb
Project Manager Name & Signature |  |  | Resident Representative/ Deputy Resident Representative: Name & Signature
Date: |  |  | Date:

## HR Plan
UNDP Iraq
Human Resource Plan 2022
Project/Programme Title: Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq
Project ID: 00128406
Output ID:
No. | Post Title (As per Approved Project Organogram) | Status (Vacant/Filled) | Name (for positions already Filled) | Number of Posts | Type of Contract | Category (National/ International) | Grade | Pro Forma | Estimated Budget | COA |  |  |  | Funds Available in Work Plan (Yes/No) | Expected or actual End of Contract | Required period of extension | Project end date | Remarks
[10 empty] | Project | Donor | Fund Code | Activity
1 | Local Project Manager | Filled | Mohammed Al-Attar | 1 | SC | National | SC9 (or SB4) |  | 8000 |  |  |  |  | Yes | 2022-12-31 | Yes | 2027-06-30
2 | Local Finance officer | Filled | Ali Al-Muwali | 1 | SC | National | SC9 (or SB4) |  | 2000 |  |  |  |  | Yes | 2022-12-31 | Yes | 2027-06-30
3
5
6
7
8
9
10
11
12
13
14
15
16
___________________________________________
Project Manager
Signature
Date:

## Procurement Plan
Procurement Plan 2022
Country Office |  | UNDP Iraq
Submitted By Project: |  | Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq
Year |  | 2022
Updated on: |  | 2022-09-15
Requesting Unit (Project Name) | ATLAS Project Number | ATLAS Output Number | Procurement Year | Type of Procurement Action (Civil Work, Goods, Services or ICs) | Procurement Category (Refer next Sheet) | Title of Procurement Action | Number of Units | Is this Request an Amendment? | Amendment value (USD) | Proposed date of Submission of Documents to Procurement | Planned Start Date | Estimated Contract Duration ( #of Days, Weeks, Months, Years) | Estimated Contract Value (USD) | Delivery Location | Comments | Primary Focal Point | Alternate Focal Point | Status (Cancelled/ CO_PO Issued/Work Completed/Close PO)
Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq | 128406 | 122419 | 2022 | IC | International Consultant | Int. EE Policy Expert | 1 | No | N/A | 2022-10-06 | 2022-11-01 | 25 | 17500
Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq | 128406 | 122419 | 2022 | IC | International Consultant | Int. EE Action Plan Expert | 1 | No | N/A | 2022-10-06 | 2022-11-01 | 15 | 10500
Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq | 128406 | 122419 | 2022 | IC | International Consultant | International EE retrofit expert | 1 | No | N/A | 2022-10-06 | 2022-11-01 | 15 | 10500
Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq | 128406 | 122419 | 2022 | IC | Nat. ESIA Expert | International EE retrofit expert | 1 | No | N/A | 2022-10-06 | 2022-11-01 | 10 | 3000
Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq | 128406 | 122419 | 2022 | Services | Workshop/Seminar Cost | Workshop/consultation meeting | 3 | No | N/A | 2022-10-06 | 2022-11-01 | 3 days | 50000
| Type |  | Procurement Category
| Civil Works |  | Contruction -Horizontal
| Goods |  | Construction- Vertical
| Individual Contracts |  | Rehabilization Infrastructure
| Services |  | Armored Vechiles
Computer Software
Contraceptives
Drugs and Pharmaceuticals
Election Items
Furniture and Fixtures
Generators
ICT Equipment
Medical and Laboratory Equipment/Supplies
Meteorological Equipment
Motor Vehicles and Parts
Pesticides/Herbicides
Phone/VHF/HF Equipment
Pre-Fabricated buildings
Printers and copiers
Renewable Energy Equipment
Rent/Lease of Copiers of ICT equipment
Safety and Security Equipment
Other Goods
International Consultants
National Consultants
Audit Services
Cleaning Services
Communication/Advocacy
Consultancy Services-Firms
NGO/CSO Engagement
Office/Warehouse Lease Agreements
Port/Custom Clearing Services
Printing/Publishing and Design
Rent/Lease of Vehicles
Security Services
Shipping and Warehousing
Software Development
Translation Services (companies)
Vehicle Maintenance
Workshop/Seminar Cost
Other services

## Programmatic Selection Plan
Programmatic Selection Processes for Responsible Parties & Low Value Grant Recipients
Country Office |  | UNDP Iraq
Submitted By Project:
Year
Updated on:
Requesting Unit (Project Name) | ATLAS Project Number | ATLAS Output Number | Selection Year | Type of Institution (NGO/ Government) | Type of Selection (Responsible Party or Grant Recipient) | Selection Process (Collaborative Advantage Analysis for RP / Call for Proposal for LVG Recipient) | Agreement Type (Responsible Party Agreement or Letter of Agreement or LVGA) | Type of Actvities/Deliverables | Proposed date of Submission of TOR to PMSU | Proposed date to start Selection Process | Contract Start Date | Estimated Agreement(s) Value (USD) | Comments | Primary Focal Point | Alternate Focal Point | HACT Applicability- YES or NO
| Type |  | Procurement Category
| Civil Works |  | Contruction -Horizontal
| Goods |  | Construction- Vertical
| Individual Contracts |  | Rehabilization Infrastructure
| Services |  | Armored Vechiles
Computer Software
Contraceptives
Drugs and Pharmaceuticals
Election Items
Furniture and Fixtures
Generators
ICT Equipment
Medical and Laboratory Equipment/Supplies
Meteorological Equipment
Motor Vehicles and Parts
Pesticides/Herbicides
Phone/VHF/HF Equipment
Pre-Fabricated buildings
Printers and copiers
Renewable Energy Equipment
Rent/Lease of Copiers of ICT equipment
Safety and Security Equipment
Other Goods
International Consultants
National Consultants
Audit Services
Cleaning Services
Communication/Advocacy
Consultancy Services-Firms
NGO/CSO Engagement
Office/Warehouse Lease Agreements
Port/Custom Clearing Services
Printing/Publishing and Design
Rent/Lease of Vehicles
Security Services
Shipping and Warehousing
Software Development
Translation Services (companies)
Vehicle Maintenance
Workshop/Seminar Cost
Other services

## Costed Monitoring Plan
Costed Annual Monitoring & Evaluation Plan 2022
Project/Programme Title: | Promoting Carbon Reduction Through Energy Efficiency (EE) Techniques in Iraq
Project ID: | 128406
Output ID: | 122419
Monitoring Activity | Purpose | Frequency | Estimated Dates | Expected Action | Partners (if Joint) | Cost (USD) - Should Link to Allocations in the Work Plan
Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly | 2022-12-15 | Slower than expected progress will be addressed by project management. | N/A | Covered by Project Manager cost N58 in AWP 2022 sheet
Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | 2022-10-05 | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. | N/A | Covered by Project Manager cost N58 in AWP 2022 sheet
Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | Quarterly | 2022-12-15 | Relevant lessons are captured by the project team and used to inform management decisions. | N/A | Covered by Project Manager cost N58 in AWP 2022 sheet
Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Not planned for 2022 | Not planned for 2022 | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. | N/A | N/A
Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | Quarterly | 2022-12-15 | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. | N/A | Covered by Project Manager cost N58 in AWP 2022 sheet
Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually | Proposed Date for 2022 Report: 1 November |  | N/A | Covered by Project Manager cost N58 in AWP 2022 sheet
Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Annually | 2022-11-15 | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. | N/A | Minister level meeting in GEF OFP office, no cost associated
Project (DIM) Audit | Audit Commissioned by the Office of Audit an investigation for Directly Implementatiom Modality in keeping with UNDP's Rules and Regulations. | Not planned for 2022 | Not planned for 2022 | N/A | N/A | N/A
Spot-Checks for Responsible Parties | Within the Harmonized Approach to Cash Transfer (HACT) framework, spot-checks conducted by a Third-Party Service Provider on Responsible Party Expenditure. Spot-checks to be completed in accordance with the Assurance Plan developed for each Responsible Party. | Not planned for 2022 | Not planned for 2022 | N/A | N/A | N/A
Audits for Responsible Parties | Within the Harmonized Approach to Cash Transfer (HACT) framework, annual audit of Responsible Party Expenditure. | Not planned for 2022 | Not planned for 2022 | N/A | N/A | N/A
Evaluation Title | Related Strategic Plan Output | UNDAF/CPD Outcome |  | Planned Start & Completion Date | Key Evaluation Stakeholders | Cost and Source of Funding
N/A | N/A | N/A | N/A | N/A | N/A | N/A