Terms of Reference

Capacity needs assessment, selection of woredas/sites  for rehabilitation of degraded lands and  short rotation plantation  Mission to SNNP, Amhara, Benshangul Gumuz and Tigray regions

I CONTEXT

The five years program on Institutional Strengthening for the Sector Development in Ethiopia has been developed and signed by UNDP and government and its implementation commenced.  The overall objective of this program is to strengthen government capacity in the forest sector at all levels and spearhead the implementation of the forestry component contained in the GTP and CRGE Strategy.

The Specific objectives of the project are to: Enhance and stimulate sustainable forest development in line with GTP and CRGE; Foster institutional strengthening at all levels; promote popular participation; Strengthen Science and Innovation and Promote private sector engagement. The five major pillars of the project are: Institutional development; Forest development; Private sector involvement; Stakeholder engagement and Science and Innovation.

II.OBJECTIVES

In line with kick start the implementation of the program, the cardinal objectives of this mission are to:

- Assess the urgent capacity needs in terms of skilled human resources, IT , equipment and furniture of forest conservation and development relevant offices in SNNPRS, Tigray, Amhara and  Benshagul Gumuz regions and design strategy on how to fill the capacity gaps quickly;

- Discuss with the regional relevant bureaus and offices of the  regional presidents  and select the project woredas;

- Discuss with the woreda administration on the establishment of project management offices and agree on how to equip the PMO with the required staff   equipment and materials ;

- Select the degraded areas within the project woredas in consultation with the district administration, kebeles and the local communities. Get  the legal document from the woreda administrations  based on the consensus reached by the kebeles administration and local communities

- Select sites for the establishment of new forest  nurseries  OR make use of the existing nurseries within the project woredas and strategize on how to fulfil the nursery equipment and material;

- Discuss and agree on the establishment of MEF replica in the regions

III .DURATION OF THE MISSION

The Mission will take place from July 29 August 17 /2015

IV EXPECTED OUT PUTS

The expected out puts of the Mission are:

- The capacity requirements in the four regions identified and strategies designed on how to full fill the capacity requirements;

- Project woredas selected;

- The required skill human resources, material and equipment for the project management offices identified and strategy designed on how to full fill the requirement;

- Degraded areas for rehabilitation and sites for short rotation plantations identified and legal document from the district administrations secured;

- New nursery sites OR existing ones identified  and strategy designed on how to make available material ,seeds and material for the opertionliaqzation of the nursery sites;

- Clear understanding on the opening of MEF replica at regional and woreda levels

V – PLANNING, PARTICIPANTS AND ACTIVITIES

The mission will be led by Dr. Tefera Mengistie, Advisor to the State Minister and NPC of the Program; Mr. Ababu Anage, National Climate Change Specialist UNDP CO; Dr. Yitebitu Moges, Chairman of the REDD+ secretariat and             from the Ethiopian Environment and Forest Research institute

The Mission will be conducted by land and UNDP and MEF will make available vehicles and DSA will be charged from the Institutional Strengthening for the Forest sector Development program.

Tentative Schedule of the Mission is briefly described here under:

| Dates | Hr. | Activity | Responsible | Minute taker |
| --- | --- | --- | --- | --- |
| July 29/2015 | 7:00 am | Depart for Hawassa briefing for the regional relevant bureaus president office on the objective of the Mission and agree on the schedule of activities in the region | Dr. Tefra Megiste and other Mision members | Dr Yitebetu |
| July 30 /2015 | The whole day | Continue working in Hawassa including on the selection of the woredas and other schedule of activities | Dr. Tefra Megiste and other Mision members | Dr. yitebertu |
| July 31/2015 | 7am | Depart to the selected woreda/s and commence discussion on the establishment of project management office(s) | Dr.Terfa Mengistie and other Mission members | Dr. Yitebetu |
| August 1/2015 | the whole day | Site visit for the selection of nursery sites and degraded areas and preparation | Dr.Terfa Mengistie and other Mission members | Dr. Yitebetu |
| August 2/2015 |  | legal documents preparation on the selection of degraded lands and nursery sites and depart to hawassa |  |  |
| August 3/2015 | 7: 00 am | Depart to - briefing for the regional relevant bureaus president office on the objective of the Mission and agree on the schedule of activities in the region | Dr.Terfa Mengistie and other Mission members | Ababu Anage |
|  |  | Continue working in including on the selection of the woredas and other schedule of activities | Dr. Tefera Mengiste and other Mission members | Ababu Anage |
|  |  | Depart to the selected woreda/s and commence discussion on the establishment of project management office(s) | Dr. Tefera Mengiste and other Mission members | Ababu Anage |
|  |  | Site visit for the selection of nursery sites and degraded areas | Dr. Tefera Mengiste and other Mission members | Ababu Anage |
|  |  | legal documents preparation on the selection of degraded lands and nursery sites and depart to | Dr. Tefera Mengiste and other Mission members | Ababu Anage |
|  |  | Depart to - briefing for the regional relevant bureaus president office on the objective of the Mission and agree on the schedule of activities in the region | Dr.Terfa Mengistie and other Mission members | TBI |
|  |  | Continue working in including on the selection of the woredas and other schedule of activities | Dr. Tefera Mengiste and other Mission members | TBI |
|  |  | Depart to the selected woreda/s and commence discussion on the establishment of project management office(s) | Dr. Tefera Mengiste and other Mission members | TBI |
|  |  | Site visit for the selection of nursery sites and degraded areas | Dr. Tefera Mengiste and other Mission members | TBI |
|  |  | legal documents preparation on the selection of degraded lands and nursery sites and depart to | Dr. Tefera Mengiste and other Mission members | TBI TBI |
|  |  | Depart to - briefing for the regional relevant bureaus president office on the objective of the Mission and agree on the schedule of activities in the region | Dr.Terfa Mengistie and other Mission members | TBI |
|  |  | Continue working in including on the selection of the woredas and other schedule of activities | Dr. Tefera Mengiste and other Mission members | TBI |
|  |  | Depart to the selected woreda/s and commence discussion on the establishment of project management office(s) | Dr. Tefera Mengiste and other Mission members | TBI |
|  |  | Site visit for the selection of nursery sites and degraded areas | Dr. Tefera Mengiste and other Mission members | TBI |
|  |  | legal documents preparation on the selection of degraded lands and nursery sites and depart to | Dr. Tefera Mengiste and other Mission members | TBI TBI |