¦¾ê¾ì½­½ìñ© ¯½§¾êò¯½Äª ¯½§¾§ö­ì¾¸

#### Lao People's Democratic Republic

ºö¤¡¾­¦½¹½¯½§¾§¾©À²ˆº¡¾­²ñ©ê½­¾

United Nations DevelopmentProgramme

Government of Lao People’s Democratic Republic

National Regulatory Authority for the UXO/Mine Action Sector

in the Lao PDR

United Nations Development Programme

PROJECT ID: 00080296

project titlE: “Support to the National Regulatory Authority for the UXO/Mine Action Sector in Lao PDR

2012 - 2015”

ANNUAL PROJECT REPORT

(APR)

## Reporting period: 01 January 2012 – 31 December 2012

## Version 06 February 2013

I. PROJECT INFORMATION AND RESOURCES

| Project Number: | 00080296 |
| --- | --- |
| Project Title: | Support to the National Regulatory Authority for the UXO/Mine Action Sector in Lao PDR 2012 - 2015 |
| Implementing Partner: | National Regulatory Authority for the UXO/Mine Action Sector in the Lao PDR (NRA) |
| Responsible Parties (if applicable): |  |
| Donors: | - Via UNDP: Australia (AusAID), Ireland, Switzerland (SDC), UNDP TRAC and United Kingdom (DFID) - Other: United States (via AGNA and Sterling International) |

| Project Starting date |  | Project completion date |  |
| --- | --- | --- | --- |
| Originally planned | Actual | Originally planned | Current estimate |
| January 2012 | January 2012 | TBC | TBC |

| Period covered by this report: | 01January 2012 - 31 December 2012 |
| --- | --- |
| Date of annual review: [Indicate if planned or actual] | 12 February 2013 |

| Total Budget | Original Budget (US$) | Latest Signed Revision (US$) |
| --- | --- | --- |
| USD 1,392,150 | USD 1,392,150 | USD 1,392,150 |
| Resources | Donors | Amount (US$) |
|  | Australia | 428,159 |
|  | Switzerland | 289,379 |
|  | Ireland | 40,543 |
|  | EU | 182,970 |
|  | UN/DFID | 90,972 |
|  | UNDP/TRAC | 80,000 |
|  | Unfunded budget | 160,128 |
|  | Grand Total through UNDP | 1,272,150 |
|  | Grand Total USA (Bilateral) | 120,000.00 |

| Summary of Expenditures for period covered by this report | Amount (US$) |  |
| --- | --- | --- |
|  | 2012 Approved budget | US$ 1,392,150 |
|  | 2012 Available budget through UNDP | US$ 1,034,220 |
|  | 2012 Total expenditure (from pre-final CDR) | US$ 977,755 |
|  | Delivery rate % | 94 % |

UNDP-TRAC

UNDP UXO Trust Fund secured

Ireland

AusAid

SDC

Other

DFID through CPR TTF

In kind contributions

2 Technical Advisors (in-kind)	United States

2 Australian volunteers (in-kind)	Australia

1 Technical Advisor working on DFA (in-kind)		 MAG

II. PURPOSE OF THE PROJECT

The objective of this Project is to assist the Government of the Lao PDR to continue strengthening the National Regulatory Authority (NRA) for the Unexploded Ordnance (UXO) Sector. The NRA is an inter-ministerial body established by a Prime Ministers Decree with key roles of coordination, regulation and monitoring to maximise the performance of the UXO sector. Its secretariat, the NRA Office supported by UNDP, provides a UXO focal point in Government administration and has instituted a framework within which implementing organizations work. The NRA is a key actor to ensure the implementation of MDG 9: “Reduce the Impact of UXO in Laos in accordance with the National Strategic Plan for the UXO sector The Safe Path Forward II” approved in June 2012.This MDG should “further function as a multiplier to MDGs 1-8, by providing increased access to assets and services for improved livelihoods.” According to the 7thNational Socio-Economic Development Plan (NSEDP), the Government should “continue addressing the UXO problem.” The Plan lists the following among targets for the Ministry of Labour and Social Welfare: “Remove UXO from about 12,500 ha; reallocation: around 11,875 ha foragriculture and 625 ha for other activities.” As part of a section on measures to achieve MDG targets, the Plan states, “Attempt to remove UXOs from risky areas to promote production and raise people’s livelihoods.” Under “Measures on coordination between sectors relating to cross-cutting issues,” the Plan calls on the Labour and Social Welfare Sector to “take up UXO issues on priority to eradicate poverty and [promote] human safety.”In addition, the Government should also “create and increase educational opportunities in remote areas for children, especially the poor, female, ethnics, and disabled children…provide housing for [disabled] officers…Effort will also be made to increase educational opportunities in remote areas for children, especially the poor, female, ethnic groups, the disabled, and the disadvantaged.” The Project comes under the UNDAF Outcome 9 of the Country Action Programme Plan 2012-2015(By 2015, national and local governments and communities have reduced the impact of unexploded ordnance on people in Lao PDR) Activity results of the Project as described in the 2012Annual Work Plan included the following: Activity Result 1: Mine Risk Education approaches improved, reinforced and better disseminated. Activity Result 2: Better information & referral of UXO survivors; a finalized victim assistance strategy (AusAID sub-project 6/ SDC output 2.3). Activity Result 3: Release of priority land for agriculture and development coordinated and regulated in accordance with risk reduction and priority needs. Activity Result 4: Effective UXO Sector coordination, regulation and information management advanced. Activity Result 5: Better institutional development of the NRA and integration into the regular set-up of the Government (SDC outcome 1&2). Activity Result 6: International treaty obligations met (SDC outcome 3).

III. PROJECT PERFORMANCE AND RESULTS

- Contribution to the Strategic Goals

UNDAF Outcome 9 By 2015, national and local governments and communities have reduced the impact of unexploded ordnance on people in Lao PDR

UNDP Country Programme Outcome By2015, the impact of UXO on people in Lao PDR reduced with collective actions of national and local governments and communities.

Progress towards achieving the Outcome By coordinating, regulating and monitoring all operators of the UXO Sector, the NRA contributed to maximizing the performance of the Sector as a whole. The following progress was recorded: New recorded UXO casualties decreased significantly in the past five years: - 302 casualties in 2008 - 120 casualties in 2009 - 118 casualties in 2010 - 99 casualties in 2011 In 2012, NRA hasrecorded the UXO accidents as follow : Total number of UXO accidents : 32 Total number of UXO victims : 52of which 15 people werekilled :1woman,6men,2 girlsand 6 boys 37people wereinjured : 10women,12 men, 3 girls, 12 boys (Data as at 23/01/2013) 2012: 44% of casualties were children. Sectoractivitesaim to ensurethat people canwork on their land without the threat of death or injury. Over the year 2012, UXO operators in Lao PDR have cleared a combined total of around5,603.08 Ha, whichincluded: ‘Agriculture land, Development land, Road, Mining Project, Dams, Power lineprojects, Tree plantation and etc… ’ Total area of land cleared: 5,603.08Ha, of which - Agriculture land: 4,806.78 Ha - Development land: 796.3 Ha PLEASE NOTE THESE ARE INTERIM FIGURES AS ALL OPERATORS HAVE NOT YET REPORTED TO THE NRA,CLEARANCE FIGURES FOR NOVEMBER AND DECEMBER 2012.More exhaustive figures willbeavailableat the beginning of February 2013. In2012, operators in Lao PDR cleared and destroyed more than81,862items, including : - Bombs : 373items - Bombies : 46,091items - Mines : 346items - Other UXO : 35052 items Analysis of completion of the NRA Annual Work Plan during the year 2012: Within the NRA Annual Work Plan, there were 46 planned activities (among the six activity results) for 2012. For the details, please refer to the Table 1: Results and contributions at output level (starting page 7). 37 planned activities have been achieved. 6 planned activities have been partially achieved. 3 planned activities have not been achieved. In terms of completion of the NRA Annual Work Plan: 80% of planned activities were “achieved”. 93% of planned activities were “achieved or partially achieved”. 7% of activities were not achieved.

Table 1.  Results and Contributions at Output level

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Expenditure | Progress towards achieving outputs; Targets achieved against indicators | Reasons if progress below target and response strategies |
| --- | --- | --- | --- | --- |
| And baseline, indicators including annual targets | List activity results and associated actions | USD |  |  |
| Output 1 | 1. Activity Result: Mine Risk Education approaches improved, reinforced and better disseminated. | 39,600 USD | 2 Staff in the MRE unit (1 officer and 1 technician) |  |
| The National Regulatory Authority for the UXO/Mine Action Sector is better able to coordinate and regulate the UXO sector |  |  |  |  |
| Indicators (Baseline, Target, MoV): | MRE Unit: |  |  |  |
|  | MRE Unit: 1.1 Monitor MRE activities conducted by operators, ensure training and support of operators and local authorities on MRE messages and national standards. |  | Achieved - The MRE Unit achieved its plans to monitor operators in Q1, Q2 and Q4, based on a 10 items check-list. This helped the NRA MRE Unit to better understand the issues and challenges in this area, and revealed that some of the provincial MRE staff at the local level require further training (to improve skills) from their respective headquarters or from UXO Lao National Office or from the NRA. There are some good and appropriate MRE materials, but others are out-dated. The NRA MRE Unit will work with operators to improve this situation. It is important to continue to monitor operators regularly and for remedial action to be taken, if necessary at the Technical Working Group level. - KAP survey 2011 is available on the NRA website, with findings disaggregated by gender, age, activity and origin of MRE messages. The meeting held in January 2012 provided an opportunity to present the results of the KAP survey, and to review all the MRE materials and MRE messages. - In 2012, the NRA MRE Unit organized a total of four workshops, one, as mentioned, on the results of the KAP survey in January, two on gender and the fourth in September concerning how best to use MRE materials. These workshops were attended by UXO operators implementing MRE activities, as well as by officials from the Ministry of Information, Culture and Tourism, and Ministry of Education. - Finally, the NRA MRE Unit analyzed the reasons for UXO accidents (information from the UXO casualtiesdatabase). It is clear that Making fire” has been identified as the main cause of UXO accidents, and specific MRE materials and messages were developed to address this, including the design of a new tee shirt with an appropriate message. The International NGO, MAG, funded the printing and production of some materials, including tee-shirts and posters. |  |
|  | 1.2 Conduct four meetings of the Technical Working Group on MRE |  | Achieved TWG meetings allow all operators working on MRE to share information and discuss issues, work undertaken and results achieved. It also will allow them to plan better for the next quarter. Among other things, it has come to light in such meetings that some operators do not have sufficient skilled staff in the area of social work. |  |
|  | 1.3 Promote adoption of a Prime MinisterialDecree on the scrap metal trade |  | Not achieved (But researched &analyzed) Data collection on the scrap metal trade in 4 provinces namely: Xiengkhouang, Huaphan, Savannaket and Attapeu indicates that the situation has changed from 2009. Scrap metal trading is no longer the main cause of UXO accidents and has decreased significantly, due to lower prices, costly maintenance of detectors and a reduction in the number of UXO / munitions that are easily available. Hence, developing a decree on the UXO scrap metal trade does not appear to be necessary for the time being. The NRA MRE Unit will continue to monitor the situation closely and will recommend any necessary action in the future, should circumstances change. The UXO scrap metal collection report is on the process for approval and an English translation will be available in the near future. |  |
|  | 1.4 Training workshop of the NRA provincial members on gender equality for MRE |  | Achieved Progress on target. The workshop was held on 12-14 March 2012 in Vang Vieng District. UXO operators and government departments that participated include: Ministry of Education and Sport, Ministry of Information, Culture and Tourism, HIB, WE, UXO- LAO, SODI and MAG. (Please refer to Part 4 of this Annual Project Report for details.) |  |
|  | Research Unit: |  |  |  |
|  | 1.5 Conduct research on scrap metal trade in Laos (funded by AGNA/US) |  | Achieved The NRA Research unit, in collaboration with the MRE unit, started the collection of dataon scrap metal in the provinces, including Xiengkhouang, Huaphan, Savannaket and Attapeu provinces. (Please see item 1.3 above). |  |
|  | 2. Activity Result: Better information & referral of UXO survivors; a finalized victim assistance strategy (AusAID sub-project 6/ SDC output 2.3) | 55,350 USD | 2 staff in the VA unit (1 officer and 1 technician) |  |
|  | VA Unit: |  |  |  |
| No. of UXO survivors whose needs are tracked (2010: 0, 2015: 10,000, MoV: NRA Database) Actual 2012: 9,325 Survivor tracking forms collected | 2.1 Tracking casualties through rehabilitation in 10 provinces (in CPS, SLV, SK, ATP, BLX, LPB, XK, HP, SVK and KHM)-visiting 1,417 villages |  | Partially Achieved The Survivor Tracking System established in 10 provinces in 2012is now operational in Savannakhet, Xiengkhouang, LuangPrabang, Huaphan, Bolikhamxay, Khammouame, Champasack, Salavan, Sekong and Attapeu. In 2012,the VA Unit collected 9,325 Survivor tracking forms. Their input into the LVIS System is pending and needs to be addressed. Approximately 5,000 additional forms are expected to be collected in 2013. In 2012, the NRA VA Unit disbursed 316,430,000 LAK (approximately 39,600 USD) to develop the Victim Tracking System. The Survivor Tracking System personnel visited 2,611 villages (in 2011 & 2012). |  |
|  | 2.2 Capacity development of district focal points on tracking UXO victim data (targeted 6 province) |  | Achieved The district focal points had been trained with respect to tracking UXO victims and collecting related data in 10 provinces (4 provinces in 2011 and 6 provinces in 2012). |  |
|  | 2.2.1 conduct workshops in AT and SK |  | Done in Q2. |  |
|  | 2.2.2 conduct workshops in CPS and SLV |  | Done in Q2 |  |
|  | 2.2.3 conduct workshops in BLX |  | Done in Q1 |  |
|  | 2.2.4 conduct workshop in LP |  | Done in Q1 |  |
|  | 2.2 Conduct four meetings of the Technical Working Group on Victim Assistance |  | Achieved In 2012, the VA Unit organized TWG meetings four times, as planned. Coordination at the Technical Working Group level furthers the development of the Network of VA organizations providing services to UXO survivors. |  |
| Victim Assistance Sector Strategy drafted (2010: no, 2015: yes; MoV: NRA Annual Report) Actual 2012: Draft strategy presented in December 2012 | 2.3 Finalize the Victim Assistance Strategy |  | Achieved The first draft of the VA strategy was discussed with operators in December. Many comments were received and changes made accordingly. Major point is that line-ministries input is still needed to ensure their involvement in meeting key VA objectives. Agreement has been reached in principle on the VA strategy. It is now awaiting translation into Lao, before receiving final review and approval. |  |
|  | 3. Activity Result: Release of priority land for agriculture and development coordinated and regulated in accordance with risk reduction and priority needs | 58,693 USD | Total area of land cleared: 5,603.08 Ha, of which : - Agriculture land: 4,806.78 Ha - Development land: 796.3 Ha (Data as of 23/01/2013) |  |
|  | Research Unit: |  |  |  |
| · No. of districts with district clearance plans based on district survey (2010: 0, 2015: 20, MoV: District Clearance Plans) Actual 2012: Pilot project in 3 districts, but not yet finalized District Clearance Plans. | 3.1 Conduct pilot phase of District Survey in additional 3 provinces, enter the data, and conduct workshops with relevant authorities & operators; prepare extension to whole country. (AusAID sub-project 2/ SDC output 1.2) |  | Partially Achieved The District Focused Approach, started near the end of 2011, has been piloted in three districts by HI, MAG and NPA, on an experimental basis. The various methodologies require further review and analysis in order to develop the best methodology to be incorporated into future UXO survey methodology – both non-technical and technical. .. The NRA organized 3 workshops on DFA with the operators involved in the process: - A surveyor refresher workshop, held in Thakhek (February 2012) - A DFA Review workshop in Vientiane (February 2012), to review the DFA process and to confirm the operating procedure. - After monitoring the pilots in June 2012, the NRA organized a workshop in Pakse on 14-15 August 2012 entitled: District Focus Approach Survey Workshop, which was attended by all five accredited humanitarian clearance operators. Started by the Research Unit, the work is now at step 6 of 10. Lead responsibility was handed over to the Clearance Unit in November, as it has the expertise required to advance the process of assessment and incorporation of lessons learned into survey methodology. |  |
|  | Clearance Unit: |  |  |  |
|  | 3.2 Conduct four meetings of the Technical Working Group on Clearance |  | Mostly Achieved TWG meetings were held in Q1, Q2 and Q3 but not in Q4 due to training of standard and senior EOD experts in December 2012 (same stakeholders as in the Technical Working Group). Please see the outcome of the meeting in section 3.5. |  |
|  | 3.3 Conduct four monitoring visits to operators |  | Achieved |  |
|  | 3.3.1 SODI (Borlikhamxai),MAG-UXO Lao KM-HIF-UXO Lao SV |  | Monitoring visits were conducted. |  |
|  | 3.3.2 MAG-JMAS-Milsearch-UXO Lao XK-LP-HP |  | Monitoring visits were conducted. |  |
|  | 3.3.3 NPA-UXO Lao SK, Attp |  | Monitoring visits were conducted. |  |
|  | 3.3.4 UXO Lao-NPA -PSD- SBH-CPS-SR. |  | Monitoring visits were conducted. |  |
|  | 3.4 Conduct workshop(s) on efficiency of clearance and survey in cooperation with the Geneva International Centre for Humanitarian Demining (GICHD) |  | Partially Achieved A draft evaluation report has been submitted by the GICHD to NRA; there is a general agreement on the recommendations and no perceived need for a workshop. |  |
|  | Clearance and QM Units: |  |  |  |
|  | 3.5 Conduct workshop in Saravan for Senior EOD experts (target 39 people) in order to exchange lessons learnt, look at ways to increase safety and efficiency and review National Standards. |  | Achieved The Workshop planned to be conducted in Q3 was postponed due to the ASEP and ASEM Summit and was held in Q4 in Vientiane Capital. Points discussed included: a 10 year plan forBombie clearance; UXO humanitarian training between the US and Lao armies; UXO technology for clearance and DFA.; . Also discussed were: communication methodology among local SEOD, how to act faster, to work more closely, submission ofinformation and data from commercial companies to the NRA regarding land cleared and insurance for workers employed in the sector. |  |
|  | 4. Effective UXO Sector coordination, regulation and information management advanced. | 210,397 USD |  |  |
|  | (SDC outcome 1&2) |  |  |  |
|  | QM Unit: |  |  |  |
|  | 4.1 Review standards and process accreditation of operators including the Lao Army (SDC output 1.5) |  | Achieved In collaboration with the QA/QC Unit, aTechnical Advisor worked on the review of relevantstandards. The report needs to be translated in Lao language for further consideration.The SOP (Standard Operating Procedures) of the Lao Army have been submitted to NRA for review. Accreditation for HI, NPA, PSD, BSL, XTD-Hi Tech and ASA have been reviewed. Provisional accreditation to Lao UNEOD, XTD, THB and Halo Trust has been issued. Full accreditation for UXO- Lao has been issued. The UXO clearance and medic training has been provided to the Lao army (with US funding). Currently, the trainees are in the field with UXO LAO to gain practical experience. |  |
| · % of operators accredited (2010: 33%, 2015: 100%MoV: NRA Annual Report) Actual 2012: 100% (as at 31st December 2012, there are 18 accredited clearance operators, 6 humanitarian and 12 commercial clearance operators) | 4.2 Establish one QA/QC team, conduct regular assessment of operations and investigate potential clearance accidents (AusAID sub-project 4/ SDC output 2.4) |  | Achieved It took time to recruit the QA/QC team, however, an effective team has been established and is fully operational. (NB. Consideration is being given to establishing a second QA/QC team, resources permitting). | It was difficult for NRA to recruit qualified SEOD staff, as many who reside in the Provinces, did not wish to be based in Vientiane (far from the family). |
|  | 4.3 Conduct site assessment |  | Achieved 17 sites have been assessed. From the reports, all operators are working to national standards. |  |
|  | 4.3.1 SK and AT |  | Achieved in Q1, the report is available. |  |
|  | 4.3.2 CPS and SLV |  | Achieved in Q4. The report is available. The mission has been completed. In Q4, the QA/QC team conducted site assessments of UXO Lao in Cpk, Sk, and XK. They observed that UXO Lao has complied with National standards and has a well prepared and capable team in each work site. |  |
|  | 4.3.3 BLK-KM-SVK |  | Achieved in Q3, Reports are available |  |
|  | 4.3.4 XK-HP-LPB |  | Originally planned for Q4, the site assessment was conducted in Q2 Reports are available. |  |
|  | 4.4 Review training standards and revise as appropriate |  | Achieved A workshop to Review Training standards was held in December 2012. Points discussed included the following: (1) appropriate standards for training at levels 1, 2, 3, and 4 (2) After training, who will give the accreditation to the trainees, as the NRA does not yet manage the training centre? (3) Appropriate survey methodology and target areas. There is general agreement on technical survey methodology by operators. The NRA must now ensure that activities are in conformity with development priorities established by Government . |  |
|  | IM Unit: |  |  |  |
| · % of operators reporting electronically to the NRA (2010: 13%[21], 2015: 80%, MoV: NRA database) Actual 2012: 44% (8 operators among 18 accredited operators) | 4.5 Manage, publicize and maintain national databases; ensure current information is being received and input into databases; enter District Survey information. |  | Achieved Entry of historic data and UXO operator’s data is on target; most UXO operators are reporting electronically to the NRA. | Clearance figures for November/December 2012 are not yet available. More reliable figures will be available beginning of February 2013. |
|  | 4.6 Visit operators when required and respond to all stakeholders' requests for data |  | Achieved IM Unit is providing responses upon request. |  |
|  | IM & PR/Programme Units: |  |  |  |
|  | 4.7 update the website. Prepare a Lao version of the website. |  | Partially Achieved Priority is given to the English website, for international exposure. In 2013, the NRA will revise the English website (Public Relations Unit). |  |
|  | Programme/PR Unit: |  |  |  |
|  | 4.8 Develop UXO sector annual work plan and UXO sector annual report (SDC output 1.1, 2.1) |  | Achieved UXO Sector Annual report 2011 was printed and distributed in September. It is an important reference document for the sector covering achievements of the UXO Sector, profiles of various operators and providing valuable information concerning funding of activities. The file is also available on the NRA website. |  |
|  | 4.9 Convene at least one UXO Sector Working Group meeting and field visit (SDC output 1.1, 2.1, 2.2). |  | Achieved UNDP, UXO operators, and concerned line ministries were invited to attend the SWG meeting on 28 September 2012.The Sector Working Group has an additional co-chair, the Ambassador of the United States of America. Minutes of the SWG are now available. |  |
|  | 4.10 Support the NRA Board Meeting and its activities |  | Achieved NRA Office supported one NRA Board Meeting in January 2012 and will organize the next NRA Board Meetingin Q1 of 2013. |  |
|  | 4.11 Convene UXO TF Steering Committee and Annual Project Review meeting (for 2011) |  | Achieved These meetings were held on 23rd January 2012. This provided an excellent opportunity to present and discuss the Annual Project Report for the year 2011. |  |
|  | 4.12 Coordinate with provincial and district authorities (SDC output 2.5) |  | Achieved Luang Prabang- On 6-7 December, the NRA organized a Regional planning workshop for UXO clearance. Among other things it sought to ensure that there would be necessary support for socio-economic development projects in northern provinces of Lao PDR’. The meeting was opened by Deputy Prime Minister, H.E Asang Laoly and co-chaired by H.E Bounhueang Duangphachan, The LPB provincial governor and representatives from all five northern provinces, UNDP and INGOs were present as well, for a total of 70 participants. The specific objective is to initiate a process of data collection from the provincial level, in order to prioritise UXO clearance, including of contaminated development priority areas. The meeting also sought to present the National UXO Sector Strategy 2011-2020, to role and Terms of Reference of the NRA, as set out in Ministerial announcement 096/NRA 27 Nov 2012, and also to discuss the implications of Notice Number 093/NRA which directs that UXO clearance support socio –economic development projects in Lao PDR. The outcome of the meeting: participants acknowledged the National Strategy and have a better understanding of the NRA role and the contents of Notice number 093/NRA. All participants have agreed to contribute necessary information regarding development projects in their respective provinces. Participants further agreed that UXO Lao should assign a survey team to conduct UXO surveys in Phongsali, LuangNamtha and Oudomxay Provinces. Other provinces that have UXO operators can cooperate directly at the provincial level to set priorities together with local authorities. The NRA will undertake similar data collection in the central and southern provinces (no later than March of 2013). |  |
|  | 4.13 Organize anniversary celebration of the entry into force of the CCM and Mine Awareness Day |  | Achieved The NRA, with the Lao Ministry of Foreign Affairs, celebrated the 4th April Mine Awareness Day and the 1st August anniversary of the entry into force of the CCM. Official meetings, UXO exhibitions by operators, and sport events were held. Attendanceat the 1st August events: approximately 700 participants. |  |
|  | 4.14 Media field visits and workshops |  | Achieved |  |
|  | 4.14.1 field visits (twice) to XK (for 4 days) |  | Done in Q1 in XiengKhouang, in presence of NRA chairman H.E Bounhueang Duangphachan. |  |
|  | 4.14.2 field visit (twice) to KHM (for 4 days) |  | Done in Q1 in Khammouane. |  |
|  | 4.15 Programme officers' field visit |  |  |  |
|  | 4.15.1 visit LP for 4 days (5 people) |  | Achieved A new Programme Officer recruited in September 2012, attended the Regional Planning Workshop in LPB 6-7 December 2012, He has completed the data gathering for UXO clearance on development projects and was responsible to take minutes. |  |
|  | 4.15.2 visit SK and SLV for 4 days (5 people) |  | Achieved Field visit took place with Lao media on 7-11 May 2012 in SK and SLV. |  |
|  | 4.15.3 visit BLX and KHM for 4 days (5 people) |  | Not Achieved Planned in Q3 but no Programme Officer was in charge in Q3. |  |
|  | 5. Better institutional development of the NRA and integration into the regular set-up of the Government (SDC outcome 1&2) | 593,716 USD |  |  |
|  | NRA management and staff: |  |  |  |
|  | 5.1 Establish a Programme function within the NRA (SDC output 1.6) |  | Achieved The former Programme and Public Relations Officer was promoted to the position of Deputy Director (Support) in June 2012 and a new Programme and Public Relations Officer has been recruited. A programme technician was recruited in October 2012, who started effectively in January 2013. |  |
|  | 5.2 Strengthen implementation of NRA Annual Work Plan through quarterly reviews (SDC output 2.7) |  | Achieved The Programme Unit is responsible for monitoring the implementation of NRA Annual Work Plan. 2012 was the first year for the NRA to use the Annual Work Plan as the main reference document. Every Unit (9 units within NRA during the year 2012) reports monthly to the Programme Unit and to NRA Senior Management, in the Lao language. Every quarter, this information is compiled, reviewed, cross-checked by the national Programme Officer and reported (internally and also in the UNDP Quarterly report).This quarterly review provides an opportunity to discuss important issues with the various units, to take stock of progress and/or difficulties. In 2012, the quarterly review process was supported by the UNDP Technical Specialist Finance & Programme. |  |
|  | 5.3 Develop and review personal development plan in line with personal evaluation and training plans (SDC output 2.8) |  | Achieved The Administration Unit regularly evaluates the capacity, training needs and performance of staff. There is no contract extension without formal evaluation. |  |
|  | 5.4 Strengthen capacity of the sub-national levels of NRA (SDC output 1.2) |  | Achieved NRA role and responsibilities were approved in document number 096/NRA, dated 27 Nov 2012, which clearly sets out the NRA role at the central and local levels. The NRA provincial coordination offices in two provinces are working under the umbrella of the provincial administration office. |  |
|  | 5.5 Develop a Gender balance policy in the NRA, with a particular focus on recruitment (SDC output 2.6) |  | Partially Achieved The Administration Unit did not develop a specific policy but gender balance has been considered in the recruitment processes: 16 positions have been advertised in newspapers (eg. the Vientiane times). The NRA recruited 15 staff members: 7 women and 8 men. |  |
|  | 5.6 Attend the Annual Program Managers meeting, international workshops on mine action technology, information management and other subjects relevant to the NRA |  | Achieved The NRA Director and UNDP Technical Specialist attended the Annual Program Managers meeting in Geneva; an important annual event. The NRA Director chaired one session (on transition and completion in Mine Action). Such meetings provide an important networking opportunity, because most stakeholders including donors are present. The NRA Director and NRA Deputy Director (Support) participated (in July 2012) in an exchange workshop on mine action in Cambodia. The NRA Deputy Director (Operations) attended the mine action technology workshop in Germany. The Information Management Officer attended IMSMA training in Switzerland and the NRA Clearance Officer attended the mine action technology workshop in Switzerland in September 2012. |  |
|  | 5.7 Organize a study tour in Cambodia for NRA Board members. |  | Not Achieved Planned in Q4 but not carried out. | Not achieved The progress is not on target due to the fact that the delegates have commitment pre-standing. |
|  | 5.8 Monitoring missions to provinces (XK, LPB, HP/ BLK, KM, SVK) |  | Achieved Monitoring missions have been conducted in all named provinces, as well as in SLV, SK and ATT. Such missions provide opportunity to consult with local authorities and to designate responsibility for target areas (between UXO Lao and NPA). More discussion will be required in the new year. |  |
|  | 5.9 training of EOD officer in the NRA (1 person for EOD level 3) |  | Achieved Organized in Q4. The meeting invited the UXO deminers level 3 who are working in the UXO sector across the country. (NRA will distribute a new training standards document in the new year). | Progress on target, please see detail on 3.5 |
|  | Finance Unit: |  |  |  |
|  | 5.10 Prepare annual and quarterly workplans and reports |  | Achieved Annual, quarterly work plans and reports are prepared by national staff including the Finance Officer in collaboration with the Programme Officer, and other units. FACE forms (financial reports and requests) were fully prepared by the Finance Officer, under the guidance and with the support of the Technical Specialist Finance and Programme. |  |
|  | 5.11 ensures all kind of payments and proper documentation; |  | Achieved All payments had proper documentation to ensure smooth financial operations within the NRA according to the rules, regulations and procedures. |  |
|  | 5.12 carry out all finance related activities such as budgeting, expenditure control and accounting; |  | Achieved The Finance Officer carried out all finance related activities such as budgeting, expenditure control and accounting. |  |
|  | 5.13 Prepare various reports for UNDP, donors and the Lao Government. |  | Achieved Various reports for UNDP, donors and the Lao Government are prepared by national staff, including the Finance Officer and Programme Officer, under guidance and with the support of the Technical Specialist Finance and Programme for the reports in English. (Some reports are prepared exclusively in the Lao language by national staff). At the end of December 2012, the NRA submitted the draft work plan for 2013 to the UNDP for review. Approval is pending. |  |
|  | Logistics and Admin Unit: |  |  |  |
|  | 5.14 Ensure logistical and administrative support for NRA activities, as well as follow-up of operators. |  | Achieved Internal NRA procurement procedures were revised in order to centralize all procurement activities under the Logistics and Administration Unit; |  |
|  | General: |  |  |  |
|  | 5.9 Commission external project evaluation of NRA (and UXO Lao) |  | Achieved Done in Q2. Final Mission Report available in July 2012, in both Lao & English. |  |
|  | 5.10 NRA's institutional capacity assessment and capacity strategy development (SDC output 1.6) |  | Partially AchievedClearance Officer participated in the Senior Management Course organized by the James Madison University in USA. Recommendations regarding Capacity Assessment by the evaluation team were received in June / July 2012; to follow-up in the coming months. Evaluation report is available. |  |
|  | 6. International treaty obligations met (SDC outcome 3) | 20,228 USD |  |  |
|  | MoFA: |  |  |  |
|  | 6.1 Update Article 7 Report (SDC Output 3.4) |  | Achieved Done in Q1. At the intersessional meeting of the Convention on Cluster Munitions, Lao PDR received congratulations for being one of the first countries to submit its Article 7 Report (before the deadline). |  |
|  | 6.2 Help prepare domestic legislation to be compliant with CCM (SDC output 3.1) |  | Not Achieved Domestic legislation has not yet been developed, but will be in the coming year. The NRA will consult with the UN and International Committee of the Red Cross with respect to state of the art legislation to ensure full compliance with the CCM. |  |
|  | 6.3 Ensure continuity of ITSU/LAU work and advocate for CCM implementation/universalization (SDC output 3.3) |  | Achieved Lao PDR was very active during the negotiation of the CCM and since its entry into force. Lao PDR hosted the first Meeting of State Parties in 2010 and was President of the Convention throughout the following year. The NRA redeployed two staff from the Research Unit to the ITSU Unit to ensure the continuity of the good work being done at the time and to ensure that various humanitarian operators continue to assist Lao PDR in fulfilling its obligations of the Convention on Cluster Munitions. |  |
|  | 6.3.1 Participate in the intersessional meeting in Geneva (2 people from the Gov) |  | Achieved Done in Q2. |  |
|  | 6.3.2 Participate in the 3 MSP in Norway (2 people from the Gov) |  | Achieved 7 persons from the Government attended the 3 MSP to the CCM in Oslo, Norway in September 2012 (4 from MOFA, 2 from NRA, 1 from UXO Lao), supported by 2 UNDP advisors. The Lao delegates played an active role on the international stage: six statements were delivered during plenary and the delegation engaged in debate on several issues. The Article 7 progress report on fulfilling the obligations of the CCM was presented. The Lao delegation also held bilateral meetings with the Ministries of Foreign Affairs of Norway, Germany, Canada, and several other donors. |  |
|  | 6.4 Finalize 10-year plan for CCM implementation setting measurable indicators, milestones, targets and costing. |  | Partially Achieved A draft 10 year plan was produced,and is now being reviewed and updated, prior to seeking approval from the NRA Board in 2013. |  |
|  |  | TOTAL: 977,755 USD |  |  |

- Contribution to aid effectiveness, i.e. update on implementation of the Vientiane Declaration and its Action Plan, HACT,etc.

Continuing UNDP technical assistance to the NRA is identified through the Government’s capacity development objectives and strategies. In addition, the creation of the Trust Fund for the Full Implementation of the Convention on Cluster Munitions in the Lao PDR within the Framework of the Vientiane Declaration on Aid Effectiveness has enabled partners to implement common arrangements and simplified procedures. Further, Government capacities have increased in results-based management, as evidenced by the implementation of the NRA’s Annual Work Plan for 2012, and the development of NRA’s Annual Work Plan for 2013, including important new initiatives for the future. The Annual Work Plan for 2012 was the main reference document for purposes of monitoring the implementation of the activities of the NRA, and also for the quarterly review and reporting. In early 2013, UNDP will provide training on the new NIM manual, including revised Standard Operating Procedures, reflecting the most recent UNDP Corporate NIM Guidelines.

- Update on partnerships

2012 was a very active and dynamic year in regards of changes and practical actions. Selected actions are highlighted below: (i) The NRA continued to implement its key responsibilities. The amended National Strategic Plan ‘Safe Path Forward II” was approved by the Prime Minister on 22 June 2012. (ii) On 27 November 2012, the role and responsibilities of the NRA were approved by the NRA Chairman. This will foster better coordination between NRA central and NRA in the provinces, and will provide all involved in the sector with a clearer understanding of the mandate, role, structure, scope and objectives of the work of the NRA. (iii) The NRA continued to work closely with Government in accessing funding for the sector from the government. On 24 December 2012, the proposal was agreed in principle by the NRA Board Chairman. Funding will depend on the availability of funds and quality of the funding request made to Government by the Sector. (iv) A milestone planning event took place in Luang Prabang Province on 6-7 Dec 2012, when the NRA organized a Regional planning workshop for UXO clearance, supporting socio-economic development projects in the northern provinces of Lao PDR. The meeting was chaired by H.E Asang Laoly and co-chaired by H.E Bounhueang Duangphachan. LPB provincial governor and senior officials from others Northern provinces, Representatives of UNDP and INGOs were present as well. The aim of the workshop was to collect data at provincial level on UXO clearance and on the development projects of the provinces, in order to determine priority areas for clearance over the next decade. Very early in 2013, the NRA will undertake similar consultations and data collection in the central and southern provinces (no later than March 2013). This is a major step for the NRA in the coordination of planning for priority-setting by various levels of government in the UXO Sector. This major initiative will also allow the provinces to allocate funds and request additional support from the central government and/or donors for UXO clearance in the now defined priority areas. (v) There was also a significant initiative undertaken by the NRA, in association with the Embassy of the United States of America in Lao PDR and JMAS, to support level 1 UXO clearance and medical training for the Lao people’s army. This pioneer initiative will help to expand and accelerate UXO clearance in Lao PDR and also helps to further develop a sustainable national capacity in the Sector. In addition, the Ambassador of the United States of America has kindly agreed to co-chair the UXO Sector Working Group along with her fellow co-chair, the Resident Representative of the UNDP. . (vi) Regarding South-South cooperation, with the support of the Japan International Cooperation Agency (JICA), the NRA and UXO Lao initiated a UXO/Mine Action Sector Exchange Program with the Cambodian Mine Action Centre (CMAC). From 27 February to 4 March 2012, the 3rd Workshop on JICA-UXO Lao and Cambodia on UXO/Mine Action Sector was held in Okinawa Prefecture-Japan to further formulate detailed plans for 6 thematic workshops to be held in the near future. In July 2012, CMAC and UXO LAO sent their own technical staff to participate in two thematic workshops concerning: (1) Demining tools, Methodology, Technology and Survey (in June 2012 in Cambodia); (2) Standard of Operations for UXO/Mine (Forum held in Lao PDR in December 2012). Funding of such initiatives will continue until 2015. There was also a visit of the Cambodian CMAA team (NRA equivalent) to Lao PDR supported by UNDP New York; and the visit of NRA to CMAA and CMAC in Cambodia, supported by Sterling International (US Department of State funding). (vii) Programme document: The NRA, UXO Lao and the UNDP are currently developing a new programme document that will guide their cooperation in the Sector for the years 2013-2015. This document sets out the key elements of UNDP support to the implementation of the National Strategic Plan “The Safe Path Forward 2” and the multi-year work plan for the sector which is currently being developed. This Programme document will focus on institutional strengthening, providing support to UXO victims, better coordination within UXO sector and accelerating prioritised land release in line with national development priorities.

- Update on gender mainstreaming

In 2011, the NRA pursued a policy of actively recruiting women for key positions. While none of NRA officers were female in 2010, three officer positions are now occupied by women (about one third of NRA officers): Research Officer, Risk Education Officer and Finance Officer. In 2012, particular attention to gender was ensured in the following projects: - The KAP Survey, the UXO casualties database and the Survivor Tracking System systematically disaggregated data according to age and gender. - District Focused Approach to UXO Survey: building on findings of the Post-Clearance Impact Assessment (PCIA) according to which “... there does seem to be different types of impact for men and women depending on post-clearance land use,” the District Survey ensured active participation of women in the preparation of the district clearance plans. - In March 2012, the NRA held a workshop on gender equality for MRE, in VangVieng. According to the KAP survey, women are not participating to an adequate degree in UXO MRE campaigns. Therefore, in 2012,the NRA held two workshops on gender mainstreaming in MRE - one in Savannakhet province at the technical level and one in Vang Vieng province at policy level. The workshops were of great interest to both male and female participants who requested more action in their provinces. . 2012 Human Resources management: Gender balance has been considered in the recruitment processes: 16 positions have been advertised in newspapers (in Vientiane times), NRA recruited 15 staff members: 7 women and 8 men.

- Update on the implementation of audit & spot check recommendations

###### The audit recommendations proposed by Ernst & Young in 2011 (audit report for the year 2010) were implemented. (Please refer to the Annual Project Report 2011 submitted in January 2012.) ###### In the second quarter 2012, the NRA received the audit report for the year 2011, with recommendations to implement in 2012. The NRA will continue to follow DIC instructions concerning the application of Lao Tax Law; and the reconciliation of CDR is already taking place. ###### In addition, spot checks by UNDP were carried out on two occasions in 2011. Generally speaking, spot checks were seen as useful opportunities for dialogue between the UNDP and NRA, leading to a better understanding and implementation of UNDP procedures and guidelines by NRA staff. ###### Spot check reports included long lists of recommendations. One “major observation” from the spot check that took place in September 2011 was: “It seems that it is mainly the NRA Finance Unit that deals with project management and knows UNDP requirements. The Spot Check Team would like to recommend that other units, such as the Programme Unit get more involved in compliance with UNDP and DIC rules and regulations to ensure a better, more efficient and more transparent management that will certainly lead to better development results.” In 2012, as mentioned in the Matrix (Table 1. Results and Contributions) Point 5.2 :The Programme Unit is in charge of monitoring the implementation of the NRA Annual Work Plan. 2012 was the first year for the NRA to use the Annual Work Plan as the main reference document. The Programme Unit is working closely with the Finance Unit on both planning and reporting, as well as in ensuring compliance with UNDP and DIC rules. The Programme Unit also has a liaison role with DIC for the UXO Sector Working Group and the related Round Table events. In 2012, no spot checks were organized by UNDP for the NRA programme.

- List main challenges and issues (if any) faced during reporting period

The main challenge of the NRA in 2011 related to the departure of six key staff members (one half of NRA key staff): two successive Risk Education (MRE) Officers, one Research Officer, one Standards/Quality Management Officer, one Finance Officer and one Deputy Director. This high turnover represented a significant challenge for the NRA and delayed some activities, such as the District Focused Approach to UXO Survey. While each departure had its own causes, an important element leading to the departure of staff was the growing difficulty for the NRA to compete with salaries offered in the private sector in Vientiane. In 2012, actions have been implemented to mitigate this situation, with a salary increase of 20% from 1st August 2012 and the family consideration (taking into account the number of dependents).An additional 5% increase was implemented from 1st January 2013 for all UNDP staff. In 2012, the NRA workforce was stable (we did not lose key staff), a very positive improvement compared to the year 2011. The finalization of the Victim Assistance strategy has been delayed. The NRA board gave feedback on the strategy and the VA officer submitted a revised version. Progress has been made in the fourth quarter 2012. The draft document has been shared with all Victim Assistance Technical Working Group members. Final approval is expected early 2013. The NRA considers that the results of the DFA pilot project (coordinated by the NRA and implemented by three INGOs) have not yet been determined. As the pilot process nears completion, consideration is necessary, before any extension to other districts or modification / agreement of a common methodology. The survey and mapping of UXO contamination in Lao PDR is still very necessary. Funds allocated to MRE work in 2012 and 2013 have been insufficient and the NRA MRE Unit contends that a significant increase is needed. In the past, UNICEF contributed to MRE activities in the UXO sector. The NRA will approach UNICEF again, in an effort to re-engage UNCEF in the UXO sector. Another challenge is to determine how best to measure MRE performance. In 2013-2014, MRE operators and the NRA will collaborate to work on this topic, under the guidance of NRA Deputy Director Operations. Currently the NRA does not receive information from all commercial clearance operators with respect to hectares cleared, thereby restricting NRA ability to report accurately in the framework of the CCM.

- Rating on progress towards results

| Activity Result 1: Mine Risk Education approaches improved, reinforced and better disseminated. |  | Positive change Negative change Unchanged |
| --- | --- | --- |
| Activity Result 2: Better information & referral of UXO survivors; a finalized victim assistance strategy (AusAID sub-project 6/ SDC output 2.3) |  | Positive change Negative change Unchanged |
| Activity Result 3: Release of priority land for agriculture and development coordinated and regulated in accordance with risk reduction and priority needs |  | Positive change Negative change Unchanged |
| Activity Result 4: Effective UXO Sector coordination, regulation and information management advanced. |  | Positive change Negative change Unchanged |
| Activity Result 5: Better institutional development of the NRA and integration into the regular set-up of the Government (SDC outcome 1&2) |  | Positive change Negative change Unchanged |
| Activity Result 6: International treaty obligations met (SDC outcome 3) |  | Positive change Negative change Unchanged |

IV. ADDITIONAL ACTIVITIES / RESULTS WHICH CONTRIBUTE TO THE OUTCOME AND/OR OUTPUTS

Overall, the NRA has been very active in advocacy for the UXO Sector, among other activities: The NRA, associated with the Lao Ministry of Foreign Affairs, celebrated the 1st August (Entry into force of the CCM): Official meetings, UXO exhibition by operators, and sport events. Attendance: around 700 participants. Ministry of Foreign Affairs officially launched the approved MDG9 logo on 1st August 2012. NRA has promoted actively the new logo with various materials: Tee-shirts, postcards, stickers, factsheets and other documents published by the NRA. The new logo had high visibility in the Lao media (both in English and Lao newspapers). In 2012, more than 50 articles were published in local newspapers (Vientiane Times and Lao language newspapers) concerning the UXO issue, and the achievements of the various operators active in the UXO Sector. On 22 June 2012, the National Strategic Plan, The Safe Path Forward II, was approved. The NRA will organize meetings with line ministries to present this document and forge stronger links and better coordination between the NRA and relevant line departments. The NRA printed the approved National Strategic Plan for dissemination, as well as other relevant documents such as the Sector overview, Lao PDR transparency report,etc…The NRA distributed 500 copies of the National Strategic plan in English. Early 2013, NRA will print Lao and English version. Lao PDR actively participated in the 3rd Meeting of States Parties to the Convention on Cluster Munitions in Oslo, Norway in September 2012. The Lao delegation with a total number of nine persons (4 from MOFA, 2 from NRA, 1 from UXO Lao, 2 UNDP advisors) made substantive statements in all key sessions and held bilateral meetings on the margins of the event with key donors who were present and available. The UXO Sector is seeking additional funding (up to 50 Million USD per year), based on needs of and the absorptive capacity of the sector. Operators have developed project proposals for consideration. Lao PDR hosted several important international events from September to November 2012, including: the Asia-Europe Parliamentary Meeting, Asia-Europe People’s forum, and the Asia-Europe Meeting (ASEM) involving high level delegations from 51 countries on two continents. The NRA, on behalf of the UXO Sector in Lao PDR, was allowed to exhibit the work of the Sector during all three important meetings (as well as the Round Table Implementation Meeting on 23rd November with the development partners).

V. FUTURE WORK PLAN

1. What are the priority actions planned for the following year to overcome constraints, build on achievements and partnership, and use of the lessons learned during 2012?

Please refer to the signed AWP for 2012.The Annual Work Plan for 2013 is currently being developed. Key activities and timeframe for each are included in the draft Annual Work Plan for 2013. Priority actions planned for 2013 include: - To integrate UXO clearance operations within the broader socio-economic development framework in Lao PDR. - To request and receive financial contributions from the Government of Lao PDR. - To record, analyse and disseminate relevant data in 10 provinces, using the Survivor Tracking System. - To take stock of the pilot project using the District Focused Approach to UXO survey, analysing results of each and integrating best elements of each pilot into future survey methodology. - To strengthen the programme function within the NRA, among other things to better follow-up on Annual Work Plan implementation.

2. List major adjustments in the strategies, targets or key outcomes and outputs planned.

The new template used for the NRA Annual Work Plan 2012 has been slightly adjusted in order to be consistent with the UNDAF Action Plan 2012-2015 and proposals submitted to UXO Trust Fund donors. It remains consistent with the National Strategic Plan The Safe Path Forward II, as all six activity results are directly driven from the six objectives of The Safe Path Forward 2.

| 3. Estimated total budget required for the following year (2013): | US$ 1,918,000 |
| --- | --- |

VI. ANNEXES

No Annex

PREPARED BY

CLEARED/APPROVED BY

“The MDG Compact for Lao PDR: Fully committed to attaining the MDGs by 2015 and the Lao PDR specific MDG 9 on the reduction of UXO impacts by 2020 on the occasion of the Vientiane High Level Round Table Meeting,” 20 October 2010.

Ministry of Planning and Investment, 7th National Socio-Economic Development Plan (2011-2015) - Abridged version (Unofficial translation from original Lao version), Vientiane Capital, October 2010.

As of 30 June 2012, UXO Sector operators included 15 non-profit organizations (AAR, COPE, CPI, CRS, NCA, HI, LDPA, MAG, NCDP, NPA, SODI, SoS, CARE International, UXO Lao and World Education) and 11 commercial operators (ASA, PSD, SBH, Lao BSL, XTD High-tech, Tong, PLC, PCL, Milsearch, BACTEC and MMG/LXML.

It should be also noted that the proportion of children among casualties increased significantly during this period:

- 2008: 35% of casualties were children

- 2009: 29% of casualties were children

- 2010: 58% of casualties were children

- 2011: 55% of casualties were children.

NRA, “Post-clearance Impact Assessment - Final Report,” January 2011.