Project Title: Decentralised Governance Promotion Program (DGPP)

Project Number:

Implementing Partner: Ministry of State Administration and Civil Service (MAEFP) and Ministry of Economy and Finance (MEF)

Start Date: 1st January 2020	 End Date: 31 December 2025  PAC Meeting date: 19 December 2019

Brief Description

Mozambique has embarked upon a new phase of decentralization, with the aim of improving governance, strengthening democracy at the sub-national levels, and striving to deliver better public services. Through a Constitutional amendment and a spate of subsequent legislation termed as the ‘Decentralisation Package’, the Government has laid the foundations for a deeper form of decentralized governance. As a political reform, it paves the way for deepening of democracy, strengthening social cohesion, national reconciliation and embedding democratic principles within all tiers of government; and as a governance reform, it creates a platform for more accountable and more responsive government, one that seeks to improve public services by responding to citizen’s needs. The government has undertaken a number of steps to implement the decentralization reforms, including laying out the principles and objectives of a National Program for Decentralization (PND) and drafting several legal frameworks. To provide further impetus to this process, the Government of Republic of Mozambique and UNDP have developed this Decentralised Governance Promotion Program (DGPP) This Program is the result of consistent dialogue with government (including at the political level); is fully aligned with the legislative changes introduced under the Decentralization Package; will form an integral part of the National Program for Decentralization (PND) which will be finalized in the first quarter of 2020; and complements support provided by other development partners, both within and outside the UN system. The Program takes a flexible, inclusive and equity-oriented approach and seeks to bring to the fore political leadership for implementation of reforms, while addressing gaps in institutional capacity at all levels. Through the Program, UNDP will assist the government to undertake foundational reforms that lead to more inclusive form of decentralized governance, shared prosperity, and a more capable local government system. This support to government is built on three pillars: (i) Inclusion and Citizen Participation, which seeks to contribute to creating an environment for peace and stability and achieve social cohesion by focusing on establishing and strengthening institutional mechanisms for enhanced inclusion, accountability and transparency, and trust building; (ii) ResponseAbility which targets strengthening of systemic capacities of sub-national governments in relation to their core mandates, and builds their ability to become more agile and responsive to citizen needs; and (iii) Democratization of Economic Opportunity which aims to enhance equity in terms of access to economic opportunities, particularly for women, youth and vulnerable segments including the disabled and the minorities. This is intended to be achieved by helping realize the potential of cities to become even more powerful engines of growth by strengthening their capacities to prepare and deliver local economic plans, with the involvement of private sector, and innovate on the way they conceive and deliver public services.

Contributing Outcome (UNDAF/CPD, RPD or GPD)UNDAF Outcome 2: Poor People Benefit Equitably from Sustainable Economic Transformation

UNDAF Outcome 4: Disadvantaged Women and Girls Benefit from Comprehensive Policies, Norms and Practices that Guarantee their Human Rights

UNDAF Outcome 6: People Equitably Access and Use Quality Health, Water and Sanitation Services

UNDAF Outcome 8: All people benefit from democratic and transparent governance institutions and systems that ensure peace consolidation, human rights and equitable service delivery

UNDAF Outcome 9: Most Vulnerable People in Mozambique Benefit from Inclusive, Equitable and Sustainable Management of Natural Resources and the Environment

| Total resources required: | $60.5 million |  |
| --- | --- | --- |
| Total resources allocated: |  |  |
|  | UNDP TRAC: |  |
|  | Donor: |  |
|  | Government: |  |
|  | In-Kind: |  |
| Unfunded: |  |  |

Agreed by (signatures):

| Ministério de Administração Estatal e Função Pública | PNUD | Ministério de Economia e Finan,cas |
| --- | --- | --- |
| Print Name: | Print Name: | Print Name: |
| Date: | Date: | Date: |

# Development Challenge (1/4 page – 2 pages recommended)

Figure 1: Governance Indicators of Mozambique (2012-2017)

Source: World Governance Indicators

Over the past two decades, Mozambique has successfully navigated myriad governance and economic challenges, whose nature and severity have varied over time. Sound macroeconomic management and several large-scale foreign-investment projects in the extractives sector led to real GDP growth averaging 7% between 2000 to 2015, making Mozambique one of the best performing economies in Sub-Saharan Africa. Moreover, Mozambique’s efforts for enhancing transparency and strengthening oversight of the extractive sector---which contributed 3.5% to GDP and 20.6% to overall revenues in 2014—were duly recognised by the Extractive Industry Transparency Initiative as representing ‘meaningful progress’.  However, the past few years have witnessed a significant and rapid deterioration in Mozambique’s economic performance and outlook, driven by a global decline in commodity prices that has reduced export growth for key commodities; high inflation; a depreciating Metical; and growing levels of public debt. Moreover, Mozambique’s strong economic performance of the past two decades has not translated into tangible improvements in living standards for all segments of society. Poverty incidence is estimated at 46.1% nationwide in 2015, being particularly high in the North (55.1%) and central (46.2%) regions of the country; employment conditions remain problematic, with nearly 40% of youth (ages 15-24) unemployed, female unemployment at 27% overall and only 14% employment in the formal sector. These challenges have been ratcheted by the crippling and widespread devastation—estimated at US$ 3.2 billion—caused by two back-to-back cyclones (Idai and Kenneth) in March and April 2019. The footprint of these climatic disasters extended beyond decimation of infrastructure across seven provinces, and covers loss of incomes, jobs, and disruptions to businesses and delivery of basic public services. Women (53% of affected population) bore the brunt of these losses, particularly in terms of economic opportunities, and of productive assets. As a result of the damage caused by the cyclones, the economy will likely contract by 2-3% in 2019.

Governance challenges appear equally serious. Mozambique’s standing in 2017 compares unfavourably with Sub-Saharan Africa on all governance indicators bar one, and the country’s performance on all indicators is marked by a steep decline between 2012 and 2017 (Figure 1). By the government’s own admission, there is growing public dissatisfaction with public services and perceptions of corruption are high. Similarly, weaknesses in governance of SOEs, public investments and public debt led to the ‘hidden debt’ crisis and to foreign debt constituting 70% of GDP in 2016.

Unpacking the Decentralization Framework

Mozambique has implemented  decentralization reforms since 1997, and made  slow, but steady progress, with a political preference for delegation as a deconcentration mechanism and devolution with decentralization, although the latter has hitherto been less of a focus.. Despite several political and governance constraints, the country has continued its journey on the path to decentralized governance with the recent Constitutional amendments and passing into law of several pieces of legislation, termed as the ‘Decentralization Package’.  The latest iteration of decentralization reforms represents a watershed in Mozambique’s history. As a political reform, it paves the way for deepening of democracy, strengthening social cohesion, national reconciliation  and embedding democratic principles within all tiers of government; and as a governance reform, it creates a platform for more accountable and more responsive government, one that seeks to improve public services by responding to citizen’s needs. Shelving the ‘gradualist’ path it has followed hitherto which has led to a narrow base of autonomous local bodies—autonomy has hitherto been limited to  53 local authorities (municipalities)  across the country—and rooted in a politically negotiated settlement, the Constitutional amendments (13 articles amended, 22 new provisions), and the package of decentralisation and election laws that followed, lay the foundations for deeper, more relevant and progressive decentralization. Indeed, the changes (Table 1) passed into law have ramifications that go beyond the business of government alone, and have implications for the functioning of the polity, the various publics the polity is intended to serve, and for peacebuilding.

| Table 1: Key Features of the NEW Decentralization Reforms |  |
| --- | --- |
| What has changed | What remains the same |
| - Autonomy: Provinces and districts have been granted political and administrative autonomy. Municipalities already enjoy administrative, patrimonial and financial autonomy, while the districts will gain autonomy in 2024, - Powers of Assemblies: Provincial assemblies have power to dismiss Provincial Governors; and have regulatory and deliberative powers. - Elections: Provincial Governors will now be elected rather than appointed. Election will be on the basis of Head of list of winning party - Representation: Institutionalization of the office of Secretary of State. | - Structure: The new decentralisation laws do not alter the structure of the sub-national level of government - Natural Resource Management: Exclusive jurisdiction over natural resources and their management retained at central level - Powers of dismissal: Central government retains powers to dismiss assemblies, the governors and also retains the supervisory role of the lower levels of government. |

Realising the potential gains will likely be a complex process and require an approach that is informed by and nuanced in Mozambique’s political economy and governance landscape. Some of the key issues that will likely influence design of these policy and implementation arrangements are summarised below.

Resolving the ‘constructive ambiguities’ in legislation The Decentralization package is the outcome of a compromise political arrangement emanating from the peace and reconciliation Accord. Consequently, what appear to be omissions or absence of critical issues in legislation—or ‘constructive ambiguities’ as they are called—actually represent a deliberate political choice and a deliberate deferral of decisions and elaboration e.g. on the manner of exercising of and the limits to powers of dismissals of elected governments; and the legal and institutional mechanisms governing vertical and horizontal fiscal distribution. Historically, the conflation of the principle of autarquia with ‘autonomy’  has allowed the central government to include entities of indirect state administration (Article 74 of the Basic Law on the Organisation and Functioning of the Public Administration 7/2012), and minor public entities (Article 6), as autonomous forms of government, lumping them with municipalities. However, in the light of the new laws and with the gradual maturity of the institutional and political systems at all tiers, these ambiguities are certain to be addressed, and resolved.

The imperative of reducing inequities Inequalities and inequities dot Mozambique’s economic and governance landscapes. The positive effects of reduction in poverty by 1% every year between 2000-2015 has been offset by growing inequality, with wealthy households able to consume thrice the amount the bottom 40% consume and wide variation in the poverty across provinces (Figure 2). There is also a clear rural-urban divide, with poverty higher in rural than in urban areas; and the shared prosperity premium was negative between 2008 and 2014 (-3.9 percent). Furthermore, gender inequalities abound, with Mozambique ranked 138 out of 160 countries on the Gender Inequality Index and less than 10% municipalities have female mayors. Discovery of gas and expansion in the extractive industry as a whole has fuelled public expectations of shared prosperity and heightened the importance of decentralisation as a means of achieving greater equity in resource sharing, with greater finances being made available to local authorities and provinces to deliver better public services.. Experience from other countries underscores the importance for decentralization in Mozambique to help address issues of equitable resource sharing.

Table 2: Service Delivery Responsibilities in Mozambique

Overcoming the overlaps Mozambique’s decentralized governance is marked by several overlaps, either ordained by law or emanating from practice. First, there is a territorial overlap, resulting from absence of demarcation of territorial jurisdiction for districts, administrative posts and municipalities—this has implications not just in terms of responsibilities for delivery of public services, but also for land management, the power to tax, and to enforce tax compliance; second, there is functional overlap, with districts, municipalities, Local Organs of the State Administration (OLEs), SOEs and other service providers performing the same or similar functions (Table 2). In addition, the exact powers and functions of the Permanent Provincial Secretary appointed by the central government, need clarification. The new decentralization laws do not help clarify these overlaps and duality of service delivery responsibilities and lack of clarity on functional assignment exists across several areas (Annex 1); and third, there are accountability overlaps that spring from the territorial and functional ones. The government has already taken very important steps towards determining competencies of different levels of government, and these will need to be consolidated through enabling rules, regulations and procedures. For example, environment is a sector which is extremely important for Mozambique as a climate-vulnerable country. However, since the central, provincial and municipal levels all have mandates in environmental management, the need for clear demarcation of roles and determination of where the responsibility of different levels of government begin and end, is critical. Lack of clarity or a slow process on this demarcation will lead to weak implementation and institutional overlap.

Improving inter-governmental relations Although the law states that the transfer of powers from the State to the executive body of decentralized provincial governance is to be accompanied by a corresponding transfer of human, financial and patrimonial resources, decentralization inevitably brings in its wake, potential conflict and contestation over these transfers. Therefore,  strong and inclusive inter-governmental mechanisms will be essential for sustainability of the reforms, for political stability, and for ensuring coherence and complementarity in service delivery to replace conflict and contestation. This includes re-defining the fiscal inter-governmental relations in the form of vertical and horizontal distribution of fiscal powers and resources; inter-governmental dispute resolution; and representation of provincial, district and municipal levels on central coordination, decision making and planning fora.

The politics is rural, but the problems and potential are urban Nearly 70% of Mozambique’s population lives in rural areas and this creates political attention to be rural focused. However, although urbanization in Mozambique is slower than that in Sub-Saharan Africa, it has contributed substantially to reduction in poverty and to shifts in the economy’s structure from agriculture to the services sector. Cities also present greater economic opportunities and have the potential for accelerated growth. By 2040, UN-Habitat estimates that half the Mozambican population will live in cities, and nearly 80,000 new households will need to be accommodated annually. For this phenomenon to not turn into a crisis, city managers in the municipalities need to focus attention on creating quality jobs; improving public services like water and sanitation; reducing the number of people living in informal settlements; and strengthening rural-urban linkages to ensure that agriculture and rural areas are part of market-based connections that drive growth.

FIGURE 3

Source: Analysis of Social and Economic Sectors, UNICEF 2018

Finance has not followed function Issues of adequate financing lie at the core of the ability of local governments to deliver on their mandates. Typically, these mandates are under or unfunded, leading to erosion of trust in government, tensions between different tiers of government, and creating opportunities for rent-seeking behaviour and elite capture. Because there has been slow progress on fiscal decentralization, and owing to persistent capacity weaknesses for revenue mobilization, provinces, districts and municipalities are reliant heavily on fiscal transfers from the central government. Moreover, it is not just the quantum of financing, but its composition which is problematic: since 2008, capital investments have been declining, and recurrent expenditures rising (Figure 3); while in absolute terms the budgets have increased, the dual effect of inflation and currency depreciation mean that the purchasing power of budgets have declined and in real terms, allocation in social sectors are below the levels of 2014. Moreover, while district level allocations have been increasing at the cost of provincial allocations, which stand at 14.7% in the 2019 Budget Proposals compared to 18.8% for districts. Municipalities receive less than 2% of the budget. These issues point to one conclusion: if sub-national levels, including municipalities are to function effectively, they will require appropriate levels of financing. Furthermore, while allocation of FCA and FIIA are based on a formula, the actual allocations differ from the budget; there is lack of transparency on actual releases which appear to be based on discretion and thus negatively impacting budget predictability; criteria for some transfers such as those for the Road Fund are not made public; and similar kind of municipalities in the same province receive different levels of funding.

The newly autonomous provincial and district governments in particular will need to clarify the functional overlaps with municipalities and then arrive at budget allocations that allow them to deliver on their legal mandates. To succeed, the legal principle of transfer of financial and, if necessary, human and patrimonial resources along with transfer of competencies from State to local authorities, has to be enforced and fully applied.

The imperative of cementing the trust and peace nexus Trust deficits lead to conflict and lack of social cohesion, and are often the result, inter alia, of absence of transparency, asymmetric flows of information, or denial or difficulty in access to information. For example, municipalities where obtaining information is more difficult are the ones least trusted and perceived to be more corrupt. While Mozambique’s Constitution provides for the Right to Information as a fundamental human right (Article 48) and a Right to Information Law and Right to Information Regulation provide the legal framework, citizens’ ability to exercise this right is constrained by unfriendly procedures, lack of service delivery standards, and no provision for punitive measures against public agencies that refuse to provide information upon a citizen’s request. Similarly, Mozambique’s performance on budget transparency and public participation on budget preparation or its oversight, is weak (Figure 5) and there are curbs on freedom of expression through e.g. the hike in media licensing and accreditation fees that makes Mozambique the most expensive country in Africa for journalists and media outlets. Investing in trust building through strong accountability, transparency, and easier access to information is therefore a key determinant of the success of decentralization reforms. It is encouraging to note that government has made some positive strides in addressing this issue, for example through MAEFP’s National Information and Documentation Centre and MEF publishing Citizen’s Budgets, but greater focus is required to facilitate citizens’ access to information.

# Strategy (1/2 page - 3 pages recommended)

In line with the drivers that form the genesis of the recent Constitutional amendments and the legislation that followed, and in keeping with UNDP’s commitments and agreements under the United Nations Development Assessment Framework (UNDAF) and the UNDP Country Program Document (CPD), as well as drawing on UNDP’s robust global experience and expertise on decentralization reforms, a strategic framework is presented to underpin UNDP’s proposed support.

- APPROACH

Our approach is shaped by the intent to address issues both of policy, and of practice. We aim to achieve this through:

- Using a program, rather than project approach

The reforms require a medium to long term time frame for implementation, hence our support takes the shape of this DGPP Decentralized Governance Promotion Program (DGPP), which will form an integral part of the government’s National Program for Decentralization (PND) and enable UNDP to perform a range of functions and provide a variety of services to governments at all levels. From policy advice to resource mobilization, from capacity building to running policy experiments, the DGPP will act as a hub for systemic strengthening, knowledge creation, cross-sector, cross-organisation coordination and partnership building to help government achieve the objectives of the PND. Furthermore, in taking this program approach, the government and UNDP will be able to identify and integrate complementarities with its other ongoing or planned support to government, and embed dimensions of gender, human rights, and sustainable development.

- Building-in flexibility

Cognizant of the many complexities, sensitivities, competing and entrenched interests, and the range of issues (some key ones of which were outlined earlier), that will continue to play out, UNDP’s support through the DGPP Decentralized Governance Promotion Program (DGPP) will aim to be flexible in the way it helps government identify and respond to citizen needs and to internal demands for advisory support. Given the varying state of socio-economic, political economy and institutional development across the country, the Program proposes to not have a single, one-size-fits-all approach to supporting the reform implementation, and instead, to tailor UNDP support to specific conditions and to priorities of the government.

- Striving for osmosis of peacebuilding and inclusion

The latest iteration of decentralization reforms represent an opportunity to recalibrate State-Citizen relations and to employ governance instruments and mechanisms that serve to achieve osmosis of peace and inclusion in the decentralized governance model. Conceptually, these are central tenets of the reform agenda and will constitute an essential element of our work to reduce inequities and strengthen social cohesion.

- Supporting and deepening political leadership

Successful reforms are the result not of technical competence alone, but of strong and consistent political leadership.. The political maturity and vision showcased by Mozambique’s national level political leaders needs to cascade at all political levels, and through this Program, we will provide strong support for this process. This would include e.g. supporting the central line government in strengthening its legislative oversight, inter-governmental coordination and coherence functions; assisting central Ministries to strengthen their policy formulation capacities; targeted capacity building initiatives for the Office of Provincial Governor and the Provincial Assemblies, as well as for the Mayors and municipal councils. It is pertinent to point out that this proposed support falls under thematic area 1 of the Background Document: Policy, Legal and Administrative Reform of the Decentralization Framework, Intergovernmental Relations and Methodological Framework.

- Addressing gender and human rights issues

Despite extensive efforts by government, several issues persist with respect to women’s empowerment and inclusion; similarly in regard to citizen’s access to and ability to exercise, fundamental rights, such as the right to information and association, conferred upon them by the Constitution, challenges linger. This Program therefore actively seeks to support government in meeting these challenges, particularly in the context of their immediate relevance for peacebuilding efforts and in furtherance of thematic area 7 of the Background Document: Cross-cutting Issues

- Phasing of interventions

Given that a number of institutional, legislative and financing frameworks are in the process of being formulated or fine-tuned, we propose to phase the interventions under the Program to sync with the evolving maturity of the decentralized governance systems in the country. This would mean, for example, that we will assist the government in addressing the more complex issues such as inter-governmental relations in an orderly, organized manner through technical advisory services; help design and run policy experiments and pilots for innovative proposals, review their results and then scale; and attend to immediate and intermediate needs for systemic capacity development ab initio.

- Government to be in leadership role

In line with our program approach mentioned above, we aim to ensure that the Program is driven by the government, with UNDP performing the role of an engaged, active and able partner. The proposals under the Program are therefore designed to be embedded within government’s institutional architecture, with the DGPP becoming an instrument of operationalization of the PND. Wherever new institutional arrangements are proposed, a clear exit strategy would be indicated in their design.

- THEORY OF CHANGE

The efficacy and relevance of our proposed approach is dependent on how deeply it contextualizes a broad spectrum of issues and perspectives—political economy, inclusion, institutional—and how smartly it shapes the pathway for change (Figure 4).

- PILLARS

Support to the government under the DGPP is built upon three pillars:

Pillar 1:  Inclusion and Citizen Participation

As highlighted earlier, divides in terms of gender, inclusion, economic growth, and human development persist across Mozambique. These have eroded social cohesion in the country and led to deep fissures and drawing of boundaries.  The new decentralization reforms, however, have opened up possibilities and created space for bridging these divides and taking steps to transform them into dividends in terms of peace, creation and sharing of prosperity and more accountable, responsive governance. Our effort under this pillar would help government at all tiers, to identify instruments of inclusion, transparency, voice, and equity, which individually and collectively, yield the Peace Dividend. Similarly, in developing strategies that help local governments to unlock the full potential of local economies and to enable prosperity to be shared, the Program will strive to generate Economic Dividends through creating more jobs, promoting entrepreneurship and improving livelihoods, particularly for women; and by focusing on and incentivising inclusion and equity as key tenets of local governance, our support will target realisation of Governance Dividends.

Pillar 2: Response.Ability

The ability of government to respond to citizen’s needs, expectations and aspirations is often the missing link in good governance. Indeed, failure to be responsive and responsible in how government organises and delivers public services and how it ensures equality and equity in all its business, is a contributing factor to civil inequities. The focus under this pillar will therefore be on creating the requisite enabling environment which local governments need for moving from being legally empowered to being operationally able to plan and deliver more and better public services. These enablers—policies, subordinate legislation, strategies, plans, capacities, data and its use, coordination—are key for building citizen’s trust in the ability of local governments as viable, relevant entities. Furthermore, we will strive to help government invest in systemic capacities including but not limited to, developing information management systems; the ability to building data analytics capacity; introduce innovations of both process and approach, turning to tech-enabled solutions and inclusive planning and monitoring using crowd-sourced needs assessment and citizen’s reporting systems. And lastly, to make local governments more agile and responsive and to enable implementation of national policies, the Program proposes to assist  the central government in designing incentives for improving performance, which would take many shapes including Challenge Funds and incentive grants to top-up existing budgets, and recognition and reward for teams at local government level that meet specific targets. Following a phased implementation process, these incentive mechanisms will be implemented for priority policies and piloted in select provinces and municipalities during the tenure of this Program. Based on results, these mechanisms could be scaled in subsequent iterations of support to the government.

Pillar 3: Democratisation of Economic Opportunities

Mozambique is expected to receive a windfall of Foreign Direct Investment (FDI), in the range of $95 billion, over the next 25 years. It is imperative that sub-national governments are not only able to access their due share of the enhanced revenues that will result from these investments, but ensure that citizens and communities, particularly the vulnerable segments such as women and disabled, benefit through local economic development plans . Similarly, Mozambique’s cities and towns have been engines of growth, with 23 cities and key towns together accounting for 61.8% of GDP. However, while some cities such as Maputo receive substantial support e.g. from the World Bank in relation to urban development, most have weak capacities for conceiving and delivering local economic plans. This Program therefore proposes to strengthen in-house capacities of municipalities and provincial governments to regenerate local economies, harness the resources of private sector in their jurisdiction and facilitate local businesses and entrepreneurs to link with national, and regional markets. To build these capacities, UNDP will work with provinces and municipalities to elaborate these economic plans; facilitate market linkages within and outside the country including through UNDP’s centres focused on private sector development and with other UN agencies such as UNCTAD and ITC; and enhance competitiveness of cities through improving their business processes, rules and incentives as related to economic planning.

Link to UNDAF/CPD Outcomes

These three pillars are aligned with the 2019 Peace and Reconciliation Accord; will be implemented in accordance with plans and priorities under the government’s forthcoming five year government plan (PQG 2020-2024); UNDP’s programmatic priorities in Mozambique as articulated in the United Nations Development Assistance Framework (UNDAF) 2017-2020 and in particular Outcomes 2,4,6,8 and 9; the Istanbul Programme of Action for least developed countries; and echo the priorities under the UNDP Strategic Plan 2017–2020 covering (i) sustainable and inclusive economic transformation (prosperity); (ii) resilience and natural resources management (Planet); and (iii) good governance, peace and social cohesion (peace).

Targeting

Two types of outputs will be delivered through the DGPP: those which are common goods, relevant for all sub-national governments, particularly for the newly autonomous provincial governments e.g. legislation and administrative simplification ; and others which either target specific tiers or are to be phased in a manner that targets certain regions or tiers of government. The latter are indicated in the next section, but the selection of institutions, sub-national tiers or regions will be made in consultation with government.

# Results and Partnerships (1.5 - 5 pages recommended)

Expected Results

The components under each of the three pillars are described in detail below:

PILLAR 1:  INCLUSION AND CITIZEN PARTICIPATION

Three outputs are envisaged under Pillar 1:

Output 1: national committee on common interests IS ESTABLISHED and operationalized

Strong inter-governmental relations are key to a successful and enduring decentralized form of government. Institutional mechanisms that preserve and promote efficient and cooperation-based—as opposed to coercive or adversarial relations based—intergovernmental relations, can support both democracy, development and delivery of public services. During the course of delivering on their respective mandates, provinces, districts and municipalities will require both coordination as well as conflict-management. While the central government retains a tutelage role, there is a need to institute a mechanism for managing relations among and between the different tiers of government that includes representation from all the tiers. This would ensure that the mechanism is inclusive, and thus has greater political legitimacy as well as being more administratively efficient. To this end, the Program proposes to help establish a National Committee on  Common Interests. This Committee could be established either under the Office of the Prime Minister, or under the Ministry of State Administration and Civil Service (MAEFP), and serve as a platform for inter-governmental coordination, coherence and complementarity. This would enable the central government to facilitate and protect political, administrative and fiscal autonomy, while creating spaces for collaboration, competition and cohesion, as well as allow for strengthening and sustaining political leadership for the decentralization reforms. The draft composition of the Committee and its mandate (Annex 2) are intended to be as inclusive as possible, allowing for representatives of all tiers of government, as well as traditional leaders.

OUTPUT 2: OPEN GOVERNMENT PRINCIPLES IMPLEMENTED AT SUB-NATIONAL LEVELS

FIGURE 5

Source: open budget partnership 2017

From a peacebuilding and state building perspective, it is important the decentralization process is built on the foundations of transparency, ease of access to information, and public participation. To achieve this, government at all tiers would need to (i) follow the principle of transparency consisting in the obligation to publicize through print, electronic and social media and community meetings, various aspects of administrative activity through a Citizen Information Platform; (ii) ensuring justice and impartiality; (iii) basing decisions on principles of equality and proportionality; (iv) developing an Expanding Civic Participation Spaces Strategy that promotes citizens’ participation and engagement, including local communities, associations, private sector and other forms of organization aimed at defending community interests and solving their own community's problems. For example, province level committees for engaging with private sector representatives and district level community forums for identifying key issues would help empower citizens through creating multiple entry points for participation in budget processes, reporting on public investments and development works, and engagement with assemblies and officials; and (v) harnessing new technologies to strengthen governance and improve transparency under a Digital Democracy Initiative which would provide the public with a range of information on a voluntary disclosure basis accessible on mobile phones, websites, and social media; allow for citizen feedback on public services, public policies, budgets, and plans; enable Citizens’ Reports on development works; and serve as a platform for crowdsourcing ideas and community needs.

OUTPUT 3: strong public grievance redress for women and social accountability mechanisms

Formal justice systems in the country remain weak, expensive and delivery of justice is time consuming—for women, access to formal justice is more problematic than it is for men. Moreover, space for communities and civil society in relation to functioning of government, is limited. We propose two interventions to counter these gaps: first, we propose to support the establishment of a Women’s Ombudsman (WO) institution in select Municipalities and select Provinces. The WO would be established in select provinces and municipalities with the worst indicators on women’s empowerment and inclusion and will deploy staff and officers of the Office of the National Ombudsman. The WO will be focused on delivering administrative justice to women, as part of a government drive for gender-responsive accountability and its staff exposed to relevant capacity building and equipped with tools and techniques for handling women’s grievances.  Second, we propose the revival of Development Observatories, which were supported by the UNDP in the past, but which need to be revitalised in the wake of the new laws and reforms, and unlike its previous iteration, embedded within governmental structures. These  Observatories, which are also included as institutions for civic engagement under the forthcoming Localising the SDG’s Project, would provide for multistakeholder participation, fulfil a social accountability function,  and be established in select Municipalities and Provinces. Their role would broadly be to provide independent advice to Governors, and Mayors on development plans, budgets, and to perform civil society-led oversight on government functioning. The PND being developed by government includes this as Thematic Area 6: Participation.

PILLAR 2: RESPONSE.ABILITY

Pillar 2 encompasses four outputs:

Output 1: STRENGTHENED LAND MANAGEMENT AND MASTER PLANNING SYSTEMS IN DISTRICTS AND MUNICIPALITIES

Clear demarcation of geographic jurisdiction is essential for determining responsibilities for land management, taxation, and for planning and budgeting for public services. To support the government in this regard, and because we view this as a foundational issue for decentralized governance, the Program proposes to (i) strengthen district and municipality capacities for land management, including updating and modernization of land registries and land cadastres; (ii) development of Master Plans for select districts and municipalities; and (iii) provide the central government technical assistance for reviewing and where necessary, drafting legislation and implementation frameworks to achieve clarity in demarcation of  territorial jurisdiction. This intervention falls under Thematic Area 5: Planning and Territorial Planning, of the under development PND.

Output 2: ENABLING ENVIRONMENT CREATED FOR RESPONSIVE, AGILE SUB-NATIONAL GOVERNANCE

There is an immediate need for supporting government to create an enabling environment for sub-national governments and provide the operational basis to exercise the powers and responsibilities vested in them by law. This includes enabling legislation (including subordinate legislation); administrative procedures and their simplification; clarification of roles through rules of business; and resolving functional overlaps. As part of this enablement process, issues of accountability of government servants, their service structures (e.g. establishing sub-national cadres of civil service), and powers of appointments, postings and transfers (APT), would need to be examined and agreed with the central government. It cannot be stressed enough that creation of this enabling environment is a building block for effectiveness, efficiency and responsiveness of sub-national governments, hence this output is a high priority one. In addition, the Program will help establish and support a Provincial Policy Dialogue Forum, which would provide provincial governments an institutional platform for sharing of knowledge and best practice, as well as for coordination and collaboration. We aim to deliver this output through dedicated teams of international and local experts who will work closely with governments at all tiers to determine the scope, scale and sequencing of technical and advisory support. Furthermore, in relation to Fiscal Decentralization, the Program will support MEF in the design, elaboration and dissemination of methodologies and guidelines for PESOE; training of technicians at the level of provincial, district and local government OGDs; technical monitoring of the process of preparation of plans of provincial OGDs and local authorities; revision of revenue legislation; and design of the OGD's tax system. It will also assist in capacity building for medium-term projections to strengthen PESOE; conception and/or revision of methodologies for the elaboration of local development plans, and Citizens Budget for decentralized entities; and create capacity for implementing the Sustainable Development Goals at sub-national levels. As per the priorities of MEF, the Program will also assist to strengthen the role of the Economic and Social Council in relation to coordination of national strategies, plans and programs and in the clear orientation of public finances in the inter-ministerial groups created (GIDE, CIRAP etc).

OUTPUT 3: DECENTRALIZATION CAPACITY BUILDING FUND

Implementing the decentralization reforms entails consistent and considerable investment in strengthening institutional and systemic capacities across all tiers of government. The new functional mandates, powers, and the need to reorient public service delivery towards greater inclusion, accountability, and transparency necessitate bridging the capability gaps in sub-national governments. Moreover, the models of collaborative and participative forms of governance, and the need to plan and implement strategies for local economic development, call for new skills, competencies and behavioural changes. We therefore propose establishing a Decentralization Capacity Building Fund. This Fund (Figure 6) will be led and managed by government (MAEFP); will enable and facilitate government to deliver its Decentralisation Capacity Building Program; will move away from a training-focus and diversify the capacity building portfolio to target gaps related to the ability of government to use data; work closer with communities; to develop a culture for open, transparent and responsive governance and for continuous learning; and to have a two-fold focus in terms of its beneficiaries: civil servants for whom the Fund could play an important role  in capacity building through the government’s civil servant training institutions , and elected representatives at all tiers and particularly in Provincial and District Assemblies as well as Municipal Councils and Boards. Importantly, it will allow for a demand-driven and flexible capacity building process, allowing sub-national governments at all tiers to tap into a financial resource pool and gain access to TA services. Annex 3 indicates the management arrangements. The proposed distribution of shares of the fund across different levels of government will be finalized subsequently, but the majority share will be earmarked for provinces and districts.

MUNICIPALITIES’ SYSTEMIC DEVELOPMENT

PROVINCIAL  and District GOVERNMENTS’

SYSTEMIC DEVELOPMENT

provision of common goods and services BY MAEF

- Accessible by all Provinces and Districts

- Eligible purposes defined by MAEFP

- Brief Grey List of ineligible expenses (e.g. purchase of cars)

- Simple access procedures

- Data analytics, action research and policy analysis

- Communication, visibility and advocacy

- Mentoring, coaching service

50% of the

total Fund

15% of the

total Fund

- Upgradation of systems, knowledge and competencies

- Risk-based M&E, QA, business planning, delivery standards, performance measurement

- Accessible by all Municipalities

35% of the

total Fund

FIGURE 6: DECENTRALIZATION CAPACITY BUILDING FUND AT A GLANCE

ecentralization Capacity Development Fund to be seeded by the central Government

Capitalized through pooling contributions by development partners

and complemented and sustained through annual allocations in the budgets of all tiers

Managed by MAEFP through a Secretariat comprising MAEFP staff and UNDP Advisory Team

Output 4: Establishment and operationalization of An inter-governmental committee on FINANCE

With the grant of autonomy to sub-national levels, it is imperative that the intergovernmental mechanisms for fiscal transfers are strengthened and aligned with the new framework of decentralized government. In this respect, the two issues that this Program seeks to address are (i) transparency of process; and (iii) representation and inclusion of the sub-national governments in decision making on the fiscal distribution. The proposal therefore is to establish an Inter-Governmental Finance Advisory Committee under the Ministry of Economy and Finance, to serve as a forum on which sub-national governments, civil society, academia and private sector are represented and which provides advice to government on fiscal distribution and fiscal oversight systems.  Details are at Annex 4.

PILLAR 3: DEMOCRATIZING ECONOMIC OPPORTUNITIES

Three outputs are envisaged under Pillar 3:

OUTPUT 1: CENTRE FOR COMPETITIVE CITIES ESTABLISHED

Mozambique’s future—like that of most African countries—is urban. Economic growth in the country is reliant upon the ability of cities to sustain and enhance their contribution to GDP through creating jobs, attracting investments (including in urban infrastructure), and facilitating businesses. Cities need to be able to respond with agility and foresight to the evolving needs of citizens, businesses and other stakeholders, and to situate this response within a context of national, regional and global competitiveness. To help cities achieve this objective, we propose to establish a Centre for Competitive Cities, or C3 which will explore and advise on policy issues related to urban regeneration, competitiveness of cities and foster collaboration with national and international stakeholders. C3 is proposed to be established as a non-profit think tank as a joint venture between the UNDP, the National Association of Municipalities in Mozambique (ANAMM), the United Cities and Local Governments (UCLG), and business associations such as the Association of Informal Economy in Mozambique (AIEMO), and the Mozambican Federation of Employers’ Organisations (CTA). C3 will develop economic strategies for cities; carry out business outlook surveys; produce a City Competitiveness Index; and set up CreateSpace, an incubator and co-working platform for collaboration and co-creation of solutions for improving urban governance and local area development. The Centre is expected to become progressively self-sustaining, hence financial support will follow a tapering trend. Annex 5 provides more details.

OUTPUT 2: IMPLEMENTATION OF LOCAL ECONOMIC PLANS WITH STRONG WOMEN’S ECONOMIC EMPOWERMENT  FOCUS

Sub-national governments are charged with the responsibility to develop plans for local economic development. To ensure that these plans address issues of women’s low employment, inability to exercise rights over assets such as land, and to start and operate a business, this Program proposes to support development and implementation of local economic development plans that have a special emphasis on women’s economic empowerment, including through : (i) an Inclusive Employment Pledge through which local employment of females in businesses operating at the local level, rises; (ii) a Local Content Pact which assigns women-owned businesses with a Preferred Vendor status in procurement of goods and services by the private sector; (iii) special initiatives for  improving women’s access to credit, improve their financial literacy and deepen their financial inclusion; and (iv) linking local women entrepreneurs with national and regional markets in partnership with the International Trade Centre’s SheTrades Initiative.

OUTPUT 3: affirmative action plan and incentives for VULNERABLE SEGMENT-FOCUSED investments

Vulnerable segments of Mozambique’s population experience different forms of exclusion. Women’s employment is very low, at 27% in the formal economy, 62% are financially excluded, and they lead lives as part of a highly patriarchal culture; disabled people make up 2.5% of the country’s population and although there is a National Disability Strategy, their employment and civic participation is low; and nearly 40% youth are unemployed. To address these issues, the Program proposes two interventions: (i) development and implementation of an Affirmative Action Plan for all sub-national governments, which would set out job quotas in the government service for women, minorities, youth and the disabled; and (ii) to incentivise vulnerable segment-focused public investment and strategies aimed at their economic empowerment, through a mix of conditional grants and Challenge Funds, designed in conjunction with the Ministry of Economy and Finance. Grants would be awarded on a competitive basis, to sub-national governments that meet defined performance criteria or develop proposals in priority areas such as enhancing women’s resilience to disasters, improving access to and quality of healthcare and security of women, and improving livelihood opportunities for youth and minorities etc. and will top-up regular budgetary resources.

Resources Required to Achieve the Expected Results

The total estimated resource required for the Program is US$60.5 million. UNDP has already started closer consultation and negotiations with the government and key donor partners on key issues that the Program  aims to tackle. Detailed breakdown of the resources plan can be found in the Results and Resources Framework section of the document.

Budget planning will be informed by UNDP´s guidelines as outlined in the Programme and Operations Policies and Procedures and implemented through UNDP´s financial and planning tool, ATLAS. The standard corporate and local pro-forma costs will apply. In all its financial investments, UNDP applies value for money principles and aligns with international best practice on procurement, human resources management and risk assessment [annual financial and performance audits].

In implementing this program, UNDP Mozambique will be tapping into UNDP’s global and regional policy networks, including those experts who have supported such complex initiatives related to DDR, conflict prevention and deepening decentralization in similar development setting as in Mozambique.

Partnerships

UNDP’s work under this program will be coordinated with other UN entities and government counterparts, as well as key international and local partners. UNDP intends to work closely withUNCDF, who have rich experience supporting integrated local governance and local development processes. In addition, we intend to establish partnerships with UCLG, ITC, World Economic Forum, and a number of local stakeholders in private sector, civil society, the local startup ecosystem, and with academia.

Risks and Assumptions

The table below summarises the various risks for this program and proposes mitigation strategies:

| Risks | Mitigation measure |
| --- | --- |
| Political Risks |  |
| National level political support for decentralization wanes | UNDP will undertake policy advocacy to ensure that political leadership is engaged and continues to support the decentralization process |
| Enmeshed party and State structures make accountability challenging | Ensure that political economy analysis forms part of the implementation plans and that accountability systems are supported that drive better accountability within political parties as well |
| Political interference in recruitments, procurements | Ensure complete transparency in all contracting by following the rules and procedures of government and/or UNDP as the case may be |
| Systemic Risks |  |
| Central government either does not allow sub-national governments to function, encroaches upon their mandates, or does not cooperate | UNDP will undertake continuous dialogue and policy advocacy with all stakeholders in government and other sectors, to strive to ensure that independence, autonomy and institutional integrity of sub-national governments is respected, protected and promoted |
| Absence of legislative oversight | UNDP to undertake policy advocacy and engage with central government cabinet members as well as with the President, to promote adequate levels of legislative accountability |
| Weak institutional and operational capacities of local actors and beneficiary groups may slow local ownership of the program approach and interventions | Incorporate institutional and operational capacity-building actions into the implementation of the program |
| Resource and Resource Management Risks |  |
| Resource availability: This proposal is built on the assumption that additional resources necessary to move forward long-term engagement and programs will be mobilized from donors | UNDP Mozambique to engage in continuous resource mobilization at country level; UNDP HQ to ensure support to resource Mobilization with donor capitals; UNDP to better position itself within the humanitarian community and coordinate closely with the aid community. |
| Civic Participation Risks |  |
| Community and local stakeholders’ empowerment is weak and in particular participation of women may be limited by social norms and practices | UNDP and government to work together to reinforce the imperative of community engagement, and putting in place measures to transform gender and power relations, working with traditional and local leadership structures |
| Private sector interest in working with sub-national governments is weak | UNDP will engage with key stakeholders in the private sector to facilitate close working relations with sub-national governments |
| Implementation Risks |  |
| UNDP role/space within the international configuration: as the situation on the ground evolves, UNDP will need to re-evaluate its space/role vis-à-vis other players. | UNDP will engage in close coordination and information exchange with other international organizations present on the ground. The CO and the Regional Bureau share up-to-date information on the UN configuration and implication for programming. |
| CO’s delivery capacity is weakened due to a significant increase in interventions under different thematic portfolios | Sequencing of the activities is key to ensure CO’s delivery capacity. Additional technical staff (including Senior Policy Advisor, local governance, finance, M&E and gender advisors) will be embedded within the government partner agencies, in particular MAEFP, MEF and MITADER , for the duration of the intervention. |
| Environmental Risks |  |
| Program implementation leads to | UNDP and government to ensure that guidelines, standards and safeguards for environmental protection are followed in every sphere of program activity. |

Stakeholder Engagement

This Program is the outcome of consistent dialogue and engagement with government, including at political and senior management levels in MAEFP, MEF, Ministry of Defence; agencies such as INGC; and with a range of development partners both through the Development Partners’ Decentralization Working Group, as well as through bi-lateral engagement. The proposals included in this Program are in line with the Decentralization Package, fully aligned with and respond to government’s needs as articulated in the draft National Program for Decentralization; and complement support provided by other development partners, both within and outside the UN system. . The Program interventions call for engagement with a diverse set of communities, associations and civil society, and will ensure that they have access to and are aware of mechanisms to submit concerns about the social and environmental impacts of a project (e.g. UNDP’s Social and Environmental Compliance Review and Stakeholder Response Mechanism). A mapping of support provided by or planned to be provided by, development partners is at Annex 5.

South-South and Triangular Cooperation (SSC/TrC)

UNDP supports South-South and triangular learning and cooperation, including by sharing knowledge, research and best practices on policies, programmes and strategies and by facilitating research and exchanges among partners from different countries and regions as well as regions, cities and municipalities facing similar development challenges. UNDP has a number of long-term strategic relationships with established development policy and research institutes, including regional bodies.

Knowledge management

The program will produce several knowledge and advocacy products for both global and regional outreach and local use. All products will ensure acknowledgement on bilateral and multilateral donor contributions and high-visibility of impact.

Sustainability and Scaling Up

Sustaining peace and recovery in the country is the main focus of the interventions. It should be noted that while UNDP support for decentralization will likely go beyond the tenure of this Program, a conscious effort has been made in the design to (i) put government in the driving seat as the implementor of the Program, with UNDP technical support embedded within key government institutions; (ii) give Government control over management of most institutional arrangements (e.g. Committees on Common Interests and on Inter-Governance Finance) from the start; and (iii) provide for a phased handing over of management and financing responsibility for various interventions (e.g. Centre of Competitive Cities which is intended to achieve incremental financial sustenance).. Throughout all the interventions, capacity development in terms of putting in place systems, mechanisms and capabilities defines UNDP’s approach and will contribute to sustainability and scaling up.

# Project Management (1/2 pages - 2 pages recommended)

Cost Efficiency and Effectiveness

The program approach proposed under the DGPP is intended to enable integration and linkages with a range of other interventions under implementation to  achieving the overall expected result of building a peaceful, just and inclusive society in Mozambique. This approach is intended to reduce the transaction costs of project designing, monitoring, implementing, overseeing and reporting, as many required functions are done for the portfolio instead of separately for each project. Portfolios are also intended to improve the integration of projects that contribute to shared results, as they are managed more closely together.

Project Management

The project will be implemented under a National Implementation Modality (NIM). The Ministry of State Administration and Civil Service (MAEFP) is proposed as the Implementing Partner. UNDP, in collaboration with MAEFP and sub-national governments will identify Responsible Parties to carry out specific activities (all such Responsible Parties will be accountable to MAEFP in accordance with the terms of the signed responsible party agreement or contract), with UNDP providing technical support for effective management, reporting and accountability.

To assist MAEFP in implementation and to provide high-level policy advice, UNDP will hire a team of international and local experts on local governance, finance, gender and inclusion, and M&E. This team will be led by a Senior Policy Advisor, who, along with the team, will assist MAEFP in not just program implementation, but in Quality Assurance; Monitoring & Evaluation; policy dialogue; risk management; reporting on progress; and partnership building. Along with nominated MAEFP staff, this team will constitute the Secretariat for this Program and also manage the Decentralization Capacity Development Fund.

Senior Policy Advisor (International): The Senior Policy Advisor (SPA) will be a highly experienced expert with vast experience of high level advisory services and team leadership. S/He will serve as the principal technical advisor and overall coordinator of the Program and will be responsible for ensuring that the Program retains its strategic focus; provide senior level advisory support to government; ensuring the coherence and implementation of all components of the Program in accordance with the agreed priorities of government; take a lead coordinating role in consultations and coordination with government at all tiers and with other stakeholders; assist the government in overseeing the work of other advisors and consultants; and help ensure that the Program is well coordinated with other initiatives implemented by the government, other UN agencies and development partners.

Social Cohesion and Decentralization Specialist (SCDS): The SCDS will be an experienced local expert, with substantial understanding, knowledge and experience of decentralization, peace building and community engagement. S/He will assist the government and the SPA on policy dialogue, stakeholder engagement and for analytical work related to decentralization, S/He will also assist in coordinating with sub-national governments and officials.

Gender Analyst: The Gender Analyst will be responsible for providing advice and assistance on design, implementation and monitoring of the Program interventions as they relate to gender. S/He will work closely with government at all tiers to ensure that plans, projects and budgets are gender sensitive and gender focused. In particular, S/He will provide advice to sub-national governments on the local economic plans, on developing the Affirmative Action Plans, Local Content initiative and supporting women-owned SMEs.

Human Rights Analyst: S/He will be responsible for providing advice and assistance on ensuring that Program interventions incorporate human rights, inclusion and participatory elements. In particular, the Human Rights Analyst will work closely with government at all tiers on helping develop inclusive platforms for citizen engagement; mechanisms for enhanced transparency and access to information; and institutional arrangements for addressing needs of vulnerable segments including the disabled, youth and minorities. S/He will work closely with government and civil society organizations to support training, data collection and monitoring, reporting, as well as initiatives related to human rights awareness in the context of decentralization.

Communication Analyst: The Communication Analyst will develop and implement a variety of communication tools to create awareness, raise visibility of the government efforts to improve decentralize governance, and to inform and engage various audiences including the public;  government officials and political leaders at all levels; businesses; development partners; and civil society. The Analyst will support the government in the design and organization of visibility, advocacy and information sharing events and also provide inputs to content of publications, digital assets (websites, blogs, podcasts, social media messaging).

Monitoring & Evaluation (M&E) Analyst: S/He will be responsible for developing an M&E framework in line with the Results Framework of the Program. This would include the systems, tools, and mechanisms for collecting, analysing and dissemination of data and evidence; assisting the Finance and Planning officials at all tiers of government on improving the quality and use of data to inform decisions and monitor the effect of interventions not just under this Program, but more widely; and to advise on improvement of government’s M&E frameworks in terms of their scope, relevance and integrity.

MAEFP Support: MAEFP will appoint a Program Manager, not below the level of a Director, along with other technical staff. It will also provide office space for the Program Team hired by UNDP to enable close, daily collaboration and coordination with the MAEFP officials. Staff appointed and office space

Project Support staff:

The 3 project managers will have the main responsibility to ensure that the results of the project are carried out. These will be assisted by a team consisting of:

- A financial manager for the results in the area of justice (given the complexity of actors and although there are few funds, it is required that the financial management of the project is done by a financial manager

- An administrative assistant for the area of justice (it will be necessary to have an administrative assistant to the judiciary, given the need for contact in the day to day with different actors in the sector (Supreme Court, RMP, IPAJ, SERNAP, palaces of justice, etc.) and shares of Following

- A financial and administrative assistant to the police

- A driver for Justice, responsible for expedient and transportation

Various monitoring mechanisms will be used to monitor that the project is making progress towards intended outputs, resources entrusted to UNDP and partners are utilized appropriately; ensure that there is continued national ownership, ongoing stakeholder engagement and sustainability and the project’s outputs contribute to intended country programme outcomes. Monitoring mechanisms and tools will include regular [quarterly] progress reporting, risk logs, field visits, annual reports and reviews as per established project management standard of UNDP. All project supervision and evaluation components will comply with UNDP rules and regulations as outlined in the POPP in the section on programme and project management.

Various monitoring mechanisms will be used to measure project progress against desired outcomes, resources entrusted to UNDP and whether partners are used appropriately; ensure continued national ownership, stakeholder involvement and sustainability, and that short-term project outcomes contribute to national program outcomes. Monitoring mechanisms and tools will include regular [quarterly] progress reports, risk records, field visits, annual reports and reviews in accordance with UNDP's established project management standard. All project supervision and evaluation components will comply with UNDP rules and regulations as described in the POPP in the program and project management section.

UNDP will also ensure financial safeguards and due diligence with regards to risk and capacities assessment of selected partners under the Harmonized Approach to Cash Transfer (HACT) Framework. According to the UNDP regulations and procedures, partners that are expected to receive more than US$ 300,000 in cash transfer during the programme cycle are required to undergo capacity assessments and assurance activities. Collaborations below such threshold are also subject to financial capacity assessments and assurance activities if deemed necessary. Project partners should also be aware that the project implementation must comply with and be subject to internal control and audit requirements as per UNDP’s rules, regulations and procedures.

# Results Framework

| Intended Outcome as stated in the UNDAF/Country [or Global/Regional] Programme Results and Resource Framework: UNDAF Outcome 2: Poor People Benefit Equitably from Sustainable Economic Transformation UNDAF Outcome 4: Disadvantaged Women and Girls Benefit from Comprehensive Policies, Norms and Practices that Guarantee their Human Rights UNDAF Outcome 6: People Equitably Access and Use Quality Health, Water and Sanitation Services UNDAF Outcome 8: All people benefit from democratic and transparent governance institutions and systems that ensure peace consolidation, human rights and equitable service delivery UNDAF Outcome 9: Most Vulnerable People in Mozambique Benefit from Inclusive, Equitable and Sustainable Management of Natural Resources and the Environment |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome indicators as stated in the Country Programme [or Global/Regional] Results and Resources Framework, including baseline and targets: Indicator 1. Voter turnout in parliamentary elections (Baseline: 48,84%; Target: 58%) Indicator 2. Open budget index value (Baseline: 38 (2015); Target: 45) Indicator 3: Overall ranking in the Mo Ibrahim African Governance index (Baseline: 52.3 (2015); Target: 54) |  |  |  |  |  |  |  |  |  |  |  |
| Applicable Output(s) from the UNDP Strategic Plan: Related strategic plan outcome 2. Citizen expectations for voice, development, the rule of law and accountability are met by stronger systems of democratic governance |  |  |  |  |  |  |  |  |  |  |  |
| Project title and Atlas Project Number: |  |  |  |  |  |  |  |  |  |  |  |
| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | ## TARGETS (by frequency of data collection) |  |  |  |  |  | ## DATA COLLECTION METHODS & RISKS |
|  |  |  | Value | Year | Year 1 | Year 2 | Year 3 | Year 4 | Year … | ## FINAL |  |
| PILLAR 1: INCLUSION AND CITIZEN PARTICIPATION |  |  |  |  |  |  |  |  |  |  |  |
| Output 1 National Committee on Common Interests is established and operational | 1.1 Institutional framework for the National Committee on Common Interests is developed and approved | MAEFP UNDP | Non-existent | 2019 | drafted | approved | - | - | - | Approved |  |
|  | 1.2 The National Committee on Common Interests is established and operational | MAEFP UNDP | Non-existent | 2019 | Composition formally established as per annex 2. | Committee fully operational | - | - | - | Committee fully operational | Reports of the Committee officially published; |
| Output 2 Open Government Principles implemented at sub-national levels | 2.1 Number of provinces, districts and municipalities officially committed to Open Government. Target is a third of total number in the country | Sub-national Governments UNDP | 0 | 2019 | Open Government Pledge ready; 50% of targeted governments make formal commitments and implement the Open Government principles as enunciated under the Open Government Partnership initiative | 100% of targeted governments make formal commitments and implement the Open Government principles as enunciated under the Open Government Partnership initiative | - | - | - | 100% of targeted governments make formal commitments |  |
|  | 2.2 Number of provinces, districts and municipalities implementing the Expanding Civic Participation Strategy. Target is a quarter of total number in the country | Sub-national Governments MAEFP UNDP | 0 | 2019 | Strategy developed and published; Strategy implemented in 50% of targeted governments | Strategy implemented in 75% of targeted governments | Strategy implemented in 100% of targeted governments | - | - | Strategy implemented in 100% of targeted governments |  |
|  | 2.3 Digital Democracy Initiative launched and digital platforms for citizen feedback, reporting and crowdsourcing are operational | Sub-national Governments UNDP Private Sector Telecom Companies CSOs | Non-existent | 2019 | In beta stage. | Fully operational | - | - | - | Fully operational |  |
| Output 3 Strong Public Grievance Redress and Social Accountability Mechanisms | 3.1 Number of provinces, districts and municipalities with established Women’s Ombudsman institution | National Ombudsman Sub-national Governments UNDP | 0 | 2019 | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | 03 province; 10 districts; 03 municipalities |  |
|  | 3.2 Number of provinces, districts and municipalities with established and operational Development Observatories | Sub-national Governments UNDP | 0 | 2019 | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | 05 province; 25 districts; 10 municipalities |  |
| Output 4 Affirmative Action Plan and Incentives for Women, youth and vulnerable group-focused Investments | 4.1 Number of provinces, districts, and municipalities implementing the Affirmative Action Plan | MITESS MINED MAEFP MGCAS Sub-national Governments UNDP | 0 | 2019 | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | 3 provinces, 25 districts, and 10 municipalities |  |
|  | 4.3 Number of provinces, districts and municipalities benefiting from Conditional grants | MAEFP MGCAS UNDP | 0 | 2019 | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities |  |
|  | 4.4 Number of provinces, districts and municipalities, with worst indicators in terms of gender empowerment and inclusion, benefiting from Challenge Funds | MAEFP Sub-national Governments UNDP | 0 | 2019 | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | 5 provinces, 25 districts and 15 municipalities |  |
| PILLAR 2: RESPONSE.ABILITY |  |  |  |  |  |  |  |  |  |  |  |
| Output 1 Strengthened land management and Master Planning systems in districts and municipalities | 1.1 Number of districts and municipalities engaged with improved land cadastres and land registries | MJCR MAEFP MITADER UNDP | Non-existent | 2019 | Drafted | In force | - | - | - | In force |  |
|  | 1.2 Number of districts and municipalities with Master Plans developed | Sub-national Governments MAEFP UNDP | 0 | 2019 | xx districts and xx municipalities | xx districts and xx municipalities | xx districts and xx municipalities | xx districts and xx municipalities | xx districts and xx municipalities | 05 districts and 05 municipalities |  |
| Output 2 Enabling environment for responsive, agile sub-national governance | 2.1 Enabling legislation is drafted and enacted | MJCR MAEFP National Assembly UNDP | Non-existent | 2019 | Drafted | Enacted | - | - | - | Enacted |  |
|  | 2.2 Number of provincial governments benefiting from own-designed ‘Rules of Business’ | Provincial Governments MAEFP UNDP | 0 | 2019 | Xx of provincial governments | Xx of provincial governments | Xx of provincial governments | Xx of provincial governments | Xx of provincial governments | Xx of provincial governments |  |
|  | 2.4 New/revised legislation with clear description of functions and jurisdictions at national and subnational government levels. | MAEFP MCJR Sub-national Governments UNDP | Non-existent | 2019 | - | Drafted/revised | Approved and in force | - | - | Approved and in force |  |
| Output 3 Decentralization Capacity Building Fund | 4.1 Rules of eligibility, access and use are developed and approved | MAEFP UNDP | Non-existent | 2019 | Drafted | Approved | - | - | - | Approved |  |
|  | 4.2 Contribution made by the government and development partners to capitalize the Fund | MAEFP MEF Development Partners UNDP | 0 | 2019 | tbc | tbc | tbc | tbc | Tbc | 15% by the government of total amount agreed; 85% by development partners of total amount agreed |  |
|  | 4.3 Number of sub-national governments accessing financial resources from the Fund | Sub-national government MAEFP MEF UNDP | 0 | 2019 | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities | X province; X districts; X municipalities |  |
| Output 4 Establishment and operationalization of the Inter-Governance Finance Committee | 5.1 TOR and composition of the Committee is drafted and approved | MEF UNDP | Non-existent | 2019 | Drafted | In force | - | - | - | In force |  |
|  | 5.2 Annual Reports of the Committee are published | MEF | 0 | 2019 | 0 | 0 | 1 | 0 | 0 | 1 |  |
| PILLAR 3: DEMOCRATISING ECONOMIC OPPORTUNITIES |  |  |  |  |  |  |  |  |  |  |  |
| Output 1 Centre for Competitive Cities (CCC) | 1.1 The Centre is established as a non-profit organisation and becomes operational | MEF ANAMM MAEFP UNDP | Non-existent | 2019 | NPO legally constituted | NPO operational as CCC | - | - | - | NPO operational as CCC |  |
|  | 1.2 Number of municipalities benefiting from economic strategy developed with support from the CCC | CCC | 0 | 2019 | 0 | 1 | 2 | 1 | 1 | 5 |  |
|  | 1.3 Number of Business Outlook Surveys conducted | CCC | 0 | 2019 | 0 | 0 | 1 | 1 | 0 | 2 |  |
|  | 1.4 The City Competitiveness Index is developed and published at least once | CCC | Non-existent | 2019 | Index developed | - | - | 01 Index publication | - | 01 Index publication |  |
|  | 1.5 Number of municipalities with established CreateSpace co-working places and Incubators | CCC | 0 | 2019 | 0 | 1 | 2 | 2 | 1 | 5 |  |
| Output 2 Women’s Economic Empowerment through Local Economic Plans | 2.1 Number of provinces and municipalities that developed and implemented a Women’s Economic Empowerment Plan | Subnational Governments MEF UNDP | 0 | 2019 | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | 05 provinces; 05 municipalities |  |
|  | 2.2 Number of provinces and municipalities that developed and implemented the Inclusive Employment Pledge | Subnational Governments MEF Businesses and Business Associations UNDP | 0 | 2019 | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | 05 provinces; 05 municipalities |  |
|  | 2.3 Number of provinces and municipalities that developed and implemented Local Content Pact for women-owned vendors | Subnational Governments MEF Businesses and Business Associations UNDP | 0 | 2019 | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | 05 provinces; 05 municipalities |  |
|  | 2.4 Number of provinces and municipalities that develop and implement special initiatives for women owned businesses and female entrepreneurs | Sub-national governmentsMEF UNDP | O | 2019 | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities | xx provinces; xx municipalities |  |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans: [Note: monitoring and evaluation plans should be adapted to project context, as needed]

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. |  |  |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. |  |  |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. |  |  |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. |  |  |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. |  |  |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) |  |  |  |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Specify frequency (i.e., at least annually) | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. |  |  |

Evaluation Plan

| Evaluation Title | Partners (if joint) | Related Strategic Plan Output | UNDAF/CPD Outcome | Planned Completion Date | Key Evaluation Stakeholders | Cost and Source of Funding |
| --- | --- | --- | --- | --- | --- | --- |
| Mid-Term Evaluation |  | 2 | 2, 4, 6, 8, 9 | February 2022 |  | 150,000 |
| Terminal Evaluation |  | 2 | 2, 4, 6, 8 , 9 | April 2024 |  | 150,000 |

# Multi-Year Work Plan

All anticipated programmatic and operational costs to support the project, including development effectiveness and implementation support arrangements, need to be identified, estimated and fully costed in the project budget under the relevant output(s). This includes activities that directly support the project, such as communication, human resources, procurement, finance, audit, policy advisory, quality assurance, reporting, management, etc. All services which are directly related to the project need to be disclosed transparently in the project document.

| EXPECTED OUTPUTS | PLANNED ACTIVITIES |  | Planned Budget by Year |  |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5 |  | Funding Source | Budget Description | Amount |  |  |
| Pillar 1: INCLUSION AND CITIZEN PARTICIPATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1 National Committee on Common Interests is established and operationalised Gender Marker: GEN 2 | Activity 1: Support provided for finalizing composition and TOR of the Committee and for creating awareness about its formulation and its mandate |  | 60,000 |  |  |  |  |  |  |  | 60,000 |  |  |
|  | Activity 2: Administrative, logistical and technical assistance to ensure full functionality of the Committee |  | 60,000 | 60,000 | 50,000 | 50,000 | 50,000 | UNDP |  |  | 250,000 |  |  |
| Output 2 Open Government Principles adopted and implemented at sub-national levels Gender Marker: GEN 2 | Activity 1 TA provided for developing plans for Open Government and for advocacy with Sub-National Governments (SNGs) to implement principles, including for designing the mechanisms for the Citizen Information Platform |  | 60,000 | 40,000 |  |  |  | UNDP |  |  | 100,000 |  |  |
|  | Activity 2 Monitoring of progress on the implementation of Open Government Principles and publishing of report on the state of play |  |  | 90,000 | 90,000 | 90,000 | 90,000 | UNDP |  |  | 360,000 |  |  |
|  | Activity1 Team hired and deployed for developing digital tools and online dashboards enabling and facilitating citizen feedback, reporting and crowdsourcing of needs |  | 750,000 | 500,000 | 500,000 | 500,000 | 350,000 | UNDP |  |  | 2.6m |  |  |
|  | Activity 2 Monitoring and reporting progress |  |  | 100,000 | 100,000 | 100,000 | 100,000 | UNDP |  |  | 400,000 |  |  |
| Output 3 Strong Public Grievance Redress for Women and Social Accountability Mechanisms Gender Marker: GEN 3 | Activity 1 TA for establishing Women’s Ombudsman institution in at least 3 provinces, 10 districts and three municipalities |  | 200,000 | 200,000 | 200,000 | 200,000 | 200,000 | UNDP |  |  | 1m |  |  |
|  | Activity 2 Annual Report of the Women’s Ombudsman published |  | 30,000 | 30,000 | 30,000 | 30,000 | 30,000 | WO and UNDP |  |  | 150,000 |  |  |
|  | Activity 3 TA for operationalizing Development Observatories in at least 5 provinces, 25 districts and 10 municipalities |  | 500,000 | 500,000 | 500,000 | 500,000 | 500,000 | MAEFP, MEFP and UNDP |  |  | 2.5m |  |  |
|  | Activity 4 Mid Term Assessment of the functioning of the Development Observatories |  |  |  | 55,000 |  |  |  |  |  | 55,000 |  |  |
| Output 4 Affirmative Action Plan and Incentives for women, youth, disabled, and minorities-focused Investments Gender Marker: GEN 3 | Activity 1¨ AT support provided for developing an Affirmative Action Plan and for supporting implementation in at least 3 provinces, 25 districts, and 10 municipalities |  | 125,000 | 100,000 | 100,000 | 100,000 | 100,000 | UNDP |  |  | 525,000 |  |  |
|  | Activity 2 Conditional grants designed by expert hired by UNDP; approved by MEFP, and provision made in the budget and grants implemented |  | 2m | 1.5m | 1.5m | 1.5m | 1.5 m | UNDP |  |  | 8m |  |  |
|  | Activity 3 TA support provided for designing, implementing and monitoring Challenge Funds in at least 5 provinces, 25 districts and 15 municipalities with worst indicators in terms of empowerment, and inclusion |  | 1m | 750,000 | 750,000 | 750,000 | 750,000 |  |  |  | 4m |  |  |
|  | Sub-Total Pillar 1 |  |  |  |  |  |  |  |  |  |  | 20m |  |  |  |
| PILLAR 2: RESPONSE.ABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1 Strengthened land management and Master Planning systems in districts and municipalities Gender Marker: GEN 2 | Activity 1 Experts hired by UNDP to support sub-national governments in strengthening their Land Cadastre and Land Registration systems and processes |  | 200,000 | 300,000 | 300,000 | 300,000 | 300,000 |  |  |  | 1.4m |  |  |
|  | Activity 2 TA support provided to at least three sub-national governments to develop Master Plans |  | 75,000 | 125,000 | 125,000 | 125,000 | 125,000 | UNDP |  |  | 575,000 |  |  |
|  | Activity 3 TA mobilized to undertake review of legal and institutional frameworks for land demarcation |  |  | 50,000 | 50,000 | 50,000 | 50,000 |  |  |  | 200,000 |  |  |
| Output 2 Enabling environment for responsive, agile sub-national governance Gender Marker: GEN 2 | Activity 1 Package of enabling legislation is drafted by team of governance and legal experts hired by UNDP |  | 200,000 | 50,000 |  |  |  |  |  |  | 250,000 |  |  |
|  | Activity 2 Simplification of administrative procedures is undertaken by a team of experts hired by UNDP for priority administrative areas determined through consultation between central and sub-national governments |  | 200,000 | 100,000 | 75,000 |  |  |  |  |  | 375,000 |  |  |
|  | Activity 3 Rules of Business for provincial governments developed by expert hired by UNDP |  | 40,000 | 20,000 |  |  |  |  |  |  | 60,000 |  |  |
|  | Activity 4 TA provided by UNDP ot identify functional overlaps between central and sub-national governments and support amendments in relevant legislation |  | 200,000 | 150,000 | 50,000 |  |  |  |  |  | 4500,000 |  |  |
|  | Activity 5 TA provided to help set up the Provincial Governors’ Dialogue Forum and propose its structure and mechanisms for its operation and sustainability |  | 100,000 | 50,000 |  |  |  |  |  |  |  |  |  |
| Output 3 Decentralization Capacity Building Fund Gender Marker: GEN 2 | Activity 1 Rules of eligibility, access and use are developed by an expert hired by UNDP and approved by MAEFP and MEFP |  | 30,000 | 10,000 |  |  |  |  |  |  | 40,000 |  |  |
|  | Activity 2 Seeding of the Fund by government (15%) and capitalising of the fund by development partners (85%) is completed |  | 4m | 6m | m | m | 4m |  |  |  | 25m |  |  |
|  | Activity 3 The Fund is operationalised, and sub-national governments begin to access and use the financial resources and their results are regularly monitored |  | 100,000 | 75,000 | 75,000 | 75,000 | 75,000 |  |  |  | 400,000 |  |  |
| Output 5 Establishment and operationalization of Inter-Governmental Finance Committee Gender Marker: GEN 2 | Activity 1 TA support for drafting TOR and composition of the Committee and assist in its notification subsequently |  | 60,000 | 15,000 |  |  |  |  |  |  | 75,000 |  |  |
|  | Activity 2 The Committee is operationalised and produces analytical and oversight reports |  | 100,000 | 100,000 | 100,000 0,000 | 100,000 0,000 | 100,000 ,000 |  |  |  | 500,000 |  |  |
|  | Activity 3 TA support to the Secretariat of the Committee for research and analysis, communication and stakeholder engagement |  | 100,000 | 100,000 | 100,,000 | 100,000 | 100,000 |  |  |  | 500,000 |  |  |
| Sub Total Pillar 2 |  |  |  |  |  |  |  |  |  |  |  | 30m |  |  |  |
| PILLAR 3: DEMOCRATISING ECONOMIC OPPORTUNITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1 Centre for Competitive Cities (CCC) Gender Marker: GEN 2 | Activity 1 TA provided to draft Articles and Memorandum of Association for establishing the Centre as a non-profit organisation |  | 20,000 |  |  |  |  |  |  |  | 20,000 |  |  |
|  | Activity 2 TA provided to help the Centre produce these strategies The Centre develops economic strategies for at least 5 municipalities. |  | 100,000 | 100,000 | 100,000 | 75,000 | 75,000 |  |  |  | 450,000 |  |  |
|  | Activity 3 TA provided for design and conduct of at least two Business Outlook Surveys |  | 75,000 | 50,000 | 30,000 | 25,000 | 20,000 |  |  |  | 200,000 |  |  |
|  | Activity 4 TA provided to design and publish the City Competitiveness Index at least once. |  | 100,000 | 100,000 | 75,000 | 75,000 | 50,000 |  |  |  | 400,000 |  |  |
|  | Activity 5 Support the establishment of CreateSpace co-working places and Incubators in at least 5 municipalities |  | 200,000 | 200,000 | 150,000 | 150,000 | 100,00 |  |  |  | 800,000 |  |  |
| Output 2 Economic Empowerment of Vulnerable groups (women, disabled, youth, and minorities) through Local Economic Plans of sub-national governments Gender Marker GEN 3 | Activity 1 Local Economic Empowerment Plans developed by at least 5 provinces and 5 municipalities with TA from UNDP |  | 100,000 | 75,000 | 75,000 | 50,000 | 50,000 |  |  |  | 350,000 |  |  |
|  | Activity 2 TA for supporting the development and implementation of the Inclusive Employment Pledge in at least 5 provinces and 5 municipalities |  | 75,000 | 75,000 | 50,000 | 30,000 | 20,000 |  |  |  | 250,000 |  |  |
|  | Activity 3 TA support for developing and implementing Local Content Pact for women disabled, minorities and youth-owned vendors is developed and implemented in at least 5 provinces and 5 municipalities |  | 75,000 | 75,000 | 50,000 | 30,000 | 20,000 |  |  |  | 250,000 |  |  |
|  | Activity 4 TA provided for advocacy and for design of a Special Funding Vehicle for Women, disabled, minority or youth owned SMEs. |  | 75,000 | 50,000 | 25,000 |  |  |  |  |  | 150,000 |  |  |
| Sub Total Pillar 3 |  |  |  |  |  |  |  |  |  |  |  | 3m |  |  |  |
| Human Resources and implementation of the portfolio: Gender marker: | Senior Policy Advisor (P5) |  | 300,000 | 300,000 | 300,00 | 300,000 | 300,000 |  |  |  | 1.5m |  |  |
|  | NOB-Social cohesion and decentralization Analyst x 1 |  | 75,000 | 75,000 | 75,000 | 75,000 | 75,000 |  |  |  | 375,000 |  |  |
|  | NOB - Gender analyst x 1 NOB - Human rights x 1 SC 4 – Communications analyst SC 5 – M&E analyst SC 4 – Procurement officer SC 4 Admin & Finance officer |  | 175,000 | 175,000 | 175,000 | 175,000 | 175,000 |  |  |  | 875,000 |  |  |
|  | MONITORING |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Sub-Total for HRs and Implementation of Portfolio |  |  |  |  |  |  |  |  |  |  | 2.75m |  |  |  |  |
| Evaluation (as relevant) | EVALUATION |  |  |  |  |  |  |  |  |  | 300,000 |  |  |
| General Management Support |  |  |  |  |  |  |  |  |  |  | 4.45m |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  | 60.5m |  |  |

# Governance and Management Arrangements

Explain the roles and responsibilities of the parties involved in governing and managing the project. While an example diagram is below, it is not required to follow this diagram exactly. A project can be jointly governed with other projects, for example, through a national steering sub-committee linked to Results Groups under the UNDG Standard Operating Procedures for countries adopting the Delivering as One approach.

Minimum requirements for a project’s governance arrangements include stakeholder representation (i.e., UNDP, national partners, beneficiary representatives, donors, etc.) with authority to make decisions regarding the project. Describe how target groups will be engaged in decision making for the project, to ensure their voice and participation. The project’s management arrangements must include, at minimum, a project manager and project assurance that advises the project governance mechanism. This section should specify the minimum frequency the governance mechanism will convene (i.e., at least annually.)

Human Rights Analyst

Gender Analyst

Social Cohesion and Decentralization Analyst

M&E Analyst

Head of Governance Unit

Project Support

Senior Policy Advisor

Head of Main Development Partner Agency

Resident Representative UNDP

Project Board (Governance Mechanism)

Program Organisation Structure

MAEFP

MEF

# Legal Context

[NOTE: Please choose one of the following options, as applicable. Delete all other options from the document]

# Option a. Where the country has signed the Standard Basic Assistance Agreement (SBAA)

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of (country) and UNDP, signed on (date).   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by [name of entity] (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Option b. Where the country has NOT signed the Standard Basic Assistance Agreement (SBAA)

The project document shall be the instrument envisaged and defined in the Supplemental Provisions to the Project Document, attached hereto and forming an integral part hereof, as “the Project Document”.

This project will be implemented by [name of entity] (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Option c. For Global and Regional Projects

This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions to the Project Document attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by [name of entity] (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

[NOTE: Please choose one of the following options that corresponds to the implementation modality of the Project. Delete all other options.]

UNDP (NIM)

- MAEFP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- AMEFPas the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- AMEFPas the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Project Document, MAEFP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - In the performance of the activities under this Project, UNDP as the Implementing Partner shall ensure, with respect to the activities of any of its responsible parties, sub-recipients and other entities engaged under the Project, either as contractors or subcontractors, their personnel and any individuals performing services for them, that those entities have in place adequate and proper procedures, processes and policies to prevent and/or address SEA and SH.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

Special Clauses. In case of government cost-sharing through the project, the following clauses should be included:

- The schedule of payments and UNDP bank account details.

- The value of the payment, if made in a currency other than United States dollars, shall be determined by applying the United Nations operational rate of exchange in effect on the date of payment.  Should there be a change in the United Nations operational rate of exchange prior to the full utilization by the UNDP of the payment, the value of the balance of funds still held at that time will be adjusted accordingly.  If, in such a case, a loss in the value of the balance of funds is recorded, UNDP shall inform the Government with a view to determining whether any further financing could be provided by the Government.  Should such further financing not be available, the assistance to be provided to the project may be reduced, suspended or terminated by UNDP.

- The above schedule of payments takes into account the requirement that the payments shall be made in advance of the implementation of planned activities.  It may be amended to be consistent with the progress of project delivery.

- UNDP shall receive and administer the payment in accordance with the regulations, rules and directives of UNDP.

- All financial accounts and statements shall be expressed in United States dollars.

- If unforeseen increases in expenditures or commitments are expected or realized (whether owing to inflationary factors, fluctuation in exchange rates or unforeseen contingencies), UNDP shall submit to the government on a timely basis a supplementary estimate showing the further financing that will be necessary. The Government shall use its best endeavors to obtain the additional funds required.

- If the payments referred above are not received in accordance with the payment schedule, or if the additional financing required in accordance with paragraph [] above is not forthcoming from the Government or other sources, the assistance to be provided to the project under this Agreement may be reduced, suspended or terminated by UNDP.

- Any interest income attributable to the contribution shall be credited to UNDP Account and shall be utilized in accordance with established UNDP procedures.

In accordance with the decisions and directives of UNDP's Executive Board:

The contribution shall be charged:

- […%] cost recovery for the provision of general management support (GMS) by UNDP headquarters and country offices

- Direct cost for implementation support services (ISS) provided by UNDP and/or an executing entity/implementing partner.

- Ownership of equipment, supplies and other properties financed from the contribution shall vest in UNDP.  Matters relating to the transfer of ownership by UNDP shall be determined in accordance with the relevant policies and procedures of UNDP.

- The contribution shall be subject exclusively to the internal and external auditing procedures provided for in the financial regulations, rules and directives of UNDP.”

# ANNEXES

- Project Quality Assurance Report

- Social and Environmental Screening Template [English][French][Spanish], including additional Social and Environmental Assessments or Management Plans as relevant. (NOTE: The SES Screening is not required for projects in which UNDP is Administrative Agent only and/or projects comprised solely of reports, coordination of events, trainings, workshops, meetings, conferences, preparation of communication materials, strengthening capacities of partners to participate in international negotiations and conferences, partnership coordination and management of networks, or global/regional projects with no country level activities).

- Risk Analysis. Use the standard Risk Log template. Please refer to the Deliverable Description of the Risk Log for instructions

- Capacity Assessment: Results of capacity assessments of Implementing Partner (including HACT Micro Assessment)

- Project Board Terms of Reference and TORs of key management positions

ANNEX 1

| FUNCTIONAL ASSIGNMENT UNDER THE NEW DECENTRALIZATION LAWS |  |
| --- | --- |
| Tier | Assignment |
| Central | - The functions of sovereignty; - The regulation of matters within the scope of the law; - The definition of national policies; - The realization of the unitary politics of the State; - State representation at provincial and district level; the definition and organization of the territory; - National defense; - Public safety and order; - Border surveillance; - The issuance of currency: - Diplomatic relations; - Mineral resources and energy; - Natural resources located in soil and subsoil, inland waters, the territorial sea, the zone adjacent to the territorial sea, the continental shelf and the exclusive eco-thermal zone; - The creation and amendment of taxes |
| Provincial | - Agriculture, fisheries, livestock, livestock, security food and nutrition; - Land management, to the extent determined by law; - Public transport, in the area not assigned to the municipalities; - Management and protection of the environment; - Forests, wildlife and conservation areas; - Housing, culture and sport; - Health in the context of primary care; - Education in the field of primary education, general education and vocational technical training; - Tourism, folklore, handicrafts and local fairs; - Hospitality, not exceeding the three star level; - Promotion of local investment; - Water and sanitation; - Industry and commerce; - Roads and bridges that correspond to local, provincial and district interest; - preventing and combating natural calamities; - Promotion of local development; - Territorial planning and planning; - Rural and community development; - Others to be determined by law. |
| Municipal | - local economic and social development; - environment, basic sanitation and quality of life; - public supply; - health; - education; - culture, leisure and sport; - local police; - urbanization, construction and housing |

Denotes areas of functional overlaps or unclear functional remit

ANNEX 2

COMPOSITION AND TOR OF THE NATIONAL COMMITTEE ON COMMON INTERESTS

Composition*

- Minister of MAEFP 						Chairperson

- Governors of all Provinces					Members

- State Representatives of all Provinces			Members

- Ten Heads of Districts** 				 	Members

- Ten Mayors of Municipalities***				Members

- Central Government Cabinet Members Minister		Members

- Three representatives of Traditional Leaders****	 	Members

- Permanent Secretary MAEFP 				Member/Secretary

*The Committee  may co-opt members as per need.

**The representatives of districts will rotate every year to ensure that all districts are represented on the Committee

***Mayors will rotate every year to ensure all municipalities are represented on the Committee

****Representatives will rotate every year so that different regions are represented

Key Functions

- The Committee shall be responsible to MAEFP and function as an advisory and coordination forum. It shall publish an Annual Report on the work of the committee as part of its commitment to voluntary disclosure and Open Government principles.

- The Committee  shall review and advise government on policies, procedures and legislation in relation to matters related to decentralization and local government, and as articulated in the laws on decentralization.

- The Committee  shall have a permanent Secretariat and shall meet biannually. The Chairperson may convene a meeting earlier than that on the joint request of at least three Provinces, or 15 Districts or 10 Municipalities, submitted in writing and explaining the rationale for the requisition. The Chairperson may also convene the meeting earlier than six months in case of an issue of national urgency.

- The advice of the Committee shall be expressed in terms of the opinion of the majority. Any dissenting notes shall be documented for record and as respect for diversity of opinion.

- The Committee  will also regularly discuss and share information and reports on national, provincial, district and municipal plans with a view to enhancing coherence, and to solicit and sustain cooperation on development, security and public services.

- The functioning of the Committee  will be governed by Rules of Procedure, to be developed by MAEFP in consultation with all the sub-national governments.

ANNEX 3

DECENTRALIZATION CAPACITY DEVELOPMENT FUND: MANAGEMENT ARRANGEMENTS

  - Purpose

The Decentralization Capacity Development Fund (the Fund) is intended to serve as a means of addressing systemic capacity gaps and needs under this Program. The Fund will be a service provider to governments at all tiers, with a focus on sub-national levels.

  - Scope

The Fund aims to have an expanded scope in terms of:

  - Not being restricted to trainings alone but to cover a wide range of interventions and support for building system-wide capabilities including for data analytics; measurement and results orientation;

  - Including elected representatives as part of the beneficiaries along with civil servants at all tiers of government.

  - Building capacity for and facilitating innovations in design and delivery of public services at sub-national levels.

  - Structure

The Fund is proposed to be housed under MAEFP with UNDP’s technical team providing strategic and operational support. The following structure is proposed:

Permanent Secretary MAEFP

Director MAEFP

Fund Operations Manager

Capacity Building Analyst

Procurement Analyst

UNDP Senior Policy Advisor

National Director MAEFP

Fund Coordinator

M&E Analyst

FUND STEERING COMMITTEEE

Permanent Secretary (Chair)

MEF Representative

Other Government Implementing Partners

UNDP Deputy Resident Representative

EU (?) Representative

UNCDF Representative

Provincial Government Representatives (3)

Municipality Representatives (3)

National Director MAEFP  (Member/Secretary)

Administration and Finance Analyst

  - Management

MAEFP will provide leadership to the Fund through active involvement of senior officials and assigning MAEFP staff with responsibilities for strategic management (through National Director acting as the Fund Coordinator), and operations (through a Director level official as Operations Manager). UNDP will provide full technical support through hiring of experts to perform administrative, procurement, M&E and capacity building functions. To facilitate government, procurements will follow UNDP rules. Oversight of the Fund management will be achieved through a Decentralization Capacity Development Fund Steering Committee, whose composition is proposed above. Overall fiduciary management responsibilities will lie with MAEFP who will be supported in executing this responsibility by UNDP.

  - Eligibility and Access

All government tiers would be eligible to access the resources under the Fund. In order to ensure targeting of resources, the majority of the funds will be available for provinces and municipalities, followed by central ministries and agencies. To access the Fund, certain performance and needs based criteria—to be developed by MAEFP, UNDP and UNCDF—will need to be met.

  - Financing

The Fund is proposed to be seeded through funding from MAEFP in kind and/or budgetary allocations and capitalised through funding from development partners.

  - Reporting

MAEFP (with support from UNDP) will produce annual reports on the progress, achievements, and challenges in Fund implementation. In addition, communication tools such as newsletters, digital assets (podcasts, blogs) will keep stakeholders informed on the work done under the Fund.

ANNEX 4

DRAFT COMPOSITION AND TERMS OF REFERENCE OF INTER-GOVERNMENTAL FINANCE ADVISORY COMMITTEE

Composition

Minister for Economy and Finance						Chair

Provincial Ministers for Economy and Finance				Members

Director General Economy and Finance Maputo City			Member

Three representatives of Municipalities					Members

Three representatives of district governments				Members

Four renowned Public Finance Experts/Development Economists*		Members

Head of Federation of Mozambican Chambers of Commerce		Member

Two representatives of the Council of Elders/Tribal Leaders 		Member

Permanent Secretary Ministry of Economy and Finance (Non-voting)	Member/Secretary

Provided that at least 10% of the voting members shall be female.

Terms of Reference

The Inter-Governmental Finance Advisory Committee will be an advisory body, established underf law, and accountable to the Ministry of Economy and Finance.  Its functions shall include:

- Deliberations and advice on  the fiscal consolidated fund and the divisible pool from which distribution is to be made to all tiers of government.

- Advise on the relevance, basis, transparency and adequacy of the vertical and horizontal distribution between the central government and the sub-national governments, of the net proceeds of the national divisible pool of funds. Further that this distribution will be:

- Review the implementation of the fiscal distribution and advise on improving implementation..

- Any other matter relating to finance referred to the Committee by the central government

The Central Government through the Ministry of Economy and Finance shall develop rules of business for the Committee and notify them in the official gazette.

*One each to be nominated by the central, provincial, district and municipal governments

ANNEX 5

C3 : CENTRE FOR COMPETITIVE CITIES

Purpose and Scope: The Centre for Competitive Cities will be a dedicated resource that explores and advises on policy issues related to urban regeneration, competitiveness of cities and their link with social development in urban areas and political foresight for better economic policies for cities.

What will it do: The Centre will:

- Carry out policy research and analysis and provide policy advisory services to government, private sector and civil society on matters relating to improving metropolitan cities’ governance, competitiveness and place branding.

- Develop, support and apply innovative policy designs addressing key SDG related targets as they relate to urban contemporary society.

- Establish platforms for collaboration between urban managers, elected representatives, businesses, communities and academia to enable disruptive approaches to be developed for expanding economic opportunities, promoting entrepreneurship and enhancing trade from cities based on their competitive and comparative advantages.

Institutional Vehicle: The Centre for Competitive Cities is proposed to be established as a non-profit think tank as a joint venture between the UNDP, UCLG, and ANAMM, and the Cities Program at the London School of Economics and Political Science.

Principle Tools: The Centre will develop and use the following tools to deliver on its mandate:

- Economic Development Strategies: The Centre will develop economic development strategies for metropolitan cities in collaboration with the city administrations. It will shelve the cookie-cutter approach that cities use at this point for their planning and will seek out partners and co-deliverers in the private and civil society sectors. These strategies will be driven both by the political vision for cities and their comparative advantages, allowing for harnessing of talent, resources and positioning to create jobs, strengthen quality of products and services and for deepening and widening of markets.

- Business Outlook Surveys The Centre will design and administer a Business Outlook Survey to understand the expectations, needs and potential for investment and jobs in cities. The survey will cover local firms and collect information on their plans and constraints for growth, job creation and competition. Analysis of the results will be juxtaposed over national regional and international trends and forecasts to articulate and position cities’ strategies better.

- Cities Competitiveness Index The Centre will develop a Cities Competitiveness Index to reflect the current standing on competitiveness criteria and to allow for trend analysis on how cities evolve in terms of their economic structures (e.g. degree of informality of their economy, number and nature of firms), ability to compete for investment, and how they score on innovation, research and development, use of technology, environmental sustainability and productivity. This Index will be used by policy makers to make decisions regarding the kind of economic strategies and institutional arrangements are required to allow cities to realize their economic potential.

- CreateSpace The Centre will pilot the establishment of CreateSpace as an incubator and offline/online platform for collaboration and co-creation of solutions for improving urban governance and local area development. By offering a physical hub, the CreateSpace initiative will facilitate collective action and support social business startups.

Mode of Engagement: The Governance Unit at the UNDP will establish and staff the Centre and enter into agreements with the local and international partners to deliver on the scope of work defined above.

Oversight, Reporting and Financing: Oversight functions, reporting and financing will be determined by the Centre’s management.

Average GDP Growth 2000-2015, World Bank Data

Board Decision of the Validation of Mozambique, EITI 2017

Mid-Year Socio Economic Update, UNDP Mozambique, 2019

Mozambique County Brief, ILO 2016

Mozambique Cyclone Idai: Post-Disaster Needs Assessment, Government of Mozambique 2019

Ibid

Estimates included in the PDNA point to a slowdown in growth to 2.5%, from the expected rate of 4.7% in 2019

Report on Transparency, Governance and Corruption, Government of Mozambique 2019

Cited in http://allafrica.com/stories/201605040005.html.

Kossler, Karl. “Conflict and Decentralization in Mozambique: Challenges of Implementation”.ConstitutionNet, December 2018

Mozambique Economic Update, World Bank 2019, accessed on worldbank.org on 25 August 2019

Mozambique Urbanization Review: Accelerating Urbanization to Support Structural Transformation in Mozambique, World Bank, 2017

Poverty and Equity Brief: Mozambique, World Bank, April 2019

Local Government System in Mozambique: Country Profile 2017-2018, Commonwealth Local Government Forum, 2018

Mozambique Urbanization Review: Accelerating Urbanization to Support Structural Transformation in Mozambique, World Bank, 2017

UN-Habitat Country Program Document 2018-2021

Analysis of Social and Economic Sectors, UNICEF 2018

National Urban Development and Decentralization Project, World Bank 2018

Ibid

Barómetro da Governação Municipal 2018, IESE

Global Right to Information Rating, Centre for Law & Democracy

As reported by CIVICUS, Decree 40/2018 was issued on 23 July 2018

For example, the National Gender Policy and its Implementation Strategy, and the National Plans for the Advancement of Women

Article 48 of the Constitution of the Republic of Mozambique

Mozambique Expects $95 billion in Gas Revenues, Bloomberg, 26 May 2019

Mozambique Urbanization Review: Accelerating Urbanization to Support Structural Transformation in Mozambique, World Bank, 2017

Reforço do Acesso a Justiça e a Promoção e Proteção dos Direitos Humanos em Moçambique 2018-2021, UNDP Mozambique 2018

Mukhopadhyay, M. and S. Quintero (2008) Gender and access to justice in sub-Saharan Africa. Report of the conference held 29-30 October 2008 in Johannesburg, South Africa. Amsterdam: KIT and CALS

Mozambique Brief, ILO 2016

Finscope Mozambique Consumer Survey 2014, Ministry of Economy and Finance Republic of Mozambique and FinMark Trust, 2015

National Basic Social Security Strategy 2016-2024, Government of Republic of Mozambique

ILO Mozambique Brief 2016

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards.  Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.

Optional, if needed

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a project budget affecting the scope (outputs), completion date, or total estimated project costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner