# Africa Adaptation Programme: Supporting Integrated and Comprehensive Approach to Climate Change Adaptation in Africa

Promoting an Integrated Approach to Adaptation in Nigeria

Final Project Review Report

March 2013

# Acronyms

# Executive Summary

# Contents

ACRONYMS	2

EXECUTIVE SUMMARY	3

Contents	5

1.0 CONTEXT	7

Background	7

Objectives of AAP Ghana	7

Expected Outputs	7

Project Implementation Framework	8

2.0 PROJECT RESULT SUMMARY	8

Results by Output	8

Output 1: Dynamic, long-term planning mechanisms to cope with the inherent uncertainties of climate change introduced.	8

Output 2: Leadership and institutional frameworks to manage climate change risks and opportunities in an integrated manner at the local and national levels strengthened.	9

Output 3: Climate-resilient policies and measures in priority sectors implemented.	9

Output 4: Financing options to meet national adaptation costs expanded at the local, national, sub-regional and regional levels.	10

Output 5:  Knowledge on adjusting national development processes to fully incorporate climate change risks and opportunities generated and shared across all levels	10

Pilot Projects	11

Sisala East District:	11

Fanteakwa District:	11

Keta District:	11

West Mamprusi District:	11

Aowin Suaman District:	11

Studies Undertaken Under AAP	11

3.0 PERFORMANCE REVIEW	12

3.1 Progress Review	12

3.1.1 Overall progress towards Country Programme Action Plan Outcomes and Outputs	12

3.1.2 Subsection for each Outcome	12

3.2 Implementation Strategy Review	21

3.2.1 Sustainability	21

3.2.2 Participatory/Consultative Process	22

3.2.3 Quality of Partnerships	23

Leadership and Institutions	23

3.2.4 National Ownership	24

3.3 Management Effectiveness Review	24

3.3.1 Monitoring and Evaluation	24

3.3.2 Timely Delivery of Output	25

3.3.2 Resource Allocation	25

3.3.4 Cost-effective use of inputs:	25

4.0 IMPLEMENTATION ISSUES	25

Staffing and Capacity Issues:	25

Monitoring & Evaluation:	26

Financial Management Issues	26

Procurement	26

AAP Regional Programmes	26

Communication Strategy	26

5.0 LESSONS LEARNT	27

Project Management	28

Stakeholder Engagement	29

Pilot Projects Influencing Policy	29

6.0 FINANCIAL STATUS AND UTILIZATION	32

Financial Summary	32

Financial Overview	32

Financial Utilisation	36

ANNEXES	38

# CONTEXT

## Background

Nigeria with an estimated population of over 150 million people (2006 Census figures) is not exempted from the issues that have risen due to the impacts of climate change at the global level. The variations in climate parameters including cloud cover, precipitation, temperature ranges, sea levels affects all the different sectors of the economy such as agriculture, health, water resources, energy etc. In Nigeria, the high level of climate risk is related to a number of factors which includes the densely populated low lying coastline, which houses a high concentration of industry and infrastructures important for GDP. The northern part of the country lies along the Sahel region and is at risk to drought and desertification. The economy of Nigeria is mostly dependent on climate-sensitive resources, with agriculture, forestry and fishing sectors employing close to 70% of the workforce. However, the challenges being faced by the incessant issues on climate change can be turned into opportunities by developing long term policies that both addresses short term vulnerability and increase long term resilience.

## Objectives of AAP Nigeria

The African Adaptation Programme in Nigeria was designed to assist the Government of Nigeria to put in place the necessary enabling environment to guide the country’s response to current and future climate risks, in the form of a national and sub-national policy framework that will provide a coherent basis for adaptation actions at different levels.

The main objective of the AAP in Nigeria was to make sure that an integrated approach to adaptation to climate change through the building of strong governance system, empowering children as agents of change and demonstrating the adaptation benefits in the agricultural sector was achieved. One of the innovations of the programme was to harness the comparative advantage of the three UN agencies in Nigeria: UNDP, UNICEF and UNIDO to assist in strengthening Nigeria’s responsiveness to climate change.

## Expected Outputs

To address the identified problems, five major outputs have been drawn out. These are supposed to address the enabling environment for climate change adaptation in the country. These are

- Dynamic, long-term planning mechanisms to cope with the inherent uncertainties of climate change introduced

- Gender-sensitive leadership and institutional frameworks to manage climate change risks and opportunities in an integrated manner at the local and national levels built

- Climate-resilient policies and measures implemented in priority

- Financing options to meet national adaptation costs expanded at the local, national, sub-regional and regional levels

- Knowledge on adjusting national development processes to fully incorporate climate change risks and opportunities generated and shared across all levels

## Project Implementation Framework

| Executing Agency: | Federal Ministry of Environment, |
| --- | --- |
| Implementing Agency: | United Nations Industrial Development Organization (UNIDO), United Nations Children’s Fund (UNICEF), Department of Climate Change. |
| Project Partners: | NIMET, Federal Universities, Women Empowerment Programme, National Planning Commission (NPC), Federal Ministry of Women Affairs, UN-HABITAT, UNWOMEN, KnowlEdge Srl |
| Technical and Supervisory Support: | UNDP Country Office, Abuja; AAP Regional Office, Dakar |
| Start Date: | October 2010 |
| End Date: | December 2012 |

# PROJECT RESULT SUMMARY

The AAP in Nigeria was able to promote the integrated approach to adaptation to climate change through the building of government systems, empowering children as change agents and being able to demonstrate the adaptation benefits in the agricultural sector. The programme responded to position the country to better attain sustainable development by reducing the risks of climate change impacts and enhancing its capacity to harness any opportunities that may be inherent in the changing climate.

# Results by Output

Output 1:  Dynamic, long-term planning mechanisms to cope with the inherent uncertainties of climate change introduced

- Training module on mainstreaming CCA into Water, Sanitation and Hygiene (WASH) sector was developed in collaboration with National Water Research Institute (NWRI) and Federal Ministry of Water Resources (FMWR). It has also been integrated into NWRI programmes for WASH sector professionals

- Twenty Eight key water and sanitation sector stakeholders (FMWR, NWRI, River Basins, Development Agencies, State RUWASSAs, Federal Ministry of Environment and some NGOs) had their capacities enhanced on the use of the model

- Several technical studies and assessments were conducted. These include: Climate Change and Water Management in Nigeria; Gender Dimensions of Climate Change/Capacity of Local Institutions Response to the Needs of Children, Women and Men at Community Level; Assessment of Gender Sensitive Climate Change Adaptation Initiatives for Sustainable Livelihoods Development

- A road map for combating climate change induced security concerns

- A framework for a path towards Green Growth for Nigeria was also developed.

- The National Policy on Climate Change

- These technical assessments results have resulted into the issues of climate change being mainstreamed into national policy on security. It has also influenced the water sector with the presidency conjuring a water summit on innovative funding of water sector in the context of climate change

Output 2: Leadership and institutional frameworks to manage climate change risks and opportunities in an integrated manner at the local and national levels strengthened.

- Four hundred and forty (440) community members are now aware of the consequences of climate change while 13 primary schools in Cross River and Niger States have rain water harvesting, solar energy and school garden facilities in place as pilot projects

- One hundred and sixty-six teachers, head teachers and health education teachers, SBMCs, PTAs have acquired enhanced knowledge and capacity on implementation of CCA in schools.

- Training on Gender Dimensions of Climate Change, especially Gender Sensitive Leadership Trainings , Capacity Building for Farmers on Climate Resilient Agricultural Practices and Model for Equitable Access to Climate Change Benefits

- Successful establishment of the Science and technology Committee on Climate Change

- Establishment of a Climate Change Research Group with the mandate to support national efforts

Output 3: Climate-resilient policies and measures in priority sectors implemented.

- The capacities of 340 tutor educators and 1,352 student teachers were enhanced at 6 focal colleges of education in the country from the 6 geopolitical regions of Nigeria including the 2 AAP pilot states.

- Systems and mechanisms of reporting and recording to prevent and mitigate violence in communities as a result of climate change and other causes have been out in place.

- State level and community participatory approach for problem solving and conflict management skills due to climate change were developed in 8 states.

- Macro-economic policy and schemes in agriculture including farming methodologies and studies have been put in place.

- Climate Change concerns integrated into government long term investments and infrastructural development plans

- Studies on the impact of climate change on water supply and sanitation was conducted in Nigeria. The study was able to confirm that major policies and strategy on Water Supply and Sanitation (WSS) are not sensitive to climate change. There is a need for the private sector to partner with government to promote climate change adaptation and mitigation programmes

Output 4: Financing options to meet national adaptation costs expanded at the local, national, sub-regional and regional levels.

- Development of a National Climate Change Trust Fund

- Development of Business and Environment Sustainability Group (BESG)

- A framework for accessing Kyoto protocol adaptation fund was established.

Output 5:  Knowledge on adjusting national development processes to fully incorporate climate change risks and opportunities generated and shared across all levels

- Federal and State MDAs, CSOs and faith-based networks were mobilized in the two pilot states to assist on Disaster Risk Reduction and emergency responses and recovery.

- Communication Strategy Document on AAP developed

- Deployment of the Threshold 21 (T21) Model for climate change and development planning.

- Science Committee on Climate Change Inaugurated

- Climate Change Media Network for reporting and recording climate change events was also established at the Federal level.

- A movie (docudrama) on Climate Change was filmed by the Actors guild of Nigeria (Nollywood)

## Technical Studies under the AAP

## Pilot Projects under AAP

# PERFORMANCE REVIEW

3.1 Progress Review

The AAP Nigeria was a major contributor towards the achievement of the ‘minimum threshold of climate activities’ outcome in the Nigerian Country Programme Action Plan (CPAP). The project, as an institutional strengthening project was able to support Nigeria in developing a localized response to the issues of climate change adaptations. The project during its implementation was able to see to the formulation, passage and adoption of the National Policy on Climate change and the design of the National Strategy and Plan of Action (NASPA) and approval are the critical indicators of the success of the AAP in Nigeria. The level of sensitization at community level, state level and within national institutions all helped to propel the desired national framework of action. The AAP also acted as a catalyst in ensuring on-going initiatives were given prominence. The recognition and establishment of a full department of climate change is another success indicator.

| ACTIVITY List activity results and associated actions | ACTIVITY RESULTS | PROGRESS PERCENTAGE/COMPLETION |  |  |  |  |  | REMARKS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output 1 Dynamic, long-term planning mechanisms to cope with the inherent uncertainties of climate change introduced |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity Result 1.1: UNDP: A strengthened and streamlined national dialogue and policy formulation process for climate change adaptation, leading to an evidence-based National Climate Change Policy and National Strategy/Adaptation Plan | - National Policies on Climate Change developed and adopted. - Pilots states engaged in state-level CC policy and strategy processes - Climate Change and Gender issues mainstreamed | 100% Completed |  |  |  |  |  | The National Climate Change Policy and Response Strategy approved by the Federal Executive Council. Annual States Climate Change Summit initiated among the 36 States of the Federation. |  |  |  |  |  |
| Activity Result 1.2: UNDP , with inputs from UNICEF and UNIDO: Raise awareness of the likely impacts of climate change and adaptation needs, linked to the national dialogue and policy formulation process for climate change adaptation, developed and implemented at the national, state and local level, in order to build broad and informed coalitions for climate change | - Media capacity on CC reporting build - Capacity of pilot communities built - CCA added in primary and secondary schools curriculum - CC advocacy networks and clubs established among NGOs and students. - Training module on mainstreaming CCA into water developed in collaboration with the Federal Ministry of Water Resources. | 100% Completed |  |  |  |  |  | CC Media Network was put in place where about 23 Nigerian Environmental Journalist had their capacity built in reporting CCA. As a result 2 journalists won the UNEP and CNN awards. |  |  |  |  |  |
| Activity Result 1.3; UNICEF: Further strengthen the climate responsiveness of key sectoral policies through advocacy based on evidence generated through the actions of the AAP | - National Water Policy, Education Policy and Teaching Curriculum using AAP-generated knowledge developed | 100% Completed |  |  |  |  |  |  |  |  |  |  |  |
|  | Action 1.3.1: Advocate for and support review of National Water Policy, Education Policy and Teaching Curriculum using AAP-generated knowledge |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2 Gender-sensitive leadership and institutional frameworks to manage climate change risks and opportunities in an integrated manner at the local and national levels built Baseline: Nigeria has limited leadership and institutional frameworks to manage climate change risks and opportunities in an integrated manner at the local and national levels, and women have not been adequately included in the development of adaptation measures. Indicator: National coordination, leadership and skills to manage climate change risks have been built through an ongoing capacity development initiative focused on key institutions, that specifically emphasises developing women’s leadership; and through proactively developing the future Nigerian leadership by empowering children to become change agents who can advocate for behavioural elements of adaptation to climate change in their communities. Targets Year 2 - Gender-sensitive initiative for CCA skills development - Strengthened national coordination structures for CCA that include women-focused NGOs and civil society groups in leadership structures Related CP outcome: | Activity Result 2.1: UNDP: Build a sound and unified platform for mainstreaming climate change adaptation through strengthening key focal institutions, building the capacity of overarching ministries, and developing coherent coordination mechanisms for climate change Action 2.1.1: Capacity needs assessment & priority areas for capacity development institutions Action 2.1.2: Medium-term strategy & programme for CCA capacity development Action 2.1.3: Accelerated work on skills development for CCA; to include gender aspects & develop women’s leadership Action 2.1.4: Strengthened national coordination structures for CCA |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity Result 2.2: UNICEF: Proactively develop the future Nigerian leadership for responding to climate change by empowering children to become change agents who can advocate for behavioural elements in their communities Action 2.2.1: Training of School Health focal points on CCA Action 2.2.2: Partnership and consensus on the review of the school curricula to include CCA Action 2.2.3: School children knowledge and skills to influence community dialogue on CCA. Action 2.2.4: Increase child participation in public debate on CCA through available communication channels |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3 Climate-resilient policies and measures implemented in priority sectors Baseline: Nigeria has few or no climate-resilient policies and measures in place in priority sectors. Indicator: Nigeria has piloted gender-sensitive climate-resilient measures in the priority sectors of education, agriculture and water, developed frameworks to upscale a number of these, and initiated the process of upscaling.: Targets: Targets UNICEF Year 2 - Learning materials for school gardening as CCA activity UNICEF: - Framework & approaches for problem solving and conflict management skills - School-based assessment tools - Teacher education programmes - experiential learning tasks designed, implemented and monitored Related CP outcome: | Activity Result 3.1: UNICEF: Build groups of climate-resilient people through improving knowledge and skills for climate change adaptation at the basic education level, through hands-on experience and developing problem solving skills Action 3.1.1: Localities & pilot CCA interventions on school-based water harvesting / school gardening Action 3.1.2: Pilot other environment-friendly applications Action 3.1.3: Learning materials and packages on Skills-Based Education for school gardening as CCA strategy Action 3.1.4: Framework & approaches for child problem solving and conflict management Action 3.1.5: School-based assessment tools to measure change in the knowledge and skills on CCA |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity Result 3.2: UNICEF: Foster systems to enhance learning for climate resilience focusing on teaching capability, experiential learning in environmental clubs, awareness raising and community engagement and dialogue with the school as the centre for action Action 3.2.1: Teacher education programmes on CC in specified teacher training institutions Action 3.2.2: Review protocol for the operations of school health clubs to include CCA Action 3.2.3: Government-led child-centered experiential learning tasks on CCA Action 3.2.4: Age- and target-specific communication materials and messages on CC Action 3.2.5: Children-led community dialogue on CC |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity Result 3.3: UNIDO: Promoting adaptation to climate change by reducing flooding through development of small hydro power generation at the Ochokwu river in Apa local government area of Benue State (to be integrated with agricultural interventions to increase production and post-harvest storage as adaptive responses) Component on Small Hydro Power Action 3.3.1: Integrate CC projections & fine-tune the feasibility study for SHP Action 3.3.2: Site preparation activities, build weir/reservoir, procure and install 1MW small hydro power (SHP) plant |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity Result 3.4; UNIDO: Promoting adaptation to climate change by developing more adaptive farming practices, through agricultural interventions to increase production and reduce post-harvest losses by processing agricultural products as adaptive responses in the Ochokwu river vicinity in Apa local government area of Benue State Component on increasing production/ adaptation to CC Agricultural mechanization and conservation agriculture Action 3.4.1: Analyse traditional methods and institutional environment, including approaches/barriers for women’s enhanced agricultural productivity; identify CAT to be introduced Action 3.4.2: Strengthen capacity of National Institute (NI) to promote technologies; finalise specifications of machinery. Action 3.4.3: Beneficiaries selection (NB gender balance criteria) & training programmes in application of CAT, O&M of machinery and equipment |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Action 3.4.4: Field testing of CT machinery and equipment, adapt to local conditions; training programmes for CA operators /repair/ maintenance Action 3.4.5: Linkages between institutions testing CT machinery; framework to transfer technology to local manufacturers Action 3.4.6: Identify participants, with gender balance, and organize a study tour to CT practicing country to share experiences and generate knowledge Action 3.4.7: Train engineers in designing modifications to adapt CT machinery and equipment to local conditions; develop manufacturer’s directory of agricultural machinery |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Enhanced post-harvest storage and processing Action 3.4.8: Hold workshops with communities in Apa LGA to understand barriers and opportunities for developing more sustainable livelihoods, and to identify spin-off effects for post-harvest processing and other productive uses, with an emphasis on employment for women and youth Action 3.4.9: Implement actions to enhance post-harvesting rice storage and value addition through installation of EE systems developed using UNIDO method of Common Facility Centre (CFC) for rice milling operations Action 3.4.10: Enhance preservation of other agricultural products (fruits, vegetables, cereals, pulses, etc) in the communities through refrigeration and value addition by means of electric power supply from SHP and installation of efficient milling machines, and other post harvest storage systems |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4 Financing options to meet national adaptation costs expanded at the local, national, sub-regional and regional levels Baseline: Nigeria has limited financing options to meet national adaptation costs and lacks a suitable institutional financial mechanism for accessing funds from the Adaptation Board Indicator: Nigeria has strengthened technical and leadership capacities to secure, expand and/or re-align funds to support climate change adaptation; has initiated integration of costs of the National Adaptation Strategy into the budgeting cycle; has developed possibilities with the Ministry of Finance for providing incentives to the private sector to fund adaptation actions; and has developed an institutional mechanism for accessing funding from the Adaptation Fund. Targets: Related CP outcome: | Activity Result 4.1: UNDP: Strengthened technical and leadership capacities of key financial and planning institutions, as well as key line ministries, at the national and sub-national levels to secure, expand and/or re-align funds to support climate change adaptation. Action 4.1.1: Consult with key stakeholders, identify main challenges in mainstreaming CCA into the budgeting cycle & expanding/re-aligning existing funds; undertake CCA financial needs assessment for Nigeria Action 4.1.2: Provide support to MoF for economic analysis of CCA needs and integration into the MTEF cycle; develop advocacy materials for key financial & planning institutions & line ministries, at national and sub-national levels; deliver training on designing climate-resilient investment plans Action 4.1.3: As part of integration of NAS, assist key ministries to re-align their budgeting processes so that these fully incorporate funding for CCA actions, bearing in mind the special needs of women to make their livelihoods climate-resilient. |  |  |  |  |  |  | AAP National and international experts Meetings and workshops Advocacy materials Training Staff time 250,000 [UNDP: 250,000] |  |  |  |  |  |
|  | Activity Result 4.2: UNDP: Expanded national resource envelope in Nigeria to support climate change adaptation, through development of private sector possibilities for funding adaptation activities; and through the global Adaptation Fund Action 4.2.1: Explore with private sector possibilities to leverage additional funding for adaptation; develop options with the MoF for providing incentives to the private sector to fund adaptation actions Action 4.2.2: Assess institutional options for accessing funding through the Adaptation Fund and assist the GoN to develop appropriate funding mechanism |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 5: Knowledge on adjusting national development processes to fully incorporate climate change risks and opportunities generated and shared across all levels Baseline: There is limited or no sharing of knowledge on adjusting national development processes to fully incorporate climate change risks and opportunities in Nigeria across and between all levels, and some critical knowledge gaps for managing climate risks adequately. Indicator: Knowledge on adjusting national development processes to fully incorporate climate change risks and opportunities is generated and shared across all levels, through a knowledge platform, there is enhanced evidence for managing climate risks and Nigeria has established an integrated monitoring framework Targets: Related CP outcome: | Activity result 5.1: UNDP: Key institutions document and disseminate knowledge on adjusting development actions in order to adapt to climate change, and Nigeria develops and implements a robust framework to monitor and adjust adaptation actions Action 5.1.1: Obtain co-funding, design and set up a National Climate Change Knowledge Platform; and commission any knowledge products required for the awareness raising and targeted training activities set out under Outputs 1 and 2 Action 5.1.2: As part of the process to develop the National Adaptation Strategy, design and develop an integrated monitoring framework to allow for iterative learning and adaptive management of climate adaptation interventions |  |  |  |  |  |  | AAP National and international experts Meetings and workshops Software Awareness raising and training materials Staff time 555,000 [UNDP: 515,000] [UNICEF: 15,000 for communication] [UNIDO: 30 ,000] |  |  |  |  |  |
|  | Activity Result 5.2: UNICEF: Enhanced evidence and knowledge generation for climate change adaptation through a better understanding of the impacts of climate change on Nigeria’s children, and through exploring the emergency preparedness and disaster risk reduction needs of Nigeria under a changing climate Action 5.2.1: Commission and complete assessment study on the ‘Impact of Climate Change on Children in Nigeria’ Action 5.2.2: Commission and complete ‘Emergency Preparedness and Disaster Risk Reduction in Relation to Climate Change Adaptation in Nigeria’ study. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity Result 5.3; UNDP, UNICEF & UNIDO: Communication strategy developed for the AAP in Nigeria and implemented as an integral part of the programme Action 5.3.1: Develop & implement AAP communication strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  | US$3,135,000 |  |

This action could include assisting ministries to develop / access risk transfer systems such as insurance – for example, index-based weather insurance.