## Project Results Pathway
Project Results and Monitoring Pathway
Basic Information |  |  | Name of Project | Plastic Waste Recycling Management: A Partnership
|  |  | Project Award ID | 00096923
|  |  | Project Output ID | 00100826
|  |  | Overall project period | January 2018 to June 2024
|  |  | Name of Programme Officer | Saloni Goel
|  |  | Government/ Private Sector Counterparts | Hindustan Coca-Cola Beverages Pvt Ltd, Hindustan Unilever Limited, HDFC Bank, Coca Cola India Foundation, CSTI, Ministry of Housing & Urban Affairs, NITI Aayog
|  |  | Implementing Partner | Hasiru Dala, BITAN, Finish Society, SMS, Aasra Welfare Association, Muskan Jyoti etc.
|  |  | Total Budget (USD) | 2018 | 2019 | 2020 | 2021 | 2022
|  |  |  | 1257046 | 3148422 | 3067697 | 3016991 | 4127622
Integrated Results and Resources Framework (IRRF) (Add rows subject to project duration) |  |  | Project Linked to Strategic Plan Outcome | SP Outcome 1: | Advance Poverty Eradication in all it's Forms and Dimensions
|  |  | Project Linked to Strategic Plan Output | SP Output 1.4.1: | Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains.
|  |  | SP Indicator Name and Number | Indicator 2.1.2.2: | Country has improved range of services provided through social protection systems to reach marginalised group
|  |  |  | Sub Component 2.1.2.2.A: | Types of services
|  |  | Linked SDG Target | Target_12.5: | By 2030, substantially reduce waste generation through prevention, reduction, recycling and reuse
|  |  | Unit of Measurement | Binary
Progress towards SP Output / indicators / Targets
|  |  | Targets - Overall for SP Indicator | Baseline (2017) | Milestone (2018) | Achievement: Mid Year (June) | Achievement: End Year (December)
|  |  | Sub Component 2.1.2.2.A: | 5000 | 9000 |  | 5356
|  |  |  | Baseline (2018) | Milestone (2019) | Achievement: Mid Year (June) | Achievement: End Year (December)
|  |  |  | 9000 | 18000 | 10717
|  |  |  | Baseline (2019) | Milestone (2020) | Achievement: Mid Year (June) | Achievement: End Year (December)
|  |  |  | 18000 | 25000
|  |  |  | Baseline (2020) | Target (2021) | Achievement: Mid Year (June) | Achievement: End Year (December)
|  |  | Means of Verification, Data Evidence Source | Quarterly Reports, Minutes of the Meetings
Country Programme Results Framework (add rows subject to project duration) |  |  | Project Linked to CPD Outcome | By 2022, environmental and natural resource management is strengthened, and communities have increased access to clean energy and are more resilient to climate change and disaster risks
|  |  | CPD Outcome Indicator | `- Plastic recycling management program to minimize negative impacts and risks to environmental and human health in India through a socio-technical model -The project aims to bring into sustainable plastic waste management practices, through a socio-technical model (segregation/collection/recycling) that is in line with Swachh Bharat Mission in India and the Plastic Waste Management Rules, 2016 &2018
|  |  | CPD Outcome Indicator | Baseline: | Target:
|  |  | Project Linked to CPD Output | CPD output | Effective solutions developed at national and subnational levels for sustainable management of natural resources and ecosystems, ozone depleting substances, chemicals and wastes
|  |  | CPD Indicator | Indicator
Progress towards CPD Output / Indicators / Targets
|  |  | CPD Indicator | Baseline as indicated in CPD (2017) | End target as indicated in CPD (2022) | Project Baseline (2017) | Project Annual Target (2018) | Achievement: Mid Year | Achievement: End Year
|  |  | Indicator 3.2.1 Number of policies and programme promoting sustainable livelihoods and incorporating gender responsive strategies for natural resources and ecosystems management | 4 | 7 | 4 | 5
[6 empty] | Baseline (2018) | Annual Target (2019) | Achievement: Mid Year | Achievement: End Year
[6 empty] | 5 | 6
[6 empty] | Baseline (2019) | Annual Target (2020) | Achievement: Mid Year | Achievement: End Year
[6 empty] | 6 | 7
[6 empty] | Baseline (2020) | Annual Target (2021) | Achievement: Mid Year | Achievement: End Year
[6 empty] | 7 | 7
[6 empty] | Baseline (2021) | Annual Target (2022) | Achievement: Mid Year | Achievement: End Year
[6 empty] | 7 | 7
|  |  | CPD Indicator | Baseline as indicated in CPD (2017) | End target as indicated in CPD (2022) | Project Baseline (2017) | Project Annual Target (2018) | Achievement: Mid Year | Achievement: End Year
|  |  | 3.2.2: Number of scalable initiatives incorporating improved management of ozone depleting substances, chemicals and/or wastes | 2 | 4 | 2 | 2
[6 empty] | Baseline (2018) | Annual Target (2019) | Achievement: Mid Year | Achievement: End Year
[6 empty] | 3 | 3
[6 empty] | Baseline (2019) | Annual Target (2020) | Achievement: Mid Year | Achievement: End Year
[6 empty] | 3 | 3
[6 empty] | Baseline (2020) | Annual Target (2021) | Achievement: Mid Year | Achievement: End Year
[6 empty] | 3 | 3
[6 empty] | Baseline (2021) | Annual Target (2022) | Achievement: Mid Year | Achievement: End Year
[6 empty] | 3 | 3
|  |  | Frequency of Data Collection | Monthly, Quarterly & Annually
|  |  | Means of Verification, Data Evidence Source | Minutes of Meetings, Monthly & Quarterly Reports, Submissions to Central/State Pollution Control Board, Urban Local Bodies etc.
|  |  | Other Projects Contributing to the CPD output |  | 00087493: India High Range Landscape, 00093341: Supporting Mercury Inventory, 00096606: Securing livelihoods Himalayas, 0009915: HPMP Phase II
Project Results Path |  |  | Progress towards the project outputs and activities
| Project Annual Outputs (From AWP) |  | Activities |  | Progress: QTR 1 | Progress: QTR 2 | Progress: QTR 3 | Progress: QTR 4
Project Multi-year Output (from prodoc)
1 | Output 1: Socio-technical model for effective management of plastic waste |  | Conducted baseline studies in various cities through specialist agencies Conducted survey meetings, stakeholder engagements etc. Trainings on project implementation |  | Various kinds of socio-technical models for effective plastic waste management being implemented in 35 cities. Initiated dialogue with the NITI Aayog to come up with a handbook for capacity building of urban local bodies and other stakeholders across the plastics value chain. 12,455.79 MTs of waste processed in Q1 of 2021 and 965 waste pickers onboarded. | Various kinds of socio-technical models for effective plastic waste management being implemented in 35 cities. Onground research and field work initiated for developing the NITI Aayog - UNDP Handbook on Sustainable Urban Plastic Waste Management. This includes one on one interactions with academia, recyclers, CSOs, govt. officials, Safai Sathis to understand various models of plastic waste management that exist in India. 3,030.49 MTs of waste processed during Q2 of 2020 and 570 waste pickers onboarded. | Various kinds of socio-technical models for effective plastic waste management being implemented in 35 cities. Onground research and field work initiated for developing the NITI Aayog - UNDP Handbook on Sustainable Urban Plastic Waste Management. This includes one on one interactions with academia, recyclers, CSOs, govt. officials, Safai Sathis to understand various models of plastic waste management that exist in India. 10,238.70 MTs of waste processed during Q3 of 2020 and 356 waste pickers onboarded. | Various kinds of socio-technical models for effective plastic waste management being implemented in 35 cities. Completion and launch of the handbook. Conducted 1st regional workshop in Mumbai for the states of Maharashtra & Goa to disseminate the learnings of the NITI Aayog-UNDP handbook. Conducted 2nd regional workshop in Tirupati for the states of Andhra Pradesh & Tamil Nadu. Entered into an MoU with the Ministry of Housing & Urban Affairs (MoHUA) to streamline the implementation of plastic waste management in line with Swachh Bharat Mission. 16,454.18 MTs of waste processed during Q4 of 2020 and 1,796 waste pickers onboarded.
| Output 2: Material Recovery Centers (Swachhta Kendra) for improved plastic waste management established in cities |  | Number of Swachhata Kendras facilities set up in citiees through no. of stakeholders consulted in establishing recovery centres Strenthening systems thinking through exchange visits and stakeholders exposure visits Project and NGO staff trainings on the project implementation, systems and approaches Organizing drives, meetings, exposure visits and rallies for programs on awareness, collection, segregation of plastics as special events in each city with ULBs, SPCBs outside the ward areas to create more support |  | Bhunabeshwar – • Source segregation training was being conducted at fortune towers. Officials, staffs and care takers of 5 corporates were trained on how to segregate waste generated in office premises into wet and dry. • A fire training programme was conducted for the safai sathis at TTS MRF. Both safai sathis of MRF and MCC were participated in the training programme. Ms. Nadia Rasheed, Deputy Resident Representative of UNDP India had visited TTS MRF along with state head of UNDP Odisha Ms. Abha Mishra and UNDP India Central Team Policy officer Jaimun Uthup. Ms. Rasheed had interactions with safai sathis and staffs of service provider CORE who are working at the MRF on inflow and outflow of waste, operational modality, working conditions in the MRF, livelihood promotions of safai sathis etc. Cuttack - Under Swachhta action plan of CMC, CMC in collaboration with UNDP-CORE organized Bulk Waste Generator Meeting for Hotels, Kalyan Mandaps, Malls and apartments. 59 participants attended the program and discussed various issues related to waste 28 Swachhta Kendras set up across the country. | Continuing the efforts on creating awareness on source segregation of waste, Aasra Welfare Association organised and conducted Awareness cum Dry Waste Collection Drive in Jogeshwari East, Vile Parle East and Andheri East Area and other neighbourhood area. The drive has helped in creating awareness and sensitizing the residents for waste segregation. On the occasion of World Environment Day, RaddiConnect organized an awareness cum collection drive in R North ward, Dahisar. The collection drive invitation was sent to all the BWG societies groups a week prior and the drive was organized successfully. An exposure visit was organized for SMS team at Swachhta Kendra at R North managed by RaddiConnect. The objective of the visit was to understand the day-to-day Swachhta Kendra operations, types of machineries, work management and other administrative procedures followed at Swachhta Kendra. Team of 4 members (Male=2, Female=2) from SMS visited the Swachhta Kendra. 28 Swachhta Kendras set up across the country. | Ministry of Jal Shakti carried out process documentation through videography of our Bhubaneswar TTS MRF as a model center to be featured in their collaterals. It was continued for 2 days. The team captured the all the activities of waste management starting from collection to segregation to processing in their camera. In the two days video shooting, the team of Ministry of Jal Shakti emphasized on machine operation and how different types waste are being processed in the MRF and captured all the relevant activities in the video. UNDP, through its urban social protection programme – Utthaan (Rise with Resilience), launched a facilitation Centre for Swachha Sathis (waste pickers) in Bhubaneswar today. In partnership with the Embassy of Japan and Bhubaneswar Municipal Corporation, the center is one of its kind and will support Swachha Sathis - known as Swachha Sathis in the state - with social protection schemes that promote their financial inclusion, health, and social security. The facility center is inaugurated by the Additional Commissioner and Dy. Commissioner of BMC in presence of officials of UNDP, HCCB, CORE and Swachha Sathis. Stree Mukti Sanghatana under Project Prithvi of Hindustan Coca-Cola Beverages Pvt Ltd and UNDP conducted a dedicated campaign to create awareness on segregation of waste. Volunteers reached out requesting the residents to store their plastic waste separately and hand it over to the collecting team during the drive. With the help of residence, Stree Mukti Sanghatana conducted Plastic collection drive in Bhandup. In which Stree Mukti Sanghatana’s team collect Mixed dry waste around 72 kg. | Team GIZ visited MRF center, Govind Nagar to understand the dry waste management system in Rishikesh and the mechanism on how to integrate the informal waste pickers into the mainstream. Virtual training on waste management for the students at Don Bosco School and Goa Home Science College. Bhoomi Pujan of Material Recovery Facility in Greater Noida to better manage plastic waste. Will setup a Swachhta Kendra in Greater Noida which will help manage 300 MT of dry waste per month & empower 400 safai sathis. Training of Sakhi Mandal members - A training on ‘Roles and responsibilities of Mohalla committee in ward wise waste management proces’ was conducted for Sakhi Mandal members. How do they get benefited with waste recycling businesses was also shared and asked their association for their livelihood purpose. Total 17 female members were participated in the training session along with of their circle Adhyaksha- Mrs Meena Ben.
| Output 3: : Institutionalization of Safai Sathis and improved socio-economic conditions of waste pickers |  | Ensuring the social security systems for NGOs for all the Safai Sathis, SHG members, and families, including children Conducting baseline assessment of Safai Sathis community to understand the gaps Conducting health camps, training programmes, skill developmnent trainings etc. Linking Safai Sathis as direct beneficiaries to various government schemes and their families as indirect beneficiaries |  | With the support of BMC and Govt. of Odisha, 8 nos. of CORE staffs has vaccinated against Covid-19 virus. Safai Sathis and other staffs are in pipeline to get the vaccine in second phase. 20 ID cards were distributed to female Safai Sathis in association with the Nagar Nigam under Swachh Survekshan event at Dehradun. A fire training programme was conducted for the safai sathis at TTS MRF. Both safai sathis of MRF and MCC were participated in the training programme. UNDP-HUL Plastic Waste Management Project celebrated the fourth Global Recycling Day on the 18th Mar 2021 with Unitec Fibres Private Limited, Tarapur. With the objective to introduce waste-pickers to the larger picture of recycling and highlighting their pivotal role in the overall processes of solid waste management and retrieving the valuable waste to get recycled, an exposure visit the recycling factory of Unitec Fibres was organized. | 20 Safai Sathis were formed on to two SHGs and engaged in operation of vehicles for collection of segregated waste in different wards of Cuttack city. Under Utthaan project these Safai Sathis were linked and have been formed into SHGs, the UNV is working to link these SHG to bank and open accounts. 10 Health camps were conducted in 10 locations of Mumbai. CARPE (Aurangabad) - Considering the government regulations 10 safai saathis over 45 years of age were vaccinated under UNDP and CARPE. A vaccination awareness was conducted with the he Safai Saathis prior to their vaccination. | Occupation ID Cards issued by Muskan Jyoti Samiti to 36 Safai Sathis in Lucknow A total of 15 Safai Sathis facilitated for Covid Vaccination (1st Dose of Vaccination administered) in Lucknow Cuttack – A meeting was held at Cuttack under the chairpersonship of Dy. Commissioner-CMC. The purpose of the meeting was to finalize the list of identified waste pickers in the city of Cuttack. CORE in coordination with UNV and support from CMC community mobilizer identified more than 700 Swachha sathis in the city Bubhaneshwar – 10 nos. of safai sathis and 34 nos. of safai sathisare being vaccinated with 1st and 2nd dose respectively in the month of July | Cuttack – 35 Swachh Sathis being trained in the 1st batch under Ama Sundargarh Swachh Sundargarh prog. The initiative in collaboration with UNDP India UNICEF India and supported by DMF, aims at Solid and Plastic Waste Management through behaviour change by awareness of the masses. Mumbai – Medical camp including the HB checking Test For anaemia detection was organized for the Daughters of Safai Sathis in S Ward. Around 73 children were the beneficiaries of the health camp. Findings of Test - Approximately 20% of Children are anaemic. Jaipur – Monthly ration kit distribution was organized under HCCB-UNDPNNJ Heritage by Center For Development Communication. The camp was conducted at Mathuradaspura MRF center, Jaipur. The kit was distributed to 157 Safai sathis, and has all the basic necessities like salt, flour, rice, oil, spices, dal. The kit will help the Safai Sathis with their ration needs, and help them set aside more for education of their kids, health and future deposits Mumbai – Prithvi PWM' Project, Stree Mukti Sanghatana-Parisar Bhaghini Vikas sangha has been connected with many Safai Sathis. SMS-PBVS provides gifts to Safai Sathis every year in Diwali as form of recognize their labour in making city clean. In this Diwali, PBVS gave bonus to 15 Safai Sathis in Chembur ward, who sell their material to PBVS. This was a small initiative taken by PBVS to help Safai Sathis and make them financially sustainable.
| Output 4: Knowledge management, monitoring and communication system developed |  | Number of training programmes on project implementation, systems and approach conducted Documentation and knowledge management of best practices, exposure visits, technical assessment, brochures, games development, case studies |  | Plastic Lao Mask Pao: The campaign was organized for 6 months at Khan Market, Delhi in collaboration with NDMC, and Haldwani where masks were exchanged for plastic. The stakeholders are apprised on the importance source segregation of plastic waste. (Currently operational at 2 locations in Delhi- Charkha Museum, CP and Khan Market and 1 in Haldwani) Launch of Utthan Project: Facilitation centre for the safai sathis under the Utthan Project inaugurated at Panaji in the presence of officials from CCP, Japan, UNDP, HDFC, etc. In the first week of February 2021, Plastic Lao Mask Pao (PLMP) campaign launched in KEast ward to help spread awareness on source segregation, recycling of plastics and to collect back plastics. The campaign kiosk had set up near Andheri (East) Railway Station, attracting citizens to segregate their waste and deposit their plastics in exchange of a reusable cloth mask, for a period of 15 days. The campaign had seen active participation of citizens enquiring about the campaign and depositing their plastics in exchange of a mask. | Celebrated World Environment Day: On World Environment Day the following activities were conducted in Rishikesh, Dehradun and Haldwani: - Plantation and Raksha sutra program in smriti van with Forest Department and HDFC Bank team at Rishikesh - Participated in plantation program organized by Forest Department in the presence of Mayor and Nagar Parishads in koyalghati, Rishikesh. - Plantation program in astha path with Municipal Commissioner and other officials from Nagar Nigam, Rishikesh. - Plants distributed to the medical staff and people who came for corona vaccination in government hospital at Rishikesh. - Drawing & Essay competition was organized for the children of safai sathis at Rishikesh. - Conducted plantation drive with the safai sathis at Dehradun. - To create awareness related to various environmental issues, video was shared with RWA members, Ward members, Municipal Commissioner, Sanitary Inspector and others from the community at Haldwani. Mumbai: On the occasion of 51st Earth Day, a weeklong campaign was started on Instagram and Facebook for supporting this year’s theme – ‘Restore Our Earth’ and to promote best practices. During this campaign, stories of 12 Green Warriors were posted on aforesaid social media platforms to inspire others. These 12 Green Warrior are following sustainable practices in their daily life, so through the short stories, the project to encourage others to start working for environment before it gets too late. | The United Nations Development Programme (UNDP), through its urban social protection programme – Utthaan (Rise with Resilience), launched a facilitation Centre for Swachha Sathis (waste pickers) in Bhubaneswar today. In partnership with the Embassy of Japan and Bhubaneswar Municipal Corporation, the center is one of its kind and will support Swachha Sathis - known as Swachha Sathis in the state - with social protection schemes that promote their financial inclusion, health, and social security. The facility center is inaugurated by the Additional Commissioner and Dy. Commissioner of BMC in presence of officials of UNDP, HCCB, CORE and Swachha Sathis. Participated in Kachra alag kro program: Participated in the kachra alag karo program organized by feedback foundation on Amrit diwas at Raghunath temple, Pragati vihar, ward no.12, where process of waste segregation was demonstrated, Prominent citizens were honored by the ward councilor and municipal commissioner for segregating their waste at the source and composting the wet waste at home. Celebrating swachhata ravivar: Every Sunday is celebrated as swachhata ravivar under which freedom from dirt campaign was initiated for creating awareness on source segregation, reducing the use of plastic, etc. at different areas in Rishikesh. Some of the Mega Events conducted on Sundays are: - A Cleanliness Campaign- "Gandagi se Ajadi Abhiyan" was organized in Govind Nagar slum area. - Gharelu Hanikarak Kachre se Azadi. - Single Plastic se Azadi Abhiyan. - Littering and Spitting se Azadi abhiyan. - Conducted a campaign at Someshwar Mandir to create awareness among citizens for source segregation of waste and demonstration of different category of waste were done. | Jammu - Nature walk in collaboration with state pollution control board and eco clubs of Education department attended by Chairperson SPCB Dr Neelu Gera, IFS, Regional Director SPCB and other senior officers. ECO CLUB members from higher secondary schools also took active part and, on the occasion, dustbins made up of multi layered plastics were displayed and all school teachers and students pledged to segregate and deposit plastic waste to our project MRF. Mumbai: 24th and 25th November 2021, with the initiative of Magic Bus Foundation, around 120 residences (Parents of students who are studying in municipal schools) Visited the Swachhta Kendra. SMS had also conducted an awareness session last year for the students who were studying in this municipal school. The aim of the visit was to spread the importance of Waste segregation at source and show them how Safai Sathis are contributing in keeping the city clean. An awareness campaign was organized under HCCB-UNDP-NNJ Heritage on plastic waste management by Center For Development Communication. The program was conducted at Rajasthan Administrative services (RAS) club, Jaipur. The event was graced by various Rajasthan administrative services officials. Ujjain – Plog run was conducted in Ujjain under the Swachhata Prerna Mahotsav Flog Run Madhya Pradesh. In this program plastic bags were distributed to all the participants from the Basix and got plastic collected. Involved in this program UMC commissioner sir, sansad mahoday etc. A cleanliness rally organized from Bhairav Mandir to Maya Market Shahee Smarak and Sabzi Mandi, Amit Gram for making citizen aware regarding source segregation and keep Rishikesh Clean and green
| Cumulative Project Delivery Status |  |  |  | Q1 | Q2 | Q3 | Q4
| Grand total budget (USD) |  |  |  | 331869.01 | 1176626.49 | 1025776.94 | 482718.56
| Delivery |  |  |  | 401945.74 | 513387.08 | 501513.94 | 745818.34
| Shortfall in delivery |  |  |  | 70076.73 | 663239.41 | 524263 | 263099.78
| Exp % against Budgets |  |  |  | 121% | 44% | 49% | 155%
Risk Log and Management (Quarterly Input)
| Risk Type** | Risk Description |  |  | Risk Assessment | Risk Mitigation strategy | Current Status | Escalation Required?
| Operational | There is a slow start to on-ground project procurement activities for Cities. |  |  | - Long time taken to finalize the processes with procurement of machineries, contracts for IPs; changing modalities of contractual. - Low expenses - Delayed recruitment of the Operations Manager - Taking longer time in submission of documents, reports for disbursements of funds from HCCB. | - Agree on the Modalities for implementation of the project for NGOs, CBOs and Companies. - Partner agencies engaged in implementing the project need to be shortlisted through a full-proof selection procedure. - These systems needed to be agreed before the start of the project - Training, awareness and involvement of the service providers on the approach. - On boarding of the waste- pickers by field-level NGOs in implementation of project activities. - Team to be geared with the SOPs on the procurement and finance of the project | Risk valid whenever a new city has to be onboarded | No
| Strategic | Long-time taken to develop a common understanding between different stakeholders, including governments on the project approach. |  |  | - Teams and stakeholders have/come with different perceptions due to different age groups, experiences and likes and dislikes. - Variance in Governance /management issues at the level of service providers (SPs) partners in the city - Complex and multidisciplinary and multi-faceted systems. - Time taken by governments to partner and allocation of space and sheds etc. | - A detailed operation manual, SOPs will be developed to define key accountabilities, management responsibilities, and operational procedures at all levels in the project. Implementation, Incorporating the lessons learnt - PSC Meetings, Technical Advisory Group (TAG), Review Meetings with Donors and Review Structure will be established and given strong support to ensure the ongoing effectiveness and efficiency in the project’s implementation. - Regular meetings, follow up on the different aspects of the projects with all Government stakeholders (eg SPCBs; ENV and UDD departments; Recyclers, NGOs etc) by the project team at all levels.. | Risk valid throughout the project timeline | No
| Operational | Unprecedented situations /events outside the control of projects |  |  | - Outbreak of a pandemics and related events - Fires, and strikes by the waste pickers. - Social unrest – Riots, civil disobedience movements - Natural disasters, floods etc. | - UNDP team to activate the task force that will lead risk mitigation during an unprecedented situation. Quick responses to meet food needs and access to Government schemes inflows. - Increase investments by project through better dialogues with Governments to do needful for the access of benefits by poor. - Increase program effectiveness and relevance through adaptive and informed decision-making - Inform effective and targeted allocation of resources to where they are most needed - Increase efficiency by safeguarding the accountable use of resources - Safeguard people and the environment - Manage and reduce to an acceptable level the safety and security risks to UNDP personnel, premises and assets. | Risk valid throughout the project timeline | No
**Risk Categories: Environmental, Financial, Operational, Organizational, Political, Regulatory, Strategic, Other
Lessons Learnt/ Reccomendations (Quarterly Input)
Measurable, specific, reporting and monitoring systems with clear indicators to be created in the project, at all levels, including the service providers, and Swachhta Kendras. The reporting system to be digitized with apt technology for transparency.
Align project implementation strategy with new policy amendments at the earliest and dialogues with the private sector for responsible investments.
Strengthen engagement with municipalities, state pollution control boards in cities
Planning IEC activities in advance for better visibility for the project and donors
Risk mitigation measures to be planned to face unprecedented times like the pandemic.
Streamlining and structuring financial and operational systems within the project.
Signed by
Srikrishna Balachandran