# 1st Quarter, 2013 Progress Report

DATE: April 12, 2013

Award ID: 00057016

Description: PAK/57016-Institutional Mechanisms for Integrated Environmental Management (JPC-1)"

Implementing Partner: Ministry of Climate Change

Period Covered: January – March 2013

1. Project Issues

| Status of Project Risks: N/A | Open Project Issues: N/A |
| --- | --- |

2. Project Performance

Activity ID:2 Deliverable Description: Consultants engagement continuity for fine tuning and approval of National Climate Change Policy for the Cabinet, having its endorsement from concerned stakeholders. Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (90%). Quality Criteria To identify the basic elements of Pakistan’s climate change policy for near to medium term future, assisting the government for sustainable economic growth by appropriately addressing the challenges posed by climate change, in particular the threats to Pakistan’s water, food and energy security.; Date 1st Quarter 2013; Results of Activities. User Perspective - One lead and three Mid level consultants hired during 2011 for formulation of Climate Change adaptation policy and action plans for adaptation and mitigation; Resource Status; Timeliness The Climate Change Policy which was approved by the Federal Cabinet on 26th September, 2012 was formally launched by the Ministry of Climate Change and UNDP on 26th February, 2013. The event was widely attended by representative of the federal government, provincial governments, donor community, civil society, academia, media and the UN Agencies. The Federal Minister for Climate Change was the Chief Guest on the occasion. In a meeting of the relevant stakeholders including Ministry of Climate Change and UNDP held during January 2013 it was decided that The National Climate Change Adaptation and Mitigation Action Plans were to be reviewed by the Consultant and put up for endorsement by the Advisory Group of MoCC as Framework for Implementation of NCCP. The same is being reviewed by the Consultant and will be pursued for endorsement by the Advisory Group of MoCC during 2nd quarter of 2013..

Financial as of March 31, 2013. Account; Fund; Donor; R. Party; Budget; Expenditure; Balance. 72100; 04000; 00012; CC; 15,750; 15,750. 71300; 04000; 00012; CC; 3,800; 3,800. 74200; 04000; 00012; CC; 4,500; 4,500. 74500; 04000; 00012; CC; 500; 500. Sub-Total; 24,550; 24,550.

OUTPUT 4: Enhanced Environmental Compliance in response to national and international guidelines, laws and regulatory frameworks Activity ID: 6 Description: One UN Programme Coordination Management 1st Quarter, 2013 Targets: - Programme Coordination and Implementation at Federal & Provincial Levels - Website Development and Up gradation - Programme Coordination and Implementation at Federal & Provincial Levels - Management and Operations

Activity ID:49.02.02 Deliverable Description: Website Development and Up gradation New website of One UN Joint Programme on Environment designed, developed, uploaded and maintained. Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (80%). Quality Criteria Relevant Information Sharing; Date 1st Quarter 2013; Results of Activities. User Perspective Online access to relevant information about One UN Joint Programme on Environment; Resource Status; Timeliness Ongoing Process.

Activity ID:49.04 Deliverable Description: Management and Operations Strengthening of the coordination unit established in Mo Climate Change, to support One UN JP Management as part of JPC-1 Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (55%). Quality Criteria Smooth functioning of coordination office.; Date 1st Quarter 2013; Results of Activities. User Perspective Strengthening of the coordination unit established in Mo Climate Change; Resource Status; Timeliness All related activities carried out as per approved AWP. Staff contracts were extended up to 31st December 2013..

Financial Summary. Account; Fund; Donor; R. Party; Budget; Expenditure; Balance. 71600; 04000; 00012; MoCC; 30,000; 221.20; 29,778.80. 71300; 04000; 00012; MoCC; 124,482; 24,958.67; 99,523.33. 71400; 04000; 00012; MoCC; 41,070; 5,892.40; 35,177.60. 72100; 04000; 00012; MoCC; 5,000; 5,000. 72200; 04000; 00012; MoCC; 800; 800. 72500; 04000; 00012; MoCC; 2,800; 716.67; 2,083.33. 73405; 04000; 00012; MoCC; 2,400; 290.31; 2,109.69. 73410; 04000; 00012; MoCC; 8,378; 1,549.35; 6,828.65. 73100; 04000; 00012; MoCC; 41,150; 1,671.77; 39,478.23. 74210; 04000; 00012; MoCC; 470; 470. 74500; 04000; 00012; MoCC; 5,809.23; 164.43; 5,644.80. 72400; 04000; 00012; MoCC; 5,200; 1,400.07; 3,799.93. Sub-Total; 267,559.23; 36,864.87; 230,694.36.

OUTPUT 7: Development of an inclusive common platform of relevant / key partners to connect policies, programmes and projects and actions by government, aid agencies, NGOs and UN Agencies and commercial activities of private sector into an agreed sustainable development. Project ID: 61 Description: CSOs implement interventions for the achievements of MDGs at local level including awareness raising campaigns on environment (including establishment of Environmental accounting system) 1st Quarter, 2013 Targets: Implementation of Grass Root Initiative Programme (GRIP)

Activity ID:61 Deliverable Description: Holding of GRIP lessons & sharing workshop Grass Root Initiative Programme launched in 2010 and under implementation which will be completed by this year end. Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (96%). Quality Criteria CSO Implement interventions for the achievements of MDGs at local level including awareness raising campaigns on environment (including establishment of Environmental accounting system); Date 1st Quarter 2013; Results of Activities. User Perspective Grass Root Initiative Programme Launched to develop an inclusive common platform of relevant/key partners to connect policies, programmes and projects and actions by government, aid agencies, NGOs and UN agencies, and commercial activities of the private sector into an agreed sustainable development.; Resource Status; Timeliness - UNDP and donor agencies apprised regarding physical and financial progress made by GRIP projects during the reporting period. - Government agencies apprised about the monitoring and evaluation mechanism of GRIP and updated on activities carried out. Information shared regarding physical and financial progress of GRIP projects with focal person of PICs in all provinces - As proposed by UNDP, USD 200,000 is expected to be earmarked for topping up activities of GRIP projects which are focused on water and energy related issues. During the 2nd quarter of 2013, finalization of CSOs will be made on basis of thematic issues and previous performance.. - Follow up activities regarding return of cheque by Basho Development Organization were carried out. PIC focal person in Gilgit Baltistan was requested to help in resolving the issue. - Final Evaluations of completed projects could not take place due to non availably of adequate funds for One UN Coordination office. These will now be conducted during April and May 2013. - A meeting was held with PCP regarding lesson learning and sharing workshop to discuss presentation. Follow will be carried out during 2nd quarter. - A lesson learning and sharing workshop which was scheduled to be held during 1st quarter of 2013 also could not take place due to non availably of funds and approval of work plan. This activity is now scheduled to take place by end of 2nd quarter..

Financial. Account; Fund; Donor; R. Party; Budget; Expenditure; Balance. 72100; 04000; 00012; CC. 72100; 30000; EFW; CC; 55,828.18; 55,828.18. Sub-Total; 55,828.18; 55,828.18.

| Activity ID:21. Deliverable Description: Management of Natural Resources in Demonstrated Regions under JPC-3 Preparation and implementation of area-based strategies for Integrated water and natural resources management Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (50%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Preparation and implementation of area-based strategies for Integrated water and natural resources management |  | Date 1st Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Implementation of Public Sector Projects jointly with Provincial Government Concerned Departments under the agreed thematic areas of JPC-3. - Protection and management of critical watersheds (including biodiversity conservation in AJK, Balochistan, GB, KPK, Punjab & Sindh) - Implementation of Reducing Emission from Deforestation and Forest Degradation (REDD+) Readiness Phase in Pakistan - Ramsar Advisory Mission (RAM) to Pakistan for Flood Management Strategy |  |  | Resource Status |  | 1xSindh, 2XAJ&K, 1xKPK public sector projects have been completed and final closure formalities of these projects are underway. 1xproject with WWF related to Ramsar Advisory mission to devise flood management strategy of selected areas has also been completed. There has been some cost saved in that project and meetings with WWF are being held in order to finalize new activities relevant to the recommendations of the strategy by the mission. Implementations on rest of the remaining nine projects are underway and successful interventions under various projects are being documented. Disbursements have been made according to the schedule and timeliness is being followed. The progress on the Gwadar and Musakheil projects has gained some momentum after extremely low pace initially and activities have been streamlined. A visit to the site is due and shall take place in the month of April to assess the actual progress on ground. For REDD+ Readiness phase in Pakistan project, district level workshops for more than 10 districts have been completed. And international consultant has been hired and a national workshop has been conducted. UN-REDD has also been taken on board where they have also committed additional TS support amounting to 109000 USD till 2014 in order to complete the roadmap process for this project. |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 72100 | 03000 |  | NET | CC | 11,95,634.10 |  | (12,525.75) |  | 1,208,159.85 |
| Sub-Total |  |  |  |  | 11,95,634.10 |  | (12,525.75) |  | 1,208,159.85 |

| Activity ID:21 Deliverable Description: Finalization of Rio + 20 Consultations for NSDS of Pakistan Finalization of NSDS of Pakistan Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (85%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Deliverable Description: Finalization for National Sustainable Development Strategy of Pakistan as Pakistan’s preparation for the Rio+ 20 UNCSD |  | Date 1st Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Consultations held at national and provincial level of all the relevant stakeholders for finalization of NSDS of Pakistan Preparations for the Rio+ 20 UNCSD |  |  | Resource Status |  | Timeliness/Progress Final Draft of the NSDS submitted to the Ministry of Climate Change for approval by the Federal Cabinet. The draft NSDS has been shared with relevant National and Provincial stakeholders by Ministry of Climate Change for final endorsement before submitting it to the Federal Cabinet for approval. The NSDS could not be sent to the Federal Cabinet because of the end of the term of the Government and will be presented for approval after the formation of the new government / federal cabinet. |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 74200 | 30000 |  | EFW | CC | 3,000 |  |  |  | 3,000 |
| 72100 | 30000 |  | EFW | CC | 2,000 |  |  |  | 2,000 |
| Sub-Total |  |  |  |  | 5,000 |  |  |  | 5,000 |

| Activity ID:13 Deliverable Description: Programme Framework for Promoting Trans-boundary Collaboration Between China and Pakistan for Karakoram-Pamir Landscape Promote Trans-boundary Technical Collaborations and Knowledge Sharing Platform Start and End Date: 1st April to 31st December 2013 % Progress to date: Completed (5%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Promote Trans-boundary Technical Collaborations and Knowledge Sharing Platform |  | Date 1st Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Promote Trans-boundary Technical Collaborations and Knowledge Sharing Platform |  |  | Resource Status |  | Timeliness/Progress The MoA of the transboundary project with ICIMOD has been signed and first instalment of 80% funds has been disbursed and inception workshop to finalize project modalities has also been held. One workshop at Gilgit shall take place in the end of April 2013. ICIMOD has delayed submission of quarterly progress report as per our formats and we are in continuous correspondence with them to abide by procedures. ICIMOD is in the process of submission of the same. |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 72100 | 04000 |  | 00012 | CC | 20,000 |  |  |  | 20,000 |
| Sub-Total |  |  |  |  | 20,000 |  |  |  | 20,000 |

| Activity ID: Deliverable Description: Enhanced Capacity of Provincial Implementation Committees (PICs) Start and End Date: 1st October to 31st December 2013 % Progress to date: Completed (100%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Strengthening of PICs for facilitating in creating enabling policy and grassroots conditions for efficient and effective management of the environment and more specifically Climate Change |  | Date 1st Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Meetings of the PICs held in respective provinces and AJ&K |  |  | Resource Status |  | Timeliness/Progress The meeting with PICs in their respective provinces could not be initiated during the 1st quarter 2013 because of the delay in the allocation of the budget for the activity and delayed approval of project extension. The meetings are scheduled to begin during June, 2013 after the general elections / formation of new provincial governments. |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 71600 | 04000 |  | 00012 | CC | 4,000 |  |  |  | 4,000 |
| 72100 | 04000 |  | 00012 | CC | 6,000 |  |  |  | 6,000 |
| Sub-Total |  |  |  |  | 10,000 |  |  |  | 10,000 |