# 2nd Quarter, 2013 Progress Report

DATE: July 08, 2013

Award ID: 00057016

Description: PAK/57016-Institutional Mechanisms for Integrated Environmental Management (JPC-1)"

Implementing sPartner: Climate Change Division

Period Covered: April - June 2013

1. Project Issues

| Status of Project Risks: N/A | Open Project Issues: N/A |
| --- | --- |

2. Project Performance

Activity ID:2 Deliverable Description: Consultants engagement continuity for fine tuning and approval of National Climate Change Policy for the Cabinet, having its endorsement from concerned stakeholders. Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (90%). Quality Criteria To identify the basic elements of Pakistan’s climate change policy for near to medium term future, assisting the government for sustainable economic growth by appropriately addressing the challenges posed by climate change, in particular the threats to Pakistan’s water, food and energy security.; Date 2nd Quarter 2013; Results of Activities. User Perspective - Climate Change Policy approved by the Federal Cabinet in September 2013.; Resource Status; Timeliness The Climate Change Policy which was approved by the Federal Cabinet on 26th September, 2012 was formally launched by the Ministry of Climate Change and UNDP on 26th February, 2013. The event was widely attended by representative of the federal government, provincial governments, donor community, civil society, academia, media and the UN Agencies. The Federal Minister for Climate Change was the Chief Guest on the occasion. In a meeting of the relevant stakeholders including Ministry of Climate Change and UNDP held during January 2013 it was decided that The National Climate Change Adaptation and Mitigation Action Plans were to be reviewed by the Consultant and put up for endorsement by the Advisory Group of MoCC as Framework for Implementation of NCCP. The document is still under review by the consultant in consultation with Climate Change Division. After review and necessary amendments the framework for implementation of NCCP will be pursued for approval by the Climate Change Division, Cabinet Secretariat..

Financial as of March 31, 2013. Account; Fund; Donor; R. Party; Budget; Expenditure; Balance. 72100; 04000; 00012; CC; 15,750; 10,228.76; 5,521.24. 71300; 04000; 00012; CC; 3,800; 2,994.01; 805.99. 74200; 04000; 00012; CC; 4,500; 4,500. 74500; 04000; 00012; CC; 500; 405.97; 94.03. Sub-Total; 24,550; 13,628.74; 10,921.26.

OUTPUT 4: Enhanced Environmental Compliance in response to national and international guidelines, laws and regulatory frameworks Activity ID: 6 Description: One UN Programme Coordination Management 1st Quarter, 2013 Targets: - Programme Coordination and Implementation at Federal & Provincial Levels - Website Development and Up gradation - Programme Coordination and Implementation at Federal & Provincial Levels - Management and Operations

Activity ID:49.02.02 Deliverable Description: Website Development and Up gradation New website of One UN Joint Programme on Environment designed, developed, uploaded and maintained. Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (80%). Quality Criteria Relevant Information Sharing; Date 2nd Quarter 2013; Results of Activities. User Perspective Online access to relevant information about One UN Joint Programme on Environment; Resource Status; Timeliness Ongoing Process.

Activity ID:49.04 Deliverable Description: Management and Operations Strengthening of the coordination unit established in Mo Climate Change, to support One UN JP Management as part of JPC-1 Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (55%). Quality Criteria Smooth functioning of coordination office.; Date 2nd Quarter 2013; Results of Activities. User Perspective Strengthening of the coordination unit established in Mo Climate Change; Resource Status; Timeliness All related activities carried out as per approved AWP. One staff member resigned from services on 21st June 2013..

Financial Summary. Account; Fund; Donor; R. Party; Budget; Expenditure; Balance. 71600; 04000; 00012; MoCC; 30,000; 14,403.94; 15,596.06. 71300; 04000; 00012; MoCC; 124,482; 41,663.41; 82,818.59. 71400; 04000; 00012; MoCC; 41,070; 9,533.36; 31,536.64. 72100; 04000; 00012; MoCC; 5,000; 5,000.00. 72200; 04000; 00012; MoCC; 800; 695.22; 104.78. 72500; 04000; 00012; MoCC; 2,800; 1,013.40; 1,786.60. 73405; 04000; 00012; MoCC; 2,400; 1,406.72; 993.28. 73410; 04000; 00012; MoCC; 8,378; 3,583.40; 4,794.60. 73100; 04000; 00012; MoCC; 41,150; 4,436.52; 36,713.48. 74210; 04000; 00012; MoCC; 470; 470.00. 74500; 04000; 00012; MoCC; 5,809.23; 727.41; 5,081.82. 72400; 04000; 00012; MoCC; 5,200; 2,559.69; 2,640.31. Sub-Total; 267,559.23; 80,023.07; 187,536.16.

OUTPUT 7: Development of an inclusive common platform of relevant / key partners to connect policies, programmes and projects and actions by government, aid agencies, NGOs and UN Agencies and commercial activities of private sector into an agreed sustainable development. Project ID: 61 Description: CSOs implement interventions for the achievements of MDGs at local level including awareness raising campaigns on environment (including establishment of Environmental accounting system) 2nd Quarter, 2013 Targets: Implementation of Grass Root Initiative Programme (GRIP)

Activity ID:61 Deliverable Description: Holding of GRIP lessons & sharing workshop Grass Root Initiative Programme launched in 2010 and under implementation which will be completed by this year end. Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (96%). Quality Criteria CSO Implement interventions for the achievements of MDGs at local level including awareness raising campaigns on environment (including establishment of Environmental accounting system); Date 2nd Quarter 2013; Results of Activities. User Perspective Grass Root Initiative Programme Launched to develop an inclusive common platform of relevant/key partners to connect policies, programmes and projects and actions by government, aid agencies, NGOs and UN agencies, and commercial activities of the private sector into an agreed sustainable development.; Resource Status; Timeliness - UNDP and donor agencies were apprised regarding physical and financial progress made by GRIP projects during the reporting period. - Government agencies were apprised about the monitoring and evaluation mechanism of GRIP and updated on activities carried out. Information shared regarding physical and financial progress of GRIP projects with focal person of PICs in all provinces - As proposed by UNDP, USD 100,000 is expected to be earmarked for topping up activities of GRIP projects which are focused on water and energy related issues. During the period under report, finalization of CSOs was made on basis of thematic issues and previous performance. Approval of topping up budget will be solicited during the beginning of 3rd quarter and MoAs will be signed with the relevant CSOs accordingly. The scaling up project activities will be completed within a period of 3 to 4 months. - Final Evaluations of seven and follow up visit of two completed projects was undertaken. Pending actions including completion of project closing formalities and final payments were released during the period under report. - Follow up meetings were held with PCP regarding lesson learning and sharing workshop to discuss presentation. - GRIP lesson learning and sharing workshop was held at Margalla Hotel, Islamabad on June 20, 2013. More than 110 participants attended the workshop. Country Director including senior members of ECCU – UNDP, Secretary CCD, Joint Secretary, officials of CCD and provincial departments also attended the event. - A Final report on GRIP projects including the proceedings of the Lessons Learning & Sharing workshop will be disseminated after printing during the 3rd quarter..

Financial. Account; Fund; Donor; R. Party; Budget; Expenditure; Balance. 72100; 04000; 00012; CC. 72100; 30000; EFW; CC; 65,270.00; 6,568.74; 58,701.26. Sub-Total; 65,270.00; 6,568.74; 58,701.26.

| Activity ID:21. Deliverable Description: Management of Natural Resources in Demonstrated Regions under JPC-3 Preparation and implementation of area-based strategies for Integrated water and natural resources management Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (50%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Preparation and implementation of area-based strategies for Integrated water and natural resources management |  | Date 2nd Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Implementation of Public Sector Projects jointly with Provincial Government Concerned Departments under the agreed thematic areas of JPC-3. - Protection and management of critical watersheds (including biodiversity conservation in AJK, Balochistan, GB, KPK, Punjab & Sindh) - Implementation of Reducing Emission from Deforestation and Forest Degradation (REDD+) Readiness Phase in Pakistan - Ramsar Advisory Mission (RAM) to Pakistan for Flood Management Strategy |  |  | Resource Status |  | Four Public sector projects i.e 1xSindh, 2XAJ&K, 1xKPK have been 100% completed and formally closed. 1xproject with WWF related to Ramsar Advisory mission to devise flood management strategy of selected areas has also been completed but there is some cost saving in the project and the funds are lying in RAM secretariat for which another visit has been planned of RAM mission in the month of October to give a final shape to the strategy document. Implementations on rest of the remaining nine projects are underway and successful interventions under various projects are being documented. Visits have been made to the projects in GB, Balochistan and Sindh and requests have been received from the projects to upscale some of the activities and in this regard meetings have been held with the IP’s to enhance their budgets by signing an addendum to the existing MoA, also the revised work plans and budget have also been finalized. The progress on the Gwadar and Musakheil projects has gained some momentum after extremely low pace initially and our office held meetings with the secretary forests and all related stakeholders so that we revised the work plan as per the existing conditions in order to streamline the activities. Also the monitoring of completed activities at project sites is currently underway For REDD+ Readiness phase in Pakistan project, provincial level workshops in all the provinces including the state of AJ&K have been completed. International consultant have been assigned to work on the RPP and also finalizing the proceedings of the workshops. Working group meetings with the provinces have also been held. ICIMOD has requested to extend the time period of the project to complete the roadmap process for which an additional amount is requested to cover the administrative cost where UN-REDD is also providing additional funds to the tune of 109,000 USD. |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 72100 | 03000 |  | NET | CC | 11,44,236.90 |  | 303,820.16 |  | 840,416.74 |
| Sub-Total |  |  |  |  | 11,44,236.90 |  | 303,820.16 |  | 840,416.74 |

| Activity ID:21 Deliverable Description: Finalization of Rio + 20 Consultations for NSDS of Pakistan Finalization of NSDS of Pakistan Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (85%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Deliverable Description: Finalization for National Sustainable Development Strategy of Pakistan as Pakistan’s preparation for the Rio+ 20 UNCSD |  | Date 2nd Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Consultations held at national and provincial level of all the relevant stakeholders for finalization of NSDS of Pakistan Preparations for the Rio+ 20 UNCSD |  |  | Resource Status |  | Timeliness/Progress Final Draft of the NSDS submitted to the Ministry of Climate Change for approval by the Federal Cabinet. The draft NSDS has been shared with relevant National and Provincial stakeholders by Ministry of Climate Change for final endorsement before submitting it to the Federal Cabinet for approval. After the formation of the new government and transformation of the Ministry of Climate Change into Climate Change Division under the Cabinet Secretariat the draft NSDS is now being pursued for approval by the Federal Cabinet. |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 74200 | 30000 |  | EFW | CC | 3,000 |  |  |  | 3,000 |
| 72100 | 30000 |  | EFW | CC | 2,000 |  |  |  | 2,000 |
| Sub-Total |  |  |  |  | 5,000 |  |  |  | 5,000 |

| Activity ID:13 Deliverable Description: Programme Framework for Promoting Trans-boundary Collaboration Between China and Pakistan for Karakoram-Pamir Landscape Promote Trans-boundary Technical Collaborations and Knowledge Sharing Platform Start and End Date: 1st April to 31st December 2013 % Progress to date: Completed (5%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Promote Trans-boundary Technical Collaborations and Knowledge Sharing Platform |  | Date 2nd Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Promote Trans-boundary Technical Collaborations and Knowledge Sharing Platform |  |  | Resource Status |  | Timeliness/Progress ICIMOD is implementing the project and held one regional workshop at Gilgit, GB and one in China. The reporting process has been very weak and no reports have been furnished to this office inspite of repeated requests. The case has been taken with the higher ups and release of next instalment has been suspended and further correspondence has been put on hold as the requirements were not met as per the agreed terms and conditions in the MoA.. |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 72100 | 04000 |  | 00012 | CC | 20,000 |  |  |  | 20,000 |
| Sub-Total |  |  |  |  | 20,000 |  |  |  | 20,000 |

| Activity ID: Deliverable Description: Enhanced Capacity of Provincial Implementation Committees (PICs) Start and End Date: 1st October to 31st December 2013 % Progress to date: Completed (100%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Strengthening of PICs for facilitating in creating enabling policy and grassroots conditions for efficient and effective management of the environment and more specifically Climate Change |  | Date 2nd Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Meetings of the PICs held in respective provinces and AJ&K |  |  | Resource Status |  | Timeliness/Progress The meeting with PICs are now scheduled to undertake after Ramadan as the new government has not settled down yet and it shall be appropriate to convene these meetings after the Eid. |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 71600 | 04000 |  | 00012 | CC | 4,000 |  |  |  | 4,000 |
| 72100 | 04000 |  | 00012 | CC | 6,000 |  |  |  | 6,000 |
| Sub-Total |  |  |  |  | 10,000 |  |  |  | 10,000 |