# 4th Quarter, 2013 Progress Report

DATE: January 10, 2014

Award ID: 00057016

Description: PAK/57016-Institutional Mechanisms for Integrated Environmental Management (JPC-1)"

Implementing Partner: Climate Change Division

Period Covered: October - December 2013

1. Project Issues

| Status of Project Risks: N/A | Open Project Issues: N/A |
| --- | --- |

2. Project Performance

Activity ID:2 Deliverable Description: Consultants engagement continuity for fine tuning and approval of National Climate Change Policy for the Cabinet, having its endorsement from concerned stakeholders. Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (100%). Quality Criteria To identify the basic elements of Pakistan’s climate change policy for near to medium term future, assisting the government for sustainable economic growth by appropriately addressing the challenges posed by climate change, in particular the threats to Pakistan’s water, food and energy security.; Date 4th Quarter 2013; Results of Activities. User Perspective - Climate Change Policy approved by the Federal Cabinet in October 2013.; Resource Status; Timeliness The Climate Change Policy which was approved by the Federal Cabinet on 26th September, 2012 was formally launched by the Ministry of Climate Change and UNDP on 26th February, 2013. The event was widely attended by representative of the federal government, provincial governments, donor community, civil society, academia, media and the UN Agencies. The Federal Minister for Climate Change was the Chief Guest on the occasion. In a meeting of the relevant stakeholders including Ministry of Climate Change and UNDP held during January 2013 it was decided that The National Climate Change Adaptation and Mitigation Action Plans were to be reviewed by the Consultant and put up for endorsement by the Advisory Group of MoCC as Framework for Implementation of NCCP. The Framework for Implementation of NCCP have been endorsed by the Climate Change Division and approved for printing..

Financial as of December 31, 2013. Account; Fund; Donor; R. Party; Budget; Expenditure; Balance. 72100; 04000; 00012; CC; 10,188; 10,187.41; 0.59. 71300; 04000; 00012; CC; 3,700; 3,686.28; 13.72. 74200; 30000; EFW; CC; 3,000; 1,321.52; 1,678.48. 74500; 04000; 00012; CC; 405; 177.97; 227.03. 72100; 30000; EFW; CC; 4,000; -; 4,000. Sub-Total; 21,293; 15,373.18; 5,919.82.

OUTPUT 4: Enhanced Environmental Compliance in response to national and international guidelines, laws and regulatory frameworks Activity ID: 6 Description: One UN Programme Coordination Management 4th Quarter, 2013 Targets: - Programme Coordination and Implementation at Federal & Provincial Levels - Website Development and Up gradation - Programme Coordination and Implementation at Federal & Provincial Levels - Management and Operations

Activity ID:49.02.02 Deliverable Description: Website Development and Up gradation New website of One UN Joint Programme on Environment designed, developed, uploaded and maintained. Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (95%). Quality Criteria Relevant Information Sharing; Date 4th Quarter 2013; Results of Activities. User Perspective Online access to relevant information about One UN Joint Programme on Environment; Resource Status; Timeliness Ongoing Process.

Activity ID:49.04 Deliverable Description: Management and Operations Strengthening of the coordination unit established in Mo Climate Change, to support One UN JP Management as part of JPC-1 Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (95%). Quality Criteria Smooth functioning of coordination office.; Date 4th Quarter 2013; Results of Activities. User Perspective Strengthening of the coordination unit established in CCD; Resource Status; Timeliness All related activities carried out as per approved AWP..

Financial Summary. Account; Fund; Donor; R. Party; Budget; Expenditure; Balance. 71600; 04000; 00012; MoCC; 49,800.00; 30,898.19; 18,901.81. 71300; 04000; 00012; MoCC; 123,059.00; 87,835.15; 35,223.85. 71400; 04000; 00012; MoCC; 29,725.00; 20,391.96; 9,333.04. 72100; 04000; 00012; MoCC; 310.00; 309.73; 0.27. 72200; 04000; 00012; MoCC; 695.00; 692.41; 2.59. 72500; 04000; 00012; MoCC; 3,300.00; 3,296.84; 3.16. 73405; 04000; 00012; MoCC; 2,000.00; 1,854.92; 145.08. 73410; 04000; 00012; MoCC; 7,528.00; 6,062.02; 1,465.98. 73100; 04000; 00012; MoCC; 41,300.00; 39,370.38; 1,929.62. 74210; 04000; 00012; MoCC; 50.00; 47.84; 2.16. 74500; 04000; 00012; MoCC; 1,000.00; 64.74; 935.26. 72400; 04000; 00012; MoCC; 5,525.00; 5,505.00; 20.00. Sub-Total; 271,442.00; 195,829.18; 75,612.82.

OUTPUT 7: Development of an inclusive common platform of relevant / key partners to connect policies, programmes and projects and actions by government, aid agencies, NGOs and UN Agencies and commercial activities of private sector into an agreed sustainable development. Project ID: 61 Description: CSOs implement interventions for the achievements of MDGs at local level including awareness raising campaigns on environment (including establishment of Environmental accounting system) 3rd Quarter, 2013 Targets: Implementation of Grass Root Initiative Programme (GRIP)

Activity ID:61 Deliverable Description: Holding of GRIP lessons & sharing workshop Grass Root Initiative Programme launched in 2010 and under implementation which will be completed by this year end. Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (100%). Quality Criteria CSO Implement interventions for the achievements of MDGs at local level including awareness raising campaigns on environment (including establishment of Environmental accounting system); Date 4th Quarter 2013; Results of Activities. User Perspective Grass Root Initiative Programme Launched to develop an inclusive common platform of relevant/key partners to connect policies, programmes and projects and actions by government, aid agencies, NGOs and UN agencies, and commercial activities of the private sector into an agreed sustainable development.; Resource Status; Timeliness - All projects closed and 100 % funds utilized. - UNDP and donor agencies were apprised regarding physical and financial progress made by GRIP projects during the reporting period. - A detailed report on GRIP projects including the proceedings of the Lessons Learning & Sharing workshop printed and disseminated..

Financial. Account; Fund; Donor; R. Party; Budget; Expenditure; Balance. 71600; 30000; EFW; CC; 28,000.00; 16,573.58; 11,426.42. 72100; 30000; EFW; CC; 27,370.00; 16,626.99; 10,743.01. 74200; 30000; EFW; CC; 5,700.00; 4,960.97; 739.03. Sub-Total; 61,070.00; 38,161.54; 22,908.46.

| Activity ID:21. Deliverable Description: Management of Natural Resources in Demonstrated Regions under JPC-3 Preparation and implementation of area-based strategies for Integrated water and natural resources management Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (75%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Preparation and implementation of area-based strategies for Integrated water and natural resources management |  | Date 4th Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Implementation of Public Sector Projects jointly with Provincial Government Concerned Departments under the agreed thematic areas of JPC-3. - Protection and management of critical watersheds (including biodiversity conservation in AJK, Balochistan, GB, KPK, Punjab & Sindh) - Implementation of Reducing Emission from Deforestation and Forest Degradation (REDD+) Readiness Phase in Pakistan - Ramsar Advisory Mission (RAM) to Pakistan for Flood Management Strategy |  |  | Resource Status |  | 1xproject with WWF related to Ramsar Advisory mission to devise flood management strategy of selected areas has also been completed but there is some cost saving in the project and the funds are lying in RAM secretariat for which another visit has been planned of RAM mission in the month of October to give a final shape to the strategy document. REDD+ Readiness phase in Pakistan project, RPP has been submitted to the world bank and in order to get the input from the provinces against the submitted RPP, a round of workshop for all the provinces in order to incorporate their feedback in the offing. Successful Implementation of 15 public sector projects and holding of 2 days workshop on “Learning & Sharing Experiences” of the public sector projects 5th meeting of the JPSC on Environment held on 31st December, 2013 under chairmanship of Secretary, Climate Change Division and Co – Chaired by UNDP & UNICEF. The JPSC approved carrying over activities of 6 projects till March 2014 for desirable conclusion. |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 72100 | 03000 |  | NET | CC | 922,455.00 |  | 842,373.59 |  | 80,081.41 |
| Sub-Total |  |  |  |  | 922,455.00 |  | 842,373.59 |  | 80,081.41 |

| Activity ID:21 Deliverable Description: Finalization of Rio + 20 Consultations for NSDS of Pakistan Finalization of NSDS of Pakistan Start and End Date: 1st January to 31st December 2013 % Progress to date: Completed (95%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Deliverable Description: Finalization for National Sustainable Development Strategy of Pakistan as Pakistan’s preparation for the Rio+ 20 UNCSD |  | Date 4th Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Consultations held at national and provincial level of all the relevant stakeholders for finalization of NSDS of Pakistan Preparations for the Rio+ 20 UNCSD |  |  | Resource Status |  | Timeliness/Progress Final Draft of the NSDS submitted to the Ministry of Climate Change for approval by the Federal Cabinet. The draft NSDS has been shared with relevant National and Provincial stakeholders by Ministry of Climate Change for final endorsement before submitting it to the Federal Cabinet for approval. NSDS is still being pursued for approval by the Federal Cabinet by the Climate Change Division. |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 74200 | 30000 |  | EFW | CC | 1,200.00 |  | 1,087.01 |  | 112.99 |
| 72100 | 30000 |  | EFW | CC | 1,000.00 |  | 932.12 |  | 67.88 |
| Sub-Total |  |  |  |  | 2,200.00 |  | 2,019.13 |  | 180.87 |

| Activity ID:13 Deliverable Description: Programme Framework for Promoting Trans-boundary Collaboration Between China and Pakistan for Karakoram-Pamir Landscape Promote Trans-boundary Technical Collaborations and Knowledge Sharing Platform Start and End Date: 1st April to 31st December 2013 % Progress to date: Completed (95%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Promote Trans-boundary Technical Collaborations and Knowledge Sharing Platform |  | Date 4th Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Promote Trans-boundary Technical Collaborations and Knowledge Sharing Platform |  |  | Resource Status |  | Timeliness/Progress After pursual of the case, the progress reports and the project terminal reports have been submitted to one UN JPE. There is one requirement left i.e submission of all expenditure details and related bills and receipts etc which ICICMOD has failed to provide even after continuous pursuance by this office. The matter was placed before 5th meeting of the Joint Programme Steering Committee on Environment chaired by Secretary, Climate Change Division held on 31st December, 2013. It was decided during the meeting that the last instalment to be with held until ICIMOD complies with the financial requirements as stipulated in the MOA. Since the One UN Joint Programme on Environment closed operationally on 31st December, 2013 the unutilized funds have been returned to the donor i.e. UNDP and the project stands closed. |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 72100 | 04000 |  | 00012 | CC | 16,500.00 |  |  |  | 16,500.00 |
| Sub-Total |  |  |  |  | 16,500.00 |  |  |  | 16,500.00 |

| Activity ID: Deliverable Description: Enhanced Capacity of Provincial Implementation Committees (PICs) Start and End Date: 1st October to 31st December 2013 % Progress to date: Completed (95%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Criteria Strengthening of PICs for facilitating in creating enabling policy and grassroots conditions for efficient and effective management of the environment and more specifically Climate Change |  | Date 4th Quarter 2013 | Results of Activities |  |  |  |  |  |  |
|  |  |  | User Perspective Meetings of the PICs held in respective provinces and AJ&K |  |  | Resource Status |  | Timeliness/Progress A 2 day Workshop held for “Sharing & Learning Experiences” Public Sector Projects |  |
| Financial |  |  |  |  |  |  |  |  |  |
| Account | Fund |  | Donor | R. Party | Budget |  | Expenditure |  | Balance |
| 71600 | 04000 |  | 00012 | CC |  |  |  |  |  |
| 72100 | 04000 |  | 00012 | CC |  |  |  |  |  |
| Sub-Total |  |  |  |  |  |  |  |  |  |