Knowledge for Development Management (K4DM) for ERD UN Wing Project

Quarterly Project Progress Report for 3rd Quarter

Reporting period: July -September 2017

Context	2

Indicator Progress	2

Key Achievements	4

Resource Utilisation	5

Lessons Learned	5

South-South and Partnerships	7

The Way Forward	7

# Context

‘Knowledge for Development Management (K4DM) for ERD UN Wing’ Project is a joint initiative of the GoB and UNDP Bangladesh which has been undertaken based on the results of K4DM Initiation Plan (IP) 2014-16 and will be executed in the context of the UNDAF Action Plan. In the context of declining ODA and increased emphasis on results, the project aims to a) simplify programming procedures and improve knowledge management, b) promote new knowledge and resource partnerships under the canopy of South-South and Triangular as well as Public-Private Partnership modality and c) support a common expert pool, strategic knowledge generation and innovative programming.

The project will is mainly anchored in the UN wing of Economic Relations Division ERD of Ministry of Finance, but will seek to reach out to all Implementing Partners including line ministries, civil society, think-tanks, academia, eminent personnel and grassroots and ultimately create an inclusive ecosystem to enable attainment of results stipulated in the UNDAF, especially in the area of UNDP supported results. Indicator Progress

| Output 1 | Indicators | Target (Year-2017) |  | Progress |  |
| --- | --- | --- | --- | --- | --- |
| South-South/Triangular and Public-Private Partnership Promoted | Number of South-South and triangular cooperation partnership developed by ERD. Number of national SS&TC partnerships delivering measurable and sustainable development benefits for participants. Existence of inter-ministerial collaboration on South-South and Triangular cooperation. Number of inter-ministerial meetings and consultations organized. | 2 South-South and triangular cooperation partnership developed by ERD. 2 national SS&TC partnerships delivering measurable and sustainable development benefits for participants. System of regular collaboration for promotion of South-South partnership among different Ministries/Divisions established. 4 inter-ministerial meetings and consultations organized. |  | A consultation on South-South and Triangular Cooperation was organized by K4DM Project on 27 July 2017 at NEC Conference Room with Ms. Shamima Nargis, Additional Secretary ( UN ) and NPD of K4DM Project in chair, Kazi Shofiqul Azam, Secretary of ERD attended as Chief Guest. Dr. A K Abdul Momen, National Consultant presented study findings in this session. In presentation, Dr. Momen mentioned that replications of best practices in socio-economic development in the countries of South will contribute to the well being of the people in this region. Mr. Sudipto Mukerjee, UNDP Country Director attended as guest of honor |  |
| Output 2 | Indicators | Target (Year-2017) |  | Progress towards targets |  |
| Programming Manuals Revised and Implemented | The revised NIM manual approved by GoB and UNDP. Joint task team of ERD, line ministry and UNDP constituted and operationalized. Number of meetings/ consultation sessions organized. | Acceptance of the revised manual by both UNDP and the Government of Bangladesh. Formation of the Joint Task Team and regular meeting of the team is organized. 4 meetings/consultation sessions organized on the NIM. |  | A sharing session on National Implementation Modality ( NIM) was held in UN Conference Room of ERD on 17 July From UNDP, a presentation was made by Sheikh Munir Hossain, Head of Finance, where the key features of this new corporate guideline for NIM was shared. It was decided thar, ERD would review NIM manual and send comments to UNDP Country Office. |  |
| Output 3 | Indicators |  | Target (Year-2017) |  | Progress towards targets |
| Strategic research/collaboration supported | Concurrence of eminent persons obtained to join the EPG (at least 20 eminent persons). Number of consultative session organized by GoB with eminent persons. |  | Initiative of developing collaboration with the Eminent Persons Group (EPG) is accepted by the Eminent Persons. 4 consultation sessions organized with the EPG. |  | A total of 10 thematic groups were formed engaging the eminent persons based on their consents. This group will contribute in thematic consultation engaging other local experts. |
| Output 4 | Indicators |  | Target (Year-2017) |  | Progress towards targets |
| Collaboration on Resource Mobilization Strengthened | Number of scopes and areas of collaboration for resource mobilization identified. Number of experience sharing event organized for GoB officials with other countries and partners. |  | 2 scopes and areas of collaboration for resource mobilization identified. 2 experience sharing event organized for GoB officials with other countries and partners. |  | Study findings of Resource Mobilization were disseminated |
| Output 5 | Indicators |  | Target (Year-2017) |  | Progress towards targets |
| Project Information Repository Platform Operationalized | A project information repository at ERD UN Wing developed Information of UNDP projects updated in the respective repository Capacity of ERD officials on ODA and project management and administration of the repository |  | Existence of an Information Repository at ERD UN Wing 75% of information are updated in the repository 180 officials from ERD and other agencies are trained |  | Training session on Information Repository continued and based on ERD observation, some new options also added in software to make its access to the user’s from any part of the country. The software was named as ERDPEDIA |

# Key Achievements

- Training on Development Effectiveness was held on 15 June 2018. Mr. Monowar Ahmed, Additional Secretary conducted the session

- A training session on Theory of Change and Results based Management was held 10 August at BICC. 30 Officials from ERD and other ministry and divisions participated in this course. Ms. Lazima Onta Bhatta, Head of RBM Unit in UNDP Regional Office conducted different sessions

- The project organized Knowledge Exchange Visit to Philippines from 22-25 August 2017, a 8 members team from ERD and other ministry visited Philippines to gather experience on diaspora engagement in national development. During the visit, the team participated in meetings and sharing sessions with the senior management of relevant organizations such as Commission on Filipinos Overseas , Overseas Workers Welfare Administration, UNDP Philippine Country Office

- 4th meeting of Project Executive Board was held on 20 August 2017 with ERD Secretary in chair. The meeting decided to extend the project upto June 2018.

.

# Resource Utilisation

Budgetary allocation for 2017 is total ---------------------, out of this amount, BDT -----------------------were spent to carry out following activities during July-September 2017

Table 1: Activities related to budget and expenditure in USD

| Activity | Budget |  |  | Expenditure |  |  | % of Delivery |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | NEX | UNDP | TOTAL | NEX | UNDP | TOTAL |  |
| South-South/Triangular and Public-Private Partnership Promoted | 1,500.00 | 12,500.00 | 14,000.00 | 82.69 | 1,000.00 | 1,082.69 | 7.73% |
| Programming Manuals Revised and Implemented | 1000.00 | - | 1,000.00 | - | - | 0.00 | 0.00% |
| Strategic research/collaboration supported | 2,000.00 | 14,000.00 | 16,000.00 | - | - | 0.00 | 0.00% |
| Collaboration on Resource Mobilization Strengthened | 1000 | 44,200.00 | 45,200.00 | 64.69 | 2,228.78 | 2,293.47 | 5.07% |
| Project Information Repository Platform Operationalized | 10,000.00 | 67,000.00 | 77,000.00 | 17.48 | 34,662.50 | 34,679.98 | 45.04% |
| Platform for engagement with NRBs established | 500.00 | 9,500.00 | 10,000.00 | - | - | 0.00 | 0.00% |
| Strategic mechanisms to review progress towards Human Development Established | 1,000.00 | 9,000.00 | 10,000.00 | - | - | 0.00 | 0.00% |
| Administrative, operational and technical support provided | 2,700.00 | 74,100.00 | 76,800.00 | 218.20 | 22,614.04 | 22,832.24 | 29.73% |
| TOTAL | 19,700.00 | 230,300.00 | 250,000.00 | 383.06 | 60,505.32 | 60,888.38 | 24.36% |

# Lessons Learned

- Learning from Philippine visit will be supportive to form institutional arrangement for engagement of NRB in national development

- Government agencies need to concentrate on ToC and Results Bases Management to ensure the effectiveness of development interventions

- Starting a project on time and taking plan and program based on emerging need is important