Knowledge for Development Management (K4DM) for ERD UN Wing Project

Quarterly Project Progress Report for 2nd  Quarter

Reporting period: April -June  2017

Context	2

Indicator Progress	2

Key Achievements	4

Resource Utilisation	5

Lessons Learned	5

South-South and Partnerships	7

The Way Forward	7

# Context

‘Knowledge for Development Management (K4DM) for ERD UN Wing’ Project is a joint initiative of the GoB and UNDP Bangladesh which has been undertaken based on the results of K4DM Initiation Plan (IP) 2014-16 and will be executed in the context of the UNDAF Action Plan. In the context of declining ODA and increased emphasis on results, the project aims to a) simplify programming procedures and improve knowledge management, b) promote new knowledge and resource partnerships under the canopy of South-South and Triangular as well as Public-Private Partnership modality and c) support a common expert pool, strategic knowledge generation and innovative programming.

The project will is mainly anchored in the UN wing of Economic Relations Division ERD of Ministry of Finance, but will seek to reach out to all Implementing Partners including line ministries, civil society, think-tanks, academia, eminent personnel and grassroots and ultimately create an inclusive ecosystem to enable attainment of results stipulated in the UNDAF, especially in the area of UNDP supported results. Implementation period is September 2014 to August 2017. Total budget of the project is USD 3.00 million which is funded by UNDP as project aid.

# Indicator Progress

| Output 1 | Indicators | Target (Year-2017) |  | Progress towards targets |  |
| --- | --- | --- | --- | --- | --- |
| South-South/Triangular and Public-Private Partnership Promoted | Number of South-South and triangular cooperation partnership developed by ERD. Number of national SS&TC partnerships delivering measurable and sustainable development benefits for participants. Existence of inter-ministerial collaboration on South-South and Triangular cooperation. Number of inter-ministerial meetings and consultations organized. | 2 South-South and triangular cooperation partnership developed by ERD. 2 national SS&TC partnerships delivering measurable and sustainable development benefits for participants. System of regular collaboration for promotion of South-South partnership among different Ministries/Divisions established. 4 inter-ministerial meetings and consultations organized. |  | Dr. A K Abdul Momen, former Bangladesh representative to UN and currently a National Consultant of K4DM Project has prepared the draft report of South -South and Triangular Cooperation. . This report mentioned that, South-South Cooperation has increasingly demonstrated contribution to development results through a variety of flexible cooperation modalities. The report also added, strong economic performance and other successes of many countries in the South in recent have proved that south is now poised to play its due role in the transformative agenda. |  |
| Output 2 | Indicators | Target (Year-2017) |  | Progress towards targets |  |
| Programming Manuals Revised and Implemented | The revised NIM manual approved by GoB and UNDP. Joint task team of ERD, line ministry and UNDP constituted and operationalized. Number of meetings/ consultation sessions organized. | Acceptance of the revised manual by both UNDP and the Government of Bangladesh. Formation of the Joint Task Team and regular meeting of the team is organized. 4 meetings/consultation sessions organized on the NIM. |  | Initiative has been taken to organize a discussion with participation of ERD officials along with UNDP to review the manual and prepare ERD observations. |  |
| Output 3 | Indicators |  | Target (Year-2017) |  | Progress towards targets |
| Strategic research/collaboration supported | Concurrence of eminent persons obtained to join the EPG (at least 20 eminent persons). Number of consultative session organized by GoB with eminent persons. |  | Initiative of developing collaboration with the Eminent Persons Group (EPG) is accepted by the Eminent Persons. 4 consultation sessions organized with the EPG. |  | A total of 35 eminent persons finally consented to join the group. First meeting of Eminent Persons Group was held on June 04, 2017 at BICC. Secretary ERD chaired the session. The eminent persons endorsed the ToR of the group and recommended the renaming of the Group as Consultative Group of ERD. The eminent persons also agreed on ERD proposal for formation of Thematic Group on different areas with their active engagement. |
| Output 4 | Indicators |  | Target (Year-2017) |  | Progress towards targets |
| Collaboration on Resource Mobilization Strengthened | Number of scopes and areas of collaboration for resource mobilization identified. Number of experience sharing event organized for GoB officials with other countries and partners. |  | 2 scopes and areas of collaboration for resource mobilization identified. 2 experience sharing event organized for GoB officials with other countries and partners. |  | Dr. Monzor Hossain, Senior Research Fellow of Bangladesh Institute of Development Studies. A dissemination workshop on the findings of the study was organized on 17 April at NEC Conference Room. The Researcher prepared National Development Cooperation Policy. The overaching goals of the strategy is to enhance the development initiatives with sustainable resource base. Six Objectives of the strategy includes- allignmnet with national development priorities, ensure development effectiveness Framework of partnership dialogue, broaden resource base, maintain debt sustainability and capacity building. |
| Output 5 | Indicators |  | Target (Year-2017) |  | Progress towards targets |
| Project Information Repository Platform Operationalized | A project information repository at ERD UN Wing developed Information of UNDP projects updated in the respective repository Capacity of ERD officials on ODA and project management and administration of the repository |  | Existence of an Information Repository at ERD UN Wing 75% of information are updated in the repository 180 officials from ERD and other agencies are trained |  | K4DM continued its support to ERD for activation of information repository. After completing technical preparation and instalment of equipment, first training session on its operational aspects was held on 18 April 2017 at ERD Computer lab. A total of 30 officials from different wings of ERD participated in the training session. |

# Key Achievements

With the objective of promotion of South-South cooperation, the project has initiated collection and compilation of best practices of different Government and non-Government organizations. South-South expert and Bangladesh’s former Permanent Representative to the UN, Dr. AK Abdul Momen, on behalf of the project, has prepared the draft report which is under review and finalization. The best practices, considered as development solutions, will be disseminated among stakeholders and Bangladesh Missions abroad for promotion in other countries.

In the context of reducing official development assistance (ODA), ERD is developing ৃ resource mobilization strategy and plan of action. Resource mobilization report

Capacity Building : With the objective of creating broader stake in capacity building for leveraging effective knowledge in development management, the project organized  training programmes on Project Management, and an Orientation on 7th Five Years Plan.

- Establishment of EPG :  formally Eminent Persons Group was launched on 4 June 2017, where 30 eminent persons participated.

- Technical installment and other preparatory work of establishing information repository has been finished. ERD officials are being trained on operational aspects of this new software.

.

# Resource Utilisation

Budgetary allocation for 2017 is total ---------------------, out of this amount, BDT -----------------------were spent to carry out following activities.

Table 1: Activities related to budget and expenditure in USD

| Activity | Budget |  |  | Expenditure |  |  | % of Delivery |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | NEX | UNDP | TOTAL | NEX | UNDP | TOTAL |  |
| South-South/Triangular and Public-Private Partnership Promoted | 1,500.00 | 12,500.00 | 14,000.00 | 82.69 | 1,000.00 | 1,082.69 | 7.73% |
| Programming Manuals Revised and Implemented | 1000.00 | - | 1,000.00 | - | - | 0.00 | 0.00% |
| Strategic research/collaboration supported | 2,000.00 | 14,000.00 | 16,000.00 | - | - | 0.00 | 0.00% |
| Collaboration on Resource Mobilization Strengthened | 1000 | 44,200.00 | 45,200.00 | 64.69 | 2,228.78 | 2,293.47 | 5.07% |
| Project Information Repository Platform Operationalized | 10,000.00 | 67,000.00 | 77,000.00 | 17.48 | 34,662.50 | 34,679.98 | 45.04% |
| Platform for engagement with NRBs established | 500.00 | 9,500.00 | 10,000.00 | - | - | 0.00 | 0.00% |
| Strategic mechanisms to review progress towards Human Development Established | 1,000.00 | 9,000.00 | 10,000.00 | - | - | 0.00 | 0.00% |
| Administrative, operational and technical support provided | 2,700.00 | 74,100.00 | 76,800.00 | 218.20 | 22,614.04 | 22,832.24 | 29.73% |
| TOTAL | 19,700.00 | 230,300.00 | 250,000.00 | 383.06 | 60,505.32 | 60,888.38 | 24.36% |

# Lessons Learned

- Response from Eminent Persons was very much encouraging to work with Government of Bangladesh for better interest of the nation

- Training session need to be more interactive

- Better coordination is required between GoB and UNDP for making conscious on operational document such as NIM Manual

- Follow up training session is required for ERD officials for effective  functioning of repository