Knowledge for Development Management (K4DM) for ERD UN Wing Project

Quarterly Project Progress Report for 1st Quarter

Reporting period: January-March 2017

Context	2

Indicator Progress	2

Key Achievements	4

Resource Utilisation	5

Lessons Learned	5

South-South and Partnerships	7

The Way Forward	7

# Context

‘Knowledge for Development Management (K4DM) for ERD UN Wing’ Project is a joint initiative of the GoB and UNDP Bangladesh which has been undertaken based on the results of K4DM Initiation Plan (IP) 2014-16 and will be executed in the context of the UNDAF Action Plan. In the context of declining ODA and increased emphasis on results, the project aims to a) simplify programming procedures and improve knowledge management, b) promote new knowledge and resource partnerships under the canopy of South-South and Triangular as well as Public-Private Partnership modality and c) support a common expert pool, strategic knowledge generation and innovative programming.

The project will is mainly anchored in the UN wing of Economic Relations Division ERD of Ministry of Finance, but will seek to reach out to all Implementing Partners including line ministries, civil society, think-tanks, academia, eminent personnel and grassroots and ultimately create an inclusive ecosystem to enable attainment of results stipulated in the UNDAF, especially in the area of UNDP supported results. Implementation period is September 2014 to August 2017. Total budget of the project is USD 3.00 million which is funded by UNDP as project aid.

# Indicator Progress

| Output 1 | Indicators | Target (Year-2017) |  | Progress towards targets |  |
| --- | --- | --- | --- | --- | --- |
| South-South/Triangular and Public-Private Partnership Promoted | Number of South-South and triangular cooperation partnership developed by ERD. Number of national SS&TC partnerships delivering measurable and sustainable development benefits for participants. Existence of inter-ministerial collaboration on South-South and Triangular cooperation. Number of inter-ministerial meetings and consultations organized. | 2 South-South and triangular cooperation partnership developed by ERD. 2 national SS&TC partnerships delivering measurable and sustainable development benefits for participants. System of regular collaboration for promotion of South-South partnership among different Ministries/Divisions established. 4 inter-ministerial meetings and consultations organized. |  | A National Consultant is working for collection and compilation of best practices of South-South cooperation. ERD has undertaken an initiative of formation of a Forum of the Finance and Development Ministers of global South. The national consultant is also working for development of the structure of the proposed Forum. ERD has incorporated representatives of different Ministries/Divisions to participate in overseas study visits organized for exploring South-South and Triangular cooperation. ERD has nominated one representative of Bangladesh Bank to a South-South Education Programme to be held on May 2017 at Beijing. |  |
| Output 2 | Indicators | Target (Year-2017) |  | Progress towards targets |  |
| Programming Manuals Revised and Implemented | The revised NIM manual approved by GoB and UNDP. Joint task team of ERD, line ministry and UNDP constituted and operationalized. Number of meetings/ consultation sessions organized. | Acceptance of the revised manual by both UNDP and the Government of Bangladesh. Formation of the Joint Task Team and regular meeting of the team is organized. 4 meetings/consultation sessions organized on the NIM. |  | The NIM is under review of ERD. Decision has been undertaken in the Project Executive Board to work jointly on the NIM. |  |
| Output 3 | Indicators |  | Target (Year-2017) |  | Progress towards targets |
| Strategic research/collaboration supported | Concurrence of eminent persons obtained to join the EPG (at least 20 eminent persons). Number of consultative session organized by GoB with eminent persons. |  | Initiative of developing collaboration with the Eminent Persons Group (EPG) is accepted by the Eminent Persons. 4 consultation sessions organized with the EPG. |  | Invitation has been sent to 48 eminent persons and 31 have given their written consent to join the group. A ToR has been developed for establishing formal collaboration with the EPG. |
| Output 4 | Indicators |  | Target (Year-2017) |  | Progress towards targets |
| Collaboration on Resource Mobilization Strengthened | Number of scopes and areas of collaboration for resource mobilization identified. Number of experience sharing event organized for GoB officials with other countries and partners. |  | 2 scopes and areas of collaboration for resource mobilization identified. 2 experience sharing event organized for GoB officials with other countries and partners. |  | A National Consultant has been hired for identifying scopes and areas of resource mobilization as well as for developing a resource mobilization strategy. Draft report and strategy has been developed. |
| Output 5 | Indicators |  | Target (Year-2017) |  | Progress towards targets |
| Project Information Repository Platform Operationalized | A project information repository at ERD UN Wing developed Information of UNDP projects updated in the respective repository Capacity of ERD officials on ODA and project management and administration of the repository |  | Existence of an Information Repository at ERD UN Wing 75% of information are updated in the repository 180 officials from ERD and other agencies are trained |  | A national consultant and a software firm has been working for development of the repository. Digitization of documents has been completed. Server, scanner and other IT equipment for establishing the repository have been procured and installed. 279 officials have been trained during the period of March to September 2016 on different subjects. |

# Key Achievements

With the objective of promotion of South-South cooperation, the project has initiated collection and compilation of best practices of different Government and non-Government organizations. South-South expert and Bangladesh’s former Permanent Representative to the UN, Dr. AK Abdul Momen, on behalf of the project, has prepared the draft report which is under review and finalization. The best practices, considered as development solutions, will be disseminated among stakeholders and Bangladesh Missions abroad for promotion in other countries.

In the context of reducing official development assistance (ODA), ERD is developing ৃ resource mobilization strategy and plan of action. Resource mobilization report

- NRB sharing sessions

- Repository

- Training

- Extension of project period

- With the objective of creating broader stake in capacity building for leveraging effective knowledge in development management, the project organized five training programmes on the subjects of (1) UN System, (2) Public Procurement, (3) Project Management, (4) Public Finance Management and (5) Effective Office Management. Total 273 officials were trained from ERD, different Ministries/Divisions and UN Agencies.

- The project has undertaken initiatives for developing knowledge partnership with the Eminent Persons Group (EPG). A ToR describing structure and formation of the group, modalities of organizing regular thematic sessions and relevant other issues has been developed which is at the approval stage. A list of 70 eminent persons has been prepared initially for inviting them to join the group.

- The project has undertaken initiative for creation of an information repository at ERD. It will be a unique document management software with easy search and download facilities which will help ERD officials in quick decision making and will work as a tool for learning management and maintaining effective institutional memory. A resource person has been engaged for developing technical specification of the repository as well as assessing stakeholders’ requirement and requirement of hardware and other related issues. A consultation meeting was organized in presence of the Senior Secretary of ERD and other senior officers of ERD to discuss the proposed structure and modalities of the repository.

# Resource Utilisation

The revised budget for (Jan-Dec) 2016 is USD 2,46,000 of which USD 85,124.82 is spent as of 30 September 2016, a delivery rate of 34 percent of total budget.

Table 1: Activities related to budget and expenditure in USD

| Activity | Budget |  |  | Expenditure |  |  | % of Delivery |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | NEX | UNDP | TOTAL | NEX | UNDP | TOTAL |  |
| South-South/Triangular and Public-Private Partnership Promoted | 1,500.00 | 12,500.00 | 14,000.00 | 82.69 | 1,000.00 | 1,082.69 | 7.73% |
| Programming Manuals Revised and Implemented | 1000.00 | - | 1,000.00 | - | - | 0.00 | 0.00% |
| Strategic research/collaboration supported | 2,000.00 | 14,000.00 | 16,000.00 | - | - | 0.00 | 0.00% |
| Collaboration on Resource Mobilization Strengthened | 1000 | 44,200.00 | 45,200.00 | 64.69 | 2,228.78 | 2,293.47 | 5.07% |
| Project Information Repository Platform Operationalized | 10,000.00 | 67,000.00 | 77,000.00 | 17.48 | 34,662.50 | 34,679.98 | 45.04% |
| Platform for engagement with NRBs established | 500.00 | 9,500.00 | 10,000.00 | - | - | 0.00 | 0.00% |
| Strategic mechanisms to review progress towards Human Development Established | 1,000.00 | 9,000.00 | 10,000.00 | - | - | 0.00 | 0.00% |
| Administrative, operational and technical support provided | 2,700.00 | 74,100.00 | 76,800.00 | 218.20 | 22,614.04 | 22,832.24 | 29.73% |
| TOTAL | 19,700.00 | 230,300.00 | 250,000.00 | 383.06 | 60,505.32 | 60,888.38 | 24.36% |

# Lessons Learned

- The Knowledge for Development Management (K4DM) Project intends to deal with some policy and procedural issues, which require involvement of senior management in decision making. This is one of the reasons for delay in initiating and implementing project activities;

- Lessons: Project activities should be initiated early for giving sufficient time to senior management for taking decisions on policy issues.

- Activities on revision of the NEX/NIM manual could not be started due to confusion on the status of the manuals and on the roles and ownership of different authorities on them;

- Lessons: Senior management of ERD and UNDP need to sit together on the manual for coming to a common understanding.

Procurement of hardware for repository was initiated in 2016, but the procurement was not completed in the due to delay in delivery by the international vendor. The project suffered this failure of delivery in 2016.

Lessons: Procurement should be initiated early and necessary follow-up should be done with the Country Office to facilitate procurement.

- The Project contains some innovative concepts, such as collaboration with the Eminent Persons Group (EPG), partnership with the Non-resident Bangladeshis (NRB), South-South/Triangular and Public-Private partnership etc. These are some unexplored areas where no prominent intervention from the Government is visible.

- Non-resident Bangladeshis (NRBs) and eminent persons who are specialists in different development areas can help the Government by providing their prudent guidance and valuable suggestions in formulation of appropriate policies and programmes as well as provide new ideas for reforms and innovation which might be valuable for national development.

- Activities on revision of the NEX/NIM manual could not be started due to confusion on the status of the manuals and on the roles and ownership of different authorities on them.

- Research and knowledge generation is an integral part of knowledge management, but the project couldn’t undertake any research this year due to delay in preparation and deciding some policy issues of project implementation.

- ERD showed much enthusiasm for creation of an information repository, a document management software, to help ERD officials in quick decision making, conducting learning management and maintaining effective institutional memory.

- ERD management is not interested to implement some of the activities mentioned in the prodoc. Implementation of project activities and delivery of the project is affected due to delay in decision making by management of the project implementing agency.

- South-South and Triangular partnership can create ample scopes for Bangladesh in national development. Bangladesh also has several good solutions of development challenges which can be shared and disseminated among other countries. Capacity development of the concerned Government officials is needed to reap the benefits of South-South and Triangular cooperation. The K4DM Project can facilitate promotion of South-South and Triangular cooperation among different Ministries/Divisions/Departments and Non-governmental organizations through capacity development of officials, collection and sharing of best practices, sensitization, consultation and different promotional activities.

# South-South and TRIANGULAR Partnerships

With an objective of promotion of South-South cooperation, the Government of Bangladesh has undertaken an initiative of formation of a Forum of the Finance and Development Ministers of the Global South. Bangladesh’s Finance Minister has written DO letter to Finance and Development Ministers of 127 countries inviting them to join the Forum. ERD has requested to the Ministry of Foreign Affairs to undertake initiative to facilitate the passing of a resolution in the UN General Assembly in favour of formation of the proposed Forum. The project has undertaken initiative to engage one resource person to assist ERD in facilitating the process of formation of the Forum as well as to collect and compile best practices of South-South and Triangular cooperation initiatives being practiced in Bangladesh and across the world.

# The Way Forward

- K4DM Project can initiate programmes on behalf of the Government in exploring the innovative partnership modalities such as partnership with Eminent Persons Group (EPG) and the Non-resident Bangladeshis (NRB) etc. Once these partnerships are established, these will work as platforms for regular dialogue and collaboration of ERD with eminent experts on development issues in future.

- The Project has undertaken different programmes of sensitization, capacity development, consultation and promotional activities on South-South and Triangular cooperation. Enhanced capacity of officials will contribute to promotion of SS/Tr cooperation and future policy formulation on SS/TrC.

- Developing strategic mechanism for human development at national level will create new opportunities for reviewing development interventions as well as help the Government agencies in adopting appropriate development policies.

- If effectiveness of the information repository is substantiated, other Ministries/Divisions may replicate similar application.

- UNDP management has decided to present the achievements of the track-funded projects before the donor communities which would create scope for further resource mobilization

- K4DM Project can initiate programmes on behalf of the Government in exploring the innovative partnership modalities such as partnership with Eminent Persons Group (EPG) and the Non-resident Bangladeshis (NRB), promotion of South-South, Triangular and Public-Private partnership etc.

- Researches on different development issues which are under ERD’s allocation can be undertaken by the project in the next year.

- After receiving guidance from the Project Executive Board, initiatives have to be undertaken on the NEX/NIM manual involving both ERD and UNDP and other stakeholders in the process.

- The Project will undertake different programmes of capacity development, collection and sharing of best practices, sensitization, consultation and promotional activities on South-South and Triangular cooperation.