REVISED FORMAT FOR INSTITUTIONAL STRENGTHENING TERMINAL REPORTS AND INSTITUTIONAL STRENGTHENING RENEWAL REQUESTS

2015 to 2017

Sections 1 to 12 and 15 to be completed by the country concerned prior to transmission to the implementing agency for comments in 14.

- Country:  ____NIGERIA_________________

- National implementing agency / ozone unit:  _FEDERAL MINISTRY OF ENVIRONMENT (NATIONAL OZONE OFFICE)_______________________

- Implementing agency:  __________UNDP__________________

- Institutional strengthening (IS) project phases (approved):

| Phase | Duration (dd/mm/yy) | Multilateral Fund funding (approved) | Multilateral Fund funding (disbursed) |
| --- | --- | --- | --- |
| 3 | Jul,2003- Jun, 2005 | US $224,547.12 | US $ 224,547.12 |
| 4 | Mar,2006-Feb, 2008 | US $260,000.00 | US $260,000.00 |
| 5 | April, 2008- March, 2010 | US $260,000.00 | US $260,000.00 |
| 6 | Dec 2010–Nov 2012 | US $260,000.00 | US $260,000.00 |
| 7 | Dec.2012- Nov. 2014 | US $260,000.00 | US$ 260,000.00 |

- a) Reporting period (mm/yy to mm/yy): ___Dec, 2012 to Sept, 2014________________________________

b) Requested (phase funding (US $), and period): ____US 260,000.00 Dec. 2014 to Nov 2016_______________________

- Data reporting:

| Reporting requirement | Reported |  | Year reported | Year submitted |
| --- | --- | --- | --- | --- |
|  | yes | no |  |  |
| Article 7 | X |  | 2013 | 2014 (data has been prepared, awaiting submission) |
| Country programme implementation | X |  | 2013 | 2014 |

- Describe the role and position of the National Ozone Unit (NOU) within the national administration, the way its work is supervised and its access to senior decision-makers (this may include cooperation with steering committees, advisory groups or inter-ministerial bodies).

The NOU’s role and position within the national administration and its operational mechanism remains the same as in the previous years. Therefore, the NOU has continued to operate within the structure of the Federal Ministry of Environment. The office is located in the Department of Pollution Control and Environmental Health and reports directly to the Director who is the head of department. The Director reports to the Permanent Secretary who is the professional head of the Ministry. The Permanent Secretary is responsible to the Honourable Minister, who is the political head of the Ministry.  The Honourable Minister is a member of the Federal Executive Council Chaired by Mr. President. The council meets weekly and through this process, environmental issues including Ozone Layer Protection are discussed when necessary.  There is also a National Council on Environment that has Commissioners of Environment from all 36 states of the Federation including the Federal Capital Territory, as members.  The Minister of Environment is the Chairman of this body that meets annually. The process ensures that relevant issues relating to Ozone Layer protection get to the State level. Other subject/sector related interministerial committees are set up when necessary. The Minister and Top Management also meet with the Senate and House Committees on Environment when necessary.

The NOU is headed by the National Ozone Officer who has a responsibility to brief the Hon. Minister and Top Management of the Ministry on the status of implementation of the MP on a quarterly basis

- Indicate the total number staff in the NOU: 4 Professional  and 3 Support Staff

- How many are paid under the IS? _____None______Full time__-____Half time_-______

- How many are paid by the Government? _All (7)____Full time__7____Half time__-______

X

Is the unit fully staffed?     xxx

YES    NO

If no, explain__________________________________________________________

__________________________________________________________

- Please provide details on the status of the implementation of the activities approved from the previous IS phase and planned activities for the requested phase.  Please add specific indicators if necessary.

| Objectives (please add as necessary) | Activities in current phase | Achievements in current phase (specify phase/mm/yy) |  | Planned activities in next phase (specify phase/mm/yy) | Expected results for next phase |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Adoption/implementation of ODS legislation and regulation to control and monitor ODS consumption |  |  |  |  |  |
| Introduction of licensing and quota system for HCFCs | Continuous sensitization on Licensing and Quota system arrangement for HCFCs. Phase VII (First and Fourth quarter of 2012) - Implementation of HCFC Quota System (adverts, meetings and allocation of Quota) (Phase VII Jan-Mar 2013). |  | Workshop for ODS Importers successfully held and updating of Register of HCFC Importers completed (Phase VII; Sept 2012) Meeting with Regulatory Enforcement Agencies (NAFDAC, SON, Nigeria Customs Service and NESREA) successfully held Round Table Meeting with the same Chemical Enforcement Agencies successfully held (Phase VII; April 2014) HCFC Quota allocation finalized and distributed to relevant agencies | Sustaining the implementation of the Licensing and Quota system arrangement for HCFC. Phase VIII (First and Fourth quarter of 2015 and 2016) | Smooth implementation of HCFC Quota system and achievement of 2015 10% reduction |
| Enforcement of control measures to sustain CFC phase-out | Further Training for Customs Officials and other relevant chemical control officers (Phase VII, June/Jul; 2013) Continuous routine meetings with all relevant Chemical control agencies (Phase VII, Mar 2013, Jun 2013, Jan/Feb 2014) |  | Three Training Sessions held involving a total of ninety Custom Officers at the Seme Border, Calabar Port and Warri Port (Phase VII/ March. 2013, July 2013 and Feb 2014) | Further Training for Customs Officials and other relevant chemical control officers (Phase VIII, June/Jul; 2015 and 2016) Continuous routine meetings with all relevant Chemical control agencies (Phase VIII, Mar 2013, Jun 2015, Jan/Feb 2016) | More trained officials and sustained CFC Phase-out Strengthened and improved co-ordination of controls measures |
| Monitoring illegal ODS trade (all ODS) | Training of Customs And Continuous routine meetings with all relevant Chemical control agencies (Phase VII, Mar 2013, Jun 2013, Jan/Feb 2014) |  | Same as activity just above (for enforcement of control measures) | Same as activity just above (for enforcement of control measures) | Same as activity just above (for enforcement of control measures) |  |
| Ratification of Amendments to the Montreal Protocol | No activity undertaken because all amendments have been ratified |  |  |  |  |
| Objective 2: Efficient and timely data collection and reporting |  |  |  |  |  |
| Monitoring customs import/export | - Continue process of Data Collection (Phase VII, Jan 2013, Jun/Jul 2013, Feb 2014) | Field Visits for data collection , Phase VII; Jan. 2013 and May 2014) Meeting held with NAFDAC to analyse Import permits and Actual imports (June 2013 and Aug. 2014) - Customs data verified (Phase VII/Jun . 2013 & May 2014) |  | Continue process of Data Collection (Phase VIII, Jan 2015, Jun/Jul 2015, Feb 2016) | Improved Customs import Data |
| Article 7 data reporting | - Massive Sensitization and Field visits in view of enforcement of new HCFC Quota system (Phase VII July 2013; Au, 2014) i.e. visits to ports, data analysis with NAFDAC | Data harmonised and reported through activities mentioned above Phase VII/Sept 2013, Sept . 2014 |  | Field visits in view of continued enforcement of the HCFC Quota system and reduction of the Quota amounts by 10% (Phase VIII July 2015; Aug, 2016) Continuous meetings with NAFDAC and Customs (Phase VIII 2015, 2016) | Prompt Data reporting |
| Country programme data reporting | Same as for A7 data | Same as for A7 data |  | Same process as above for Article 7 Data reporting | Timely reporting of CP Data |
| Objective 3: Consultations and coordination with other national agencies/stakeholders |  |  |  |  |  |
| Steering Committee | Monitoring of On-going Halon Decommissioning process (Phase VII/ June 2013) - Meeting with Chillers Steering Committee | - Completed Halon Decommissioning at NNPC - Decommissioned Halon transported to Halon Bank (Phase VII, July 2014) - Verification of Chiller owners for CFC stocks (Phase VII July- Sept Oct 2014) |  | Monitoring of On-going Halon Decommissioning process (Phase VIII/ June 2015) Supporting ODS Disposal activities such as Quantification and Collection of CFCs (Phase VIII /Feb/March 2015) | Optimal utilisation of Halon Bank Facility Successful quantification and collection of CFC stocks. |
| Industry associations | Continuous support to Industry associations (Phase VII /2013&2014) Continuous support for NGOs (phase VII; Sept 2013 & 2014) | Successful mediation on an internal issue within the Nigeria Association of Refrigeration and Air Conditioning Practitioners - NARAP (Phase VII/May/ Jun/July 2013) -Supported one NGO for Ozone Layer Protection awareness activities in Akwa Ibom State (Phase VII, Sept 2014) |  | Continuous support to Industry associations (Phase VIII /2015&2016) Continuous support for NGOs (phase VII; Sept 2015 & 2016) | Cooperation and effective result-oriented support for HCFC phase-out. |
| Objective 4: Supervision of timely implementation of phase-out activities and reduction in ODS consumption |  |  |  |  |  |
| Terminal phase-out management plan implementation | Continuous monitoring of on-going ODS phase out projects (Phase VII / first quarter and third quarter, 2013 and 2014) | ODS projects monitored nationwide (Phase VII/ April-June/July; 2013 & 2014) 56 beneficiaries verified |  | Continuous monitoring of on-going ODS phase out projects (Phase VIII / first quarter and third quarter, 2015 and 2016) | Closure of projects. |
| HCFC phase-out management plan preparation/implementation | Continuation of HPMP Implementation and Monitoring of HCFC phase out nationwide (Phase VII) | Successfully made submissions and obtained Tranches II & III (Phase VII 2012 and 2013) including a Verification report of the HCFC Quota system submitted and approved in 2013. |  | Continuation of HPMP Implementation and Monitoring of HCFC phase out nationwide (Phase VII / June 2015, Dec 2015; Mar/April & July/Sept 2016. | Successful completion of implementation of HPMP and preparation of stage II |
| HCFC subprogramme 1: Supply of foam systems Upgrade of 2 local systems facilities for supply of fully formulated systems with methyl formate and/or methylal for RPF applications | Completion of upgrade of facilities (Phase VII June 2013) | Subprogramme initiated successfully. Upgrade on course with reconstruction of workshop, installation of laboratory and installation of blending Tank (March 2014). |  | Completion of upgrade of facilities (Phase VIII March 2015) | Production, Supply and use of methyl formate as HCFC alternative |
| HCFC subproject 2: Individual project for automotive integral skin foam | NA | Project completed. |  | NA. Already completed. | NA. |
| HCFC subprogramme 3: Sub-programme for the commercial refrigeration equipment manufacturing sub-sector | Supply and installation of machines (June 2013) | Arrival and Inspection of Machines achieved (Phase VII,. 2014) Distribution of Machines to 30 beneficiaries (Phase VII, Sept. 2014) |  | Supply and installation of next set of machines (June 2015) | Completion of subproject and conversion to HCFC alternatives |
| HCFC subprogramme 4: Subsector phase-out plan to phase out R-22 in the AC sub-sector | NA | NA |  | Not in First stage implementation | Not in First stage implementation |
| HCFC subproject 5: Pamaque HC Production Pilot | Completion of subproject Phase VII; March/April) 2013). | Subproject at advanced stage; installation of tanks fittings completed pilot production trial successfully done (phase VII, Aug 2012) |  | Exploration of market penetration; (March/April 2015). | Mass production and availability of HC Refrigerant as alternative to HCFC |
| HCFC subprogramme 6: Servicing Sector | NA | NA |  | NA in current stage | Not in First stage implementation |
| HCFC Implementation Unit (7) | Continuous administrative support for effective HPMP implementation (Phase VII 2013) | Supported 6 missions to project sites and meetings and achieved 2013 Freeze (Phase VII 2012, 2013 & 2014) |  | Continuous administrative support for effective HPMP implementation (Phase VIII 2014) | Successful completion of implementation of Stage 1 HPMP and achievement of 2015 10% Reduction. |
| Objective 5: Awareness raising and information exchange |  |  |  |  |  |
| Information dissemination to key stakeholders, including International Ozone Day | Continuous marking of the Day through more awareness creation activities such as Mass Rallies, Road Shows and Children’s programmes with expanded media involvement (Phase VII /Sept. 2013& 2014) Ministerial-Media Interactive Session on MP activities in Nigeria | Secondary School Outreach programme with 1000 units of customised awareness promotional materials (note pads, pens, t-shirts, face caps and school bags) distributed to additional secondary schools and the general public. Phase VII/ Sept/ 2013 & 2014. Programme aired by the Federal and State Radio corporations nationwide as well as Nigerian Television Authority (Phase VII, Sept 2013 & 2014) Supported the Handing over ceremony of Low Pressure Foaming Machines to 30 beneficiaries under the HPMP Implementation (Phase VII, Sept 2014) |  | Continuous marking of the Day through more awareness creation activities such as Mass Rallies, Road Shows and Children’s programmes with expanded media involvement (Phase VIII /Sept. 2015& 2016) | More awareness created and public support for ODS phase-out in Nigeria especially towards achieving the HCFC 2015 10% Reduction and sustainability of ODS phase out activities |
| Objective 6: Regional cooperation and participation to Montreal Protocol meetings |  |  |  |  |  |
| Regional network participation | In-Country preparatory meetings (Phase VII/Mar. & Aug/Sept 2013 & 2014) | Two preparatory meetings held towards the ODSONET meetings in 2013 and Mar. 2014 (Phase VII) |  | Same will continue in the next phase | Successful Regional cooperation and participation at ODSONET Meetings |
| Open-ended Working Group / Meeting of the Parties | In-Country Preparatory meeting (Phase VII/Jun & Sept/Oct 2013 & 2014) | Meetings held with Stakeholders to prepare Nigeria’s position; Phase VII June & Oct 2013 and June 2014 |  | Same will continue in the next phase | Successful participation at OEWG Meetings and Meeting of the Parties. |

- Financial report:

| Item of expenditure | Budget for current phase (US $) | Disbursement (for current phase) (US $) |  | Estimated budget (for requested phase) (US $) | Government funding (in kind contribution) (US $) |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Actual | Obligated |  | Current phase | Requested phase |
| Staff (including consultants) | 20,000.00 | 25,000 (Consultants only) |  | 20,000. 00 | 110,000.00 | 110,000.00 |
| Equipment | 10,000.00 | 5,600.00 |  | 10,000.00 | 50,000.00 | 50,000.00 |
| Operational cost (i.e. meetings, consultations, etc.) | 14,000.00 | 17, 560.00 |  | 14,000.00 | 50,000.00 | 50,000.00 |
| Public awareness | 140,000.00 | 99,120.00 | $26,800.00 | 140,000.00 | 50,000,00 | 50,000,00 |
| Other | 76,000.00 (Travels) | 65,920.00 (For local travels) | $ 20,000.00 | 76,000.00 | 50,000.00 | 50,000.00 |
| TOTAL | 260,000.00 | 213,200 | 46,800** | 260,000.00 | 310,000.00 | 310,000.00 |

** NOO in agreement with the UNDP Country office marginally revised budget line allocations in the course of implementing the project to address priority needs. There is a balance of $46,800 that is expected to be utilised by the end of 2014.

- Please evaluate the IS performance in meeting the following indicators:

| Indicator |  | Evaluation |  |  | Comments |
| --- | --- | --- | --- | --- | --- |
|  |  | Very good | Satisfactory | Poor |  |
| 1. | Effectiveness of import control measures |  | X |  |  |
| 2. | Integration of ozone protection issues into national plans | X |  |  |  |
| 3. | Completion of phase-out projects | X |  |  |  |
| 4. | Efficient data reporting |  | X |  |  |

- Government endorsement:

| Action plan authorized by (name): | Mr. A.K. BAYERO |
| --- | --- |
| Signature of authorising authority: |  |
| Title: | Director, Pollution Control and Environmental Health |
| Supervising Organization/Agency/Ministry: | Federal Ministry of Environment |
| Date: | 12th September 2014 |

- Submission of action plan:

| Name of implementing agency: | UNDP |
| --- | --- |
| Name of Project Officer: | Mr. Etienne Gonin |
| Signature of Project Officer: |  |
| Date: | 14th September 2014 |
| Comments of the implementing agency: | The Institutional Strengthening project is working effectively in Nigeria, where all staff of the NOU are supported by the Ministry’s budget, thus allowing maximum funding for the activities. The NOU focuses on the HPMP implementation and its proactive coordination allowed the country to meet the 2013 HCFC consumption target. It has developed a successful cooperation with the two Implementing agencies of the HPMP, UNDP (lead) and UNIDO (cooperating). |

- Executive summary:  please provide summaries for the information required below in no more than one paragraph each.  These paragraphs will be used in documents for the Executive Committee Meeting.

- Terminal report

This report covered activities that were undertaken during the Phase VII of the I.S. from December 2012 - September 2014. During that period, the IS project allowed for continuation of successful implementation of ODS phase-out activities in Nigeria. The implementation of Stage 1 of the HPMP activities continued with the achievement of the 2013 Freeze and the HCFC Quota System becoming fully operational. Other traditional operations such as data reporting, participation in regional and international meetings, consultative work with domestic stakeholders and awareness raising were undertaken successfully. While checking that the phase-out of first generation ODSs was maintained, the NOU also ensured that Nigeria proactively implemented its HCFC phase-out programme, in line with international obligations.

- Plan of action

The Plan of action is intended to consolidate and sustain the phase-out of ODSs already achieved as well as the effective implementation of the first phase of the HPMP to achieve the mandatory 2015 10% HCFC consumption reduction that Article 5 countries have committed to. Activities linked to stage II of the HPMP will be prepared and start being implemented during the phase being requested.